Review of DZero CTT Upgrade Proposal (4/8/04)

Darin Acosta, John Anderson, Bill Freeman

# Introduction

The committee is convinced that the upgrade to the L1 Central Track Trigger (L1CTT) is needed for operation in Run 2b. Without an increase in the track equations to utilize the full resolution of the fiber tracker, the fake rate at Run 2b luminosities makes the track trigger non-functional, compromising physics.

The approved baseline for the L1CTT is an upgraded Digital Front-End daughter board (DFEA), with larger FPGAs to handle a 3(5X increase in the track equations. However, the current electronic system is stated to be untenable: the upgraded DFEA daughter boards in current L1CTT crate+controller system would require 12 hour downloads to program, which is deemed very unlikely to succeed during operations.  Although the reviewers question the necessity of frequent downloads in the collision hall, and whether the downloads could not be made more robust, we will assume the necessity of a higher bandwidth connection since that is the central tenet of this upgrade proposal.  Other benefits from this upgrade include improved testability of the system and an improved distribution of the clock and control signals. Thus, the full scope of the L1CTT upgrade includes the following:

- DFEA daughterboard (approved in baseline)

- DFEM motherboard

- DFEA backplane

- DFEA crate controller

- Optical DCL (crate controller interface)

- LVDS splitter

As part of the DFEM motherboard project, a DSAT tester module is also included to allow DFEM/DFEA bench testing without the crate backplane and controller. In total, the L1CTT system is housed in 2 crates of 20 motherboards each. Each motherboard would contain two DFEA daughter boards (which may be integrated on-board). Two new crate controllers are required. Each of the first 5 items is critical to the success of the L1CTT.

The scheduled completion date for the L1CTT upgrade is June 2005 according to the Project file. The final deadline for completion of the Run2b project, as mandated by DOE, is April 2006.  However, the proponents of the design would like to take advantage of a shutdown beginning this summer, and have a subset of the upgraded L1CTT boards placed in-situ in the hall by September 2004. The upgraded L1CTT would receive signals in tandem with the current L1CTT using an LVDS splitter box, allowing the system to be tested with real data in the collision hall environment.

# Technical Feasibility

The DFEA daughter board development is well advanced, with a prototype in hand based on the XC2V4000 FPGA and with track equation firmware for the full tracker resolution already developed. A dedicated engineer at Boston University has been identified. What remains to be decided is the FPGA choice (will the XC2V6000 be available?) and whether to merge the mother/daughter boards to improve robustness.  The existing Run 2a DFEA daughter board connectors have been a source of unreliability. Consultation with Jamieson Olsen after the review indicates that the connector failures are mostly metal fatigue failure in the cantilever spring contacts causing the spring to break or no longer supply sufficient contact force. An integrated design will likely lead to a more mechanically robust solution, but may lead to a modest increase in the layer count of the PC board. However, issues regarding the crate power distribution, controller, and testing have been identified and are discussed below.

The proponents of the L1CTT upgrade propose a 48V power solution in place of the low voltage/high current solution of Run 2a. This simplifies engineering and also improves the operation maintenance of the L1CTT system since the proposal would allow all signal connections to be made at the back of the crate. The risk is that the system may induce EMI effects to other sensitive D0 electronics. The reviewers recommend performing up-front engineering to ascertain that the design of the 48V plant does not adversely affect other detector systems, possibly performing an in-situ mock-up test.  Various options regarding the placement, shielding and wiring of the power plant need be determined prior to finalizing the layout of boards or backplanes. It may be advantageous to use a power system where each board has its own converter on-board, but it may be better to have an array of power converter units in an external box, with a twisted pair to each slot position in the backplane.

The reviewers question the design choice made for the high-bandwidth crate controller. The system requires only 2 such modules (plus spares), yet engineering for a fully custom solution is proposed.  The basis of the design is a new VME controller under design by the CMS group at The Ohio State University, which is proposed as a low-cost, radiation tolerant design for the 60 peripheral crates of the CMS Endcap Muon System. The design employs a gigabit Ethernet link (utilizing raw Ethernet packets, no TCP/IP protocol), and a Xilinx Virtex-2 Pro FPGA with RocketIO technology.  However, since the L1CTT crates use a custom read/write interface rather than VME, the OSU design must be modified. The L1CTT proposal includes engineering to develop schematics, layout, firmware, and testing for essentially a new board design. This in itself indicates that the Project file should have explicitly a second, pre-production, revision of the board built-in.  The Linux software drivers for the Ethernet interface developed by OSU can be re-used, however, as can some of the core Xilinx firmware for the RocketIO interface.  We feel that the risk associated with developing a new interface of this complexity, given the limited engineering and tight schedule, is high. The OSU designers currently have a PC board in hand, but the firmware and testing that must be done to validate the design remains to be completed.

The reviewers are not convinced that a commercial solution (fully or partially) could not be found to satisfy the bandwidth needs of the L1CTT in order to justify the $100K expense of the crate controller project (and which is in danger of significant schedule slippage).  Since the backplane is under redesign as well, other interface and bus technologies could be utilized. The software effort needed to integrate a standard controller is likely to be less than that required to debug software performing gigabit frame extraction.

As part of the DFEM motherboard development, the Boston group proposes to develop a DSAT tester module that allows testing of the DFEM/DFEA combination without a crate backplane and controller, which is to mitigate the risk associated with schedule slippage of the latter.  The engineering resources at Boston are stated to be available and independent of the DFEA/DFEM development. However, the reviewers question the value of investing resources and time in developing this modestly sophisticated tester board based around a Virtex-2 FPGA. Given the large amount of RAM and logic resources in modern FPGAs, particularly the XC2V6000 proposed for the DFEA, it is the opinion of the reviewers that most of the test functionality could be built into the DFEA/M module itself (e.g. add the PC and JTAG interface to the board, and input/output spy FIFOs in the FPGAs).  The specific objection of not having the SCL link available off-site is also questionable.  The SCL is a rather simple protocol and easily simulated.

The proponents have placed a lot of value in being able to perform in-situ tests of the upgraded L1CTT system during this year’s shutdown.  Concerns about the schedule (see below), however, indicate that this will be very difficult to meet.  The reviewers thus suggest developing contingency plans for testing outside of the collision hall using Monte Carlo test vectors (or even data recorded by the current system). For a digital system, this ought to be sufficient, provided that the necessary test circuitry (input/output FIFOs) is built into the design. Objections about timing skew at the inputs of the boards are met by simply referring to the experience in the extant system, where skew has been controlled by careful system design. In any case, there will be serious conflicts for access to the collision hall during access times as other upgrades to CFT and the calorimeter will be occurring simultaneously with L1CTT work.  This will inevitably increase any estimates       of time spent commissioning in this area.

The reviewers are of the opinion that the pinout of the connector on the backplane is not optimal and will cause un-needed complexity, possibly leading to signal quality issues and therefore a risk for cost overrun. The design is, by definition, mirror-image in that each half of the board performs logic upon one sector of the detector.  The connector pinout should also be mirror-image in that the cable order (see page 4, Hazen talk) should be from top to bottom:

in1

in2

in3

in4

out1

out2

out4

out3

in8

in7

in6

in5

# Schedule

There is a risk for schedule slippage if the design decisions on the power, FPGA choice, and board merger are not made soon. Given that the 48V option requires upfront engineering to check for any negative impact on other D0 electronics, it is even likely that the schedule will slip by at least the amount of time it takes to reach these decisions.

There is a concern that the identified engineering resources for the backplane and controller development are insufficient to meet the stated schedule.  The backplane and controller tasks require ~1.3 FTE of an FNAL electrical engineer over the next 6 months (April(September 2004, assuming 1768 hours per FTE-year). The identified FNAL engineer for these 2 projects is Jamieson Olsen, who when asked during the review, is able to commit 0.5(0.75 FTE during this period.  This indicates significant slippage in the controller and backplane tasks, which when combined with a second crate controller revision implies that the two are not likely to be ready before mid-2005.

The LVDS splitter development task, scheduled to start May 2004, does not yet have an identified FNAL engineer. There is about 1 month slack before it is late for a summer shutdown test.

These schedule concerns indicate that making a September 1, 2004 deadline for installation of a partial (but complete slice) during this year’s shutdown is unlikely.

# Contingency

The cost basis given for PC boards is predicated upon the mother/daughter approach; the potential for moving to the integrated design is justification for providing some excess contingency (on the order of 15%) for the bare PC board fabrication line item.

The crate controller with the gigabit Ethernet link and Xilinx RocketIO is a new design not based on the previous Run2a L1CTT controller, and new technology for the identified engineer.  The reviewers recommend higher contingency, 30(40%, for the crate controller labor costs.

# Cost

The L1CTT crate controller is a new design, but with only a single development cycle listed in the Project file. The reviewers recommend that a second, pre-production revision be put in explicitly.

Additional cost and schedule comments from Bill Freemen are attached directly to the end of this file.

# Milestones and Tracking

Milestones should be added for three technical decisions that must be made very soon (several weeks) in order to allow the project to proceed on-time:

- Whether to design around a high-current/low-voltage power distribution as in Run2a, or to switch to a 48V power supply and employ DC-DC power converters on the boards. As stated earlier, testing should be done to ascertain that the 48V choice does not negatively impact other detector electronics.

- Whether or not to merge the DFEA daughterboard onto the motherboard. Merging avoids connector reliability issues, but prohibits future upgrades and will increase the complexity of the board to some degree.

- Choice of FPGA. Current target FPGA is the Xilinx Virtex XC2V6000, which is as of yet unavailable. Fall-back is the XC2V4000. The difference in chip resources between the XC2V6000 and XC2V4000 is stated to be 60% versus 80%, respectively.  If not already done, a simulation of the Run 2b track equations in the XC2V4000, or a test using the existing DFEA daughterboard pre-production prototype, should be done to ascertain that a design around the smaller chip is feasible and without timing problems before committing to it.

Additional Cost and Schedule Comments

Reviewed by: Bill Freeman

# Findings

- The Project has incorporated the proposed changes into a draft MS Project resource-loaded schedule.  The changes incorporate new WBS elements as well as changes to pre-existing WBS elements.

- Engineer, technician, computing professional, and physicist resources are assigned at the lowest task level.

- A portion of the CTT sub-project cost is funded via an existing NSF-MRI grant administered through Boston University. The remainder is funded through DOE funds.  The Project intends to fund the increased scope of work through the allocation of existing DOE management reserve funds.

- The cost changes as presented to the committee are summarized in Table 1.

- The M&S costs associated with the new WBS elements are given in FY04 dollars.

- The revised M&S costs associated with pre-existing WBS elements are given in FY04 dollars.

- Fermilab labor rates are based on FY02 dollars.

- The costs as presented do not include any indirect overheads applied by Fermilab. These are ~ 30% on FNAL labor, ~16 % on Fermilab M&S procurements, including FNAL P.O.s issued to universities not subject to the pass-through rate or 1.5% for those universities subject to the pass-through rate.

- Contingency fractions have not been assigned for many of the new WBS elements.

- Cost account and work package entries have not been made for many WBS elements.

- Three key decisions need to be made in the next few weeks for which there are no corresponding milestones in the schedule. These are:

  - A decision on the use of 48v crate power rather than 3.3 v power

  - A decision on whether a separate DFE daughterboard/motherboard combination will be retained or the two will be integrated into a single board.

  - Which FPGA will be used in the next revision

# Comments

- Attachment 1 details some specific missing or incorrect items found while reviewing the MS Project schedule file.  This is not an exhaustive list.  There may be other items needing addition/correction.

# Recommendations

- The proponents should carefully review the resource profiles arising from the RLCS to insure that key personnel are not overcommitted.  This is especially important in view of the aggressive schedule required to be ready for the proposed prototype testing phase following the late summer '04 accelerator shutdown. Adjust the schedule accordingly.

- The proponents should make comparisons between cost numbers that are in the same units, i.e. FY02 to FY02 dollars or FY04 to FY04 dollars, to determine the amount of management reserve actually needed.

- Indirect costs should be included in the determination of the amount of management reserve needed to fund the CTT improvements.

- The project management should determine how it wishes to handle/assign contingency on the new WBS elements.  The trigger project management should review the contingency that remains as a fraction of the ETC to confirm that the remaining contingency is adequate.

- Add milestones to the MS Project schedule for the three decisions mentioned in Finding 10.

- The proponents should thoroughly review/comb the MS Project file with the DZero scheduler to enter information that is currently missing or out-of-date on various tasks, and correct other small errors.  This includes entries in the "Responsible Institution" and "Funding Source" fields, the "Cost Account", "Work Package", and "PMT" fields, and the "Notes" field that contains the WBS Dictionary and Basis of Estimate information.  BOE information should be made consistent with the revised cost and labor numbers.

- Backup material justifying new cost estimates should be collected and collated for easy reference.

- Once the change request is approved, the appropriate set of tasks should be (re)baselined in the MS Project file and the new baseline information, cost accounts, and work packages should be added to the project's COBRA program.

TABLE 1

Cost Changes Presented to the Committee at WBS Level 4

ATTACHMENT 1

Items Needing Correction in MS Project file

- Several of the new CTT Milestone tasks currently have durations of 1d.  These should be set to zero days.  These are:

1.2.3.8.3		interface specs (hardware+timing) finished

1.2.3.8.3		interface specs (hardware+timing) finished

1.2.3.8.10	ready for production

1.2.3.8.12	first BP received

1.2.3.8.17	delivered to Boston

1.2.3.9.11	CC ready

1.2.3.10.3	specs done

        - ready for platform test

- Delete blank task (ID 322)

- Tasks 204, 205, 228, 241-287, 306-323; Most tasks in these ranges are missing institution and funding source entries, as well as cost account, work package and PMT entries.  Task 288-305 have entries but the cost account and work packages are incorrect.

- Tasks 245, 248, 250, 262, 321 are missing resource assignments.

- Task 276 is called "hardware procurement" however there is no associated M&S non-labor dollar amount entered for this task?  Should there be?

- Task 209 (1.2.3.6.1.5	Test) has both InKind and MandSPass resources assigned.  This will need to be split into two tasks, if it is truly to be funded both by equipment and MRI funds.

- Task 313 has $7000 budgeted as MandS labor for BU technician support however only 11 hours of Tech time is assigned to the task.  That's a pretty expensive tech!

- Task 314 has a task type of "Fixed Work" (and is effort driven) – it should be fixed duration (and not effort driven) and hours/duration adjusted to reflect the anticipated budget need. ($18,000?); Task 314 also has a "deadline" date of 4/3/04 that should be removed.

- Suggest renumbering WBS 1.2.3.16 subtasks to begin at 1.2.3.16.1 rather than 1.2.3.16.2, since this part has not yet been baselined.

- Task 221-222, 230; Task 222 has same description as 221 and 230 but only has ETU resource assigned and explicitly has INKIND[0] assigned.  Also the three tasks have different predecessors and different start dates.  This should be checked/corrected as necessary.

- There are a number of tasks where the university labor hours are not consistent with the indicated M&S labor cost.  Several of these are on tasks that are funded out of the MRI so in some sense this inconsistency doesn't matter as far as the use of EQU contingency goes. However it may matter in terms of the accuracy of the estimated labor needs and hence it may impact the schedule.  In several cases it seems that a labor rate different from that stated in the notes was assumed.  For example, on task 223 there is a reference to  $40 per hour + 61.5% university overhead in the notes which does not correspond to the $22.5 per hour effective hourly rate one gets by dividing the budgeted inkind dollar amount of $ 1800 by the 80 hours of budgeted labor ( 40 tech + 40 engineer).

- Many of the notes that describe the WBS dictionary and BOE are either missing or have not been revised to reflect the proposed baseline changes. These should be adjusted/corrected, where appropriate.