# USGS Integrated Earth System Science Data Bases, Knowledge, and Products in the Great Lakes:

# A Pilot Project Plan to Address Nearshore Fish Habitat and Recreational Water Quality in Southwestern Lake Erie

by

Peter Barnes (GD, CA), Sheridan Haack* (WRD, MI), Scott Lundstrom (GD, CO), Don Rosenberry (WRD/NRP, CO), Jacqueline Savino (BRD, MI), Rob Striegl (WRD/NRP, CO), and Mark Wolcott (BRD, WI)

# *Project Contact

“Earth system science (ESS) takes the main components of planet Earth – the atmosphere, oceans, freshwater, rocks, soils, and biosphere – and seeks to understand major patterns and processes in their dynamics.  To do this, we need to study not only the processes that go on within each component (traditionally the realms of oceanography, atmospheric physics, and ecology, to name but three), but also interactions between these components.  It is the need to study and understand these between-component interactions that defines ESS as a discipline in its own right.”  Lawton, 2001

This recent quotation from the journal Science defines earth system science, a discipline in its own right for which the USGS is uniquely qualified. This Pilot Project Plan accompanies a Joint Planning Document that outlines Great Lakes nearshore habitat and water quality issues and a USGS earth system science approach to address them.  Application of earth system science in a purposeful pilot project will demonstrate the value added from integrated science and will provide managers with better tools to oversee the nearshore margin of the Great Lakes, an area that largely has been neglected by previous discipline-based science.

Project Summary

This project proposes to develop approaches and explore methods in the USGS application of earth system science to determine linked biological, hydrological, geological and land use processes significant to understanding and managing changes that influence Great Lakes nearshore environments.  The issues to be addressed will be taken from the USGS Great Lakes Strategic Plan in consultation with collaborators and partners in the Great Lakes Region. The first Task (#1) is iterative hypothesis development in conjunction with collaborators and stakeholders.  The second Task (#2) is a pilot study to develop a template for USGS interdisciplinary field and data compilation.  This interdisciplinary pilot project will serve as a model template for Great Lakes-wide earth system science, encompassing data acquisition and presentation, analyses of processes, and understanding of process linkages.  In addition, predictive tools will be developed to assess the impacts of natural and anthropogenic change and perturbations to nearshore environments.

# Project Objectives and Strategy

# The proposed pilot effort seeks to develop (1) interdisciplinary hypotheses, (2) uniform interdisciplinary data collection approaches, (3) an interdisciplinary USGS database, (4) an integrated scientific understanding and (5) a conceptual model of linked coastal and nearshore processes directed toward DOI and Federal Great Lakes Management Issues.

# A two-year pilot study will approach this goal by developing preliminary interdisciplinary hypotheses regarding the linkages between hydrologic, biologic, geologic and anthropogenic processes and nearshore fish habitat and recreational water quality as influenced by changes in water level and climate.  In year one, customer and client input will be sought in a workshop to refine overall scope and outcomes of the integrated pilot study, to solidify study site selection, and to build partnerships.  In this proposal, a site in southwestern Lake Erie will be recommended for the pilot study as it would build upon an ongoing USGS study and reduce costs due to logistical considerations.  However, customer and client input may redefine final site selection.   In the second half of year one and the first half of year two we propose a WRD/BRD/GD/NMD pilot field study that develops uniform approaches and combined data collection protocols to test hypotheses.  The field study will focus on understanding the linked physical, biological and land use processes significant to nearshore fish ecology and recreational water quality in Southwestern Lake Erie. We plan for the pilot study to provide a conceptual model of the interdisciplinary linkages and their response to change, as exemplified by water level change.  The pilot study methods and products will be used as a USGS template for Great Lakes-wide earth system science, encompassing data collection, compilation and presentation, and process analysis.

USGS will be required to apply new approaches, skills and perspectives to data comparison and integrated analysis to assure USGS success in newly integrated endeavors.  For our integrated strategy to be successful, we see the need for a post doctoral scientist trained in earth science system disciplines, and a staff person skilled in metadata, GIS and large database management, to be involved in the project from the start.  In addition, effective integrated field and data compilation efforts might benefit greatly from temporary relocation of staff and might also facilitate the success of the interdisciplinary work.

# Potential Impacts and Major Products

# Understanding earth system science linkages in the near shore will allow the USGS to describe and explain/model how natural and anthropogenic changes in coastal areas will affect natural resources.  Scientists will better understand the processes and linkages that occur in the nearshore margins of the Great Lakes, an area that largely has been neglected by previous studies.  Lake and watershed managers will be better able to manage water and biological resources in these nearshore areas, and predictions will be possible for assessing the impacts of natural and anthropogenic perturbations such as water level change, to nearshore environments.  Major anticipated products from the pilot effort are:

# • Hypotheses linking changes among coastal and nearshore hydrology, geology, biology and land use.

• Identification of processes that will become “unlinked” by future natural or anthropogenic change (e.g., as a result of new development; construction of a breakwall; new road; sand mining).

# • Unified database and GIS of USGS and collaborator earth system science information.

# • Interdisciplinary and disciplinary scientific reports and journal articles describing nearshore character and processes, as well as articles describing new approaches to conducting earth system science

• Draft conceptual models or reports that link cause and effect responses to physical and biological change at the pilot study site (straw decision support tools).

• Development of new tools for addressing earth system science research questions that make use of cross-disciplinary techniques.

By developing and providing a tested earth system science template for coordinated hypothesis generation, data collection, interpretation and conceptual integrated model development, the USGS will provide leadership for assessing earth system processes within the Great Lakes.

# Timeline

# YEAR 1

# Month

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TASK 1, A | TASK 2 |
|  |  | Workshop |  |  |  |  | 1st Data |  |  |

# YEAR 2

# Month

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TASK 2 | TASK 1, B |
|  |  | 2nd Data |  |  |  |  | Workshop |  |  |

### Work Plan

# Task #1 – Hypothesis development, refinement and product definition.

# Task Summary and Objectives

A) The first objective is to develop hypotheses, approaches and collaborators for earth system science data collection/ interpretation/ presentation to be used as direction for the pilot study.

B) The second objective is to define and present, in preliminary but new and creative formats, the value added by applying an earth system science approach to Great Lakes nearshore issues learned in the pilot effort.  The outcome will be a template for conducting additional earth system science studies and analysis based on interdisciplinary datasets as a template for other areas and other issues in the Great Lakes.

# Work To Be Undertaken

# Convene regional meeting of USGS Great Lakes researchers, with stakeholders and potential collaborators for nearshore studies before and after the field and data analysis effort (Task #2).

# Write meeting reports with recommendations for USGS integrated research focus and products including stakeholder and collaborator perspectives and apply outcome to implementing the pilot field study site selection, research focus and product goals.

- Develop additional syntheses through face-to-face meetings.

- Define key elements of successful earth system science as applied to nearshore issues

# Planned Outreach

# Assess the desire and need for a Regional Science Advisory Committee, a small standing committee of internal and external scientists that would provide guidance, support and collaboration for USGS integrated research in the Great Lakes.

# Assure ongoing interaction and dialog with USGS Great Lakes Coordinator; include coordinator in face-to-face project meetings

# Meet with stakeholders to discuss preliminary results and planned products.

Preliminary Task 1 Budget Estimate: 				First year	Second Year

# Coordinating Committee salary	6-8 @ 2pp ea	$30K		$30K

# Regional meeting with collaborators, stakeholders	$30K		$30K

# Total								$60K		$60K

# Task #2 – Hypothesis testing, field observations, preliminary linkage and database development.

# Task Summary and Objectives

# Conduct short-term interdisciplinary USGS-led study of fish habitat and nearshore recreational water quality as they might be influenced by short- and long-term changes in water level and climate.   The first objective is to develop a linked data set, and a linked interpretation of biological, hydrological, geological and land use processes in the pilot area to use in assessing the preliminary hypotheses developed in Task #1.  The second objective is to explore methods for interdisciplinary field data collection, coordinated database development, data analysis and data presentation.  Although exploratory, results are expected to be useful in developing a conceptual model of the linkages for use by resource manages in assessing earth system science effects of change (climate, lake level, development, discharge, erosion, etc.)

# Work To Be Undertaken and Description of Methods and Procedures

# Collect retrospective data.

- Collect short-term, small scale interdisciplinary dataset at the same temporal and spatial scales (approx. 1 month of field work;  we anticipate the distal extent of study area is 4 km offshore or water depth of 12 m, onland a few 10s to 100s of meters from shore).  Employ approach in which all researchers participate in both disciplinary and interdisciplinary data collection efforts, to foster interdisciplinary thinking, discussion and ideas.

- Interdisciplinary data collections may include:

# High resolution geomorphic and geologic mapping of coastal and benthic habitat/groundwater aquifers including bathymetric/coastal LIDAR (EEARL?).

# Geologic studies of sediment dynamics toward predicting substrate/habitat response to change events.

# Biologic assessment of fish and invertebrate communities and their response to changing sediment dynamics and ground water regimes.

# Hydrologic studies of ground water-surface water flow dynamics and their potential to impact fish habitats and microbial ecology and nearshore water quality.

# Studies of spatial and temporal changes in ground and surface water chemistry in relation to water quality for fish habitat and human recreation.

# Analysis of ecology of water and sediment borne microorganisms impacting fish habitat and recreational water quality.

# Assessment of coastal land use change using photogrammetry and retrospective data analysis.

- Perform multivariate data analysis with goal of understanding interdisciplinary linkages.

- Produce temporal and GIS-based interdisciplinary data synthesis and presentation.

- Analyze data from first round of data collection; determine data gaps, linked and indicator variables; discuss and refine field collection protocols; develop new hypotheses and propose new methodologies.  This activity will include face-to-face investigator meetings, coordinated examination and analysis of data sets, and coordinated structuring of databases and GIS coverages. Interpretations of interdisciplinary analyses would be enhanced and facilitated by shared post docs and graduate students.

# Initiate development of journal articles based on research, to be published in Second or later FY.

- Develop preliminary synthesis of USGS earth system science as applied to nearshore fish habitat and recreational water quality issues.   Summarize how integrated datasets, developed from coordinated field protocols and coordinated data analysis, generate new understanding of linkages among nearshore processes.

# Planned Outreach

# Lead special session at annual meeting of International Association of Great Lakes Research (IAGLR).

# Meet with stakeholders to discuss preliminary results and planned products.

# Develop project website for communicating data and research discussion

# Generate abstracts and preliminary reports

# Draft interdisciplinary database in GIS format

Preliminary Task 2 Budget Estimate: 				First year	Second Year

Extra Staffing

Earth System Science trained Postdoc					$50k		$50k

Database and GIS development (senior analyst)			$50k		$50k
Sub total 									$100k		$100k

Field studies

Geomorphic and geologic mapping of substrate   			$40k		$10k
Bathymetric/coastal LIDAR (EEARL)  							$25k	
Photogrammetry  								$10k		
Analysis of land use change  						$10k 		$10k

Bluff, coast, and nearshore sediment dynamics  			$25k		$25k
Ground water/surface water character and dynamics	 		$25k		$25k
Ground and surface water chemistry influencing habitat  		$25k		$25k
Fish and habitat response to physical change 	 			$25k		$25k

Coastal and wetland ecosystem response to change			$25k		$25k
Coastal microbial ecology and response to change  			$25k		$25k
Sub total 									$210k		$195k

Product and information development 
Project coordinating and science integration meetings  		$15k		$15k
GIS applications								$30k		$30k
Publications/Web site development  					$10k		$10k
Sub total 									$55k		$55k

Operations subtotal							$365k		$350k

USGS research staffing estimate (8 co-PI’s ~ half time @ ~ $50k) 	$400k		$400k

Grand Total									$765k		$750k

# Potential Collaborators (Initial list, in alphabetical order)

# Great Lakes Protection Fund

# Great Lakes Fishery Commission

# NOAA

# Regional Water Management Agencies

# US Fish and Wildlife Service

# US Army Corps of Engineers

# US EPA

# Sea Grant

# State DNR’s

# The Nature Conservancy

# Potential Clients (Initial list, in alphabetical order)

# Great Lakes Fishery Commission

# Great Lakes Commission

# International Joint Commission

# National Park Service

# Public interest groups, Local and Regional

# Regional Water Management Agencies

# US Fish and Wildlife Service

# US Army Corps of Engineers

# US EPA

# State DNR’s