## INSTRUCTIONS
Instructions to Complete Part C
There will be one iteration of CADRe for each project milestone. For CADRes that parallel IPAO reviews, data shall be provided to the CADRe developer team from the IPAO after the SRR or PDR review to minimize impact on project. For CADRes that are out of sequence with the IPAO, the CADRe developer will work directly with the project to obtain necessary data.
Steps to Complete Part C
1) The "Project WBS & LCCE" tab should be filled out. Here, the costs are reported to exactly match the lowest level of the project's own WBS. Typically, this information will be at the project's cost account level and it should be those account names which are used here. (See "NASA WBS & LCCE" for formatting guidance).
2) The "Project WBS Dictionary" tab should be filled out to the lowest level of the project's WBS listed with a definition provided with each one.
3) The costs provided in the "Project WBS & LCCE" tab need to be mapped into the "NASA WBS & LCCE" tab.
To facilitate mapping from the project WBS to the NASA WBS, it is necessary to utilize columns A & B on the left of the NASA WBS elements. In the case where multiple Project elements are being mapped to a single NASA element, all the Project elements should be listed in this first column. In the case of a single Project element being mapped to more than one NASA element, the percentage allocation of the Project element associated with the appropriate NASA element needs to be specified in the second column. If there is a one-to-one mapping, a 100% allocation should be entered.
4) The "Basis of Estimate" tab should be filled out describing how the estimate was derived (i.e. grassroots, parametric model, analogy, vendor quote, etc.).
5) The Detailed Element WBS Costs template should be filled out when the project has the information
to breakout Non-Recurring and Recurring Costs. Generally for a single spacecraft project,
this information is not obtainable.
Notes
1) Included any bypass funding at the lowest level possible.
2) Center specific elements will have their own unique CMO factors which need to be included.
3) Elements provided by other centers need to include those center CMO costs in the appropriate WBS
elements. If not included then a note "Item is not in Full Cost" should be added.
4) Add the HQ G&A factor at the end of Part C. This factor will be provided by PA&E.
5) Any contractor fees and Caltech fees should be spread across the applicable WBS items.
6) Please use N/A (Not Applicable) and Not Available as follows:
N/A.--> Use this notation when the particular parameter is not relevant or does not apply to the project.
Not Available--> Use this notation when information would be relevant, but the project is unable to
provide it.

## Project WBS & LCCE
Report As of Date: |  |  | Summary Costs (Thousands of Then-Year Dollars)
|  |  | <------------------Actual Costs-------------------> |  |  |  | <------------Estimated Costs------------>
| NASA WBS Elements | Level | Cur FY - n | Curr FY -2 | Curr FY -1 | Curr FY | Curr FY +1 | … | FY n | Total
| System Name | 1
| Project Management | 2
| Systems Engineering | 2
| Safety and Mission Assurance | 2
| Science/Technology | 2
| Payload(s) | 2
| Flight System | 2
| Launch Vehicle/Services | 2
| Mission Operations System (MOS) | 2
| Ground Data System (GDS) | 2
| System Integration, Assembly, Test & Check Out | 2
| Education & Public Outreach | 2
Reserves
Project Subtotal
| Coporate G&A | 1
| Center Management Operationss (CMO) | 1
Total

## Project WBS Dictionary
WBS Element Name | Level | Description of inclusions and exclusions

## NASA WBS & LCCE
Report As of Date: |  |  |  | Summary Costs (Thousands of Then-Year Dollars)
|  |  |  | <------------------Actual Costs-------------------> |  |  |  | <------------Estimated Costs------------>
Project WBS Element | % Allocation to NASA WBS | NASA WBS Elements | Level | Cur FY - n | Curr FY -2 | Curr FY -1 | Curr FY | Curr FY +1 | … | FY n | Total
|  | System Name | 1
|  | Project Management | 2
|  | Systems Engineering | 2
|  | Safety and Mission Assurance | 2
|  | Science/Technology | 2
|  | Payload(s) | 2
|  | Payload Management | 3
|  | System Engineering | 3
|  | Payload Product Assurance | 3
|  | Instrument n | 3
|  | Instrument n Management | 4
|  | Instrument n Systems Engineering | 4
|  | Instrument n Assurance | 4
|  | Antenna | 4
|  | Optics | 4
|  | Sensors/Detectors | 4
|  | Structures & Mechanisms | 4
|  | Thermal Control | 4
|  | Electronics | 4
|  | Power | 4
|  | Pointing Subsystem | 4
|  | Harness & Cabling | 4
|  | C&DH | 4
|  | Ground Support Equip | 4
|  | Integration, Assembly Test & Check out | 3
|  | Flight System \ Spacecraft | 2
|  | Flight System Project Management | 3
|  | Flight System Systems Engineering | 3
|  | Flight System Product Assurance | 3
|  | Spacecraft | 3
|  | Spacecraft Management | 4
|  | Spacecraft Systems Engineering | 4
|  | Spacecraft Product Assurance | 4
|  | Spacecraft Structures & Mechanisms Total | 4
|  | Structures/Mech. Management | 5
|  | Structures/Mech. Systems Engineering | 5
|  | Primary Structures | NL
|  | Load Carrying Shell/Truss | 5
|  | Equipment Compartments | 5
|  | Booms | 5
|  | Adapters | 5
|  | Secondary Structures | NL
|  | Equipment (Instrument) Mountings | 5
|  | Ballast Mass | 5
|  | Mechanisms | NL
|  | Positioning | 5
|  | Deployment and Storage Equipment | 5
|  | Docking Mechanisms | 5
|  | Pyrotechnics | 5
|  | Structures/Mech. Subsystem I&T | 5
|  | Spacecraft Thermal Control | 4
|  | Thermal Management | 5
|  | Thermal Systems Engineering | 5
|  | Active Devices | NL
|  | Cryogenic Devices | 5
|  | Liquid Loops | 5
|  | Electric Cooling (Thermoelectric) | 5
|  | Electric Heaters Thermisters & Thermostats | 5
|  | Shutters | 5
|  | Passive Devices | NL
|  | Radiator Panel/Fins | 5
|  | Coatings | 5
|  | Heat Pipes | 5
|  | Insulation | 5
|  | Conductive Structures | 5
|  | Heat Activated louvers | 5
|  | Sun Shields | 5
|  | Second Surface Mirrors | 5
|  | Thermal Subsystem I&T | 5
|  | Spacecraft Electrical Power & Distribution | 4
|  | EPS Management | 5
|  | EPS Systems Engineering | 5
|  | Electrical Power Generation | NL
|  | Solar Cells | 5
|  | Nuclear Reactor | 5
|  | Radioisotope Thermionic Generator | 5
|  | Chemical (Fuel Cells) | 5
|  | Aux Power Unit(s) | 5
|  | Electrical Power Conditioning | NL
|  | Power Control Electronics | 5
|  | Power Conversion Electronics | 5
|  | Power Dissipation Devices | 5
|  | Power Distribution Electronics | 5
|  | Electrical Power Storage | NL
|  | Batteries | 5
|  | Charge Control Electronics | 5
|  | Harnesses & Cables | 5
|  | EPS Subsystem I&T | 5
|  | Spacecraft GN&C | 4
|  | GN&C Management | 5
|  | GN&C Systems Engineering | 5
|  | Attitude Determination | NL
|  | Earth (Horizon) Sensors | 5
|  | Sun Sensors | 5
|  | Star Tracker/Sensors | 5
|  | GPS Receivers | 5
|  | Imagers | 5
|  | Magnetometers | 5
|  | Altimeters | 5
|  | Inertial Reference Unit | 5
|  | Rate Gyros | 5
|  | Accelerometers | 5
|  | Bearings and Power Transfer Assembly | 5
|  | Attitude Control | NL
|  | Reaction Wheels | 5
|  | Momentum Wheels | 5
|  | Control Moment Gyros | 5
|  | Energy Storage Devices (Flywheels) | 5
|  | Magnetic Control Devices | 5
|  | Spin Control Devices | 5
|  | Control Electronics | 5
|  | GN&C Subsystem I&T | 5
|  | Spacecraft Propulsion | 4
|  | Propulsion Management | 5
|  | Propulsion Systems Engineering | 5
|  | Tanks | NL
|  | Oxidizer Tanks | 5
|  | Fuel Tanks | 5
|  | Propellant Tanks | 5
|  | Pressurant Tanks | 5
|  | Plumbing | 5
|  | Maneuvering Thrusters | NL
|  | Bipropellant | 5
|  | Monopropellant | 5
|  | Solar Electric | 5
|  | Ion | 5
|  | Electrostatic | 5
|  | Electromagnetodynamic | 5
|  | Cold Gas | 5
|  | Translation Thrusters | NL
|  | Bipropellant | 5
|  | Monopropellant | 5
|  | Solar Electric | 5
|  | Ion | 5
|  | Electrostatic | 5
|  | Electromagnetodynamic | 5
|  | Cold Gas | 5
|  | Solid Propellant | 5
|  | Liquid Propellant | 5
|  | Propulsion Subsystem I&T | 5
|  | Spacecraft Communications | 4
|  | Telecom Management | 5
|  | Telecom Systems Engineering | 5
|  | Antennas | NL
|  | Omnidirectional | 5
|  | Sprial | 5
|  | Horn | 5
|  | Patch | 4
|  | Parabolic | 5
|  | Waveguides/Routers | NL
|  | Diplexers | 5
|  | Triplexers | 5
|  | Multiplexers | 5
|  | Multicouplers | 5
|  | Coaxial Switches | 5
|  | RF Switches | 5
|  | Filters | 5
|  | Waveguide | 5
|  | Radio Frequency Equipment | NL
|  | Receivers | 5
|  | Transmitters | 5
|  | Transceivers | 5
|  | Transponders | 5
|  | Modulators | 5
|  | Demodulators | 5
|  | Traveling Wave Tube Assembly (TWTA) | 5
|  | Solid State Power Amplifiers | 5
|  | GPS Receivers | 5
|  | Downconverters | 5
|  | Upconverters | 5
|  | Telecom Subsystem I&T | 5
|  | Spacecraft C&DH | 4
|  | C&DH Management | 5
|  | C&DH Systems Engineering | 5
|  | Processors | 5
|  | Solid State Memory | 5
|  | Decoders | 5
|  | Command Units | 5
|  | Telemetry Units | 5
|  | Command Sequencers | 5
|  | Timing Units | 5
|  | Frequency Generators | 5
|  | Signal Conditioners | 5
|  | Data Switches | 5
|  | COMSEC | 5
|  | Interface Units | 5
|  | Tape Recorders | 5
|  | Disk Recorders | 5
|  | C&DH Subsystem I&T | 5
|  | Spacecraft Software | 4
|  | Software Management | 5
|  | Software Systems Engineering | 5
|  | CSCI Name 1 | 5
|  | CSCI Name 2 | 5
|  | Software Subsystem I&T | 5
|  | Entry/Decent/Lander | 3
|  | Rover | 3
|  | Spacecraft Retirement & Disposal | 3
|  | Launch Vehicle/Services | 2
|  | Mission Operations System (MOS) | 2
|  | MOS Management | 3
|  | MOS Systems Engineering | 3
|  | Mission Operations Center | 3
|  | Science/Data Operations Center | 3
|  | Data Distribution & Archival | 3
|  | Communications/Network Infrastructure | 3
|  | Training | 3
|  | Ground Data System (GDS) | 2
|  | GDS Management | 3
|  | GDS Systems Engineering | 3
|  | Mission Operations Center | 3
|  | Hardware | 4
|  | Software | 4
|  | Other | 4
|  | Science/Data Operations Center | 3
|  | Hardware | 4
|  | Software | 4
|  | Other | 4
|  | Data Distribution & Archival | 3
|  | Hardware | 4
|  | Software | 4
|  | Other | 4
|  | Ground Stations | 3
|  | Communications/Network Infrastructure | 3
|  | Hardware | 4
|  | Software | 4
|  | Other | 4
|  | GDS Integration & Test | 3
|  | Hardware | 4
|  | Software | 4
|  | Other | 4
|  | System Integration, Assembly, Test & Check Out | 2
|  | Education & Public Outreach | 2
Note on C200: Expand if applicable
Note on C201: Expand if applicable
Note on C194: Only include SW Subsystem if SW is carried on Orbiter. If carried on anther element (e.g. rover), include there.

## Cost Assumptions
COST GROUND RULES AND ASSUMPTIONS
BASIS OF ESTIMATE
Project WBS | Level | Basis of Estimate (BOE)

## Detailed Element WBS Costs
Report As of Date: |  | Thousands of Then-Year Dollars
Element Name: |  | Non-Recurring Costs
| Elements of Cost |  | Cur FY - n | Curr FY -2 | Curr FY -1 | Curr FY | Curr FY +1 | … | FY n | Total
Burdened Project Direct Labor
Burdened Raw Material, Purchased Parts, and Purchased Equipment
Burdened Support Contract Labor
Burdened Other Direct Charges (ODCs)
Total
Recurring Costs
|  |  | Cur FY - n | Curr FY -2 | Curr FY -1 | Curr FY | Curr FY +1 | … | FY n | Total
Burdened Project Direct Labor
Burdened Raw Material, Purchased Parts, and Purchased Equipment
Burdened Support Contract Labor
Burdened Other Direct Charges (ODCs)
Total
Total Costs
|  |  | Cur FY - n | Curr FY -2 | Curr FY -1 | Curr FY | Curr FY +1 | … | FY n | Total
Burdened Project Direct Labor
Burdened Raw Material, Purchased Parts, and Purchased Equipment
Burdened Support Contract Labor
Burdened Other Direct Charges (ODCs)
| Total |  | Must sum to entries on Summary Sheet

## Schedule Data
As of mm/dd/yy
|  |  | ATP | SRR MDR/DR | PDR | CDR | ARR I&T Start Date | ARR I&T END Date | TRR | Pre Ship Review | LRD
Mission
SPACECRAFT ELEMENT
Spacecraft Bus
Attitude Control Subsystem
Command and Data Handling
Communications Subsystem
Proplusion Subsystem
Structure Subsystem
Thermal Control Subsystem
Wire harness
PAYLOAD ELEMENT
Instrument 1
Instrument 2
Insturment 3
GROUND SEGMENT

## Risk Info
INSERT RISK INFORMATION FROM THE PROJECT INCLUDING: Risk Ground Rules and Assumptions RISK LIST 5X5 RISK MATRIX S-CURVE