DRAFT

LONG-TERM STEWARDSHIP

BASELINE PLANNING HANDBOOK

September 2003

U.S. Department of Energy

National Nuclear Security Administration Service Center

Environmental Programs Department

This page is intentionally blank.

CONTENTS

Acronyms	ii

1.0	INTRODUCTION	1

1.1	LTS Background	1

1.2	Roles and Responsibilities	1

2.0	DOCUMENTING LTS PLANNING ACTIVITIES IN THE BASELINE	3

2.1	PCT Plan and LTS Plan Preparation	4

2.2	Transitioning LTS Work	5

2.3	Determining and Documenting LTS Phase Activities During the EM Project Phase	7

2.4	Milestones	7

2.5	Lifecycle Funding Needs	7

3.0	LTS-PHASE BASELINE GUIDANCE	9

3.1	Work Breakdown Structure (WBS) Development	9

3.2	Risk Management and Analysis	12

3.3	Schedule	13

3.4	Cost Estimating	13

3.5	Performance Measures	13

4.0	PROJECT REPORTING	14

4.1	IPABS-IS PEM	14

4.2	Periodic LTS Updates and Performance Review	14

5.0	REFERENCES AND RESOURCES	15

6.0	Glossary	16

Appendix A - Critical Decision-4 Turnover and Closeout Requirements and Template

Appendix B - Project Closure and Transition Plan Content and Checklists

Appendix C - Example LTS Plan Outline

Appendix D - Example WBS Template

Acronyms

CERCLA	Comprehensive Environmental Restoration, Compensation, and Liability Act

D&D	decontamination and decommissioning

DOE	U.S. Department of Energy

EM	Office of Environmental Management

EP	Environmental Programs Department

ER	environmental restoration

Handbook	Long-Term Stewardship Baseline Handbook

HQ	DOE Headquarters

HSWA	Hazardous and Solid Waste Amendments of 1984

IPABS	Integrated Planning, Accounting, and Budgeting System

IPABS-IS PEM	IPABS-Information System Program Execution Module

KCP	Kansas City Plant

LANL	Los Alamos National Laboratory

LTS	Long-Term Environmental Stewardship

LTRA	Long-Term Response Action

M&O	management and operations

MOA	memorandum of agreement

NFA	No Further Action

NNSA	National Nuclear Security Administration

NRDA	Natural Resource Damage Assessments

PARS	Project Assessment and Reporting System

PCT Plan	Project Closure and Transition Plan

PRS	potential release site

PSO	Principal Secretarial Offices

RCRA	Resource Conservation and Recovery Act

SNL	Sandia National Laboratories

SNL/NM	Sandia National Laboratories/New Mexico

TL	Task Leader

WBS	work breakdown structure

# INTRODUCTION

The U.S. Department of Energy (DOE) National Nuclear Security Administration (NNSA) Service Center Environmental Programs Department (EP) acknowledges the following definition of long-term stewardship (LTS):

The proactive management approach toward sustainable use and protection of natural and cultural resources affected by DOE operations and operational legacies, including activities ensuring protection of human health and the environment following closure of Office of Environmental Management (EM) projects.

As EM projects move toward mission completion, planning, integrating, and documenting LTS is increasingly important to help ensure smooth transition to the site steward.

The purpose of the LTS Baseline Handbook (Handbook) is to provide suggestions for properly documenting LTS planning and execution in EM project life-cycle baselines (baselines). Due to the range of LTS activities anticipated at sites and the magnitude of information required in baselines, site offices are encouraged to use a graded approach to integrate LTS planning into EM project closure and transition. This Handbook is intended to provide approaches for addressing LTS in baselines that have not already been documented in existing EM guidance and requirements (e.g. DOE M 413.3-1).

The initial development of the Handbook began in the summer of 2001 when it appeared that LTS planning guidance would not be forthcoming for the non-closure sites.  The initial Handbook was developed prior to the NNSA reorganization and was oriented to provide guidance to those sites that had reported through the Albuquerque Operations Office.  Upon stand up of the new NNSA organization, and the commensurate movement of management responsibilities from Operation Offices to Site Offices, it became necessary to update the Handbook to reflect NNSA’s new structure.

The Handbook is intended to provide LTS planning information for all EM projects at NNSA sites that will have LTS activities after EM mission completion.  Most of the LTS activities remaining at a site will related to environmental restoration, however, legacy waste and decontamination and decommissioning projects may also have LTS requirements.

This Handbook should be considered guidance for sites reporting through EP.  Although not guidance, the Handbook was also developed to provide beneficial planning information for the NNSA sites managed independently by the Site Offices.  Other sites are also welcome to use the Handbook as they find appropriate.

## LTS Background

The draft Long-Term Environmental Stewardship Strategic Plan (DOE, 2002a) contains long-term stewardship principles, goals, and objectives and both programmatic and site-specific planning assumptions. Strategic Plan implementation is accomplished by incorporating LTS principles and objectives into planning and operations, either through site-specific LTS plans or other existing planning efforts and baseline scope, cost, and schedule documentation. In addition, EM has distributed fact sheets providing guidance on EM Completion and Transition of Long-Term Response Action (LTRA) responsibilities. LTRA activities and responsibilities outlined in the fact sheets are synonymous with LTS activities and responsibilities described in this Handbook.

This Handbook outlines approaches for integrating LTS into baseline documentation, based on site-specific planning. However, until Secretarial policy regarding transition is finalized, the specific site steward for NNSA sites cannot be identified or assigned.

## Roles and Responsibilities

Organizational roles and responsibilities unique to LTS are:

- DOE Headquarters (HQ)

- EM is responsible for planning for LTS, including developing LTS cost estimates and ensuring all activities necessary for closeout of the EM projects have occurred.

- NNSA, as site landlord, is responsible for all mission activities at NNSA sites, including coordination with EM and the site steward on LTS activities at the sites.

- NNSA Service Center Environmental Programs Department (EP) is responsible for supporting the NNSA site offices and for directly managing several EM projects. EP provides technical and programmatic expertise to support planning, implementation, and transition to LTS. EP also provides integration between the projects, other sites and HQ; HQ advocacy; site office technical and programmatic support; and assists with budget development.

- Site Offices are responsible for LTS management, negotiating and evaluating performance measures, and incorporating LTS into management and operations (M&O) contracts.

- M&O contractors are responsible for executing LTS pursuant to site steward requirements.

- Other parties with a vested interest in LTS, including regulators, stakeholders, and other site tenants and lessees have responsibilities such as participating in advisory boards and providing land use planning input.

# DOCUMENTING LTS PLANNING ACTIVITIES IN THE BASELINE

Baseline documentation should include separately tracked and managed project scope descriptions, costs, and schedules for LTS. This separate tracking allows DOE to anticipate the resources necessary for LTS. Primary baseline planning activities include:

- Documenting EM Project closure activities and transition including preparing a Project Closure and Transition (PCT) Plan

- Defining LTS and the developing the LTS Plan

- Identifying LTS-phase activities, milestones, and life-cycle funding requirements.

LTS should be integrated into existing baselines, however, for budget purposes LTS for each project will be documented in a unique Project Baseline Summary (PBS). EM Project Closeout and LTS Phase baseline activities are described in Section 3.0. Figure 2.1 presents a generic timeline for EM Project completion and LTS activities.

Figure 2.1.  EM Completion and Transition

*The term LTS is interchangeable with Long-term Response Action (LTRA) as defined in the January 2003 EM Fact Sheet, “Definition of EM Completion and DOE Site Closure.”

The Integrated Planning, Accounting, and Budgeting System (IPABS) Handbook (DOE, 2002b) contains generic, nonspecific site guidance for preparing the LTS PBSs. EM developed the Long-Term Stewardship Plan Guidance for the Closure Sites (DOE, 2002c) and the Office of Legacy Management will be responsible, or share responsibility, for developing additional LTS guidance.

## PCT Plan and LTS Plan Preparation

DOE M 413.3-1 requires that “All projects shall have a project transition/closeout plan that clearly defines the basis for attaining initial operating capability, full operating capability, or project closeout, as applicable.” EM Project planning also requires the preparation of a LTS Plan during the transition period (Figure 2.1). The EM Project baseline should include the scope, cost, and schedule for all activities associated with preparing the PCT Plan, LTS Plan, and any other document affecting transition to LTS. If these plans have not been prepared, the scope, cost, and schedule for preparing them should be included in the baseline. Sites have flexibility regarding integration of LTS planning and LTS-phase activities into the work breakdown structure (WBS) since no specific guidance on the WBS structure has been provided by EM.

### PCT Plan– Documenting EM Project Closure and Transition

The PCT Plan is an internal document developed by project teams to ensure systematic, efficient, and complete EM Project closure. It states the necessary actions to administratively close-out the EM Project as required to meet DOE M 413.3-1, RCRA/Hazardous and Solid Waste Amendments of 1984 (HSWA), state, and other requirements.

The PCT Plan also describes the transfer process and LTS responsibilities to be transferred from EM to the site steward. The transfer process should take into consideration requirements for project closeout as described in DOE M 413.3-1 and the EM National Focus Project Fact Sheet, “EM Completion: Transitioning LTRA Responsibilities.”

When the project is complete, long-term remediation systems are operational, and surveillance, monitoring and maintenance activities are in place, DOE Order 413.3 Critical Decision-4 (CD-4) documentation will be submitted to obtain project closeout approval. The process and guidance for reaching CD-4 approval is provided in Appendix A. CD-4 is presented to the Acquisition Executive and the appropriate Energy System Acquisition Advisory Board (ESAAB). The NNSA sites’ Acquisition Executive is the Deputy Secretary (S-2). EM should coordinate with the site steward organization on CD-4 documentation to ensure readiness to assume LTS responsibility. Appendix B also includes an example PCT Plan outline and associated checklists, including a crosswalk to CD-4 prerequisites and post-closure activities.

### Defining LTS – The LTS Plan

LTS plans are public documents and the primary mechanism for describing LTS implementation. For this reason, LTS plans should be developed according to DOE P 141.2, Public Participation and Community Relations. Input should be solicited from stakeholders, including regulators and local government, and either incorporated or otherwise addressed. The LTS Plan also should be prepared in coordination with the site steward to facilitate smooth transition.

LTS Plans should be prepared during transition, well in advance of project completion (Figure 2.1) and can be written at  a summary level if adequate elements of LTS are described in other documents. Other documents may be cited (rather than reiterated) if they are reasonably retrievable. Health and safety, quality assurance, stakeholder involvement, emergency response, and other pertinent plans should be reviewed and modified, if necessary, to incorporate LTS considerations.

LTS plans should describe Site Office LTS requirements and list primary assumptions and risks. Regulatory acceptance documentation and a summary site status describing remedies and remaining hazards, risk assessment results, and performance criteria and limitations should be completed and included in the LTS Plan.  An example of how this information may be documented using a Response Action Reference Matrix is provided in the June 2003 National Focus Project Fact Sheet, “EM Completion: Transitioning LTRA Responsibilities.” Appendix C includes suggested LTS Plan contents and an example outline.

## Transitioning LTS Work

Transitioning LTS responsibilities will require early and frequent interaction between project personnel and the site steward. Scope, cost, and schedule for activities related to transition should be clearly documented in the baseline. Work elements related to transition are included in the following sections.

### Planning for Transfer

The documentation necessary for transfer should be discussed and agreed to with the site steward at least 3 years in advance of project closure. Project closure requires a CD-4 decision (Section 2.1.1). However, it may be necessary to formalize agreements prior to the submission of a CD-4 request. A Memorandum of Agreement (MOA) may be used to reach agreement on the transfer of LTS activities. If an MOA is used, it should include the steps and conditions necessary for project turnover, the organizations responsible for conducting LTS activities and the amount and timing of funds transfer. Guidance for developing an MOA and obtaining approval will be forthcoming. Even though the final decision on transfer is at the S-2 level, documents initially will be drafted by project personnel. Therefore, the activities associated with transfer, such as drafting a MOA and CD-4 package, should be incorporated in the EM project life-cycle baseline.

### LTS Plan Integration

Site steward staff should be involved during development of the LTS Plan to ensure acceptance of the document. EM project and site steward personnel should ensure that the LTS Plan and supporting documentation are compatible with site policies, procedures, and the Site-Wide Integrated Safety Management Plan, as applicable. Additional information about safety management and authorization basis can be found at http://www.doeal.gov/laaoabt/internet/GenInfo.htm.

### Information Management

Activities for transitioning and integrating EM information and records management should be included in EM project baselines, including records management required for LTS planning efforts. EM Project information such as PCT Plan-related archives, active files, and real estate data should be accessible for integration into site steward institutional environmental systems and procedures and the Site-Wide Integrated Safety Management Plan.

### Permitting Issues

Permit-related activities such as corrective action close-out, post-closure permits, state requirements, and other regulatory activities necessary to close the EM project should be included in project baselines as part of LTS planning. Project personnel should communicate with the site steward and regulators, as appropriate, to ensure that regulatory requirements and authorities are understood and clearly identified and documented. The PCT Plan should provide information on permit requirements and status. Also, the EM CD-4 template (Appendix A) requires a summary of the status of regulatory requirements prior to turnover.

### Programmatic Risks and Vulnerabilities

Programmatic risks and vulnerabilities such as remedy failure, federal tort liability, and other risks could significantly affect scope, schedule, and/or LTS costs. EM project and site steward personnel should identify and quantify programmatic risks in a Programmatic Assumptions Document. Examples of programmatic risk include:

- Active sites – Potential release sites (PRSs) that cannot be remediated because the area or facility is still operational. The current cleanup scope does not include active sites and therefore, they are not included in site baselines. Active sites are a programmatic risk because they should be remediated as they become inactive, posing a site steward management responsibility.

- Excess facilities – Process contaminated facilities that become excess after EM mission completion may be a site steward responsibility.

- Ongoing Comprehensive Environmental Response, Compensation, and Liability Act (CERCLA) issues – Several aspects of CERCLA could affect post EM completion costs. Natural Resource Damage Assessment (NRDA) liability could occur if natural resource trustees chose to pursue damages. CERCLA liability may also occur if waste management facilities used by DOE become Superfund sites.

- Newly identified PRSs – Site stewards may be responsible for PRSs identified after EM mission completion.

### Alternative Lessees, Tenants, and Stakeholders

EM Project personnel, the site steward, and NNSA should coordinate on issues affecting lessees, tenants, and stakeholders. The EM Project baseline should include scope, cost, and schedule for addressing potential issues with alternative lessees, tenants, or third parties that might have a vested interest or could be affected by transition or LTS activities. For example, SNL/NM maintains facilities and test sites on lands permitted by the U.S. Air Force and the U.S. Forest Service for use by DOE. Transition planning should include involvement and input from all such stakeholders.

### Budget Transfer

The site steward will need to request budget for LTS no later than 2 years in advance of EM project closeout. The LTS cost estimates contained in the approved EM baselines are identified in LTS PBSs in the IPABS database. No transfer of funds from EM to the site steward will take place as EM does not include the costs for LTS in its planning budget.

### Public Involvement

Public involvement will be necessary during LTS and should be performed in accordance with the policy DOE P 141.2. EM Project personnel should coordinate with the site steward on transition of public participation plans and public involvement issues such as disseminating information, public meetings, and reasonable public access to unclassified documents.

## Determining and Documenting LTS Phase Activities During the EM Project Phase

As identified in the EM National Focus Project Fact Sheet, “Definition of EM Completion and DOE Site Closure”, as response actions are completed projects and subprojects are transitioned to operations and maintenance (O&M). The time period during which response actions move from the EM Project to LTS is identified in Figure 2.1 as Transition. Sites should identify transition activities in the baseline WBS, including preparing the LTS Plan and PCT Plan and conducting site maintenance and interim O&M activities such as:

- Monitoring of landfills (e.g., ground water, methane)

- Maintenance of restricted use-area fencing

- Monitoring of ground water related to a specific PRS or engineered system.

Scope, cost, and schedule for O&M activities with regulatory-approved final decision should be included as part of the EM project in the baselines.

The EM Project baselines also should include activities for project turnover. Project turnover requires understanding and documenting engineering system requirements and performance evaluation, institutional controls, funding issues, and land use constraints. Documentation must be complete, controls in place, and systems operating according to regulatory and technical requirements prior to transfer to the site steward.

## Milestones

Project baseline schedules should present LTS start dates, end dates, duration of significant planning and LTS-phase activities, and milestones. LTS milestones include:

- Project completion date

- LTS Plan completion

- DOE approval of final radioactive-contaminated (only) PRS

- Submittal of final closure documentation to the regulatory authority

- Regulatory authority approval of the final closure document (e.g., the final permit modification request, Corrective Measure Implementation Report, or final No Further Action Report)

- Date of Resource Conservation and Recovery Act (RCRA) post-closure permit issuance, for sites under RCRA 40 CFR 265, Part G

- Estimated EM mission completion (same as LTS start date)

- Dates of active remediation system shut-down and transition to monitoring and/or closure

- Estimated LTS completion date

Milestones will be unique to each project, depending on project completion definitions, applicable regulatory requirements, and specific site features and contaminants of concern.

## Lifecycle Funding Needs

Sites will develop and annually update a funding estimate for LTS annual and lifecycle costs.  These costs will be captured in the LTS PBS for each project. Guidance concerning the number of years to consider in estimating lifecycle costs varies; however, when possible for planning purposes, sites should use known lifecycle periods supported by backup documentation. When the LTS lifecycle is not known, a 70-year planning window is recommended. Sites estimating LTS to extend more than 70 years should document duration expectations in appropriate baseline technical summary documents.

Sites may consider planning in terms of the 30-year RCRA post-closure monitoring period. However, monitoring does not necessarily end at the end of 30 years if contaminants in the monitored media are still present above standards. Thus, the 70-year period is intended to prevent stakeholder concerns that monitoring could be terminated after 30 years, regardless of remaining risk.

# LTS-PHASE BASELINE GUIDANCE

This section provides guidance for incorporating LTS requirements into program or project life cycle baselines.

## Work Breakdown Structure (WBS) Development

Sites should develop an appropriate LTS WBS. A national DOE-mandated LTS WBS does not currently exist, but Appendix D includes an example WBS and list of typical LTS activities and major elements that should be described in baselines. Sites are unique, both in project maturity and complexity. However, the template should be evaluated and useful components incorporated in baselines. The WBS outline also is useful for presenting and reporting LTS baseline requirements. WBS levels 5 through 9 are directly related to LTS and described in this document and Appendix D. WBS levels 1 through 4 are not described because they are not specific to LTS. WBS levels 1 and 2 identify EM HQ and the specific EM HQ program (i.e., ER or WM), Level 3 indicates that the work is done in either a plant or a laboratory, and Level 4 identifies a specific plant or laboratory. A WBS Level 5 LTS number is assigned for each site (see Appendix D example).

Site Offices are encouraged to estimate LTS activities to at least Level 6 to provide consistency within EM portions of baselines and facilitate reviews and validation of estimates.

LTS work has many activities in common with other EM project tasks, including project management, program and technical support, land use planning, monitoring and maintenance, scheduling, risk quantification and management, and cost estimating. This Handbook generally follows the example WBS template in Appendix D, which also includes graphics illustrating the WBS structure.

The following sections provide information associated with LTS-specific issues or activities. Specific guidance does not exist for all of the WBS levels and activities indicated in the template, but in most cases guidance is provided for WBS levels 6 and 7. Some WBS Levels 8 and 9 activities also are addressed.

### Project Management

Project management baseline documentation is described in the Project Control System Handbook.

### 3.1.2	Technical Management and Support

This section describes general baseline technical management and support requirements. Areas specific to LTS that could be included in the LTS portion of baselines are:

#### 3.1.2.1		Technical Evaluations

Appropriate technical evaluations should be performed during LTS to optimize opportunities and minimize duration and costs. Evaluations may be conducted for engineered system performance reviews, new technologies, integrating technologies, formal program reviews, and site-wide strategic planning. System performance reviews should be conducted and options developed to correct deficiencies, as necessary. Costs associated with performing formal reviews should be included in baselines.

EM work is dynamic and it is expected that closure strategies, identification of additional corrective action sites, and other closure-related issues will have an impact on LTS. Site-wide strategic planning options will be considered through ongoing evaluations and new technologies will be evaluated to identify potential applications at post-EM completion sites.

#### 3.1.2.2		Regulatory Support

LTS regulatory support costs included in baseline documentation will depend on the post-EM completion regulatory framework. Discussions with regulators regarding requirement should begin well in advance of LTS, to ensure adequate planning. Examples of regulatory support activities include:

- Routine scheduled meetings

- Preparing position papers on issues that could affect the LTS-phase of work

- Discussions and negotiations with regulatory personnel on emerging issues, strategies, and LTS completion

- Maintaining and updating permits

- Preparing reports for regulatory authorities.

The following websites provide information about potentially applicable Federal and DOE requirements. State and local requirements should also be considered.

- http://lts.apps.em.doe.gov/center/reports/pdf/overview_statutes_regs.pdf 
Major Environmental Statutes, Regulations, and Executive Orders for Long-Term Stewardship at DOE sites

- http://lts.apps.em.doe.gov/center/reports/pdf/DOE_Orders_Policies_Table.pdf 
Overview of DOE Order and Policy directives relevant to long-term stewardship

#### 3.1.2.3		Risk Assessment and Evaluation

Baseline documentation also may need to include post-EM completion risk assessment activities, such as:

- Evaluating the risk knowledge based on changes of facility operations, site-wide environmental issues, or unexpected conditions

- Monitoring and evaluating sites’ engineered systems performance during LTS and modifying systems or implementing alternate strategies when necessary

- Assessing human health and ecological risks associated with site performance and land use changes

#### Information Management

Information management activities documented in baselines should include activities, such as:

- Implementing and maintaining long-term storage and retrieval of electronic and hard copy data, reports, and correspondence

- Preparing and delivering internal project communications

- Designing and maintaining websites

- Maintaining accessibility to information by public, regulators, and others

#### Stakeholder Involvement

Planning and implementing LTS will require a credible, effective stakeholder participation process. This will include communication with the public, other tenants and site owners, and related parties. Activities that might be part of baseline documentation include:

- Planning and holding public meetings

- Preparing and distributing brochures, reports, updates, and other information

- Preparing official public notices for significant events or decisions

### 3.1.3	Land Use and Institutional Controls

Institutional controls are legal or administrative means of limiting access to, or warning of hazards associated with a property. Land use plan modifications, engineered remediation systems, resource management issues, or newly identified contaminated sites determine or affect institutional controls identified and documented in baselines. The EM Project should include integration of LTS issues and land use planning, including periodic reviews to ensure continuing validity of current institutional controls, in the baseline.

### 3.1.4	Site Wide Environmental Monitoring and Physical Controls

LTS activities not related to specific PRSs should be included in the LTS portion of baselines. Non-site specific post-closure environmental monitoring can be incorporated into the baseline by media type and should include a section describing physical controls, as appropriate. Media monitored during LTS could include groundwater, surface water, soils and sediments, and biota.

The organization of scope descriptions and associated resource sheets for monitoring activities will depend on the volume and complexity of work. However, the scope should be clearly defined and coordinated with site-wide monitoring plans to reduce potential redundancy.

### 3.1.5	PRSs With Engineered, Signed, and/or Fenced Units

Physical controls include barriers, fences, engineered systems, locked gates, or patrols used to protect human health and the environment. Sites with PRSs that require physical controls should be identified in the LTS portion of baselines through scope descriptions and resource sheets. The Appendix D WBS template distinguishes these PRSs according to the following Level 7 divisions:

- Signed and fenced units

- Engineered units

Signed and fenced units consist of structural controls and, as needed, security controls. These units are typically associated with sites that contain regulated substances above background or unrestricted use levels in surface or near surface soils, or sites that present a physical hazard. Examples include:

- Fencing restricting access at testing areas containing depleted uranium fragments from ordinance detonation, or firing sites containing residual lead or other heavy metal fragments; associated sign to post warnings

- Fencing around mineshafts, adits, and pits to restrict access; associated sign to post warnings

Controls providing protection from hazards present in surface or near surface soils that may or may not be implemented in conjunction with fenced units include:

- Native soil or vegetative covers to minimize erosion and infiltration of water through units with residual constituents of concern

- Berms to protect units from runoff and reduce erosion

Units requiring structural controls are generally low maintenance sites and depending on complexity and quantity, can be grouped for baseline documentation purposes. LTS activities include:

- Monitoring and maintenance – ensuring that physical controls are in place and effective, and repairing damaged areas

- Surveys and object removal – performing visual, radiation, and other survey methods to evaluate the presence of hazards. Object removal, including removing uranium fragments revealed by natural weather processes, might be required occasionally to reduce hazards

Engineered units contain engineered controls that detect, control, and/or contain contaminant migration or collect contaminants and can have monitoring systems to determine remedial system effectiveness. Generally, engineered units also have structural controls. Examples of engineered units include:

- Landfills with designed cover, caps, and or leachate collection and detection systems

- Contaminated areas with vadose zone extraction and monitoring systems

- Groundwater pump and treat systems to remove contaminants

- Other designed containment systems such as lined impoundments and barrier walls.

The scope of work required for monitoring and maintaining engineered unit systems can be significant. Thus, each engineered unit should have individual scope descriptions, schedules, and resource sheets. LTS activities may include:

- Monitoring and maintenance of engineered and structural controls

- Data management and reporting

- Evaluating system integrity

## Risk Management and Analysis

DOE O 413.3 and the Project Controls System Handbook contain risk analysis requirements. Risk analysis includes risk management, and analysis of both programmatic (out-of-scope) risks and contingency (in-scope risks). Project risks should be listed in the baseline. These risks should be organized into two categories:

- Risks that might occur during LTS but do not affect the LTS portion of work

- Risks that might occur as a direct result of LTS activities and engineered or structural controls

Costs due to risks not affecting LTS work or not a result of LTS activities are not included in the baseline lifecycle cost estimate. However, the risks should be identified in other LTS baseline documentation to make the LTS managers aware of potential project risks. Risks that might occur during the LTS-phase of work include:

- Active sites could become inactive, possibly requiring investigation and remediation work

- New sites might be identified that require mitigation

The risk of excess facilities becoming inactive and requiring decommissioning and decontamination should be documented as suggested in the D&D Handbook.

Risks that could affect LTS include:

- Unexpected system failures

- Remedial Actions that do not meet performance requirements

- NRDA liability suits

- Regulatory changes (e.g. changes in cleanup levels) affecting closure strategies or operations. (The long-term nature of LTS increases likelihood of regulatory changes.)

- Newly identified contaminants of concern

- New technologies that could eliminate risks or otherwise accelerate termination of LTS

- Changes in land use scenarios or conditions that affect closure (e.g. changes in future land-use from industrial to residential)

Risks should be described in baseline documentation, including estimates of potential effects on scope, schedule, and cost. The scope, schedule, and cost to develop and maintain a Risk Management Plan also should be included in LTS baselines.

## Schedule

Resource loaded project schedules are required for EM projects and should be included for LTS work. Refer to Project Control Systems Handbook for detailed information. EM IPABS guidance requires the schedule to include milestones as described in Section 2.5 Milestones.

## Cost Estimating

LTS activity-based cost estimates are required in EM baselines and should be included for LTS estimates. Refer to Cost Estimating Handbook for detailed guidance.

## Performance Measures

EM and the site steward will negotiate LTS performance measures. Examples of potential LTS-related performance measures include:

- Meeting post-closure permit dates

- Reduction in number of PRSs requiring LTS

# PROJECT REPORTING

The scope, cost, and schedule for project reporting required during LTS should be included in the baseline. EM Reporting requirements include updating IPABS-IS PEM, yearly updates and site monitoring and evaluation reports.  Some reporting through the Project Assessment and Reporting System (PARS) may be appropriate, although most LTS activities will not require PARS reporting. Reporting in the Facility Information Management System of certain LTS related information is also required.

## IPABS-IS PEM

IPABS-IS PEM data and reporting requirements have changed annually. EM will notify sites of new or changed requirements and performance measures. Project baseline summary managers and site managers need to be aware of these changes and provide timely input. The scope and cost of meeting IPABS-IS PEM reporting requirements should be presented in the baseline.

## Periodic LTS Updates and Performance Review

Yearly updates and reviews will proceed through the baseline change control process described in the Project Control System Handbook. The scope and cost to prepare the yearly baseline update should be budgeted in the baseline. The report should include the following:

- Engineering system and site-wide monitoring data results and interpretation

- Physical controls and systems operation descriptions, including significant issues affecting performance

- Significant changes in land use planning, institutional controls, and any other issue that could impact the baseline scope, schedule, or budget

- An explanation of expectations and accomplishments for the next year

LTS updates may also be necessary to:

- Ensure continued effectiveness of engineered and institutional controls

- Evaluate remedy controls to optimize maintenance and monitoring costs

- Minimize duplicative documentation

# REFERENCES AND RESOURCES

DOE G 1324.5B, Records Management Program, January 12. http://www.directives.doe.gov/cgi-bin/explhcgi?qry1981735854;doe-285

DOE P 141.2, Public Participation and Community Relations, May 2, 2003.

DOE Manual 413.3-1, Project Management for the Acquisition of Capital Assets, U.S. Department of Energy Office of Management, Budget and Evaluation, March 28, 2003. http://www.sc.doe.gov/sc-80/sc-81/man/intro.pdf or http://oecm.energy.gov/policies

DOE O 413.3, Program and Project Management for the Acquisition of Capital Assets, October 13.  http://www.directives.doe.gov/cgi-bin/explhcgi?qry1441935954;doe-114

DOE. 2002a. Long-Term Environmental Stewardship Strategic Plan, Revision 2, Draft. Albuquerque Operations Office, Office of Environmental Programs, March 6.

DOE. 2002b. IPABS FY 2002 Guidance Documents, Volume 2: FY 2002 IPABS Users Manual, Office of Environmental Management. https://ipabs-is.em.doe.gov/ipabs and https://ipabsreporting.em.doe.gov/

DOE. 2002c. Long-Term Stewardship Plan Guidance for the Closure Sites, Draft. Office of Environmental Management, May.

DOE 2003. Definition of EM Completion and DOE Site Closure. Office of Environmental Management Corporate Projects Initiative National Focus Project. January 2003.

DOE 2003. EM Completion: Transitioning LTRA Responsibilities. Office of Environmental Management Corporate Projects Initiative National Focus Project. June 2003.

DOE. 2003*. Baseline Review Handbook. National Nuclear Security Administration Service Center, Environmental Programs Department.

DOE. 2003*. Cost Estimating Handbook. National Nuclear Security Administration Service Center, Environmental Programs Department.

DOE. 2003*. Handbook for Integrated Project Management. National Nuclear Security Administration Service Center, Environmental Programs Department.

DOE. 2003*. Project Control System Handbook. National Nuclear Security Administration Service Center, Environmental Programs Department.

*	This document is available from NNSA Service Center EP. It is anticipated that this document will be published as a final document in 2003.

# Glossary

active site – a potential release site that is not addressed in the EM Project baseline because of its continued use.

baseline –Environmental Management Project life-cycle baselines

EM mission completion – Per FY2002 IPABS User’s Manual, Chapter 4,  (DOE, 2002b) and Definition of EM Completion and DOE Site Closure, Office of Environmental Management Corporate Projects Initiative National Focus Project (January 2003)

Mission complete indicates that the scope of the project has met the relevant criteria used for overall site completion (deactivation and decommissioning of all facilities have been completed, all releases to the environment have been cleaned up in accordance with agreed-upon cleanup standards, groundwater contamination has been contained or long-term treatment or monitoring is in place, nuclear materials and spent fuel have been stabilized and/or placed in safe long-term storage, and legacy waste has been disposed of in an appropriate manner). Each PBS is required to have a mission complete date.

engineered controls – designed remedial alternatives that inhibit or control the spread of contamination, contain or remediate the contaminated media, or control the infiltration of water at contaminated sites. Examples include pump and treat systems, landfill caps, and lined disposal cells.

excess facilities – facilities no longer needed for mission and/or at the end of their lifecycle use.

institutional controls – legal or administrative means of limiting property access or warning of hazards.

site steward – the organization or office that will be responsible for long-term stewardship at a site.

Memorandum of Agreement (MOA) – a written agreement between EM and the site steward describing conditions necessary for transfer of LTS.

Natural Resource Damage Assessment – a calculation of damages to natural resources resulting from a discharge of oil or a release of a hazardous substance covered under CERCLA (as amended by SARA) or the Clean Water Act, in order to recover damages from a responsible party or parties.

Project Closure and Transition Plan (PCT Plan) – an internal document developed by project teams to ensure systematic, efficient, and complete EM Project closure. It states the necessary actions to administratively close-out the EM Project as required to meet DOE M 413.3-1, RCRA/Hazardous and Solid Waste Amendments of 1984 (HSWA), state, and other requirements. DOE M 413.3-1 requires that “All projects shall have a project transition/closeout plan that clearly defines the basis for attaining initial operating capability, full operating capability, or project closeout, as applicable.”

physical controls – barriers, fences, engineered controls, locked gates, or patrols employed at PRSs to ensure protection of human health and the environment.

potential release site (PRS) – an area of land impacted by a hazardous substance. For this document, the term includes solid waste management units, areas of concern, operable units, and other specific areas requiring LTS

Response Action – activities necessary to address a potential risk to human health or the environment

Site office – Site offices are individual NNSA offices responsible for managing a site or sites. NNSA Site Offices include Los Alamos Site Office (LASO), Sandia Site Office (SSO), Pantex Site Office (PSO), Kansas City Site Office (KCSO), Lawrence Livermore Site Office, Nevada Site Office, Y-12 Site Office, and Savannah River Site Office.

structural controls – physical controls preventing access to or containing a PRS, including berms, fences, gates, walls, and warning signs.

transfer – the change of project management and control of LTS from EM to the site steward, occurring following EM Project close-out, usually represented by a milestone.

transition and closeout  - as specified in DOE Manual 413.3-1, the progression of a project from implementation to turnover for operations. For EM projects, initial operating capability may be defined as the transition to long-term maintenance and surveillance. This occurs at Critical Decision-4.

Appendix A - Critical Decision-4 Turnover and Closeout Requirements and Template

The following template is provided to assist in preparing for a Critical Decision-4 (CD). The CD-4 decision is a briefing presented by the Site Manager or Federal Project Director to the Acquisition Executive (AE), who is either the Deputy Secretary (S-2), Under Secretary (S-3), or the Assistant Manager for Environmental Management (EM-1) and the appropriate Energy System Acquisition Advisory Board (ESAAB).

The project type will dictate the requirements and information that needs to be presented to the ESAAB. For Environmental Restoration and Decommissioning and Decontamination projects or sites, CD-4 requires the following:

- the cleanup activities have been completed,

- the EM completion criteria met,

- regulators and stakeholders are satisfied,

- regulatory documents (releases, permits, licenses, agreements, etc.) are current,

- buildings and land are in the agreed upon condition,

- receiving organization is ready to assume responsibility,

- funds are available for post-closure activities,

- documents and contracting officer authority transferred (if necessary),

- staffs have transitioned, and

- all parties are in agreement that the project or site is ready for the acquisition executive to approve the turnover from one organization to another.

The following CD-4 Transition (Turnover)/Closeout template outlines information that is required by 413.3 and addressed by the ESAAB. Because the board is comprised of senior managers, the briefing should be developed in appropriate detail. Back-up slides and additional detail should be available if questions are asked or additional information requested.  In addition, a decision memorandum should be prepared from the Site Manager through EM-1 and the Under Secretary, if the Deputy Secretary is the Acquisition Executive . Conditional approvals may also be granted (i.e. approval granted when certain conditions are met or actions completed).

Critical Decision-4 Transition (Turnover) and Closeout

- Project/Site Name: Name of project or site to be turned over

- Date: ESAAB Meeting Date

3. Project/Site Location :  City and state

4. Field Office: Managing Field Office

5. Releasing HQ Organization: Program Office releasing the project or site (EM)

6. EM Completion Date: As defined in the National Focus Project Fact Sheet, “Definition of EM Completion and DOE Site Closure”.

7. Receiving HQ Organization:  Program Office receiving the project or site (i.e., Office of Science)

8. Site Closure Date (if known): Enter a date or TBD

9. Planned Turnover Date: Enter the date the project or site is scheduled for turnover

10. State & Federal Regulatory Authorities: Enter the names of State and Federal Regulator organizations (i.e., New Mexico Environment Department, EPA)

11. Describe Project/Site Turnover Agreements:

Identify pre-CD-4 turnover agreements such as prior CD decisions, MOAs, or Memorandums and include copies. Summarize key elements of agreements, such as turnover requirements, site conditions, turnover packages, spare parts, documents and records, vendor data, and key dates.

12. Describe Item(s) Being Turned Over, and the Current Condition of Each Item:

Include buildings and facilities as well as areas (i.e., technical areas) and current condition (i.e., greenfield, restricted use, limited access, use restrictions, etc.). For line item construction projects, verify that the facility, equipment, or system has been checked, tested and evaluated, commissioned, has undergone an operational readiness review with deficiencies corrected, and has a final safety analysis report. Operating and maintenance procedures, trained staff, project records, design packages, and documents transferred to operators or occupants must also be included.

13. Summarize the EM Scope of Work Performed for Turnover Including EM Completion Criteria: Example: Demolished buildings 123 and 567 and shipped all contaminated debris offsite; capped Pond A with YY, buried 10 tons of LLW in an onsite landfill in Area B, and developed a groundwater remediation strategy.

14. Summarize the Receiving Organizations Scope of Work Including Any Work Started By EM and Being Completed by Receiving Organization (if applicable):

Example: Groundwater monitoring in areas A&F will be done by the receiving organization from MM/YY to MM/YY, experiments on XX will be conducted in Lab ZZ until MM/YY, waste generated after MM/YY will be disposed by the receiving organization. Also describe steward responsibilities and list planning (such as the LTS Plan) and regulatory documents that must be revised, closed, transferred, or obtained from state or federal organizations.

15. Summarize Any EM Scope Of Work That Will Extend Past the Turnover Date, if applicable:

Example:  Ship final four tons of soil to XX on MM/YY, obtain final release for Area A from the Department of Health, resolve all contract and closeout issues, budget actions, and final reports.

16. Summarize the Status of Regulatory Requirements for Turnover Item(s), if applicable:

Identify the status of regulatory requirements such as permits, licenses, reports, and federal facility agreements for facilities, buildings, or areas being turned-over, including actions (i.e., closed, pending, transferring to receiving organization, etc.).

17. Are Resources Available and in Place for Turnover (staff, funds, and facilities):

Provide both organizations’ prior year, turnover year, and next year funding profiles for turnover item(s) and describe any issues, such as funds transfers, reprogramming actions, or shortfalls. Include staffing levels, staffing plans, and transition of federal staff (transfers, relocations, new hires, RIFs, etc.). Describe training that has been provided and verify that staff is in place and ready to assume responsibility. Verify that administrative facilities have been transferred, equipped, and are ready for staffing, if applicable.

18. Identify Outstanding Items that must be Completed to Finalize EM Completion and Turnover, if applicable:

Example: Transfer $200K from EM to Office of Science, complete report on XX, and modify the permit for ZZ.

NOTE: If the information requested is already provided in another document, reference the document and attach a copy.

References:  As a Reference and Guide to completing turnover utilize the Long-Term Stewardship Site Acceptance Criteria and Environmental Cost Element Structure

DOE Manual 413.3-1 Chapter 7

This page is intentionally blank.

Appendix B - Project Closure and Transition Plan Content and Checklists

The PCT Plan should describe the project transition, covering the following topics and including adequate documentation of applicable prerequisites for Critical Decision-4 (DOE M 413.3-1, Section 7.9.1) and management agreement for final fiscal cost and administrative closure:

- Authorities and responsibilities – describe EM, NNSA, and regulators’ responsibilities, including responsibilities of specific personnel for meeting closure actions and provision of a trained and qualified operations and maintenance staff.

- Records management – present records management requirements and procedures for ensuring EM activities are properly documented through project completion. Records document project completion, minimize future legal liability, and guide work during LTS. Records management must comply with National Archives and Records Administration policies and DOE Guidance 1324.5B.

- Regulatory activities – detail regulatory procedures and requirements for achieving closure of various types of impacted areas. Closure requirements differ for areas of concern closed under the formal RCRA process (e.g., Corrective Action Management Unit), through voluntary corrective actions, or by DOE (radioactively-contaminated only sites). Information should also be provided on permit requirements and status.

- Disposition of government property – address actions required for ensuring all excess equipment and materials are disposed of in accordance with DOE property disposition regulations and internal site requirements.

- Financial closeout – detail closeout requirements for subcontracts and permits.

- Project completion report - document site conditions describing remedies and remaining hazards, results of human health and ecological risk assessments, and verification of performance criteria and limitations.

- Final Safety Analysis Report or other appropriate safety documentation.

- Operating and maintenance procedures.

- Completed acceptance testing documentation, including corrected deficiencies.

- Completed readiness assessment or operational readiness review.

EM project managers should consistently use a closure checklist and project record checklists for ensuring documentation requirements, including those satisfying DOE M 413.3-1 Prerequisites for Critical Decision-4.

Example Closure Checklist

| Category | Description | ( |
| --- | --- | --- |
| Records | Submit LTS related project records to the Site Steward. Submit other project records to the Records Center for archiving. | ( |
|  | Review records inventory list with the Federal Project Director for completeness. | ( |
|  | Provide Repository with current contact information (telephone number, organization). Review and change ownership of the information in the project databases (site tracking, compliance, case management, lab, etc.). | ( |
|  | Provide designated record owner information to the Records Center. | ( |
| Property | Submit subject property information and recommended reapplication to the Project Manager. | ( |
|  | Redirect any property and equipment purchases to the Site Steward. | ( |
| Financial | Confirm post-CD-4 requirements are budgeted for by receiving organization | ( |
|  | Close out all reimbursements. | ( |
| Performance Criteria EM Completion Criteria | Verify performance criteria have been met. Meet with Project Control Specialist to review status, any outstanding action items related to the baseline (baseline review, etc.). | ( |
|  | Review and update all scope documents and underlying assumptions. | ( |
|  | Review and brief the Site Steward on the regulatory status of each site. | ( |
|  | Conduct field tour with Site Steward to brief the history and status of each site. | ( |
|  | Discuss all sources of information and their location to the Site Steward. | ( |
|  | Meet Site Steward to identify and resolve any transition issues. | ( |
| General Administrative | Meet with Administration Team for financial and contracting closeout review. | ( |
| Management Review | Meet with project manager, Federal Project Director, and Site Steward to review completion of each checklist item. | ( |
|  | Review final standing with respect to Transition Plan | ( |

Appendix C - Example LTS Plan Outline

Appendix C contains an example outline for LTS plans. LTS plans should refer to, rather than duplicate, documents and plans that provide detail, minimizing the need to update more than one document as plans change. LTS plan appendices should be used to provide detail.

1.0	Introduction

| Objectives | State the purpose of the LTS and how it should be used. |
| --- | --- |
| Scope | Describe physical boundaries addressed by the plan and the breadth of activities it encompasses. Include map(s). |
| LTS Plan Summary | Summarize key aspects of the LTS Plan. A timeline may be helpful to depict anticipated events. |
| Limitations/ Assumptions | Describe limitations and assumptions associated with potential funding, technical, and political issues. |
| Authority and History | State authority under which the LTS is written and will be maintained. Summarize how the LTS plan was developed |

2.0	Site Description

| Background | Summarize operational history including former occupants and operators, what operations were conducted and when, contaminants that were generated and media affected, and acquisition history. Summarize remediation history including cleaning up site contaminants; closing, stabilizing, and decontamination and decommissioning (D&D) of onsite facilities. |
| --- | --- |
| Physical Setting | Describe relevant geology, hydrogeology, topography, and climate. Provide the location and characteristics of natural, archaeological, and cultural resources. |
| Real Estate | State the location, legal description, and boundaries. Describe adjacent ownership, liens, property rights, or other real estate issues associated with the site. Describe current land use and land use agreements. |
| Risk Based End State Vision | Summarize the Risk Based End State (RBES) Vision that was developed as required by DOE Policy 455.1. |
| Affected Community | Describe nearby communities and affected by the site, including employment history, growth, and economic relationship of the site and community. |

3.0 	LTS Approach

| Site Conditions | Describe anticipated conditions at EM project completion, including units that will have engineering, institutional, and physical controls. Describe discrete LTS-managed areas, location, and residual and physical hazards. State assumptions associated with site end state. |
| --- | --- |
| Land Use | Describe current and future land use and restrictions. Describe how the engineered, institutional, and physical controls will affect land use; potential land use changes as engineering controls progress; land uses restrictions; and offsite areas that are directly impacted by LTS activities. Include map(s). |
| Conceptual Site Model | Summarize the current understanding of known or potential contamination problems by diagramming the conceptual site model describing relationships between contaminant sources, release mechanisms, exposure pathways and routes, and receptors. Use the Conceptual Site Model that was developed as part of the RBES Vision. |
| Engineered, Institutional, and Physical Controls | Describe each engineered, institutional, and physical control and how it will be being implemented and maintained. Include anticipated effectiveness of each control, surveillance and maintenance activities, and roles and responsibilities for maintaining the controls. Reference other documents describing controls. |
| Monitoring | Describe media to be monitored, frequency, response thresholds, and integration with the Site steward’s Site-Wide Monitoring Program. |
| Risk Management | Discuss uncertainties associated with LTS and how they are managed, including factors such as regulatory changes, onsite and offsite land use change, failures in controls, technology effectiveness, changes in ambient subsurface conditions, and changes in facility use. |

4.0	LTS Management

| Roles and Responsibilities | Identify groups responsible for LTS site and administrative activities (include document management) and describe their responsibilities. Include regulatory agencies responsible for enforcing LTS activities. Describe the site steward management and LTS management teams. |
| --- | --- |

5.0	Regulatory Framework and Authorities

| Legal Authorities | The legal authorities under which LTS will be conducted should be identified and tied to LTS activities. Refer to documents prepared under those authorities. Include contracts with private parties (e.g., land access agreements). These websites provide information about potentially applicable requirements. State and local requirements should also be researched. http://lts.apps.em.doe.gov/center/reports/pdf/overview_statutes_regs.pdf - Federal http://lts.apps.em.doe.gov/center/reports/pdf/DOE_Orders_Policies_Table.pdf - DOE |
| --- | --- |
| Compliance Plan | Describe regulatory framework considerations (e.g., decision logic and criteria for changes in sampling plans or required reporting). |

6.0	Information Management

| Communication Plan | Describe communication required between LTS managers, site workers, regulators, and the public. Include reporting requirements. Include or reference a points of contacts list. |
| --- | --- |
| Records Management | Describe electronic and physical records management systems. Identify records to be managed (e.g., LTS plan [and revisions], sampling and surveillance and maintenance data, audit reports, training records, legal agreements, permits). Identify how and where records will be stored and accessed. |

7.0	Health and Safety

| Worker Safety | Describe a health and safety program including health and safety training requirements. Reference health and safety plan or provide as an appendix. |
| --- | --- |
| Public Safety | Refer to access restrictions described in the institutional controls section. |
| Emergency Response | Describe emergency response capabilities and arrangements with local, state, and Federal response programs. |

8.0	Quality Assurance

| QA Plan | Summarize and reference the LTS Quality Assurance Plan. |
| --- | --- |

9.0	LTS Funding and Scheduling

| Funding Sources | Describe known and anticipated LTS funding source(s) and management. |
| --- | --- |
| Costs | Provide cost estimates and assumptions. |
| Schedule | Provide schedule for LTS activity start and end dates, including milestones and anticipated dates. |

LTS Plan Appendices

The example below provides information may be contained in LTS Plan appendices. Appendices should be used to describe specific remedies or provide information not contained in existing, cited documents.

Example Site-Wide Groundwater Monitoring System

Description, Goals, and Uncertainties

Location and Legal Description

Conceptual Site Model

Regulatory Framework

Closure Goals/Contingency Plans/Corrective Actions

Assumptions and Uncertainties

Land Use Restrictions/Institutional Controls

Operation and Maintenance

Surveillance

System Operations

Sampling

Well Maintenance

Data Analysis and Reporting

Cost and Schedule for Site-Wide Groundwater Monitoring

Appendix D - Example WBS Template

| Handbook Section | Example WBS Levels and Work Elements |
| --- | --- |
| 3.1 | Level 5 (1.4.2.6.4.) – Site LTS Summary |
| 3.1.1 |  | Level 6 – Project Management |
|  |  | Level 7 – Management Budget Personnel Reporting (DOE/Site steward) |
|  |  | Level 7 – Baseline Development Programmatic Issues Scope Schedule Budget and Cost Estimating |
|  |  | Level 7 – Administrative Support |
|  |  | Level 7 – Project Controls |
|  |  | Level 7 – Legal Support |
| 3.1.2 |  | Level 6 – Technical and Management Support |
| 3.1.2.1 |  | Level 7 – Technical Evaluations Strategic Planning Technology Reviews, Integration, Deployment System Performance Reviews Contingency and Corrective Action Plans Five-Year Reviews |
| 3.1.2.2 |  | Level 7 – Regulatory Support RCRA/CERCLA Issues NRDA Issues NEPA Issues State and Other Regulatory Issues and Requirements |
| 3.1.2.3 |  | Level 7 – Risk Assessment and Evaluation Site Performance and Land Restrictions Human Health Assessments Ecological Assessments |
|  |  | Level 7 – Health and Safety, Quality Assurance, Training |
|  |  | Level 7 – Geographic Information Systems |
| 3.1.2.4 |  | Level 7 – Information Management Updating Site Conditions Records Management Website Development |
| 3.1.2.5 |  | Level 7 – Stakeholder Involvement Communications with Lessees and Other Site Owners Public Participation |
| 3.1.3 |  | Level 6 – Land Use and Institutional Controls Task Management Land Use Management Plan and Reviews Resource Management Active Sites and Surplus Facilities |
| 3.1.4 |  | Level 6 – Site Wide Environmental Monitoring and Physical Controls |
|  |  | Level 7 - Task Management Level 7 – Ground Water Monitoring Sampling Well Maintenance Structural Controls Maintenance Equipment and Supplies Data Management and Reporting |
|  |  | Level 7 – Surface Water Monitoring Sampling Structure Maintenance Structural Controls Maintenance Equipment and Supplies Data Management and Reporting |
|  |  | Level 7 – Air Monitoring Sampling Structure Maintenance Structural Controls Maintenance Equipment and Supplies Data Management and Reporting |
|  |  | Level 7 – Soils and Sediments Monitoring Sampling Structural Controls Maintenance Equipment and Supplies Data Management and Reporting Level 7 – Biota/Other Monitoring |
|  |  | Level 7 – Structures, Engineered Systems, and Physical Controls Sampling Structural Controls Maintenance Equipment and Supplies Data Management and Reporting |
| 3.1.5 |  | Level 6 – PRSs with Engineered Units and/or Signed and Fenced Units |
|  |  | Level 7 – Signed and Fenced Units Task Management Surveys (i.e., radiation, visual) Sampling Structural Controls Monitoring Equipment and Supplies Data Management and Reporting |
|  |  | Level 7 – Engineered Units |
|  |  | Level 8 – Example: Landfill with Leachate Collection, Vadose Zone Extraction, and Ground Water Monitoring |
|  |  | Level 9 – Leachate Collection System Operation and Maintenance Sampling Structural Controls Monitoring Equipment and Supplies Data Management and Reporting |
|  |  | Level 9 – Vadose Zone Extraction and Monitoring Operation and Maintenance Sampling Structural Controls Monitoring Equipment and Supplies Data Management and Reporting |
|  |  | Level 9 – Ground water Monitoring Operation and Maintenance Sampling Structural Controls Monitoring Equipment and Supplies Data Management and Reporting |
|  |  | Level 8 – Example: Former Disposal Cell, Ground Water Pump and Treat and Monitoring |
|  |  | Level 9 – Ground Water Pump and Treat System Operation and Maintenance Sampling Structural Controls Monitoring Equipment and Supplies Data Management and Reporting |
|  |  | Level 9 – Ground Water Monitoring Monitoring Well Maintenance Structural Controls Maintenance Equipment and Supplies Data Management and Reporting |