20 April 2005

To:	Paul Philp, DOE Project Manager, Run IIb D-Zero Detector Project

From:	Vivian O’Dell, Project Manager, Run IIb D-Zero Detector Project

Subject:	Run IIb D-Zero Detector Project Report for February 2005

Attached is the monthly report summarizing the February 2005 activities and progress for the Fermilab RunIIb D-Zero Detector Project.

electronic cc:

M.	Abolins

J.	Appel

E.	Arroyo

L.	Bagby

E.	Barberis

A.	Bean

J.	Blazey

A.	Bross

W.	Cooper

M.	Demarteau

D.	Edmunds

T.	Erickson

H.	Evans

S.	Fuess

G.	Ginther

U.	Heintz

M.	Hildreth

R.	Hirosky

D.	Hoffer

K.	Johns

M.	Johnson

- Knapp

R.	Lipton

J.	Livengood

P.	Lukens

R.	McCarthy

H.	Montgomery

M.	Narain

A.	Nomerotski

V.	O’Dell

P.	Padley

R.	Partridge

V.	Pavlicek

TJ	Sarlina

R.	Sidwell

P.	Slattery

K.	Stanfield

RP	Smith

J.	Strait

L.	Stutte

E.	Temple

C.	Trimby

V. 	White

M.	Witherell

D.	Wood

T.	Wyatt

C.	Yoshikawa

Fermi National Accelerator Laboratory

Run IIb D-Zero Detector Project

Fermilab Experiment Number E925

Progress Report No. 27

February 2005

- Project Description

The Tevatron Collider at Fermilab offers a unique capability to elucidate many of the major issues currently facing particle physics. Its high center-of-mass energy and recently upgraded luminosity offer us the capability of shedding light on the Higgs mechanism - which has the potential of offering insight into the origin of mass - and pushing the boundaries of searches for supersymmetry and other new phenomena beyond the Standard Model.  It also makes accessible improved precision measurements of the W boson and top quark properties that, by further constraining the Standard Model, provide increasingly stringent tests of its precepts.  The Tevatron offers the most cogent experimental probes of Standard Model physics, and beyond, during the coming 3+ years.

The Run IIb D-Zero Detector Project has been designed to allow the D-Zero Experiment to continue operating in the high intensity Tevatron environment for the remainder of the coming decade. The integrated exposure of the D-Zero Detector to colliding beam will result in radiation damage to the silicon detector that will compromise its efficiency. Adequate b-tagging is an essential ingredient of the Run II physics program. In order to maintain adequate b-tagging, D-Zero is adding an inner layer detector of radiation-hard silicon to enhance tracking efficiency as the Run IIa detector ages. In addition, the trigger system must be upgraded in order to provide sufficient rejection and to limit the dead time at the higher instantaneous rates that will be delivered by the Tevatron as the run progresses. The Run IIb D-Zero Detector Project provides for the additional D-Zero Layer 0 silicon detector and the upgrade of the D-Zero trigger, DAQ, and online systems in order to enable the continued efficient running of the experiment, and the acquisition of forefront physics data, for the foreseeable lifetime of the Tevatron collider program.

- Overview of Project Status

All production hybrids have been burned in at KU and shipped to FNAL. All production digital jumper cables have been received from Compunetics. The 1% test stand has been moved to Lab C and work has started to read out up to 48 channels (the full L0). Mechanical, thermal and flow measurements were made on the L0 support structures and analysis of the data is underway. Design of fixturing for module installation progressed and designs for the fixturing for installing the Layer 0 in the DZero detector were developed and will be pursued both at FNAL and U. Washington.

The Production Readiness Review for the ADF was held on February 11th. No changes to the preproduction version of the board were suggested, and the board went into production Feb 18th. The first assembled production boards are expected back during the first week of March.

Meanwhile, the EM algorithm in the TAB firmware is being debugged. A TAB/GAB crate + TAB board + GAB board + all the ADF to TAB cables were sent from Columbia to Fermilab for the integration tests on the sidewalk.

The Cal Track-Match testing found some problems with two of the UFB boards and they were returned to the assembler. There are also problems with the JTAG testing of the MTCxx and this has generated some schedule slip. The crate manager testing was successfully completed and this board is now ready to be tested at DZero. The DFEA2 boards of the L1CTT upgrade passed their Production Readiness Review on Feb. 14th and the boards are going into production. Two DFEA2 boards have been tested on the platform. The old and new DFEA boards (RunIIa and RunIIb versions) give identical results with identical inputs using the RunIIa (doublet) algorithm. The next step will be to put singlet equations in the new board. Testing of the L2 Beta boards with fake inputs at 1 kHz was done during two weeks of continuous operation. New firmware for tracking events as they arrive at the Betas was verified during this testing.

Much of the trigger simulation software needed to simulate the Run2b trigger is now in preliminary version. Data from a special run at higher luminosity was taen for the trigger rate tool verification. Extrapolations from lower luminosity data are in reasonable agreement with higher luminosity data, giving some confidence in the validity of the results. Testing continued on the AFEIIt prototype board. Testing of the TripT prototype chips are complete and the chip will be ready for production submission soon.

In the online group, plans for upgrading the L3 nodes were finalized and a purchase for 96 new nodes was submitted. Infrastructre upgrades needed to install the nodes were begun. Orders for the additional CPU needed for the server and host systems have been placed. Disk storage options are being studied. Approximately half of the control system upgraded PowerPC’s were in hand in the beginning of February and and order was placed for the remaining SBC’s.

- Project Milestone Summary (as of 28 February 2005)

The DOE baseline milestones are shown in Figure 1 as solid diamonds.  These fixed milestones are defined in the modified DOE Project Execution Plan approved in December 2003.  Shown as open diamonds on the same line, are the project’s projected dates for achieving the milestones.  Actual dates of achieving milestones are shown as solid stars.  The silicon, trigger and online milestones are shown separately with milestones sorted by current forecast date.

Table 1 shows the difference in the current forecast and last month’s forecast for achieving the DOE milestones. This table lists approved DOE milestone dates along with the project’s current (and previous month’s) forecast for achieving them. The list is sorted by DOE Milestone date. Milestones with forecast dates that have changed significantly in the last month are discussed in Section IX of this report.

Figure 1:  Run IIb D-Zero Detector Project DOE Level 2/Director’s Milestones.  Closed (open) diamonds represent baseline (current forecast) dates.  Closed stars represent completed milestones.

| L2/Director's Milestones vs Current Forecast |
| --- |
| (Sorted by L2/Director's Baseline Date) |
| Milestone Description | L2/Director's Baseline (2/05) | Last Month's Forecast (1/05) | This Month's Forecast (2/05) | L2/Director's Variance (work days) | Monthly Variance (work days) | Notes |
| WBS 1.2 Trigger |  |  |  |  |  |  |
| L1 Calorimeter Trigger TAB/GAB Prototyping Complete | 05/03/04 | 05/26/04 | 05/26/04 | 18 | 0 | Complete |
| Start Production TAB Fabrication | 02/25/05 | 10/08/04 | 10/08/04 | (90) | 0 | Complete |
| L2 Silicon Track Trigger Production and Testing Complete | 10/17/05 | 06/21/05 | 06/21/05 | (82) | 0 |  |
| L1 Trigger Cal-Trk Match Production and Testing Completed | 01/03/06 | 05/09/05 | 06/01/05 | (142) | 16 |  |
| L1 Calorimeter Trigger Production And Testing Complete | 01/05/06 | 07/15/05 | 07/15/05 | (114) | 0 |  |
| L2 Beta Trigger Production And Testing Complete | 01/05/06 | 06/15/05 | 08/08/05 | (98) | 37 |  |
| L2 Trigger Upgrade Production and Testing Complete | 01/05/06 | 06/21/05 | 08/09/05 | (98) | 33 |  |
| L1 Central Track Trigger Production And Testing Complete | 01/10/06 | 09/08/05 | 09/08/05 | (79) | 0 |  |
| L1 Trigger Upgrade Production and Testing Complete | 04/10/06 | 09/08/05 | 09/08/05 | (141) | 0 |  |
| WBS 1.3 Online/DAQ |  |  |  |  |  |  |
| Online System Production and Testing Complete | 10/07/05 | 06/17/05 | 05/23/05 | (96) | (18) |  |
| WBS 1.6 Layer 0 Silicon Detector |  |  |  |  |  |  |
| Freeze Mechanical Parameters | 01/06/04 | 12/15/03 | 12/15/03 | (9) | 0 | Complete |
| Release Sensors for Production | 05/26/04 | 02/26/04 | 02/26/04 | (63) | 0 | Complete |
| Release Hybrids for Production | 06/04/04 | 03/25/04 | 03/25/04 | (50) | 0 | Complete |
| Release Analog Cables for Production | 06/04/04 | 03/19/04 | 03/19/04 | (54) | 0 | Complete |
| All Analog Cables Delivered and Tested | 03/11/05 | 08/10/04 | 08/10/04 | (141) | 0 | Complete |
| All Sensors Delivered and Tested | 05/23/05 | 09/28/04 | 09/28/04 | (159) | 0 | Complete |
| All L0 Hybrids Delivered, Stuffed, and Tested | 08/25/05 | 01/25/05 | 01/25/05 | (150) | 0 | Complete |
| All Adapter Cards Delivered and Tested | 10/17/05 | 03/18/05 | 03/18/05 | (148) | 0 |  |
| Silicon L0 Module Production Complete | 11/29/05 | 04/22/05 | 04/22/05 | (151) | 0 |  |
| Layer 0 Silicon Detector Ready to Move to DAB | 05/25/06 | 09/09/05 | 09/09/05 | (173) | 0 |  |
|  |  |  |  |  | status date: | 2/28/2005 |

Table 1:  Run IIb D-Zero Detector Project DOE Level 2/Director’s Milestones vs. Current Month and Previous Month’s forecast.  Entries are sorted by DOE L2/Director’s Milestone date.  Monthly variances are also provided.

- Management Highlights – V. O’Dell

A Director’s review of the DZero RunIIb upgrade project was held February 4-5. We are working on incorporating the comments from the review. In particular, including the L0 installation fixturing into the project is being done and canvassing the project to see where money can buy schedule is ongoing.

The ADF passed its PRR on Feb 18th and has gone into production. The L1CTT DFEA2 boards  passed their PRR on Feb 11th and is also going into production. The AFEII project has now gone through the internal DZero reviews and we are working on scheduling a Director’s review.

Procurement Highlights – V. O’Dell

The L3 node procurement started in February ($200k). The PowerPC procurement was also started in February ($100k). We are planning to updated the University of Washington’s MOU/SOW to reflect adding the installation tooling. This will likely cost about $80k

- Trigger Highlights (WBS 1.2) – B. P. Padley, D. Wood

There was significant progress on all subtasks during February.  The last board for the calorimeter trigger upgrade was released for production after a successful review.  Likewise, the main component of the CTT upgrade, the DFEA2 board, was approved for production.

  - Level 1 Calorimeter Trigger (WBS 1.2.1) – M. Abolins, H. Evans

The Production Readiness Review of the ADF v2 boards was held on February 11.  The review committee was satisfied with the board design and the tests on the pre-production versions.  They had no modifications to suggest and the boards were therefore released for production on February 18th.  We expect the first few assembled production boards to arrive at MSU during the first week of March with the rest of the boards showing up one to two weeks later.

Nevis continued work on implementing the new EM algorithm in the TAB firmware.  A first attempt at this implementation was tried, but was found to have unexpected behavior.  Solutions to these are being pursued.

In anticipation of the upcoming integration tests at Fermilab, a substantial fraction of the TAB/GAB system hardware was shipped to the Lab.  This shipment included: the TAB/GAB crate, a TAB, a GAB, and all the ADF-to-TAB cables.

Work on the Run IIb L1Cal infrastructure also continued at Fermilab during February.  Power distribution to the area was completed and work started on equipping the five Run IIb L1Cal racks with crates and rack monitor interfaces.

  - Level 1 Calorimeter/Track Matching (WBS 1.2.2) – K. Johns

Bench (loop) testing of the first production MTCM crate manager was completed.  We will next test this card in the L1CalTrack crate at D0 during spring break.  The UFB flavor boards were assembled.  JTAG testing found two bad cards that were returned to the assembler.  JTAG testing of the production MTCxx cards ran into additional problems.  This testing is complicated because of the numerous JTAG chains on the board with many devices.

  - Level 1 Track Trigger (WBS 1.2.3) – D. Lincoln, M. Narain

DFEA2 - DFEA2 passed the production review readiness on Feb 14th.  As a result, we obtained quotes for the production parts and started to place orders.  As expected, the item with the largest lead time – 8 weeks- are the power converters.  The minor modifications to the production version of the board layout were completed.  Quotes for production of PCB were obtained and the order placement process was initiated with the BU purchasing office.

In-situ testing Status – Two DFEA2 boards have been tested on the platform.  With fibers and cables mapping resolved, the old (DFEA) and new (DFEA2) boards give identical results to identical inputs (for doublet equations).  This is an important step in confirming the satisfactory operation of the new board.  The next step is to put on singlet equations onto the new boards.

Test Stand – Work has started to understand the software and test procedures needed for testing of the production boards at FNAL.  With the addition of Norik Khalatyan (BU), commissioning prospects have picked up, although the L1CTT group still seeking additional postdoc support, presumably from Fermilab.

  - Level 2 Beta (WBS 1.2.4) – R. Hirosky

Tests continued of the new Beta with fake data (two weeks of continuous operation at an event input rate of ~1KHz).  Data were continuously processed through the L2 calorimeter jet and electron algorithms with no errors.  The fake events generate a factor of 10 or more objects than real data, and no slow downs or processing glitches were observed.

New firmware from Orsay was verified during the above tests.  This firmware provides a new tool to track events received by the Betas as they arrive in pieces from multiple broadcast sources.

  - Silicon Track Trigger (WBS 1.2.5) – U. Heintz

There is no significant progress to report since the last update.

  - Trigger Simulation (WBS 1.2.6) – E. Barberis, M. Hildreth

There was significant progress on the L1CTT and L1Cal simulators during this month focused on improving the underlying IIa trigger simulator framework software.  A preliminary version of the new L1CTT simulator (in its IIa incarnation) was released and is foreseen to be available for further testing in March.  The design of the interface to the IIb equations was also briefly discussed.  The L1Cal simulator was interfaced with the L1CalTrack simulator.  Testing is underway from the L1CalTrack side.  The next step in the work on the L1Cal simulator is the interface to L2.  A proposal and a commitment was made to write a first version of the new L2 software which interfaces to L1Cal by April, when we hope to have a first  version of all simulators (excluding L2STT) as an integrated chain.

Work has also progressed on the trigger terms studies using the trigger rate tool.  A new run, taken at a higher luminosity, is now available for the calculation of the predicted rates at 20E30.  We compared the rates estimated with the old run to the rates estimated with the new one and found reasonable agreement, indicative of no deviation from linearity in the extrapolation of rates to higher luminosity.  We documented the electron algorithms studies in a D0 internal note, and concentrated on the study of trigger terms containing jets: either multijet, or jets plus a muon.  We used the trigger rate tool on Monte Carlo simulation in order to estimate the efficiency of the different terms on different signal samples.

  - Analog Front End II (WBS 1.2.8) – A. Bross

Testing continues on the AFE II prototypes.  All the boards (21) have now been loaded and will be available for test and evaluation.  Testing and evaluation of the TriPt prototype chips is complete.  Only one change (output buffer amp) has been identified for the engineering run.  We will be ready for submission in March.  Actual March submission will depend on approval from the Fermilab Directorate.

- DAQ/Online Highlights (WBS 1.3) – S. Fuess

  - Level 3 Systems (WBS 1.3.1) - D. Chapin, G. Watts

During February 2005 we finalized plans for the purchase of nodes for the Level 3 processing farm.  A requisition for 96 nodes, at a cost of ~$200K, was submitted.  The requisition package, modeled on Computing Division offline farms purchases, included the complete specification and bid package.  [The requisition was approved at all levels on 21-Mar-2005, and is now in the hands of Fermilab Purchasing.]  We also initiated the infrastructure improvements required to support the new nodes, with an electrical upgrade [scheduled on 28-Mar-2005] and air conditioning upgrade [completed 10-Mar-2005].

We also continue to follow the performance metrics for the Level 3 filter code, in consideration of a possible need for Level 3 computing capacity beyond the 96-node purchase now in progress.  New versions, each with incrementally greater functionality yet better performance, are being introduced approximately monthly.

  - Network and Host Systems (WBS 1.3.2) – J. Fitzmaurice, S. Krzywdzinski

Control and Monitoring systems: 1.3.2.2, 1.3.2.3

There were no scheduled tasks in this area during February.  Considerable operational experience with the new systems is being obtained with the current system.

Storage, DAQ Host, ORACLE, & File Server Systems: 1.3.2.4, 1.3.2.6, 1.3.2.7, 1.3.2.8

We continue to improve the operational performance of the Linux Cluster systems that are the backbone of the central computing functions.  Problems with the RedHat Cluster software that we utilize have been addressed in recent updates.  We are migrating to the latest version as opportunity allows.  In general, these central systems are now operating extremely well, supplying adequate computing capacity with a high degree of reliability.

The complete RunIIb plan calls for an augmentation of the minimal central system configuration now in operation.  Six servers are being added to the four operational clusters (DAQ, Database, File Server, and Online functions).  The new servers will provide the computing capacity needed for the duration of RunIIb, plus give a much-needed configuration flexibility.  The requisitions for the purchase of these systems and peripherals were submitted in February.  [The systems have been ordered, with delivery expected 18-Apr-2005.]

We are also investigating the options for completing the disk storage requirements.  We have quotes for a variety of system configurations and vendors, and are studying the characteristics of each system.  We expect to make storage purchases in April, 2005.

  - Control Systems (WBS 1.3.3) – F. Bartlett, G. Savage, V. Sirotenko

We are in the process of purchasing Motorola PowerPC mv5500 processors for the Control System upgrade.  Approximately 50% of the new nodes were in hand at the beginning of February.  A requisition for the remaining nodes was submitted in February [and has been in the hands of Fermilab Purchasing since 17-Mar-2005].

  - DAQ/Online Management (WBS 1.3.4) – S. Fuess

This is a continuing task for the long term management activities of the DAQ/Online subsystem.

- Silicon Detector Layer 0 Highlights (WBS 1.6) – A. Bean, R. Lipton

  - Readout (WBS 1.6.2) – A. Nomerotski, R. Sidwell

All production hybrids have been burned in at KU and shipped to Fermilab.  In total, about 100 hybrids are ready to be used for the module production.  All production digital jumper cables have been received from Compunetics.  Evaluation of the cables is in progress.

Three racks with 1% test stand have been moved into the Lab C clean room and work started to set up all necessary infrastructure to read out up to 48 (whole L0) channels.  The stand is located in the vicinity of both the L0 assembly table and the prototype support structure with 10 mounted L0 modules so can be used to readout both.

  - Mechanical Design and Fabrication (WBS 1.6.3) – W. Cooper

Dimensional and load measurements continued on the second layer 0 support structure.  Programs developed for analysis of the first support structure were transferred to Kansas State University, where analyses of coordinate measurement machine data of the second structure will be done.  Thermal and flow measurements were completed on both Layer 0 support structures.  Analysis of the measurements should be completed shortly.

The design of fixturing to hold the support structure during module installation progressed well. Except for details of end rings for the support structure rotating fixture, designs were completed and prepared for fabrication.  Fixtures to install sensor – hybrid modules on the L0 support structure were received.  CMM measurements of connector alignment on hybrids and other hybrid mechanical parameters were made.  Techniques to align cables on hybrids were reviewed in order to accommodate the precision with which the connectors are aligned.

Dimensions for final spacers to position hybrids were proposed and distributed for comment.  Spacers will be ordered as soon as comments are evaluated.

Procedures and tooling to install L0 at D0 had been discussed in a joint Fermilab and University of Washington meeting.  Two approaches for fabricating the main Layer 0 installation tool were developed.  Both approaches will be pursued, one at Washington and the other at Fermilab, in order to ensure that a sufficiently accurate tool will be available at the earliest possible time.

As a side-effect of BTeV cancellation, a significantly increased level of engineering support became available for Layer 0.  A tentative matching of task assignments and technical personnel was developed in order to ensure the new personnel will be used effectively.  The increased level of technical support should be significant in ensuring that Layer 0 will be completed on schedule.

  - Detector Modules and Final Detector Integration (WBS 1.6.4, 1.6.5) – L. Bagby

The HV power supply problems reported last month were due to loose connections on the crate backplane. One HV crate, with a complete compliment of pods, has been installed in the test stand at SiDet. The other HV crate is ready for installation in MCH2.

The LV isolated power supply system at SiDet is operational. The supply is configured to provide power to the Interface Board and the Adapter Card. Readout tests can now be performed through the entire system rather than with only with a ‘purple card’.

Schedule Variance Analysis (as of 28 February 2005)

Schedule variances are reported against director’s milestones in section III.  Nine milestones have already been successfully achieved.  All remaining milestones are projected ahead of the DOE baseline dates.

  - D-Zero Run IIb Trigger Upgrade (WBS 1.2)

The Cal Track-Match upgrade lost 16 days in the last month due to problems found during testing of the boards. However, this upgrade is currently scheduled to end on June 1, 2005, well ahead of the shutdown schedule, so there is some slack in the schedule. We will continue to closely monitor it’s progress. The L2 Beta lost 37 days in the last month. However considerable progress has been made and the board that is now under test appears to work well. The L2 Trigger upgrade milestone slip of 33 days in the last month is just a reflection of the L2 Beta upgrade slip.

  - D-Zero Run IIb Online (WBS 1.3)

There is no unfavorable schedule variance for this subproject.

  - D-Zero Run IIb Layer 0 Upgrade (WBS 1.6)

There is no unfavorable schedule variance for this subproject.

- Department of Energy Milestones (as of 28 February 2005)

No additional milestones were predicted or achieved during the month of February.  Table 2 shows the status of the DOE Milestones.

| L1 DOE Milestones vs Current Forecast |
| --- |
| (Sorted by L1 Baseline Date) |
| Milestone Description | L1 Milestone (2/05) | Last Month's Forecast (1/05) | This Month's Forecast (2/05) | L2/Director's Variance (work days) | Monthly Variance (work days) | Notes |
| WBS 1.2 Trigger |  |  |  |  |  |  |
| L2 Trigger Upgrade Production and Testing Complete | 01/05/06 | 6/21/2005 | 08/09/2005 | (98) | 33 |  |
| L1 Trigger Upgrade Production and Testing Complete | 04/10/06 | 09/08/2005 | 09/08/2005 | (141) | 0 |  |
| WBS 1.3 Online/DAQ |  |  |  |  |  |  |
| Online System Production and Testing Complete | 10/07/05 | 06/17/05 | 05/23/05 | (96) | (18) |  |
| WBS 1.6 Layer 0 Silicon Detector |  |  |  |  |  |  |
| Layer 0 Silicon Detector Ready to Move to DAB | 05/25/06 | 9/09/2005 | 9/09/2005 | (173) | 0 |  |
|  |  |  |  |  | status date: | 2/28/2005 |

Table 2:  Run IIb D-Zero Detector Project DOE Level 1 Milestones vs. Current Month and Previous Month’s forecast.  Entries are sorted by DOE L1 Milestone date.  Monthly variances are also provided.

- Cost Performance Report (as of 28 February 2005)

This report is generated from COBRA and provides a summary of the WBS 1.2-1.4 costs of the Project down to Level 3 of the Work Breakdown Structure.  Silicon detector subproject closeout costs are not tracked here.  Input data originates with the status (% Complete) of the Project schedules as reported by the Level 2 managers and actual costs extracted from the Fermilab accounting system.  Where possible, costs are accrued for items that have been delivered, but not yet invoiced. Financial summaries are shown for this reporting period (columns 2-6) as well as the project to date (columns 7-11).  Column 12 contains our baseline BAC, and will only be changed after the formal implementation of the Change Control process.  Column 13 is the projected BAC, based on the current month’s schedule.

- Obligation Reports (as of 28 February 2005)

The DZero Obligation Reports can be found below. The first report shows total obligations without the cost of the original Run IIb silicon and related closeout costs. The second report shows all obligations.