## Pipeline Projects
Major Russian Oil Pipeline Projects
Name | Length (miles) | Cost | Current Capacity (th. bbl/d) | Expected Capacity (th. bbl/d) | Location | Completion Date | Notes
Adria Reversal Project | 470 | $300 Million for expansion. | 100 | 300 | Central Europe (Hungary, Slovakia) to Croatian Adriatic Port of Omisalj | Unknown - but once approval given--> immediate | Environmental hold-up in Croatia; Unlikely to move forward
CPC - Caspian Pipeline Consortium Expansion | 940 | $1.5 billion | 540 | 1330 | Kazakhstan to Novorssiysk, RF | 2009 | Some agreements made, but still held up due to Russian insistence on higher tariffs
Baltic Pipeline System (BPS-II) | 1600 | $500 million | 1000 | 1300 | Exports from Timan-Pechora region via Baltic Sea port of Primorsk and/or Ust-Luga | 2011 | Latest export capacity of 1.2 million bbl/d
Kharyaga-Indiga | 320 | $2-6 billion | 0 | 500 | Baltic Sea (NE of Primorsk) |  | Transneft proposal. Not ice-free like Murmansk.
Murmansk | various | $6 billion | 0 | 3000 | Baltic Sea (NE of Primorsk) | none | Project for pipeline and terminal - Lukoil pipeline proposal, lost out to Indiga route
Eastern Pipeline (Taishet-Skovorodino-Perevoznaya) | 2480 | $16-18 billion | 0 | 1000 | Phase 1: Taishet to Skovoronio (near Lake Baikal). Phase 2: Skovorodino to Pacific Coast | 2009 (First Stage) | 2 stages: first to Skovorodino, and then to Pacific Coast. Environmental concerns with Lake Baikal and Perevoznaya Bay