## Schedule
| Lead | 2003-04-21 | 2003-04-28 | 2003-05-05 | 2003-05-12 | 2003-05-19 | 2003-05-26 | 2003-06-02 | 2003-06-09 | 2003-06-16 | 2003-06-23 | 2003-06-30 | 2003-07-07 | 2003-07-14 | 2003-07-21 | 2003-07-28
Resolution of Critical Chits | Neumeyer | bar: 2003-04-21 to 2003-05-05
Start Conductor Machining | Chrzanowski | bar: 2003-04-28 to 2003-05-19
Pull-out tests in Cu (w/o inserts) | Kalish | bar: 2003-04-21 to 2003-05-05
Cyclic Pull-out tests, Inserts & Cu | Kalish | bar: 2003-04-28
Collar Bond Improvements & shear tests | Kalish | bar: 2003-05-05 to 2003-05-19
Cyclic Collar Shear Tests | Kalish | bar: 2003-05-12
Cyclic Friction Tests | Kalish | bar: 2003-05-19
Prepare Mech Prototype | Kalish | bar: 2003-04-21 to 2003-05-19
Test Mech Prototype | Kalish | bar: 2003-05-19 to 2003-05-26
Elec Testing Peer Review | Baker | bar: 2003-06-02
Prepare Elec Prototype | Baker | bar: 2003-06-09 to 2003-06-30
Test Elec Prototype | Baker | bar: 2003-07-07 to 2003-07-28
Develop Est for Continuous Joint Monitoring | Marsala | bar: 2003-04-21 to 2003-05-19
Design Review & Decision Point on Cont Mon | Marsala | bar: 2003-05-26
Fabrication of Cont Joint Monitoring System | Marsala | bar: 2003-05-26 to 2003-07-28
Complete Chit Resolution | Neumeyer
Peer Review - TF Flag and Box | Chrzanowski | bar: 2003-05-12 to 2003-05-19
Peer Review - Shear Shoe/Fasteners | Chrzanowski | bar: 2003-05-19
Peer Review - Hub Assembly | Chrzanowski | bar: 2003-05-26
Peer Review - Bundle Fabrication & Assy | Chrzanowski | bar: 2003-06-02
Final Design Review | Neumeyer | bar: 2003-07-28
Original plan
Progress
Done
| Torque Collar Decision | 2003-04-21: 23; 2003-04-28: 24; 2003-05-05: 25; 2003-05-12: 26; 2003-05-19: 27
|  | 30 | 1 | 2 | 3 | 4
| Peer Review: Analysis | 2003-04-21: 7; 2003-04-28: 8; 2003-05-05: 9; 2003-05-12: 10; 2003-05-19: 11
|  | 14 | 15 | 16 | 17 | 18
| Comp Tests Complete | 2003-04-21: 21; 2003-04-28: 22; 2003-05-05: 23; 2003-05-12: 24; 2003-05-19: 25
| Preliminary Package inc'l Chit Resolution | 2003-04-21: 28; 2003-04-28: 29; 2003-05-05: 30; 2003-05-12: 31; 2003-05-19: 1
| Dry Runs, Review | 2003-04-21: 4; 2003-04-28: 5; 2003-05-05: 6; 2003-05-12: 7; 2003-05-19: 8

## Agenda
Welcome | R Goldston |  | 8:30 | 15 | 15 | 8:30
Introduction | C Neumeyer | Overview of Design Review | 8:45 | 15 | 15 | 8:45
Overview | C Neumeyer | Old v. New Design | 9:00 | 30 | 30 | 9:00
| " | Loads and Load Paths |  |  | 0 | 9:30
| " | Old v. New Design |  |  | 0 | 9:30
Design | J Chrzanowski | Description/Fabrication/Assembly | 9:30 | 30 | 30 | 9:30
| M Kalish | Fasteners | 10:00 | 15 | 15 | 10:00
Break |  |  | 10:15 | 15 | 15 | 10:15
Inspect TF Bundle at D-site | J Chrzanowski |  | 10:30 | 30 | 30 | 10:30
Structural Analysis | I Zatz | Structural FEA | 11:00 | 60 | 60 | 11:00
Lunch |  |  | 12:00 | 60 | 60 | 12:00
Thermal/Electrical | A Brooks | Thermal/Electrical FEA | 13:00 | 15 | 15 | 13:00
Component Testing | M Kalish | Pull-Out Tests | 13:15 | 20 | 20 | 13:15
| " | Collar Shear Tests |  |  | 0 | 13:35
| " | Friction Tests |  |  | 0 | 13:35
| " | e-beam Tensile Tests |  |  | 0 | 13:35
Prototype Mechanical Tests | M Kalish | Prototype Mechanical Tests | 13:35 | 10 | 10 | 13:35
Instrumentation | H Schneider | Joint Voltage Drop Instrumentation | 13:45 | 15 | 15 | 13:45
Prototype Electrical Tests | E Baker | Prototype Electrical Tests | 14:00 | 15 | 15 | 14:00
Discussion/Chit Resolution | Committee |  | 14:15 | 90 | 90 | 14:15
Debriefing | Committee |  | 15:45 | 30 | 30 | 15:45
Adjourn |  |  | 16:15 |  | 0 | 16:15

## SuperChits
SC# | Summary | Action
1 | Measure contact surfaces of existing assembly to determine achievable precision | Chrzanowski
2 | Can voltage taps pick up locally high contact resistance at far corner? | Neumeyer/Brooks
3 | Add upper tier to FEA model, include proper friction between box and flag, consider out of plane loads, perform analysis over the range of conditions to establish design margins and operating envelope, analyze 2-out-of-3 load path cases, express margin as contact pressure/req'd contact pressure, exercize model with fit-up variations, cyclic loading may cause friction joint to "walk" causing more load to be passed to shear pin | Zatz
4 | How are allowables for collar wet lay-up derived from test data? | Kalish
5 | Use actual distribution of contact pressure in analysis of joint heating | Zatz/Brooks
6 | Analyze bundle stress considering back-back cooling tubes | Zatz
7 | Add insert strip behind coolant tube to improve hoop pressure distribution | Chrzanowski
8 | How will operating envelope be chosen to ensure Tpeak<120C, given variability of contact resistance? Consider temperature monitoring, reconsider design assumption for nominal contact resistance, establish upper limit on allowable joint resistance during maintenance measurement | Neumeyer
9 | Document design criteria, considering creep and fatigue at elevated temperatures, copper fatigue criteria should be based on 120C, establish allowables and performance for shear shoe connection | Zatz
10 | Perform cyclic testing at elevated temperature | Kalish
11 | Use Fuji paper to confirm adequate pressure, see if fabrication tolerances are such that joint contact is maintained everywhere | Kalish
12 | Quantify spline load with thermal expansion of inner leg, confirm that it always helps | Zatz
13 | If spline shows no scuffing, are the lateral loads being taken by the flex joints (which would load the flags?) | Zatz
14 | Test max/min friction coefficient | Kalish
15 | Are box bolts to ring modeled discretely or is the model merged? | Zatz
16 | Include loads due to eddy currents in hubs | Neumeyer
17 | Consider shear dog | Kalish
18 | Investigate sleeve bladder to eliminate seals at ends of boxes during potting | Chrzanowski
19 | Consider Inconel 718 studs preloaded to 0.9 yield , add more bellevilles, is bolt hotter than flag at any time during pulse sequence? | Kalish
20 | Analyze pitting on existing flags to understand cause | Dudek
21 | Need to perform fatigue tests on collar wet lay-up | Kalish
22 | Consider removal of centerstack to facilitate TF reassembly, perform schedule impact | Chrzanowski
23 | Is there enough room for a stud tensioner? Are the studs long enough? | Kalish
24 | Run taplok tests at actual bolt-to-taplok engagements | Kalish
25 | Consider continuous monitoring of joint resistance, consider strain gauges to measure stresses in hub to determine load distribution, install linear position sensors to measure thermal displacement of TF inner leg assembly | Marsala
26 | Consider use of threaded shear keys | Kalish

## Chits
# | SC# | Origin | Summary | Action
1 | x | Anderson | Analyze bolted joint at end of e-beam welded flag | e-beam dropped
2 | 1 | Anderson | Measure contact surfaces of existing assembly to determine achievable precision | Chrzanowski
3 | 2 | Reiersen | Can voltage taps pick up locally high contact resistance at far corner? | Brooks
4 | 3 | Reiersen | a. Add upper tier to FEA model | Zatz
| 4 |  | b. How are allowables for collar wet lay-up derived from test data? | Kalish
5 | 5 | Reiersen | Use actual distribution of contact pressure in analysis of joint heating | Zatz/Brooks
6 | 6 | Dudek | Analyze bundle stress considering back-back cooling tubes | Zatz
7 | 7 | Titus | Add insert strip behind coolant tube to improve hoop pressure distribution | Chrzanowski
8 | 3 | Reiersen | Perform analysis over the range of conditions to establish design margins and operating envelope | Zatz
9 | 8 | Reiersen | How will operating envelope be chosen to ensure Tpeak<120C, given variability of contact resistance? Consider temperature monitoring. | Neumeyer
10 | 8 | Reiersen | Reconsider design assumption for nominal contact resistance. | Neumeyer
11 | 9 | Reiersen | Document design criteria, considering creep and fatigue at elevated temperatures | Zatz
12 | 3 | Reiersen | Comprehensive assessment of design margins lacking. | See 8
13 | 10 | Reiersen | Perform cyclic testing at elevated temperature | Kalish
14 | x | Reiersen | Perform friction tests on prototype joint | Disagree
15 | 9 | Reiersen | Copper fatigue criteria should be based on 120C | See 11
16 | 3 | Titus | Express margin as contact pressure/req'd contact pressure | Zatz
17 | 11 | Titus | Use Fuji paper to confirm adequate pressure | Kalish
18 | 12 | Titus | Quantify spline load with thermal expansion of inner leg, confirm that it always helps | Zatz
19 | 13 | Titus | If spline shows no scuffing, are the lateral loads being taken by the flex joints (which would load the flags?) | Zatz
20 | x | Titus | a. Perform fatigue test on e-beam weld | e-beam dropped
| 14 |  | b. Test max/min friction coefficient | Kalish
| x |  | c. Add fillet radius to e-beam joint | e-beam dropped
21 | 3 | Titus | a. Analyze high friction-no thermal case | Zatz
| 15 |  | b. Are box bolts to ring modeled discretely or is the model merged? | Zatz
| 3 |  | c. Exercize model with fit-up variations | Zatz
| 3 |  | d. Include proper friction between box and flag | Zatz
22 | 16 | Titus | Include loads due to eddy currents in hubs | Neumeyer
23 | 3 | Titus | Concern about high friction case | See 21a
24 | 11 | Titus | Perform local analysis of interface to see if fabrication tolerances are such that joint contact is maintained everywhere | See 17
25 | 17 | Voss | Consider shear dog | Kalish
26 | 18 | Titus | Investigate sleeve bladder to eliminate seals at ends of boxes during potting | Chrzanowski
27 | 19 | Titus | a. Consider Inconel 718 studs preloaded to 0.9 yield | Kalish
| 19 |  | b. Add more bellevilles | Kalish
28 | 3 | Hawryluk | a. Consider out of plane loads | Neumeyer/Zatz
| 3 |  | b. Consider high friction, low termperature case | See 21a
29 | 20 | Dudek | Analyze pitting on existing flags to understand cause | Dudek
30 | 3 | Bell | What is min contact pressure without shear key and box? | See 8
31 | 21 | Dudek | Need to perform fatigue tests on collar wet lay-up | Kalish
32 | x | Voss | Run transient analysis for e-beam welded joint | e-beam dropped
33 | 22 | Hawryluk | Consider removal of centerstack to facilitate TF reassembly. Perform schedule impact. | Chrzanowski
34 | x | Hawryluk | FMEA for e-beam welded joint | e-beam dropped
35 | 23 | Hawryluk | Is there enough room for a stud tensioner? Are the studs long enough? | Kalish
36 | x | Titus | Add fillet radius to e-beam joint. | e-beam dropped
37 | x | Voss | Add fillet radius to e-beam joint. | e-beam dropped
38 | x | Irby | Electro-form instead of e-beam weld. | e-beam dropped
39 | 24 | Dudek | Run taplok tests at actual bolt-to-taplok engagements | Kalish
40 | 25 | Irby | Consider continuous monitoring of joint resistance | Marsala
41 | 11 | Irby | Use contact film (Fuji paper) | See 17
42 | 26 | Voss | Install linear position sensors to measure thermal displacement of TF inner leg assembly | Schneider
43 | 26 | Anderson | Recommend monitoring of thermal growth of centerpost | See 42
44 | 16 | Voss | Consider strain gauges to measure stresses in hub to determine load distribution | Zatz/Marsala
45 | 3 | Voss | Cyclic loading may cause friction joint to "walk" causing more load to be passed to shear pin | Zatz
46 | 8 | Petersen | Establish upper limit on allowable joint resistance during maintenance measurement | Neumeyer
47 | x | Bell | Maintain 2kV CHI capability | Out of scope
48 | 19 | Bonanos | a. Is bolt hotter than flag at any time during pulse sequence? | Kalish
| 20 |  | b. Does bolt carry current and lengthen? | Neumeyer
| 19 |  | c. Add more belleville washers in series | See 27b
49 | 9 | Reiersen | Establish allowables and performance for pin connection | See 11
50 | 26 | Reiersen | Conduct pre-ops tests with deflection measurements to confirm predicted behavior | Neumeyer
51 | 20 | Irby | More analysis needed of pitting damange | See 29
52 | x | Mueller | Consider use of short bolts and making the flags more flexible | Disagree
53 | 27 | Lewicki | Consider use of threaded shear keys | Kalish

## Tasks
| MDays | FTE
Baker | 30 | 0.4 | Elect Proto Tests
Messino | 8 | 0.10667
Baker Techs | 9 | 0.12
Brooks | 5 | 0.066667 | Chits 3, 5
Chrzanowski | 5 | 0.066667 | Chits 2,7,26,33
Chrz Techs |  | 0
Dudek | 0 | 0 | Chit 29
Kalish | 60 | 0.8 | Pull-out tests | Collar tests | Friction tests | Mech Proto tests | Chits 4b,13,17,20b,25,27,31,35,39,48a,48c,53
Kalish Techs |  | 0
Marsala | 60 | 0.8 | Cont Monitoring Estimate | Chits 40,44
McBride | 30 | 0.4 | Elect Proto Tests
Meighan | 10 | 0.13333 | Pull-out tests | Collar tests | Friction tests
Neumeyer | 50 | 0.66667 | Chits 9,10,22,28,46,48b,50 | Document calculations
Schneider | 75 | 1 | Pull-out tests | Collar tests | Friction tests | Mech Proto tests | Elec Proto tests | Chit 42
Zatz | 75 | 1 | Chits 4,5,6,8,11,16,18,19,21,28b,44,45