August 7, 1999

Silicon Subsystem Report

July 1999

Subsystem Manager’s Summary (M. Gilchriese)

Cost and Schedule Summary Status

Milestones corresponding to the baseline schedule are marked with a *. Additional milestones are included, and will be included, as needed to monitor progress

    - Pixel System

Costs are within allocated limits. Seven of 12 prototype sectors from Energy Science Laboratory, Inc have been delivered but the rate is slower than desired. The planarity uniformity of some sectors is not within specification and iterations with ESLI are partly responsible for the delay. The fabrication of the first prototype disk support ring is near completion, and final machining should be completed by mid-August and the ring delivered to LBNL for inspection and measurement. Preparations for testing a full disk with dummy heat loads and cooling accelerated rapidly in July. A suitable power supply(1kW), chillers and instrumentation were either found, ordered or specified for tests at LBNL and coordinated with Hytec, Inc that will perform TV holographic testing at their facility. Final drawings for fabrication of two prototype frame panels and the connecting joint were completed by Hytec, Inc and tooling preparations for assembly are underway at Allcomp, Inc. Although we are some months behind the baseline schedule (particularly for fabrication of the first prototype ring), progress remains steady and we addressing many of the systems issues that must be solved to fabricate real disk structures. At the moment, we don't foresee a long term impact on the mechanics schedule from these delays. However, the cooling interface(nominally a non-US responsibility) remains a major concern. The validation of evaporative cooling made at the review in May has led to the tentative adoption of C3F8 as the nominal working fluid(for both pixels and SCT), although other fluids are still being tested. This fluid requires an 8-10 bar pressure to operate and, although the pressures within the pixel structure are much less than this(nominally 3-4 bar), we remain very concerned about startup and fault conditions that may cause an overpressure within the pixel structure itself. At best overpressure would result in permanent deformations of the low mass structure, and, at worst, rupture of the cooling lines or connections. We are in the process of urging the ID management to perform a failure analysis ASAP and are trying to determine what expertise we can bring to this as part of a review. Should this process drag on beyond about November, we will be delayed in our part of the mechanical design.

The 2nd round prototype sensors are under fabrication with one vendor and should begin shortly with the second. How these sensors will be studied in detail remains to be determined since they will be delivered too late for testing in the usual SPS beams. At a minimum laser testing will be done, but this type of testing still needs to correlated carefully with assemblies already tested in the beam. New Mexico has volunteered to try to take the lead in this. Alternative test beam locations are under study but with little enthusiasm, pending the outcome of laser testing.

Considerable progress was made in solving the last problems before submitting the FE-D IC to Temic for fabrication. The origin of the large time dispersion seen in existing prototype chips is now understood and reproduced in simulation, and has been fixed. Other circuit problems are also now understood and fixed, and FE-D is in the final verification and simulation stage with submission expected by mid-August and delivery(with incentive payments made) planned for mid-October. The collaboration has agreed on a plan to begin work on the Honeywell version(FE-H) as best it can given the continued absence of Technical Assistance Agreements with European groups. According to Honeywell, no new concerns have been raised(yet) by the U.S. government, and TAA approval should occur sometime between mid-September and mid-November. We are planning on the later date and have organized the available design team as best possible under the circumstances. It will be some months before we have a handle on the real schedule for FE-H submission.

We continue to experience delays with the US vendor(R&D Circuits) of the flex 1.x hybrid. Production of 1.x is on schedule at CERN after some initial delay, and tested parts should be delivered by the end of August. This will be barely in time to assembly flex modules for the September test beam period(starting around September 20). Additional vendors are being investigated in the US.

Planning for production module assembly is proceeding slowly. Among the most difficult issues is the dispensing of adhesive that glues the flex hybrid to the back of the sensor on a module. This must be done carefully and to relatively high precision to both allow automated wire bonding on a good, hard surface and to avoid putting glue in undesirable spots on the sensor. A number of methods have been tried and rejected, and now a precision gluing station is being designed at LBNL. The difficulties we had thinning recent dummy wafers have been understood to be faults in the wafer fabrication, not the thinning process. New dummy wafers are under fabrication and we expect to thin the first full FE-B wafers in August as well. We have re-evaluated the module envelope dimensions including uncertainties in the dimensions of the thinning, passive components, flex hybrid, etc. The layout of the barrel region is very sensitive(to the few hundred micron level) to the module envelope dimensions and we are studying the trade-off between a conservative module envelope, which reduces the acceptance for low PT tracks and an aggressive envelope that assumes success in thinning, finding smaller components, etc. We hope this process converges by the end of September. At the same time we expect final simulation results comparing a 300 micron-pixel-length B-layer with a 400 micron one.

    - Silicon Strip System

Cost are within allocated limits(including recent BCPs). For a change, the news is, so far, encouraging on the IC electronics. The CAFE-P continues to perform well. Six CAFE-Ps have been mounted successfully on a hybrid with old digital read-out chips from the SSC era and the performance is good. Good results were obtained just at the end of the month when connecting these chips to a 12 cm detector. Threshold uniformity, noise values and stability all look good. One of these chips was irradiated to 17 Mrad and the performance is still good. The result of negotiations with Temic regarding the ABCD wafers that had three potentially relevant parameters out of spec was (1) delivery of two wafers for free to CERN for testing and (2) agreement to reprocess a lot for delivery by mid-September. It is expected that the parameters out of spec will not affect the performance and so far this is borne out by measurements. The new ABCD with trim DACs in each channel to adjust the threshold (to be more uniform) are stable even without backside metallization  and appear to function well (pre-rad) in all respects tested so far on a handful of chips. Six ABCDs have been mounted on a hybrid and tested successfully and then bonded to a 12 cm long detector also with success. The operation appears to be stable, the threshold uniformity good(after trimming) and the noise levels as expected. This single-sided module will be tested in a beam in early August. So far all work on the ABCD has been done at CERN. Honeywell completed fabrication of the ABC wafers a week ahead of schedule, but one parameter was slightly out of spec pre-rad but in spec post rad(up to 25 Mrad). Negotiations with Honeywell resulted in the delivery of one wafer to LBNL in early August and the very first (one day) test results are very encouraging. This wafer will be diced and CAFE-P/ABCs mounted on hybrid in early August. A decision will be made by mid-August about how to proceed with Honeywell - to grant them a waiver and accept all of the wafers or ask them to reprocess. At the moment, the US view is to grant the waiver, given that all parameters are within spec post-rad.

Negotiations on the conditions of the Frame Contract continued and the first meeting with Honeywell was held (after multiple meetings with Temic). This is going slowly since we are attempting to define with both Temic and Honeywell a mechanism for a yield guarantee for production quantities.

Hybrid delivery is on track to meet the need for testing ICs and fabrication of a few modules at LBNL for the September test beam. Preassembly of parts for these modules has started.

    - ReadOut Driver System

Costs are within allocated limits. A workshop was help at University College London \on July 19-20 to review the state of the SCT and pixel off detector electronics.  Representatives of all the ROD interfaces were present (timing interface module, ROD crate processor, back of the crate card (optical interface), and ROD software.  Updated status presentations on each of the areas were presented. It is clear that the interface definitions are improving.   Completing the interface definitions is essential to the ROD development. This will be an ongoing effort.  The next meeting will be held the week of September 20 at CERN.

Progress has been made on the interfaces, Architecture and simulation code.  A short version of the meeting notes is shown below:

Latency and Module Mapping

John Lane presented the current status of the latency.  There were no problems in this area.  The written feedback that describes the latency was not all in. There is a possibility that the latency of the ROD will be reduced from 3 to 2 clock ticks.

Mapping of modules to the ROD data stream is proceeding.  It appears that ROI mapping is preferred.  This area should be better understood in a month or two.

Read Out Driver (ROD)

The ROD design and schedule was presented.  The schedule which includes the production (current ROD US ATLAS baseline) was agreed to by SCT and pixel community.  The ROD interfaces will also adopt a similar schedule. This is important because these interface cards are needed to test the complete functionality of the ROD.  The ROD discussion was centered around the following items.

A new model of the ROD was presented by Richard Jared.  The model was completed by Mark Nagel. The contents of the model was generally excepted. The model has the decoder FIFO (192 words) incorporated in the decoder FPGA.

A new function was pointed out by Gareth Moorhead. This was to issue the calibration strobe to all but a few modules and triggers to all modules.  This has not been part of the requirements.  The request is quite reasonable for it provides for testing of cross-talk between modules.  This request will have to be included in the requirements.

It was also pointed out that the model did not cover the need to issue commands of very long length to one module at a time. This will be included into the model.

Throttle was discussed. The current status is that the SCT will probably not need throttling.  The pixel needs are not completely understood at this time. Currently the ROD will not have throttling but will have the capability to incorporate it if needed.

ROD Crate Controller (RCC)

The RCC functionality was presented by John Hill. The drawing will be updated and placed on the web. The RCC discussion was centered around the interfaces.

The TIM RCC VME interface will use A24 D16 for communication.

The RCC ROD VME interface will use A24 D32 for communication.

The ROD FPGA serial PROM will be written by the RCC over VME.

John Hill will determine if VME Broadcast in the VME64x standard.

Back Of Crate (BOC)  (Optical interface to the front end modules)

Maurice Goodrick presented the BOC material. Maurice will provide new updated (draft form) diagrams and a short write up of the BOC and related interfaces, to be placed on web.

Maurice will determine what the current interlock system is for the fibers. This needs to be understood for it will effect the prototype card design.

Power utilization of the BOC needs to be completed so that the number of power pins on the back plane can be checked. This information is also needed to determine cooling and power supply requirements.

The Pixel MCC will always start data output on the same phase of the 40MHz clock.

Timing Interface Module TIM

John Lane presented the TIM material. John will provide new updated diagrams and a short write up of the TIM and related interfaces, to be placed on the web sight.

The following issues are decisions were made:

The busy logic will be on the TIM.

The busy signal from the ROD to TIM will be on the back plane.

The TTC0-7 lines in the ROD TIM Interface document need the following changes (Lane).

TTC4  was 1 start bit + 24L1 ID bits + 12 BC ID bits (+trigger type)

should be 1 start bit + 24L1 ID bits + 12 BC ID bits

TTC5 was ROD Clear

Should be 1 start bit +8 trigger type bits.

TTC6 was unused

should be reserved for periodic reset.

Latency adjustment to the fast signal Level 1 Accept (L1A), Event Counter Reset (ECR) and Bunch Counter Reset (BCR) and Calibration signal (CAL) will be done in the TCC system.  This means that there will be no latency adjust on the ROD.

A simulated beam crossover counter and level 1 counters will be needed in the ROD to provide the BC ID value for ROD initiated calibration related triggers and resets. The beam crossover counter may require a preset value on reset.

At what time are the ECR and BCR issued in the TCC system? Are the signal generation times time-critical? What is the correct definition of the two signals? These questions need addressing.

P3/J3 Back Plane

Richard Jared presented the P3/J3 Back Plane material.  Richard will provide updated (draft form) diagrams and a short write up of the P3/J3 Back Plane, to be placed on the web sight.

Martin Postranecky presented a variant of the P3 back plane that was accepted.

The clock signal will go to the BOC card and then sent to the ROD.

The TIM will be in slot 6 (Lane).

Philippe Farthouat must be contacted to determine the connector type for P3/J3.

Roy Wastie will layout the P3/J3 back plane.

Timing calibration

Richard Nickerson presented the timing calibration of the front end modules. These document were created over one year ago.

The accuracy of the timing needed at the modules is 0.5ns, 1.0ns is probably suitable.

One document of the set of 3 is missing.  Richard will make an attempt to find the document and pace it on the web.

Richard Nickerson and Tony Weidberg are no longer in a position to support the timing calibration effort.  It was agreed the Cambridge is the logical place to support the timing calibration effort because to the BOC effort at that institute.  The off detector electronics group recommended that Andy Parker take on the timing and calibration responsibility. In the advent that Cambridge can not support the effort, it should be supported by John Lane from UCL.  Recommendations will be made to Alex.

ROD Primitives

Richard Jared presented a first draft of possible ROD primitives.  The ROD is currently based on a register based I/O system.  This means that there are only 5 addresses that the RCC can read or write to. Primitives that access the ROD were described.

It is clear that this list processing concept must be evaluated to see that it will not break and provide the needed compatibility with the software.

Simulation

Damon Fasching presented simulations of the ROD for Pixels and SCT RODs. The results show that the SCT 96 link ROD will work with the 192 word decoder FIFO at 2.5 times normal occupancy and that there is sufficient bandwidth for the Pixels The event generator of the pixels needs updating.

Architecture of the ROD is very near completion. There are no major changes that resulted from the meeting.

Test beam support is continuing at a low level.

# Detailed Reports

    - Pixel System

1.1.1.1	Mechanics (E. Anderssen, D. Bintinger, M. Gilchriese)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| *ID Eng. Review at CERN | 20-Oct-98 | 20-Oct-98 |  | Done |
| Select prototype ring concept | 1-Nov-98 | 1-Feb-99 |  | Done |
| Select materials for frame proto. | 15-Mar-99 | 7-Apr-99 |  | Done |
| Complete fab 1st prototype ring | 1-Apr-99 | 30-Jun-99 | 15-Aug-99 | Delay |
| Complete frame Phase I | 1-Jul-99 | 1-Jul-99 | 15 Aug-99 | Delay |
| Complete fab 1st prototype disk | 1-Jul-99 | 1-Jul-99 | 15 Sep-99 | Delay |
| *Select sector baseline concept | 1-Sep-99 | 1-Sep-99 | 1-Oct-99 | Delay |
| *Module attachment CDR | 1-Sep-99 | 1-Sep-99 | 1-Oct-99 | Delay |
| *Compl test of 5-disk prototypes | 1-Sep-99 | 1-Sep-99 | 1-Oct-99 | Delay |
| Complete frame Phase II | 1-Oct-99 | 1-Oct-99 | 1-Oct-99 | OK |
| Complete frame Phase III | 1-Feb-00 | 1-Feb-00 | 1-Feb-00 | OK |

LBNL

1.1.1.1.1 Design

Design studies by Hytec, Inc for the overall pixel support frame continue.  An analytical FE model of the support frame sandwich panel has been prepared and steps are underway to check the adequacy of representation.  The model, and modifications thereof, will be used to compare with test results of prototype panels. The design for aluminum tube prototype sector 5 was completed and drawings for parts were submitted for fabrication.  Aluminum tube prototype sector 5 is designed for the 66 module (11 sectors) disk of the June 99 pixel layout.

1.1.1.1.2 Development and Prototypes

ESLI, San Diego, has delivered 4 of the planned 12 prototype sectors to be used in fabricating the first prototype pixel disk.  The delivery of 3 further sectors is expected the first week of August with the remaining five to be delivered by mid-August.  The first 4 sectors have good general appearances and the weights indicate acceptable average radiation lengths.  However of these first four sectors, 2 meet our planarity requirements and 2 do not.  The 2 that do not are still useful for a prototype disk.  The planarity problem has been discussed with ESLI and ESLI is now selecting interior glassy carbon coolant tubes with better planarity, which should result in more planar sectors.

The prototype disk support ring, the precision support for the disk sectors, is presently being bonded together.  After curing, the ring will have the precision mounting holes for the sectors machined into it.  It is estimated that the ring bonded assembly will be completed by 15 August.  A clean space at LBNL has been chosen for the fabrication and testing of the prototype disk.

Infrared imaging of the Genoa fabricated pixel barrel stave was completed.  This stave showed the expected heat profile with powers of 80, 100, and 120 Watts.  Pictures were posted on the web.

Replacement honeycomb was ordered and received from YLA for prototype panels of the Pixel Overall Support Frame.  The original honeycomb had one rough edge that that did not allow proper bonding to facing sheets.  The new honeycomb is made from XN50 woven cloth that has a tighter weave pattern due to the much lower number of fibers per tow.  YLA also exercised greater care in machining the second batch.  Sanding of the honeycomb is an option to improve the edge quality, a step to be avoided from an obvious cost implication.  The first panel using the replacement honeycomb has been completed.  Another panel using a densified form of reticulated viterous carbon foam as core will also be fabricated.  The panels will be tested for static stiffness and then lightweighted by cutting out portions of the panel to achieve the proposed ATLAS frame design geometry.  Stiffness tests will then be repeated to evaluate the effect of the cut-outs

The corner block design for the overall support frame panels is being finalized in preparation for the next frame prototype phase.  The corner blocks are used in joining the frame panels together to form the support structure.  Tooling for producing the corner elements is partially completed awaiting the final dimensions of the corner elements.

1.1.1.1.3 Disk Production

No activity.

1.1.1.2 Pixel Sensors (S. Seidel)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| *Start market survey | 2-Nov-98 | 1-Dec-98 |  | Done |
| *2nd prototype PDR | 1-Dec-98 | 1-Dec-98 |  | Done |
| *Complete market survey | 5-Mar-99 | 12-Feb-99 |  | Done |
| *2nd prototype FDR | 29-Mar-99 | 22-Feb-99 |  | Done |
| *Compl. Test 1st prototypes | 13-Apr-99 | 13-Apr-99 |  | Done |
| *Compl. 2nd prototype design | 27-Apr-99 | 1-May-99 |  | Done |
| *Compl. Fab of 2nd prototypes | 21-Sep-99 | 21-Sep-99 | 21-Sep-99 | OK |

1.1.1.2.1 Design

No activity.

1.1.1.2.2 Development and Prototypes

Following final characterization, six Prototype 1c wafers were shipped from UNM to IZM and 2 to Udine for dicing and assembly into modules.  UNM ordered and received 2 new radioactive sources for improved calibration of the pixel DAQ test stand.  M. Hoeferkamp, P. Skubic, and J. Snow participated at the test beam with other ATLAS collaborators.

1.1.1.2.3 Production

UNM obtained FY ’00 external funding for 2 undergraduate technicians to conduct the characterization of the Second Prototypes and the Production wafers.  One has now been fully trained; the second will begin training on 16 August.

      - Pixel Electronics (K. Einsweiler, R. Kass)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| Compl. Design HSOI test die | 16-Apr-98 | 1-Nov-98 |  | Done |
| Compl. Fab HSOI test die | 26-Aug-98 | 31-Mar-99 |  | Done |
| Compl. Design DMILL test device | 15-Dec-98 | 15-Dec-98 |  | Done |
| Submit 2nd Honeywell SoI test die | 15-Jan-99 |  |  | Not known |
| 1st design review of DMILL proto | 25-Jan-99 | 23-Feb-99 |  | Done |
| *FDR DMILL 1st prototype | 25-Jan-99 | 15-Jun-99 | 21-Jul-99 | Done |
| *Compl. Design DMILL 1st proto. | 26-Feb-99 | 30-Jun-99 | 9-Aug-99 | Delay |
| 1st design review of Honey. Proto | 1-Jun-99 | 1-Oct-99 | 1-Oct-99 | Delay |
| Compl. Eval. HSOI test die | 1-Jul-99 | 1-Aug-99 | 1-Sep-99 | Delay |
| *FDR Honeywell SoI 1st prototype | 5-Mar-99 | 15-Nov-99 | 15-Nov-99 | Delay |
| *Compl. Design Honey. SoI proto. | 2-Apr-99 | 1-Dec-99 | 1-Dec-99 | Delay |
| *Compl. Fab of DMILL 1st proto. | 23-Jul-99 | 15-Oct-99 | 15-Oct-99 | Delay |
| *Compl. Fab of Honey. SoI 1st proto | 25-Aug-99 | 1-Mar-00 | 1-Mar-00 | Delay |
| *Compl eval. DMILL prototype | 9-Dec-99 | 1-Jun-00 | 1-Jun-00 | Delay |
| *Compl eval HSOI prototype | 15-Feb-00 | 1-Jun-00 | 1-Jun-00 | Delay |
| *Review design approach | 19-Jan-00 | 15-Jun-00 | 15-Jun-00 | Delay |
| *Select rad-hard vendor | 29-Jan-00 | 15-Jul-00 | 15-Jul-00 | Delay |

# 1.1.1.3.1 Design

# LBNL

# Our highest priority remains the DMILL front-end chip submission (FE-D).  The schematic and layout for the entire chip is now completely frozen, and we are completing the last few verifications and simulations. After a working week in Bonn in late July, all technical issues have been resolved, and we are quite pleased with the design of the chip.

# The major technical hurdles at the beginning of July included revisions to the front-end design to deal with problems uncovered by LBL measurements, completion of a new design for the sense amplifiers at the bottom of column for data readout, and completion of the intricate placement and routing of all remaining digital blocks in the bottom of the chip.

# For the front-end, a very large effort has been made by CPPM in the last month, and our recent lab measurements, showing large channel to channel variations in timing, have been confirmed. After some effort, it was possible to reproduce the measurement results with decent accuracy in SPICE simulations. The problem was that the output node of the discriminator was much more sensitive to capacitive loading than the designer had realized. Under some biasing conditions, risetimes of 100ns could be seen. Small channel variations on these poor risetimes then led to the large observed variations. A modification of the design has been made, which involved taking the final output from a different node in the discriminator. In simulation this leads to much improved performance. In addition, it was realized that there were much more serious problems with capacitive loading in the BiCMOS design than anticipated as well. Although the BiCMOS design has better performance for timewalk due to very small charges, its timing dispersion is quite poor, and no acceptable improvements were found. Hence, for the final submission, we have returned to the previous all CMOS version of the front-end. Some last attempts are being made to improve its marginal timewalk performance by reducing parasitic capacitances on critical nodes. We will have to evaluate the final chips before and after irradiation to see whether they meet our requirements for ATLAS. It is possible that we will have to accept a higher in-time threshold than we would like,which could potentially reduce the lifetime of the detector somewhat.

# For the sense amplifiers, which have the difficult task of recovering the data from the bus in the column pair which connects all of the pixel back-ends to the end of column logic. The drivers that one could fit into the 400m pixel in DMILL are just barely adequate to the task, and after irradiation become very marginal. A very effective sense amplifier design was needed to recover the data signals at 20 MHz readout rate. A new bipolar design, which is a joint LBL/Bonn/Marseille design, appears to work extremely well. It uses bipolar input transistors, which have many advantages in this case. In particular, they produce a very large gain with very stable current thresholds, while providing a very low input impedance to the data bus (which gives data line swings of only about 50mV). We will operate these circuits at a rather low bias  (about 10uA each), and be able to adjust their current threshold in the few uA region, which appears to give excellent performance, even after irradiation. The layout of the design was done by Bonn, and many simulations have been performed over the last week in LBL.

# Finally, the last bits of digital layout at the bottom of the chip have been completed in Bonn. After extensive large digital simulations in LBL, two very minor changes were made to the schematic. The digital readout has now successfully gone through SPICE simulations of several hundred ms of hits at above design luminosity (several thousand random hits have been processed). These large and CPU intensive simulations are now being repeated for the final schematic, including the new sense amplifiers. Several process corners are being investigated, but we do not anticipate any surprises at this time.

# The complete reticle for this TEMIC DMILL engineering run has been finalized. We received an example GDS file for the layout of the scribe regions, and so we are planning to do the entire reticle layout in Bonn. This should insure that the geometry to the layout is exactly what we want. The reticle will include two pixel array chips (FE-D). It will also include an MCC prototype from Genova containing many improvements towards a final version, but not yet representing a complete chip. There are also prototypes of opto-link chips (all CMOS versions of the driver and receiver chips). The opto-electronics designs are based on those of the SCT, but have been transferred from a commercial rad-soft bipolar process to DMILL by Siegen and Ohio State University. A special process monitor bar has been developed by LBL to allow reliable extraction of SPICE models from the FE-D wafers so that we can cross-check our design performance against expectations. Finally, a rad-hard LVDS buffer is included which will allow us to make a complete rad-hard version of the single-chip support card that we use for testing single chips in the lab and testbeam. With this buffer, we have the capability to operate a single pixel chip (or electronics/sensor assembly) while it is being irradiated to LHC fluences.

# We now expect to submit the GDS files to TEMIC about Aug. 9. We have arranged to accelerate the fabrication time to roughly 9 weeks instead of the usual 12, in order to get results as quickly as possible from the submission. Hence, we expect to be testing these new wafers in our labs roughly around Oct. 15. We already have appropriate wafer probing capability set up in our lab for testing these chips, but we will be upgrading the corresponding software over the next few weeks in order to be fully ready when the wafers return. The probing is likely to be divided between Bonn and LBL, and we have also supplies Bonn with an appropriate interface card, and some chip testing software.

# In order to exercise the chips to the fullest extent possible, and in particular to develop the capability to label chips as “known good die”, and be sure that this classification will remain true after exposure to the full radiation doses of ATLAS, we are developing an improved test system. This system uses many of the same techniques present in commercial IC testers, but applies them in a focussed way to the specific chip testing problem that we have. We believe this is essential to do parametric testing of certain parts of the chip (modified clock frequencies, power supply voltages, and signal phasing), and evaluate for each die how far away they are from our specifications. Many chips would then be characterized before and after irradiation. This will allow us to develop “strict selection criteria” which a chip should pass before irradiation, in order to be sure that it would pass “standard selection criteria” after irradiation. The initial conceptual design of this system is complete, and we hope to complete the detailed schematics over the coming two months, in order to have working boards by late Fall this year. This system should be critical for evaluating our upcoming rad-hard pixel chip submissions, and arriving at the optimal final chip design and vendor for ATLAS late in 00.

# Ohio State

The radiation hard version of the DORIC4 chip is now ready for submission in a multi-project run with other pixel chips .  The layout bug in the current version of the bias circuit for LVDS cells has been fixed in Bonn.  The circuit was simulated using DMILL corner models with BSIM3 and ELDO (included post-radiation) and some minor improvements were made in response to the result of the simulation.  The design is expected to be submitted in mid-August and we expect the chip delivery in October.

We are still discussing ITAR agreement compliance and security with OSU officials.  Hopefully, all remaining issues will be resolved soon.

The installation of CADENCE on our workstation(s) is proceeding and progress has been made in learning to simulate some circuits.

# 1.1.1.3.2 Development and Prototypes

# LBNL

# The Honeywell SOI multi-project submission which we made in Nov. 98 has returned to LBL and undergone preliminary evaluation. A test program written by our engineer for the CERN IC tester in Geneva is now working, and we expect to get extensive new results within the next month. We have therefore delayed our plans to irradiate several die in the 88” cyclotron at LBL until after the end of the several month shut-down. We expect to irradiate some of these devices in Sept. or Oct. timeframe. We have also received corner models for the HSOI process from Honeywell, which we will be evaluating in more detail by making systematic comparisons to the test chip performance.

# 1.1.1.3.3 Production

No activity.

      - Pixel Hybrids (R. Boyd, S. Timm)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| * Compl. Assembly of 1st proto. | 14-Jan-99 | 10-Nov-98 |  | Done |
| * 1st prototype design review | 18-Feb-99 | 18-Feb-99 |  | Done |
| * Compl. Tests of 1.0 protos. | 15-Apr-99 | 15-Mar-99 |  | Done |
| * Select hybrid type | 15-Apr-99 | 1- Mar-99 |  | Done |
| Compl. Design of 1.x proto. | 1 - Apr- 99 | 21-Apr-99 |  | Done |
| Fabrication of 1.x compl |  | 1-Aug-99 | 1-Sep-99 | Delay |
| Singulate 1.x proto compl |  | 15-Aug-99 | 15-Sep-99 | Delay |
| Assembly of 1.x proto compl |  | 1-Sep-99 | 17-Sep-99 | Delay |
| Prototype 1.x tests complete |  | 15-Oct-99 | 15-Nov-99 | Delay |
| Module assy with 1.x compl |  | 15-Sep-99 | 15-Oct-99 | Delay |
| Design of proto 2.0 begins |  | 1-Sep-99 | 13-Jul-99 | OK |

1.1.1.4.1 Design

Oklahoma

Delivery of v1.2 Flex Hybrids from R&D circuits has once again been delayed. Processing of a third batch was begun the last week of June, but was abandoned when it was discovered that they were using the wrong base metalization (rolled Cu instead of sputtered/plated) and in order to take advantage of better photoresist materials which were received in late July. At this writing, they are unable to complete drilling of the via holes because of equipment problems. They have been working on this problem for about one week and estimate that it will take about one week to complete fabrication after this problem is solved. Several sample circuits were received in early July from previous failed runs and one has been assembled. It will be sent on to Albany for evaluation of testing assembled circuits.

The v1.1 Flex Hybrid delivery from CERN has also been delayed for unknown reasons. The via holes have been etched and production is proceeding, with delivery (after testing) expected by the end of August. Due to the late delivery, one panel of circuits will be delivered to LBNL so that at least one or two can be singulated by hand for construction of a module for the September test beam. Three panels are to be delivered to OU where, likewise, at least one will be singulated by hand for module assembly. The balance will be delivered to Spectralytics for laser singulation.

The delays have a one month impact on the rest of this year's schedule and may delay the completion of design for v2.0, since some evaluation of v1.x Flex Hybrids will be required so that what is learned from them can be incorporated into the new design.

We have also received a quotation of $3200 from Compunetics (Monroeville, MA)  for construction of 50 v1.x Flex Hybrids and an estimated delivery of 4 weeks ARO. We have asked for a cost estimate on a delivery of 2 weeks ARO.  They also quoted a price of $34.50/flex circuit for production of 3500 pieces (for budgetary purposes). They are currently fabricating flex circuits for D0 at Fermilab which have similar details.

Dyconex of Zurich has declined to quote on the design, stating that it is not within their capabilities.

Several design meetings for v2.0 were held in July between LBNL and OU, with Genoa being included in one of those. The greatest challenge is the very restrictive envelope proposed for the barrels. Several iterations will be required to find a compromise between electronic, mechanical and physics requirements to come to an appropriate layout scheme. Drawings clarifying the constraints will be developed and circulated by R. Boyd and M. Olcese (Genoa) for discussions in meetings to take place in September. Issues to be resolved include minimum clearance available in r, placement of components and maximum component height.

1.1.1.4.2 Development

OU

No activity.

Albany

The probe card for testing the FE pads of the flex hybrid is now on its way to us.  We will use two VAMUX64 chips (designed by OU) to multiplex the outputs from the probe card into a multimeter to measure resistance. Once the probe card is received, we will forward connector details to OU so that the circuit board design for the VAMUX64 chips can be finalized.

We now have a complete VME setup for module testing here at Albany, complete with PLL, PCC, and all required power supplies. We are in the process of debugging the system and establishing communications between the software and hardware. A module will be required shortly to complete the configuration and begin test verification.

1.1.1.4.3 Production

No activity.

1.1.1.5 Pixel Modules (R. Boyd, K. Einsweiler, K. K. Gan, M. Gilchriese)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| *Compl. 1st proto. Design | 29-Oct-98 | 1-Mar-99 |  | Done |
| *1st proto. Design review | 18-Feb-99 | 18-Feb-99 |  | Done |
| *Compl. Tests of 1st protos. | 18-Mar-99 | 17-Sep-99 | 17-Sep-99 | Delay |
| *Select module type |  | 18-Mar-99 | 22-Feb-99 | Done |
| *2nd proto. Design review | 17-Sep-99 | 10-Sep-99 | 10-Sep-99 | OK |

1.1.1.5.1 Design/Engineering

LBNL

Difficulties thinning dummy wafers from IZM in Berlin reported last month have been understood. These dummy wafers were not fabricated to specifications expected for real wafers. In particular, there was a substantial build up of material on the edges of the wafer and (contrary to requests) the wafers were not coated with photoresist by IZM. The wafers are held by tape (on the bumped side) on a chuck for the thinning process. The absence of photoresist and the high points at the wafer edges caused the wafer to be supported at a few spots rather than uniformly (the tape adhesive was not deep enough to solve this problem). At some point in the grinding process the wafer becomes so thin that its intrinsic strength is too low and it cracks under the grinding pressure. This was explained to IZM and they have promised to make dummy wafers without the "flash" on the edges for new trials in August. Real wafers (FE-B from Alenia with indium bumps protected by photoresist) are also expected in early August.

Design work for tooling for module assembly continued this month under the direction of F. Goozen. The major issue under study in July was the controlled dispensing of adhesive that glues the flex to the back side of the sensor. This must be done carefully to provide a uniform, hard surface for wire bonding and control the location of the glue. A number of different techniques were tried with limited success and the current thinking is to make a precision glue dispenser based on x-,y- and z-axis stages and a controlled "syringe".

1.1.1.5.2 Development and Prototypes

# LBNL

# We had expected to have several new modules for the July H8 testbeam. However, due to delays in module assembly by IZM (bump-bonding delays), PC board fabrication delays, and Flex fabrication delays, none of the new assemblies is yet ready. We decided to bring our existing Flex 1.0 module back to the testbeam to further explore the readout problems that we had observed at CERN in the May testbeam. This has been a very productive effort, involving close collaboration between LBL and Genova. LBL provides the expertise on the pixel chips, and also the DAQ and test software, whereas Genova is the designer of the MCC chip which readouts out the module. We have uncovered several classes of minor problems, and have significantly improved out diagnostic capability for operating modules.

# The first minor problem involved the observation of synchronization errors on the module. In this case, about every 10K events, one of the pixel chips on the module would not produce the proper “end of event” words that are required for the MCC to carry out error-free event building. The geographical distribution of the errors suggests a signal quality problem in the distribution of the fast LV1 trigger signal around the Flex. We will now examine the signal quality in more detail in the lab. It seems likely that the problem arises due to the larger than expected capacitive loads that the long and narrow distribution busses on the Flex create. Future versions of the MCC and Flex may be modified to reduce the fanout of  16 in the present design to a fanout of 8, by using two separate busses for the two sides of the module.

# The other remaining problems appeared to be an interaction between occasional “large” events observed in the testbeam due to peculiar noise environment. The result was that about once every 15 minutes, one of these large events would cause the MCC to fail in its event building task, and require a software reset to continue data taking. There are two different problems here. The first is, what are the large noise events ? Normally, the 50K channel pixel module produces 1-2 real hits, no noise hits, and the correct end-of-event words). Here, the primary suspicion is that the very minimal decoupling available in the first version of the Flex design does not provide adequate noise immunity. The second problem, mpre serious, is that there seems to be a weakness in the MCC when handling large events. The chip is known to handle obvious problems correctly, but further simulations and should in explaining the observed distribution of error flags, and the occasional failure of the event builder. Again, now that we can monitor the problem in more detail, we can try harder to duplicate the effects in our labs. Up to know, the modules have always performed quite well in the lab, and no sign of event building failure has been observed.

# These “system test” results are critical to finalizing the MCC design for the next generation submission, to be made in early 00. That chip should be very close to a pre-production version, and should be capable of reliable operation even under quite noise conditions.

Ohio State

Work is continuing on the packaging of VCSELs. We now have a procedure for depositing Au/Cr traces on Macor after several attempts.  A test run of 26 wire bonds has 100% success rate.  The pull strength on 3 test bonds are high, 10, 11, and 12 grams.  This is well above the minimum of 6 grams considered acceptable.  The 3-dimensional mask for depositing the traces has been redesigned.  The previous version has machined slits on a bend brass sheet.  This has the disadvantage of a round corner at the bend and the fine metal traces are weak and prompt to breakage.    In the new mask, we use two metal sheets with fine teeth mounted at right angle to form slits.  The teeth are significantly stronger than the slits from the previous prototype.  We have successfully deposited traces using the new mask.

We prototyped two VCSEL mounting jigs.  The first prototyped has the VCSEL placed face down in a pocket and the orientation of the chip is observed via a small hole (125 m) under the chip.  Unfortunately, the drilling of a 3-mm long hole is not practical.  The next prototype is a three-piece design with the VCSEL placed face up: a base piece for housing the base of the optical package, a 50 m stainless steel sheet with three pockets for the VCSEL and PIN, and a top piece to push the sheet against the base piece.  The prototype is also not satisfactory because it is not possible to mount the thin sheet flat to the level of 25 m.  We are working on a third prototype in which the jig is made out of one piece of aluminum with a small area machined down to 50 m to replace the stainless steel sheet.  If this is successful, we can then mount the VCSELs and measure the coupled optical power.

1.1.1.5.3 Production

No activity.

1.1.2	Silicon Strips

1.1.2.1  IC Electronics (A.A. Grillo)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| *Send out market survey | 1-Sep-98 | 17-Aug-98 | 17-Aug-98 | Done |
| *FDR for 2nd CAFÉ-M | 15-Sep-98 | 11-Sep-98 | 11-Sep-98 | Done |
| *Procurement in place for 2nd proto | 9-Oct-98 | 13-Nov-98 | 13-Nov-98 | Done |
| *FDR for 2nd ABC | 23-Oct-98 | 26-Jan-99 | 26-Jan-99 | Done |
| *Closing date for market survey | 26-Oct-98 | 25-Sep-98 | 25-Sep-98 | Done |
| *Submit 2nd CAFÉ-M | 30-Oct-98 | 26-Jan-99 | 26-Jan-99 | Done |
| *Issue call for tender | 9-Nov-98 | 9-Nov-98 | 9-Nov-98 | Done |
| *Submit 2nd ABC | 16-Nov-98 | 1-May-99 | 1-May-99 | Done |
| *FDR for 2nd ABCD | 11-Dec-98 | 15-Dec-99 | 15-Dec-99 | Done |
| *Closing date for tender | 21-Dec-98 | 22-Jan-99 | 22-Jan-99 | Done |
| *Submit 2nd ABCD | 27-Jan-99 | 8-Apr-99 | 8-Apr-99 | Done |
| *CERN finance comm. Approval | 15-Mar-99 | 15-Mar-99 | 15-Mar-99 | Done |
| *Frame contract in place | 15-Apr-99 | 30-Sep-99 | 30-Sep-99 | OK |
| *Compl. Fab of 2nd CAFÉ-M | 19-Apr-99 | 8-Apr-99 | 8-Apr-99 | Done |
| *Compl. Fab of 2nd ABC | 19-Apr-99 | 3-Aug-99 | 3-Aug-99 | OK? |
| *Test systems complete | 26-Apr-99 | 31-Jul-99 | 20Aug-99 | Delay |
| *1st ICs avail. For 2nd proto hybrid | 18-May-99 | 30-Aug-99 | 30-Aug-99 | OK |
| *Compl. Fab of 2nd ABCD | 30-Jun-99 | 26-Jun-99 | 30-Sep-99 | Delay |
| Compl. metallization 1st ABCD | ------------ | 15-Jul-99 | 7-Aug-99 | Hold |

1.1.2.1.1  Design/Engineering

LBNL & UCSC

Continued simulations of the fix for the ABC bug (See June’s report.) are still positive.  There is some difficulty fitting the fix into the existing chip floor plan.  It is not clear yet whether the die size will have to increase but RAL is working to make it fit.  Final, post-layout, simulations are awaiting that conclusion.

The CAFÉ-P tester has been exercised with the old (CAFÉ-M) probe card to test 44 channels and works correctly.  We are still waiting the new probe card to be able to test all 128 channels together.  The probe card was delayed but is due by 9-Aug.  If needed, we will screen sufficient CAFÉ-Ps for the first single sided CAFÉ-P/ABC module with the old probe card.  We are also working on engineering of enhancements to the tester which will be needed for large volume production testing.

The hardware design for the new ABC tester is complete.  There is still considerable amount of software to write for full test capability.  However, there is capability to run simple data patterns for a rudimentary wafer screen.  More complete testing of the chips will be done on hybrids for the initial evaluation.  It is still expected that RAL will do the bulk of the wafer screening of this pending prototype lot.  LBNL will screen a few chips for the first couple of evaluation modules and then focus on detailed ABC chip performance evaluation.

1.1.2.1.2  Development and Prototypes

LBNL & UCSC

The issue with the ABCD wafers was resolved this month.  Formally, CERN has rejected the lot of wafers because three PCM parameters are out of spec.  Temic has agreed to give us two wafers free of charge for evaluation.  They have further agreed to process a new engineering lot of wafers to be completed by 15-Sep.  They also have given us an offer to purchase the remaining 6 wafers from the existing lot at a reduced price of 30150 FRF/wafer (roughly $4,900/wafer).  The two wafers received by CERN have been tested at wafer probe showing a yield of 40% and 38% each.  This is approximately what is expected from a normal lot.  One wafer has been diced and two 6-chip hybrids have been built using each of the 2 ABCD designs on the wafer.  The plan is to connect these each to a 12cm detector so that the design and, in particular, the stability issues can be evaluated.  Depending upon the results of these tests, the collaboration will decide whether or not to purchase the remaining 6 wafers or not.  The main purpose for purchasing the extra wafers will be to get the module building program moving without waiting for the new lot in mid-September and to provide extra chips beyond the number available on the expected 8 wafers for more module building.

Honeywell completed fabrication of the ABC wafers the last week of July, a bit earlier than targeted by the amended PO to accelerate the process.  However, we have a similar problem as with ABCD in that one of their process monitor parameters was found to be out of spec.  The parameter (VTN, threshold voltage for NMOS devices) is 25mV below the lower limit for pre-rad measurements.  However, it is within spec by more than 100mV for the post-rad measurements.  The designers are confident that this will not cause the chips to be non-functional.  Some of our European collaborators have expressed concern, as they did with the Temic lot, that we should not base our technology decision in December upon a wafer lot which is not typical.  The difficult question to answer is how “representative” is this lot.  Honeywell has agreed for now to give us one wafer to evaluate so that we can better determine the effects of this VTN value and aide our decision in granting the waiver they seek for the remaining wafers.  We expect to test this wafer the first week of August and to negotiate a resolution to this issue with Honeywell and our European collaborators shortly after that.

We have mounted our existing CAFÉ-P hybrid on a 12 cm detector to continue the chip evaluation.  In the absence of ABCs, we are using the few remaining CDPs we have left from SSC days.  The performance with 2 CAFÉ-Ps and 2 CDPs is quite good with expected noise levels and stability limits.  We are now completing the single-sided module with 4 more chip pairs so that we can test the performance of all 6 and look for any noise or stability issues induced by the added chips.

1.1.2.1.3  Production

Temic and CERN have exchanged responses to the proposals made at our 7-Jun meeting on the Frame Contract.  There doesn’t seem to be any “show-stoppers” but details are still being ironed out.  We had a similar meeting with Honeywell on 29-Jul.  Overall the meeting was positive and both sides are trying to be flexible concerning legal and administrative differences.  We are hopeful that we can come to a common agreement soon but there are many issues still to resolve, most of them are business and not technical in nature.  We have another meeting scheduled with Honeywell on 19-Aug.

1.1.2.2 Silicon Strip Hybrids (C. Haber)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| Complete design of 1st prototype | 17-Nov-97 | 17-Nov-97 |  | Done |
| Complete fab of 1st prototype | 2-Feb-98 | 23-Mar-98 |  | Done |
| Preliminary design review | 3-Aug-98 | 7-Dec-99 | 7-Dec-99 | Delay |
| *Compl. 2nd proto subs. design | 29-Oct-98 | 15-Jun-99 | 15-Jun-99 | Done |
| *Compl. 2nd proto cable design | 29-Oct-98 | 1-Sep-99 | 1-Sep-99 | Delay |
| *Compl. 2nd proto fanout design | 29-Oct-98 | 1-Sep-99 | 1-Sep-99 | Delay |
| *Compl fab of 2nd proto substrate | 11-Mar-99 | 15-Aug-99 | 15-Aug-99 | Delay |
| *Compl fab of 2nd proto cable | 11-Mar-99 | 1-Oct-99 | 1-Oct-99 | Delay |
| *Compl fab of 2nd proto fanout | 11-Mar-99 | 1-Nov-99 | 1-Nov-99 | Delay |
| *Compl procure of 2nd proto comps | 11-Mar-99 | 1-Jul-99 | 15-Aug-99 | Delay |
| *Compl. 2nd proto assembly | 17-May-99 | 1-Sep-99 | 1-Sep-99 | Delay |
| *1st 2nd proto hybrids available | 14-Jun-99 | 1-Sep-99 | 1-Sep-99 | Delay |

LBNL

1.1.2.2.1 Design

The new hybrid layout for the Cafe-P and ABC chips was completed last month, checked and sent to the vendor for fabrication. The vendor requested some small modifications to assist in alignment during fabrication and we provided these.

1.1.2.2.2 Development and prototype fab

The vendor is fabricating the hybrids and we await shipment.

1.1.2.2.3 Production

No activity.

1.1.2.3 Modules for Silicon Strips(C. Haber)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| *Preliminary design review | 3-Aug-98 | 1-Apr-99 | T BD | Delay |
| Complete fabrication of 1st dummy modules | 15-Aug-98 | 15-Aug-98 |  | Done |
| Prototype tooling complete | 1-Apr-99 | 1-Aug-99 | 1-Sep-99 | Delay |
| *Compl. Design of proto assy/test | 14-Jun-99 | 15-Nov-99 | 15-Nov-99 | Delay |
| *Compl. Fab of tooling for proto | 14-Jun-99 | 15-Nov-99 | 15-Nov-99 | Delay |

LBNL

1.1.2.3.1 Design of Assembly and Test

New drawings of the assembly fixtures were received from RAL and these are being reviewed.  Design continues on a folding fixture for the hybrids.

1.1.2.3.2 Development and prototypes

The new calibration plate was submitted for fabrication and received last month.  The plates included optical map data.  This data was presented to us in an unusable form.  We have discussed this with the vendor and they have agreed to re-map the plates.  We are currently evaluating to determine whether a simpler approach to the mapping than originally specified will be acceptable.

An attempt was made to machine some of the PG for the test of thermal performance last month but it was unsuccessful.  We pursued some alternate approaches based upon suggestions received from Europe and last month were able to finally get a good result. This material was used to produce a full two-sided module for thermal studies.  This module is now ready for preliminary tests.

As part of the ASIC testing program a fully loaded single sided module was built to test the Cafe-P with old CDP chips.  This was built using the up-to-date construction jigs and methods and bonded with a program written for the automatic wirebonder.  The construction and bonding exercise was successful.

1.1.2.3.3 Production

No activity.

1.1.3  ReadOut Drivers(R. Jared, A. Lankford)

| Milestones | Baseline | Previous | Current | Status |
| --- | --- | --- | --- | --- |
| *Select PreROD implementation | 30-Oct-98 | 26-Mar-99 |  | Done |
| *Requirements review | 30-Nov-98 | 18-Nov-98 |  | Done |
| *Compl. System design | 28-Dec-98 | 15-Jul-99 |  | Done |
| Compl. SCT ROD simulation | N/A | 7-Jul-99 |  | Done |
| Compl. Pixel ROD simulation | N/A | 1-Aug-99 | 1-Aug-99 | OK |
| Compl. DSP eval. Setup | N/A | 15-Aug-99 | 15-Aug-99 | OK |
| *System design review | 11-Jan-99 | 20-Aug-99 | 20-Aug-99 | OK |
| Compl. Decoder VHDL code | N/A | 1-Oct-99 | 1-Oct-99 | OK |
| Compl. gather VHDL code | N/A | 1-Oct-99 | 1-Oct-99 | OK |
| *Compl. PreROD layout | 15-Feb-99 | 1-Oct-99 | 1-Oct-99 | OK |
| *Compl. PreROD procure | 1-Mar-99 | 1-Oct-99 | 1-Oct-99 | OK |
| *Compl. PreROD PCB fab | 16-Mar-99 | 15-Oct-99 | 15-Oct-99 | OK |
| Compl. Mux VHDL code | N/A | 1-Nov-99 | 1-Nov-99 | OK |
| Compl. Controller VHDL code | N/A | 1-Nov-99 | 1-Nov-99 | OK |
| *Compl. PreRod Design | 29-Jan-99 | 1-Nov-99 | 1-Nov-99 | OK |
| *Compl. PreROD 1st assembly | 30-Mar-99 | 1-Nov-99 | 1-Nov-99 | OK |
| Compl DSP C code | N/A | 1-Dec-99 | 1-Dec-99 | OK |
| Compl. Initial test stand SW | N/A | 1-Dec-99 | 1-Dec-99 | OK |
| *Compl. protoROD debug/test | 9-Jul-99 | 1-Feb-00 | 1-Feb-00 | OK |
| PreROds prod. Fab complete | N/A/ | 1-Jul-00 | 1-Jul-00 | OK |

1.1.3.1.1  Strip Test Beam Support   (A. Lankford)

UC Irvine

Hardware and software support for laboratory and beam tests of SCT electronics and modules is ongoing. Activity in July consisted of providing technical support to users of systems already in the field.

1.1.3.1.2  Pixel Test Beam Support  (R. Jared)

Minor support effort was supplied in July.

1.1.3.2.1  ROD Requirements (R. Jared)

Contacts have been made with the user community to define and/or justify the following requirements:

- The calibration strobes and triggers will be issued independently to a user defined number of front end length. This will allow for testing of cross-talk between modules

- Capability to dynamic throttling of individual links during data taking will not be performed, but the capability will be maintained in the ROD design.

- The ROD will provide of arbitrary long command lengths to the front end modules.

These issues were discussed at the pixel and SCT workshop in Europe.  Initial consensus was reached on many of the requirement issues.  It is expected that September meeting at CERN will provide the concurrence to start the change procedure of the requirements.

1.1.3.2.2  ROD Essential Model (R. Jared)

The essential model defines the essential functionality of the ROD and defines the interfaces of the ROD to other functional units. It is complete, except for refinements that are ongoing during the development of the implementation model. No refinements of the essential model were made during June

1.1.3.2.3  ROD Implementation Model (R. Jared)

The architectural definition of the ROD has progressed to the point were the interfaces between FPGAs is the focus of the effort.  As these interfaces are clarified, coding will commence. The simulation of the SCT ROD have been essential to this progress.

1.1.3.3.7	Preprototype ROD (R. Jared)

Complete simulation of the SCT ROD data path have been performed.  These simulation show that 96 links will satisfy the bandwidth for an occupancy the is 2.5 times the TDR occupancy. Simulation of the pixel RODs is proceeding.  There is a need to improve the pixel event generator.  Architectural studies are completed.