## SQA_Model
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
1. | 1. Advise on the selection, | Review and recommend appropriate
| tailoring and appropriateness of | government/industry standards that
| standards for a particular | apply to software development.
Software | software development acquisition.. | Provide specific cost effective tailoring
Development |  | recommendations, as needed.
Standards | 2. Apply the criteria of a wide | Perform audits, reviews inspections, and
| range of software development | evaluations. (See appropriate PA’s)
| standards in the software quality | Evaluate the contractor’s plans and
| assurance program. Through | procedures for consistency with the
| activities such as: Audits, reviews, | requisite contract model and project needs.
inspection, evaluation, etc., to
verify implementation of software
development practices.
3. Assure consistency of
contractor plans with the project’s
life cycle needs.
2. | 1. Advise and recommend on | Review and verify the allocation of
| design methodologies and | requirements to lower level components
Design | techniques such as: Various | within the system.
Methodologies | CASE tools, benefits of structured | Verify that all requirements are allocated to
and Techniques | design, object oriented design, etc. | the design.
| 2. Determine adequacy, | Review and verify that the design
| completeness, and acceptability of | documentation is complete, and consistent
| the design | with the system level specification.
Evaluate to assure that the design
methodology supports the target language
capabilities.
3. | 1. Participate in the IPT | Review, evaluate and recommend approval
| contractor selection process. | of the Software Quality Assurance and
FAA |  | Software Development Plans.
Pre-Award |  | Conduct Pre-Award surveys.
Process |  | Participate in Software Capability
Evaluations (SCE).
Review and comment on Screening
Information Requests (SIR).
Recommend appropriate software quality
assurance requirements for procurement.
Generate the appropriate reports.
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
4. | 1. Evaluate contractor developed | Review and analyze contract, SOW, CDRLs.
| software quality assurance plans, | Extract SQA requirements.
Planning | procedures, and instructions. | Compare SQA plans to requirement’s
documents and applicable standards.
| 2. Develop FAA QRO Contract | Identify cases of nonconformance in plans,
| Plan (Contract Review Record | procedures, and seek appropriate corrective
| and QA Plan) IAW the QRO | action.
| Guidebook. | Review and analyze SQA plans, procedures,
and other contract data for specific audit
topics.
Implement FAA surveillance activities in
accordance with the FAA QRO Contract
Plan.
5. | 1. Assess system engineering | Review and analyze the system
| products, and assure requirements | requirements documents and their
Requirements | traceability throughout the | significance in acquisition.
Management | software life cycle. | Evaluate the process used by the system
engineering function in developing,
| 2. Assure requirements | documenting, and decomposing
| documentation is complete and | requirements for the system.
| consistent . | Trace requirements from the lowest level
decomposition to the system requirements
document.
Trace requirements from the system
requirements document to the lowest level
decomposition.
6. | 1. Use software engineering | Evaluate the project tools which support
| project tools in conducting | software development (e.g., CMVC,
Software | software quality assurance | DOORS, Cadre Team Work, Interleaf, etc.).
Tools | activities. | Verify the contractor has demonstrated
project tools function correctly
| 2. Advise on the use of project | Verify that project tools are under
| tools as related to the quality of | configuration control.
| the software products. | Use project tools to obtain software quality
assurance audit data for evaluation.
| 3. Assure project tools function | Evaluate the outputs of project tools in
| correctly and are adequately | making product and process acceptability
| controlled. | decisions.
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
7. | 1. Determine the adequacy of | Review and analyze the documentation
| contractor generated software | requirements for the project (e.g., DID, CDRL,
Software | documentation (e.g., SRS, SDD, | SOW, etc.).
Documentation | plans, reports) IAW contract | Assess the adequacy of contractor
Review | requirements. | generated documentation (software related)
in accordance with contract requirements.
Generate comments and recommendations
as to the acceptability of project
documentation for computer software.
Assess the adequacy of software related
documentation in meeting its intended
purpose.
8. | 1. Minimize risk related to the | Verify that a contractual vehicle is addressed
| project. | to identify and manage risk areas.
Risk |  | Review and analyze the software life cycle to
Management |  | identify abnormal conditions (tools, staffing,
schedule, etc.).
Evaluate and provide comments on tracking
of identified project risks.
Monitor risk management activities, and
track identified risks related to the project.
Communicate risk issues to FAA project
personnel.
9. | 1. Analyze and determine | Review proposals to extract cost and size
| software development cost of | estimates.
Software | programs using cost and size | Extract information from software
Size and | estimation tools. | engineering environments to make decisions
Cost |  | effecting project and contract attributes.
Estimation |  | Generate cost and schedule reports using
industry approved cost models.
Evaluate model outputs against proposed
estimates, and examine the differences.
Perform software cost realism studies
and produce a cost realism report on
cost processes, projects and services
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
10. | 1. Participate on SCE teams. | Review and verify the SCE methods.
Develop and implement an SCE strategy.
Software Eng | 2. Contribute to FAA process | Evaluate contractor processes for
Inst.Capability | improvement activities. | consistency with the CMM.
Maturity |  | Verify that the contractor's SEI CMM rating is
Models and | 3. Perform follow-up on SCE | maintained through the contract performance
Software | findings. | period.
Capability |  | Verify that the process improvement plan (PIP)
Eval (SCE) |  | activities take place.
11. | 1. Assess the source code for | Assess source code for existence and
| compliance with programming | adequacy of the coded comments, header
Evaluating | standards and conventions. | information, and proper indentation of
Source Code |  | constructs as prescribed by the
| 2. Assure coded routines are | programming standards and conventions
| compliant with other design | manual. (Product Focus)
| requirements (e.g., complexity). | Verify that coding practices employed
are consistent with the project standards
and conventions, and other contract
requirements. (Process Focus)
Verify that the complexity level and appropriate
use of language constructs meets design goals
12. | 1. Assure SDFs comply with | Access SDF contents via manual or
| project requirements. | electronic means.
Software |  | Evaluate SDF contents for consistency with
Development |  | applicable contract standards, and other
Files (SDF) |  | requirements.
Seek corrective action for instances of
noncompliance IAW Corrective Action PA.
13. | 1. Use Statistical Methods and | Determine the population and implement
| evaluate data through samples | statistical sampling if necessary
Statistical |  | Use the criteria contained in the sampling
Sampling |  | plan to determine if the results indicate that
further action is required.
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
14. | 1. Assess the adequacy of the | Evaluate and advise on software test
| software test process in meeting | documentation adequacy, including:
Software | contract requirements. | Test Plans, test cases, test procedures, reports,
Testing |  | and test data.
| 2. Assure the adequacy of | Use the requirements verification matrix
| software development test | (VRTM) to verify that all requirements, are
| products (plans, reports, | tested, demonstrated, inspected, and analyized.
| procedures, etc.). | Evaluate unit level testing to ensure
coverage of logical paths and functionality.
Evaluate integration testing to ensure that
functional threads, interfaces of units and
components operate as expected.
Verify that CSCI testing includes testing the
requirements documented in the Software
Requirements Specification, or equivalent.
Verify that the system level test includes the
requirements of the System Specification, or
equivalent, for the software and target
hardware platform.
Monitor or witness software testing for all
levels of test.
15. | 1. Apply independent analysis on | Review and analyze government
| software metric reports and draw | requirements and methods for metrics.
Software | conclusions. | Select appropriate metrics.
Metrics |  | Analyze pertinent metrics before drawing
| 2. Apply independent software | conclusions.
| metric data collection and | Research and evaluate trend anomalies.
| produce metric reports. | Evaluate actual measures to planned goals.
Analyze and report results.
Audit contractor process outputs.
Review contractor reports and other
documentation.
Extract information using database queries.
Analyze test results.
Produce a metric report, including a
description and analysis for each metric.
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
16. | 1. Assess cost and schedule | Review and analyze contractors Cost
| data against plans. | Performance Report (CPR), or other similar
Earned |  | data.
Value |  | Review and analyze data to make
Reporting |  | recommendations to IPT on cost, schedule,
Requirements |  | and staffing.
17. | 1. Validate, through inspection, | Verify that adequate controls exist for all
| that the test software contains | validation materials and devices.
Automatic Test | all test cases, and the criteria | Test and inspect test programs for
Equipment | for acceptance is consistent | completeness.
(ATE) | with the test specification. | Monitor test program demonstration.
Compare the test results for a unit under
| 2. Validate the ATE system | test with the expected results, and verify
| using an industry accepted test | that the method used is consistent with
| method (Fault Insertion, Error | IEEE and industry approved standards.
| Seeding Known Good Unit, etc.). | Execute the test software on the ATE
system and verify that the system will
accept good product and reject bad.
18. | 1. Audit contractor SQA | Identify audit areas.
| systems for conformance to | Review and analyze contractor procedures.
Software | the contract. | Develop audit guide and schedule .
Audits |  | Conduct audits and reviews against
contractor data to determine compliance
and adequacy.
Document audit findings.
Seek corrective action for instances of
noncompliance in accordance with the
corrective action PA.
|  |  | Conceptual (Pre-Contract Award) Phase | Software Requirements Analysis Phase | Preliminary Design Phase | Detailed Design Phase | Code & Unit Testing Phase | CSC Integration & Testing Phase | CSCI Integration & Testing Phase | Systems Integration & Testing Phase
Process Area | Goals | Activities
19. | 1. Identify and resolve any | Identify the problem and determine the
| breakdown in the contractor’s | impact.
FAA | quality system. | Determine the appropriate method for
Corrective |  | requesting corrective action IAW the QRO
Action |  | Guidebook.
Determine appropriate time frame for the
contractor to correct the problem.
Perform follow-up action to verify that the
problem was corrected.
20. | 1. Assure that the SCM | Review and verify the contractor’s
| processes and procedures are | procedures for configuration identification,
Software | compliant with contract | change control, and status accounting are
Configuration | requirements. | IAW contract requirements.
Management |  | Review and verify the project’s
(SCM) |  | developmental configuration control used
for deliverable and nondeliverable software
and documentation is adequate.
Audit the contractor’s SCM process and
procedures.
Initiate corrective action for instances of
noncompliance.
ASU-200 SQA _ MODEL
ASU-200 SQA _ MODEL
ASU-200 SQA _ MODEL
ASU-200 SQA _ MODEL
ASU-200 SQA _ MODEL
Version 1
January 23, 1998
SQA_MDL2.XLS
Version 1
January 23, 1998
SQA_MDL2.XLS
Version 1
January 23, 1998
SQA_MDL2.XLS
Version 1
January 23, 1998
SQA_MDL2.XLS
Version 1
January 23, 1998
SQA_MDL2.XLS
FORWARD
The Software Quality Assurance (SQA) Model was developed as a framework for implementing quality assurance programs on software intensive projects. The model provides a reference for comparing actual activities against model best practices and can be used as a guide for implementing new SQA programs. The model is intended to cover the full life cycle from pre-award through fielding and includes software quality assurance activities directly associated with the pre-award phase and with supporting product teams.
The SQA model is intended for use as a lower level supplement to the FAA-iCMM (F.A.A. integrated capability maturity model), which covers all the essential elements of acquisition, engineering, and program management.
PURPOSE: The SQA Model is intended for use for the following purposes:
· Documenting SQA processes
· A reference model of what constitutes a good SQA program
· A process improvement tool for meeting CMM levels
· Identifying competencies
· Aid in determining potential workload
· New employee guide
· Management tool for determining SQA effectiveness
MODEL ORGANIZATION and FORMAT: The model is organized by process areas, which in turn relate to specific software quality assurance objectives. Each process area has specific goals and activities designed to meet those goals. Activities have been applied to the major life cycle of the development process. Procedures for each process area are currently under development.
PROCESS AREA: Process areas represent a set of related activities, which when performed collectively, can achieve a defined goal or goals. The SQA process areas are specifically intended to provide the essential elements for conducting Software Quality Assurance.
GOAL: The outcome or product of the Process Area.
ACTIVITY: Base Practice or sequence of activities that are employed to meet a goal.
PROCEDURE REFERENCE: Refers to procedures (not physically contained in the model) that will provide guidance on how to accomplish an activity.
ASU-200 SQA_MODEL
Page 1 of 9
Page 3 of 9
LIFE CYCLE: In order to provide a better understanding as to when activities should be performed in the software development life cycle, activities were mapped to major phases.
These time periods are:
· Conceptual (Pre-contract award)
· Software Requirements Analysis
· Preliminary Design
· Detailed design
· Code & Unit Test
· Computer Software Unit Integration & Test
· Computer Software Component Integration & Test
· Systems Integration & Test
It should be understood that not all activities begin and end in a single phase and some activities will extend beyond the phases listed above
(e.g. beyond Systems Integration & Test).
GENERIC PROCESS AREAS: During the development of the SQA model, several process areas were determined to be generic and not unique to the area of SQA. These have been left out of the actual model but should still be considered as important and should be addressed when establishing or measuring an SQA program:
Ability to work as team. Establishing and conducting value added quality assurance (software or hardware) requires working closely with product team, contractor and other quality assurance personnel.
Communication. Effective verbal and written communication to management, product team members and contractor personnel both formal and informal is a vital process in a good quality assurance program.
Providing Formal and OJT Training. Assisting junior level SQA personnel or other QA members with
SQA activities are an important part of any quality assurance program. The goal for this process area involves maintaining the organizations ability to increase needed skill areas where required.
REFERENCES:
1. FAA-iCMM (Federal Aviation integrated Capability Maturity Model).
2. Quality/Reliability Officer Guidebook ASU-200
POLICY: This model constitutes a guide for conducting effective SQA and should be considered as the SQA portion of the QRO Guidebook with ASU management endorsement.
Page 5 of 9
Page 6 of 9
Page 7 of 9
Page 4 of 9
ASU-200 SQA _ MODEL
Version 1
January 23, 1998
SQA_MDL2.XLS
ASU-200 SQA _ MODEL
Version 1
January 23, 1998
SQA_MDL2.XLS
ASU-200 SQA _ MODEL
Version 1
January 23, 1998
SQA_MDL2.XLS
Page 8 of 9
Page 2 of 9
Page 9 of 9

## Verif_Log_Instr
| Process Area |  | Goals |  | Activities | Evidence
X | 1. When all goals for this process area | X | 1. When a all activities required to satisfy | X | 1. When the activity has been implemented | 1. Document the artifacts that support the
| have been satisfied place an "X" |  | the goal are implemented place an "X" |  | place an "X" in the appropriate box. | implementation of the activity.
| in the appropriate box. |  | in the appropriate box.
X
X
X
X
X
ASU-200 SQA_MODEL VERIFICATION RECORD - INSTRUCTIONS
STATUS: (corsponding to activity)
1. GIVE THE STATUS FOR WHERE YOU ARE IN RELATIONSHIP TO SATISFYING EACH ACTIVITY (EVIDENCE).
2.
3.
COMMENTS:
1. PROVIDE COMMENTS WHEN NECESSARY (E.G. FOLLOW-UP, RISK MANAGEMENT AREAS, ETC.)
2.
3.

## Verification_Log
CONTRACT NO. |  | APMQ /
PROGRAM NAME: |  | SQA SUPPORT:
LIFE CYCLE PHASE:
Process Area | Goals | Activities | Evidence
1. Software Development | 1. Advise on the selection, | Review and recommend appropriate
Standards | tailoring and appropriateness of | government/industry standards that
| standards for a particular | apply to software development.
software development acquisition..
Provide specific cost effective tailoring
| 2. Apply the criteria of a wide | recommendations, as needed.
range of software development
| standards in the software quality | Perform audits, reviews, inspections, and
| assurance program. Through | evaluations. (See appropriate PA’s)
activities such as: Audits, reviews,
| inspection, evaluation, etc., to | Evaluate the contractor’s plans and
| verify implementation of software | procedures for consistency with the
| development practices. | requisite contract model and project needs.
3. Assure consistency of
contractor plans with the project’s
life cycle needs.
Process Area | Goals | Activities | Evidence
2. FAA Pre-Award | 1. Participate in the IPT | Review, evaluate and recommend approval
Process | contractor selection process. | of the Software Quality Assurance and
Software Development Plans.
Conduct Pre-Award surveys.
Participate in Software Capability
Evaluations (SCE).
Review and comment on Screening
Information Requests (SIR).
Recommend appropriate software quality
assurance requirements for procurement.
Generate the appropriate reports.
Process Area | Goals | Activities | Evidence
3. Software Engineering | 1. Participate on SCE teams. | Review and verify the SCE methods.
Institute’s Capability
Maturity Models and | 2. Contribute to FAA process | Develop and implement an SCE strategy.
Software Capability | improvement activities.
Evaluations (SCE) |  | Evaluate contractor processes for
| 3. Perform follow-up on SCE | consistency with the CMM.
findings.
Verify that the contractor's SEI CMM rating is
maintained through the contract performance
period.
Verify that the process improvement plan (PIP)
activities take place.
Process Area | Goals | Activities | Evidence
4. Software Size and | 1. Analyze and determine | Review proposals to extract cost and size
Cost Estimation | software development cost of | estimates.
programs using cost and size
| estimation tools. | Extract information from software
engineering environments to make decisions
effecting project and contract attributes.
Generate cost and schedule reports using
industry approved cost models.
Evaluate model outputs against proposed
estimates, and examine the differences.
Process Area | Goals | Activities | Evidence
5. Software | 1. Determine the adequacy of | Review and analyze the documentation
Documentation | contractor generated software | requirements for the project (e.g., DID, CDRL,
Review | documentation (e.g., SRS, SDD, | SOW, etc.).
plans, reports) IAW contract
| requirements. | Assess the adequacy of contractor
generated documentation (software related)
in accordance with contract requirements.
Generate comments and recommendations
as to the acceptability of project
documentation for computer software.
Assess the adequacy of software related
documentation in meeting its intended
purpose.
Process Area | Goals | Activities | Evidence
6. Planning | 1. Evaluate contractor developed | Review and analyze contract, SOW, CDRLs.
| software quality assurance plans, | Extract SQA requirements.
procedures, and instructions.
Compare SQA plans to requirement’s
| 2. Develop FAA QRO Contract | documents and applicable standards.
Plan (Contract Review Record
| and QA Plan) IAW the QRO | Identify cases of nonconformance in plans,
| Guidebook. | procedures, and seek appropriate corrective
action.
Review and analyze SQA plans, procedures,
and other contract data for specific audit
topics.
Implement FAA surveillance activities in
accordance with the FAA QRO Contract
Plan.
Process Area | Goals | Activities | Evidence
7. Earned Value | 1. Assess cost and schedule data | Review and analyze contractors Cost
Reporting | against plans. | Performance Report (CPR), or other similar
Requirements |  | data.
Review and analyze data to make
recommendations to IPT on cost, schedule,
and staffing.
Process Area | Goals | Activities | Evidence
8. Design Methodologies | 1. Advise and recommend on | Review and verify the allocation of
and Techniques | design methodologies and | requirements to lower level components
| techniques such as: Various | within the system.
CASE tools, benefits of structured
| design, object oriented design, etc. | Verify that all requirements are allocated to
the design.
2. Determine adequacy,
| completeness, and acceptability of | Review and verify that the design
| the design | documentation is complete, and consistent
with the system level specification.
Evaluate to assure that the design
methodology supports the target language
capabilities.
Process Area | Goals | Activities | Evidence
9. Requirements | 1. Assess system engineering | Review and analyze the system
Management | products, and assure requirements | requirements documents and their
| traceability throughout the | significance in acquisition.
software life cycle.
Evaluate the process used by the system
| 2. Assure requirements | engineering function in developing,
| documentation is complete and | documenting, and decomposing
| consistent . | requirements for the system.
Trace requirements from the lowest level
decomposition to the system requirements
document.
Trace requirements from the system
requirements document to the lowest level
decomposition.
Process Area | Goals | Activities | Evidence
10. Risk Management | 1. Minimize risk related to the | Verify that a contractual vehicle is addressed
| project. | to identify and manage risk areas.
Review and analyze the software life cycle to
identify abnormal conditions (tools, staffing,
schedule, etc.).
Evaluate and provide comments on tracking
of identified project risks.
Monitor risk management activities, and
track identified risks related to the project.
Communicate risk issues to FAA project
personnel.
Process Area | Goals | Activities | Evidence
11. Software | 1. Assure SDFs comply with | Access SDF contents via manual or
Development | project requirements. | electronic means.
Files (SDF)
Evaluate SDF contents for consistency with
applicable contract standards, and other
| look at PA for corrective action | requirements.
Seek corrective action for instances of
noncompliance IAW Corrective Action PA.
Process Area | Goals | Activities | Evidence
12. Software Configuration | 1. Assure that the SCM processes | Review and verify the contractor’s
Management (SCM) | and procedures are compliant | procedures for configuration identification,
| with contract requirements. | change control, and status accounting are
IAW contract requirements.
Review and verify the project’s
developmental configuration control used
for deliverable and nondeliverable software
and documentation is adequate.
Audit the contractor’s SCM process and
procedures.
Initiate corrective action for instances of
noncompliance.
Process Area | Goals | Activities | Evidence
13. Software Audits | 1. Audit contractor SQA systems | Identify audit areas.
for conformance to the contract.
Review and analyze contractor procedures.
Develop audit guide and schedule .
Conduct audits and reviews against
contractor data to determine compliance
and adequacy.
Document audit findings.
Seek corrective action for instances of
noncompliance in accordance with the
corrective action PA.
Process Area | Goals | Activities | Evidence
14. Software Metrics | 1. Apply independent analysis on | Review and analyze government
| software metric reports and draw | requirements and methods for metrics.
conclusions.
Select appropriate metrics.
2. Apply independent software
| metric data collection and | Analyze pertinent metrics before drawing
| produce metric reports. | conclusions.
Research and evaluate trend anomalies.
Evaluate actual measures to planned goals.
Analyze and report results.
Audit contractor process outputs.
Review contractor reports and other
documentation.
Extract information using database queries.
Analyze test results.
Produce a metric report, including a
description and analysis for each metric.
Process Area | Goals | Activities | Evidence
15. Evaluating | 1. Assess the source code for | Assess source code for existence and
Source Code | compliance with programming | adequacy of the coded comments, header
| standards and conventions. | information, and proper indentation of
constructs as prescribed by the
| 2. Assure coded routines are | programming standards and conventions
| compliant with other design | manual. (Product Focus)
requirements (e.g., complexity).
Verify that coding practices employed
are consistent with the project standards
and conventions, and other contract
requirements. (Process Focus)
Verify that the complexity level and appropriate
use of language constructs meets design goals
Process Area | Goals | Activities | Evidence
16. Statistical Sampling | 1. Use statistical methods to | Determine the population and implement
| evaluate data through samples | statistical sampling if necessary
Use the criteria contained in the sampling
plan to determine if the results indicate that
further action is required.
Process Area | Goals | Activities | Evidence
17. Software Testing | 1. Assess the adequacy of the | Evaluate and advise on software test
| software test process in meeting | documentation adequacy, including:
| contract requirements. | Test Plans, test cases, test procedures, reports,
and test data.
2. Assure the adequacy of
| software development test | Use the requirements verification matrix
| products (plans, reports, | (VRTM) to verify that all requirements, are
| procedures, etc.). | tested, demonstrated, inspected, and analyized.
Evaluate unit level testing to ensure
coverage of logical paths and functionality.
Evaluate integration testing to ensure that
functional threads, interfaces of units and
components operate as expected.
Verify that CSCI testing includes testing the
requirements documented in the Software
Requirements Specification, or equivalent.
Verify that the system level test includes the
requirements of the System Specification, or
equivalent, for the software and target
hardware platform.
Monitor or witness software testing for all
levels of test.
Process Area | Goals | Activities | Evidence
18. Software Tools | 1. Use software engineering | Evaluate the project tools which support
| project tools in conducting | software development (e.g., CMVC,
| software quality assurance | DOORS, Cadre Team Work, Interleaf, etc.).
activities.
Verify the contractor has demonstrated
| 2. Advise on the use of project | project tools function correctly
tools as related to the quality of
| the software products. | Verify that project tools are under
configuration control.
3. Assure project tools function
| correctly and are adequately | Use project tools to obtain software quality
| controlled. | assurance audit data for evaluation.
Evaluate the outputs of project tools in
making product and process acceptability
decisions.
Process Area | Goals | Activities | Evidence
19. Automatic Test | 1. Validate, through inspection, | Verify that adequate controls exist for all
Equipment (ATE) | that the test software contains all | validation materials and devices.
test cases, and the criteria for
| acceptance is consistent with the | Test and inspect test programs for
| test specification. | completeness.
| 2. Validate the ATE system using | Monitor test program demonstration.
an industry accepted test method
| (Fault Insertion, Error Seeding | Compare the test results for a unit under
| Known Good Unit, etc.). | test with the expected results, and verify
that the method used is consistent with
IEEE and industry approved standards.
Execute the test software on the ATE
system and verify that the system will
accept good product and reject bad.
Process Area | Goals | Activities | Evidence
20. FAA Corrective | 1. Identify and resolve any | Identify the problem and determine the
Action | breakdown in the contractor’s | impact.
quality system.
Determine the appropriate method for
requesting corrective action IAW the QRO
Guidebook.
Determine appropriate time frame for the
contractor to correct the problem.
Perform follow-up action to verify that the
problem was corrected.
ASU-200 SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
STATUS:
COMMENTS:
1.
2.
3.
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
STATUS:
STATUS:
1.
2.
3.
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
COMMENTS:
COMMENTS:
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
STATUS:
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
COMMENTS:
COMMENTS:
COMMENTS:
COMMENTS:
COMMENTS:
1.
2.
3.
COMMENTS:
COMMENTS:
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
SQA_MODEL VERIFICATION RECORD
STATUS:
STATUS:
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
STATUS:
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
STATUS:
1.
2.
3.
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
ASU-200 SQA_MODEL VERIFICATION RECORD (page 2)
COMMENTS:
1.
2.
3.
COMMENTS:
COMMENTS:
1.
2.
3.
COMMENTS:
1.
2.
3.
COMMENTS:
COMMENTS:
1.
2.
3.
COMMENTS:
1.
2.
3.
COMMENTS:
1.
2.
3.
COMMENTS:
1.
2.
3.
COMMENTS:
1.
2.
3.
SQA_MODEL VERIFICATION RECORD
ASU-200 SQA_MODEL
PILOT IMPLEMENTATION VERIFICATION
Date:
VERIFICATION SUMMARY:
RECOMMENDATION FOR CHANGES:

## SQA_Implement
PROCESS | ARTIFACTS | QRO Surveillance | PROCEDURE | FINDINGS
AREA |  | Activities | SUMMARY
Software | Comment Record | Document Review | Review SIR
Development | SIR Record | Corrective Action | Recommend SW Std's
Standards | Corrective Action Record | Audits | Evaluate Plans
| Audit Guide | Inspections | Evaluate Procedures
Review Notes
Design | Audit Report | Document Review | Review Design for:
Methodologies | Progress Report | Corrective Action | Adequacy, Completeness, Acceptability of
and Techniques |  | Audits | Math Models, CASE Tools, OO Design,
|  | Inspections | Data Flow Diagrams, Analysis & Trade-Off-Studies
FAA | Written Recommendations | Document Review | Review SIR Provide Comments to IPT
Pre-Award | Pre-Award Audit Report | Corrective Action | Review, Evaluate, Recommend approval of QA
Process | Audit Guides | Audits | Review on other SW related plans
Inspections
Planning | QRO Contract Plan | Document Review | Review and Analyze contract
| Audit Guides | Corrective Action | documents (i.e. SOW, CDRL's, etc.)
| Audit Schedule | Audits | Review contractor SQA Plans
Requirements | Progress Reports | Document Review | Review SLS ensure consistency, & traceable to
Management | Memo's | Corrective Action | (ORD, ICD, & SOW)
|  | Audits | Review SRS for completeness, correctness,
|  | Inspections | consistency, and testable.
SQA is performing internal audits (Interface Reqmt's)
Software | Progress Reports | Evaluate CASE Tools | Evaluate Project Tools & Verify the contractor has;
Tools | Audit Records | Trainned personnel | demonstrated project tool function correctly, under
control, outputs are used to determine acceptability
Verify SQE is familiar with the tool(s) & their usage
Software | Audit Reoprt | Document Review | Review and evaluate contract documents
Documentation | Audit Guide | Audits | (e.g. CDRL's, DID's, SOW, etc.)
Review | Memo's | Inspections | Review for completeness, correctness, & readability
(Trace Forward, and Backward to reqmt's)
Risk | Progress Status Reports | Document Review | Review contract for Risk Requirements
Management | Memo's | Monitor | Evaluate, track project risk
|  | Track | Communicate risk issues to FAA project personnel
Software | Cost Realism Report | Document Review | Study & Understand contractor SW Eng Envir
Size & Cost | Worksheets | Audit | Use industry approved parametric model (e.g. SLIM)
Estimation | Parametric Model Outputs |  | determine staffing, maturity, & practices
PROCESS | ARTIFACTS | QRO Surveillance | PROCEDURE | FINDINGS
AREA |  | Activities | SUMMARY
SEI-CMM | Audit Guides | Monitor | Use deficiency records to focus on audit activities
& | Deficiency Records | Audit | Monitor contractor process improvement activities
SCE's | Memo's | Document Review | Track SCE rating, ensure contractor maintains rating
Evaluating | Audit Reports | Document Review | Review & analyze programming std's & conventions
Source Code | Corrective Action Record | Evaluate | and verify Headers, comments, size, etc. against
| Data Worksheets | Audit | requirements. Also, evaluate specific design
| Memo's | Inspection | qualification (e.g. complexity, automated tools, etc.)
Risk | Progress Status Reports | Document Review | Review contract for Risk Requirements
Management | Memo's | Monitor | Evaluate, track project risk
|  | Track | Communicate risk issues to FAA project personnel
Software | Cost Realism Report | Document Review | Study & Understand contractor SW Eng Envir
Size & Cost | Worksheets | Audit | Use industry approved parametric model (e.g. SLIM)
Estimation | Parametric Model Outputs |  | determine staffing, maturity, & practices
SEI-CMM | Audit Guides | Monitor | Use deficiency records to focus on audit activities
& | Deficiency Records | Audit | Monitor contractor process improvement activities
SCE's | Memo's | Document Review | Track SCE rating, ensure contractor maintains rating
Evaluating | Audit Reports | Document Review | Review & analyze programming std's & conventions
Source Code | Corrective Action Record | Evaluate | and verify Headers, comments, size, etc. against
| Data Worksheets | Audit | requirements. Also, evaluate specific design
| Memo's | Inspection | qualification (e.g. complexity, automated tools, etc.)
Software | SDF Audit Record | Evaluate | Audit project SDF's & evaluate contents for:
Development | Deficiency Records | Audit | Format & Style Adherence, Internal Consistency,
Files | Memo's |  | Traceability & external consistency, Compliance
with development std's, & Compliance with contract
Statistical | Caluc. Sample Size computations | Audits | Use sampling techniques to determine sample size
Sampling | Control Charts | Inspections | Monitor/Audit processes using statistical methods
| Upper & Lower Control Limits | Monitor | (e.g. SW Eng Indicators, process artifacts, etc.)
Software | Comment Record | Document Review | Review Test CDRL & SOW (MTP)
Testing | Audit Reoprts | Monitor | Assure adequacy of SW Test products (plans, procedures, etc.)
| Test Log | Wittness | Evaluate Test Strategies (Complete & traceable to reqmt's)
|  | Audit | Monitor/Wittness all test conducted IAW approved
test procedures and are under CM control
PROCESS | ARTIFACTS | QRO Surveillance | PROCEDURE | FINDINGS
AREA |  | Activities | SUMMARY
Software | Metric Report | Document Review | Understand FAA Metric Programs (PMS)
Metrics | Metric Charts | Data Collection | Evaluate contractor developed metric reports (feedback to IPT)
| Comment Record | Data Analysis | Collect data that supports measures, and the source
| Excel Spreadsheet | Audits | Produce chart(s) with description and analysis statement
| Other forms of data |  | Produce Metric Reports on a monthly basis
Earned | Worksheets | Document Review | Review CDRL (Cost & Schedule Reporting)
Value | Metric Charts | Data Collection | Calculate the cost & schedule variances (report to IPT)
Reporting | Comments in Progress Report | Data Analysis | Review staffing section of the CPR (determine if staffing is met)
Requirements |  | Audits | When staffing level is at risk, provide comments to IPT
Automatic | Comments in Progress Report | Document Review | Assure test programs are complete & under CM control
Test | Audit Reports | Audits | Compare test results with (UUT) expected results for defects
Equipment | Corrective Action Record |  | Review ATE Log & decrepency reports to assure operastion
(accepts GOOD, rejects BAD products)
Software |  | Document Review | Review SQA & SW Dev. Reqmt's (Plans, Procedures)
Audits |  | Corrective Action | Dev. Audit Guide & Schedule (Frequency)
|  | Data Analysis | Perform Process/Product Audit, analyze findings C/A
|  | Audits | schedule & perform FOLLOW-UP audits/verify C/A taken
FAA | Corrective Action Reports | Document Review | Identify & determine impact of problem
Corrective | Other Reports | Audits | Determine appropriate C/A method (IAW QRO Guidebook)
Action | Audit Guides | Corrective Action | Communicate problem with contractor/ask for correction date
| Memo's |  | Perform FOLLOW-UP, verify problem was corrected
Software | Corrective Action Reports | Document Review | Review SDP and CMP for Identification, Control, Status
Configuration | Other Reports | Audits | Accounting, and Audits. Audit CM for compliance to reqmt's
Management | Audit Guides | Corrective Action | Initate C/A and document findings
| Memo's |  | Perform FOLLOW-UP, verify problem was corrected
SQA_Model Implementation Assessment
SQA_Model Implementation Assessment
SQA_Model Implementation Assessment