## Actions
AMS Integration Action Items Last Update: June 26th, 2007
No. | Integration Actions | Responsible | Date assigned | Date Due | Open | Closed | Comments/Status NOTE! MIT stands for AMS Mechanical Integration Team
0 | Invite M.Molina to ALL integration meetings anywhere in the world. | A. Lebedev, S. Ting | Since the beginning of Time | Every Meeting | X |  | Will end when AMS re-enters the earth's atmosphere with ISS.
1 | Distribute weekly Integration telecon phone number to AMS Integration Team. Telecon at 3 PM Geneva every Tuesday. | K. Bollweg | 2007-03-12 | 2007-03-19 |  | X | Closed 19-Mar-07. Reopened & closed on 20-Mar with new toll-free numbers. K.Bollweg will report any major integration issue to Prof. Ting for a decision.
2 | Add Eric Perrin to Integration Team e-mail distribution. | K. Bollweg | 2007-03-12 | 2007-03-19 |  | X | Closed 19-Mar-07. Also added T. Martin & C. Clark.
3 | Add window for Magnet Field Mapping to schedule | J. Heilig, K. Bollweg | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Closed on 10-Apr.
4 | Setup FTP site for repository of AMS 3D CAD models | A. Eline | 2007-03-12 | 2007-03-19 |  | X | Closed 19-Mar-07. The FTP site was been set up - see e-mail from Mike Capell dated March 20th distributed with Revision 2 of this list.
5 | Establish system for dropping CAD models onto FTP site, tracking that includes a clear identification of the model date, who is responsible for delivering the model, and when an updated model is needed with a due date. | R. Becker | 2007-03-12 | 2007-03-19 |  | X | Use YYMMDD for date. Available CAD files are on site as of 6-Apr to close original action. Robert is updating the model status list. Some users are experiencing a read-write problem
6 | Verify CAD model interfaces and interferences, place checked models on server for access by integration team, and notify integration team members as required when conflicts exist. | R. Becker | 2007-03-12 | On-going | X |  | Robert is the official "Keeper of the Holes." He will use the naming convention in the AMS/USS ICD and will work with C. Cargiulo, F. Cadoux, & J. Kastelic. First release 13-Apr-07. Robert expects to have it done by May 4th. Robert said he would post by 22 June.
7 | Establish integration team mailing list. | A. Eline | 2007-03-12 | 2007-03-19 |  | X | Received test e-mail on March 19th and the list was updated on the 20th. It will continue to be updated as required.
8 | Cable balcony common design to be proposed by AMS MITeam; reactions at bolt locations will provided to CGS for crates bolt analysis. Groups deviating from this common design have to send their balcony model with structural analysis to AMS MITeam for approval. | F. Cadoux | 2007-03-12 | 2007-04-23 | X |  | Update from Franck on 7-May: - we have defined (probably) a maximum of 3 different design . - I still have to perform FEA on : "J" balcony design, "Tracker" balcony design. - We should "close" the design studies for the next Integration meeting in June (time for drawings & manufacturing). - Balcony Weight estimate (for all Crates): 12860 gr | Close design by end of June. Proceed with production in July. Will focus on mods for Tracker balconies. Will meet E. Perrin on 6/21. Tracker - U balcony, J/ECAL balconies weight is still on the order of ~12.8 kg for all balconies. | M. Molina needs to check masses of cables and balcony weights and their effect on the crate links.
9 | Provide information on all MLI layout and fixation. Especially LUSS around RICH to Lower Support Ring of the VC and back of Main Radiators around electronics crates. Also for coverage of the TTCS condensor tubes (JvE to talk to MM). | M. Molina | 2007-03-12 | 2007-04-23 | X |  | Delays due to possible US vendor - some of these around the VC support rings are now provided by MIT. Finalize layout & fixation by end of June - same as action 11. | no update to RICH MLI. Early MLI for VC support rings is about to be contracted. Two proposals in hand. Main radiators & TTCS condensor tubes in September.
10 | Provide information U-TOF MLI fixation point for TRD MLI to K.Luebelsmeyer | G. Laurenti | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Giuliano recommends using X =0 & Y=0 with 2 " diameter velcro patch. Per Craig on 17-Apr, no velcro is needed. Closed May 8th - no velcro needed. | no update
11 | Define fixation of MLI/Beta cloth on Tracker planes and provide pins to Eric Perrin | M. Molina | 2007-03-12 | 2007-04-23 | X |  | CGS contractor will install pins in tracker. | No update - part of early MLI.
12 | MLI fixation devices and pins will be delivered by MLI responsible to each sub-detector in time for the AMS pre integration in order to check any interference. Pre-installation of these devices will be made by MLI responsible. | Various | 2007-03-12 | As required | X
13 | Provide updated presentation on Clean Room space allocation with schedule. Also include plans for all storage outside Clean Room for flight & non-flight hardware, PSS, lifting fixtures, shipping crates, etc. | V. Plyaskine | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN.
14 | Clarify interface between MLI and Star Tracker Lens. | M.Molina & C. Gargiulo | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN. Corrado sent e-mail on 17-Apr outlining this interface. Will be discussed further at CERN during TIM.
15 | Presentation on clean room procedures. | K. Bollweg | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN. Deferred to next Integration meeting at CERN on June 7/8.
16 | Provide AMS Cleanroom Handbook | K. Bollweg | 2007-03-13 | 2007-04-23 | X |  | By April TIM @ CERN. Deferred to next Integration meeting at CERN on June 7/8.
17 | Check MLI or just Beta cloth on -Z surface of Tracker plane #5 and verify model thermal configuration. | M. Molina & C. Clark | 2007-03-12 | 2007-03-19 |  | X | Per Craig, there is nothing on the +Z plane #1 of the Tracker; the bottom has beta cloth + MLI. Marco confirmed this is correct on 21-Mar.
18 | Check low emmisivity surface(s) between Tracker & ACC and verify model thermal configuration. | M. Molina & C. Clark | 2007-03-12 | 2007-03-19 |  | X | Per Craig, the inner shell of the ACC as well as the Tracker are to have low emmissivity surfaces. Marco confirmed the ACC inner does have the low e coating on 21-Mar. On 3-Apr Marco said the low emmissivity coating is not needed on the Tracker.
19 | Add time to schedule to install MLI to back of Main Radiators between STA VC removal and Flt VC Installation. | J. Heilig | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. John has added two weeks - though he hasn't received any inputs from the collaboration.
20 | Send final drawings of TRD MLI to K. Luebelsmeyer. Not sure if these drawings have been sent. Trent will check on 19 June. | J. Cornwell | 2007-03-12 | 2007-03-19 | X |  | Craig will check with John Cornwell; Klaus will send to Marco. As of 27-Mar, Craig will pester John again. Per Craig on 3-Apr, the design is being revised to reverse the MLI to improve static discharge. Final drawings to Klaus by 6-Apr. E-mail from Terry Wille/EC on 6-Apr indicated drawings were not ready. As of 27-Apr the drawings were still stuck in checking at NASA behind work for upcoming flight. As of 15-May, the drawings are released and C. Clark will send to R. Becker for AMS CAD ftp site.
21 | Inform AIDC during weekly videoconference of proposal to incorporate Main Radiator Linear Bearings & brackets into temporary mounting jigs. | R. Becker | 2007-03-13 | 2007-03-29 |  | X | AIDC was asked to modify a radius of one piece of hardware during telecon on 28-Mar. R. Becker notified AIDC at video con on 4-Apr of the linear bearing design. Robert presented the design at AIDC on 16-Apr. AIDC was asked to implement the linear bearing modification.
22 | CGS will provide +X, +Y corner Zenith Radiator mock-up for pre-integration in September 2007. This must include loop heat pipes to Cryocooler. | M. Molina | 2007-03-13 | 2007-09-01 | X |  | This is the corner that is most crowded.
23 | Coordinate TTCS plumbing lines rounting on wake VC rings with SCL. | R. Becker & J. van Es | 2007-03-13 | 2007-03-22 |  | X | Was completed at integration meeting at SCL on 23-Mar. New action items to be added - see AI #39.
24 | Verify if Main Radiators can be moved out with Tracker Radiator Jig and TTCS Boxes in place. | C. Gargiulo | 2007-03-13 | 2007-03-22 |  | X | Both ram & wake Main Radiators can be moved out. However, both of the upper radiator brackets must be dismounted at the crates & USS and removed. Linear bearings will be positioned so that the TRD Gas System box does not need to be moved or removed. Preliminary design scheduled to be ready by 29-Mar per AI #25.
25 | Develop preliminary design for Main Radiator Linear Bearings & brackets | C. Gargiulo | 2007-03-13 | 2007-03-22 |  | X | Preliminary design scheduled to be ready by 29-Mar; was presented during 27-Mar telecon.
26 | Develop design for new LUSS lifting brackets | F. Cadoux | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN. (Originally assigned during January TIM at JSC.) The preliminary design is done, drawings are in work. CGS needs funding to do this analysis. CAD model sent to CGS week of 11 June, 2007. Nastran model was sent by Jacobs to CGS. CGS is working out bugs in transmission.
27 | Develop design for modified LUSS shipping cover & verify clearance with RICH, ECAL & LTOF | F. Cadoux | 2007-03-13 | 2007-04-23 | X |  | By April TIM @ CERN. (Originally assigned during January TIM at JSC.) The preliminary design is done, drawings are in work and will be sent to Giuliano by July TIM. CGS still needs funding to do this analysis.
28 | Fabricate new LUSS lifting brackets | G. Laurenti | 2007-03-13 | 2007-09-01 | X |  | (Originally assigned during January TIM at JSC.)
29 | Fabricate modified LUSS shipping cover | G. Laurenti | 2007-03-13 | 2008-07-01 | X |  | (Originally assigned during January TIM at JSC.) Since this will not be needed until shipping to ESTEC in 2008, a due date is moved to July, 2008.
30 | Verify usefulness of STA VC rotation device at SCL for Tracker & ACC deintegration at CERN off the RAS. Note: this device is also still expected to be required at SCL. | K. Bollweg | 2007-03-13 | 2007-03-23 |  | X | Closed 19-Mar-07: The rotation device at SCL can be used. However, modifications discussed at integration meeting still need to be done. Total weight carrying capability is 1875 kg X 2 = 3750 kg = 8267 lbs. A stand to temporarily set 2 of the 4 USS interface points is still needed while caster wheel brackets or acoustic stands are installed on the VC inteface points to the USS. See AI # 37.
31 | Routing on VC conical flanges of: Tracker Cables, TTCS pipes and wiring, AMSWire cables, TAS fibers, PDS cables, ACC Fiber & Cable Routing, etc. | F. Cadoux | 2007-03-12 | 2007-04-23 | X |  | Mtg held at SCL/SM on March 22nd. Franck is continuing to work with Antonio Alvino. Antonio coming to CERN in early July, 2007 before TIM..
32 | UTOF Special rolling table dwg to be sent to Klaus | G. Laurenti | 2007-03-12 | 2007-03-19 |  | X | Giuliano will send revised drawings to Klaus on 4-Apr. Will incorporate TRD hardware while on UTOF special rolling table (new requirement). Klaus received drawings on 10-Apr. Giuliano will work with Klaus to implement mods.
33 | Send UTOF bracket to corner bracket to Aachen via CERN | G. Laurenti | 2007-03-12 | 2007-04-23 | X |  | By April TIM @ CERN. Giuliano agreed with Klaus to send bracket to Aachen for fit-check in September or to test with the TRD at CERN.
34 | Find another integration secretary than Mike Capell | S. Ting | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Ken is the secretary!
35 | Lowest ECAL blanket fixation provided by C.Clark will not work with proposed cable routing. Work with Franck Cadoux to develop alternate. | C. Clark | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Joe Kastelic & Franck are exchanging CAD files. See presentation dated 27-Mar by Frank Cadoux. The strap from the lower ECAL bracket can be attached to the lower cable bracket with cable ties. Joe K. to define standard grounding wire existing design. Franck to decide which holes he wants the grounding wires attached to.
36 | Add schedule for TTCS pipework on naked flight VC | J. Heilig | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN (JH added two weeks in the schedule).
37 | Work out VC rotation sequence utilizing rotation device and caster wheels at SCL, acoustic test stands, and temporary stands. | K. Bollweg, P. Mott, & R. Stafford Allen | 2007-03-23 | 2007-04-23 |  | X | By April TIM @ CERN. Held telecon with Phil Mott & Ron Mackay on 29-Mar and worked out an acceptable procedure. Will present at April TIM.
38 | Resolve interferences between external Magnet hardware and the USS, VC Shipping Crate, & PSS in the low shipping configuration as well as access issues at the launch pad. | K. Bollweg, R. Mackay, & R. Becker | 2007-03-23 | 2007-04-23 | X |  | By April TIM @ CERN. See e-mail from K. Bollweg dated 26-Mar for details.
39 | Add other new action items from integration meeting at SCL on 22/23-Mar. This involves the TTCS lines and interferences with cabling, crates, and other plumbing. | K. Bollweg, R. Mackay, A. Alvino, & R. Becker | 2007-03-23 | 2007-04-10 |  | X | Robert will send out an e-mail with a presentation documenting all the interferences by May 15th!!! (Overcome By Events - OBE)
40 | Identify all known Cable Balcony interferences for further discussion at April 3rd integration telecon - especially at the U Crates (request by K. Lubelsmeyer). | F. Cadoux | 2007-03-27 | 2007-04-03 |  | X | Also see AI #8. Provide comments to Franck by 9-Apr. Prelim FEM is done - revisions in work with mods from M. Capell. Will defer work on balconies to work on ram & wake cabling. K. Lubelsmeyer is happy with the current proposal. Will try to have integrated proposal at April TIM. Maybe complete balcony design ~1 week after TIM. As soon as Franck receives the bridge design from Karlsruhe he will perform additional calcs.
41 | Establish routing, locations, & orientations for all "normal" helium vents on the Magnet. (As opposed to "emergency" vents from BDs addressed in AI #38.) This may require attachment to TRD M Structure. | K. Bollweg, R. Mackay, R. Becker, & K. Lubelsmeyer | 2007-04-03 | 2007-04-23 | X |  | Try to set up splinter meeting at April TIM. Discussed at 3-Apr & 10-Apr telecons.
42 | Perform cable force test on TRD Cables and provide results. | K. Lubelsmeyer | 2007-04-10 | 2007-04-17 |  | X | Test performed and results provided on 13-Apr. Franck & Klaus to discuss test results at April TIM.
43 | Post AMS schedules on NASA AMS website. | J. Heilig | 2007-04-10 | 2007-04-23 |  | X | Posted on 12-Apr.
44 | Develop April TIM Integration Splinter Meeting schedule and preliminary agenda. | K. Bollweg | 2007-04-10 | 2007-04-17 |  | X | Preliminary schedule and agenda provided with this spreadsheet.
45 | Need detailsfor GPS attachment to radiators. | C. Zurbach | 2007-04-27 | 2007-06-06 | X |  | Marco will send Claude the "thru hole" pattern on the radiator for confirmation. Also check bonding.
46 | Can the PSS be used for the TV tests? Can the PSS support AMS when rotated 90 degrees? Does a new stand need to be developed? | C. Tutt, J. Burger, & K. Bollweg | 2007-04-27 | 2007-05-08 |  | X | Based on the ESTEC drawings provided to J. Burger, C. Tutt & K. Bollweg reviewed the operations required to rotate the USS in the PSS as well as putting the PSS on the 3.16m X 3.16m "Siesmic Structure" at the bottom of the TVT chamber. There would be significant modifications required to the PSS to adapt it to the Siesmic Structure. Thus, a new structure will be required...sorry Robert.
47 | Can the PSS be used for the EMI tests? Does a new stand need to be developed? | M. Capell & T. Urban | 2007-04-27 | 2007-05-15 |  | X | Per M. Capell at the 8-Jun-07 integeration meeting at CERN: The PSS will be used for the EMI tests.
48 | TVT Stand Design, Analysis, Fabrication, and Test. | MIT | 2007-04-27 | Various | X |  | ESTEC needs design by 01-Sep-07. Stand needs to be delivered to ESTEC in August '08.
49 | Determine how to rotate USS without keel attached for TVT. | J. Kastelic | 2007-04-27 | 2007-06-06 | X |  | The USS can be rotated about the Y axis on the primary sill trunnions. A method of using the secondary sill trunnions to react the moment or some acceptable attachment to the lower USS needs to be developed.
50 | Lifting fixtures development for TVT test to rotate USS (in PSS?) with Z-axis horizontal. | MIT | 2007-04-27 | Various | X |  | ESTEC needs design by 01-Sep-07. Lift hardware needs to be delivered to ESTEC in August '08. Need to decide if this is done inside or outside of TVT Chamber.
51 | Update the CGSE model at the launch pad. Also see AI #41. | A. Grechko | 2007-04-27 | 2007-07-01 | X |  | New vacuum line to evacuate PVVV identified on 04-Jun-07
52 | Determine requirements for shipping SFHe in cargo plane and trucks between ESTEC & KSC. | K. Lubelsmeyer & S. Harrison | 2007-05-15 | 2007-06-07 | X
53 | Provide CAD model of AMS test beam area clearly identifying all ferrous metals in the area so that a loads assessment can be done on the magnet. | R. Becker | 28-Oct-05 & 2-May-07 | TBD* | X |  | This was transferred from the OPMT on 2-May-07 (#05-081). The due date is TBD because the location and availability of the Beam test has not been determined. As of 19 June, 2007 the location is known and a floor plan is being developed.
54 | Develop a risk mitigation plan for TTCS in-situ welding during flight integration. Relook at connections or welding at TTCB to TTCS tubing. Preintegration requires electronics to be nearby. Also considerpump controller inside TTCB. | M. Capell | 20-Feb-07 & 2-May-07 | 2008-03-01 | X |  | This was transferred from the OPMT on 2-May-07 (#05-081). Per M. Capell on 12-jun-07, this due date should be March, 2008. Mike plans to put a crate next to the welder and test in Feb '08.
55 | Confirm that the blankets for RICH and ECAL will be available for Pre-Integration activities at CERN. | M. Molina | 23-Feb-07 & 2-May-07 | 2007-04-23 |  | X | This was transferred from the OPMT on 2-May-07 (#05-106). M. Molina confirmed on 8-Jun-07 that the blanket will be available.
56 | Make measurement of the amount of helium that is used during a quench and recharge a test objective. | S. Harrison | 9-Aug-06 & 2-May-07 | 2007-04-15 | X |  | This was transferred from the OPMT on 2-May-07 (#Mag-Review-01). KB needs to review/update with SH.
57 | Add at least one additional thermal cycle to the magnet testing in the MATF. For example: Step 7B - Warm the magnet system to room temperature and recool to 1.8K. | S. Harrison | 9-Aug-06 & 2-May-07 | 2007-03-23 | X |  | This was transferred from the OPMT on 2-May-07 (#Mag-Review-04). This is under review by KB & SH with Bruce Strauss/DOE.
58 | Show how the resistance of the inter-coil joints is planned to be measured in the coming test program. (Related to magnetic field decay) | S. Milward | 9-Aug-06 & 2-May-07 | 2007-04-15 | X |  | This was transferred from the OPMT on 2-May-07 (#Mag-Review-05).
59 | Present plans to measure the expected endurance on the system before flight. | S. Harrison | 9-Aug-06 & 2-May-07 | 2007-04-15 | X |  | This was transferred from the OPMT on 2-May-07 (#Mag-Review-07).
60 | Perform a Test Readiness Review with a committee of independent experts. Experts must have access to the full test plan. | S. Harrison | 9-Aug-06 & 2-May-07 | 2007-01-15 |  | X | This was transferred from the OPMT on 2-May-07 (#Mag-Review-11). Magnet test plan was reviewed without comment by C. Tutt…any further action required? Who else should review?
61 | Turn/lay down the TTCS tubing loops/pigtails to resolve interference with UTOF. Check LTOF as well. | R. Becker to contact B. Verlatt | 2007-06-06 | 2007-06-15 | X |  | Also consider refabricating without all the pigtails as it can be easily shown with a simple test that they are not needed. Their purpose was to prevent yielding of the TTCS tubing; however, the tubes are YIELDED to make the loops! As of 19 June, R. Becker to speak with B.Verlatt again and get new plan and closure date.
62 | CAD model needed for three vertical composite channels for TTCS tubing, cryocooler tubing, and cables | CGS/G. Duchini | 2007-06-06 | 2007-06-20 | X |  | Per M. Molina on 19 June: work ongoing with A. Alvino - design due out by 26 June.
63 | Deliver FEM of VC shipping fixture to SCL/SM | P. Mott | 2007-06-08 | 2007-06-15 |  | X | Sent 18-June (a) SHIPFIXTURESTATIC – Full Shipping Fixture Model with LMSO VC (b) SHIPFIXTUREGAP – Full Shipping Fixture Model with CONM2 for VC (c) SHIPPINGFIXTURETOPPANEL- Simple Plate Model of Top Cover (d) SHIPPINGFIXTURESIDEPANEL- Simple Plate Model of Side Cover
64 | Modify Flight VC shipping fixture for SFHe top-off test at SM and to accommodate Magnet external hardware. | R. Mackay, K.Bollweg | 2007-06-06 | 2007-12-01 | X |  | As of 19-June: The STEP files of the VC Shipping Fixture and Cryocooler models have been uploaded to the JSC file exchange website and are located in the Share Folder.
65 | Reconfigure Tracker Cable Paddles to small panels to solve interference with Star Tracker bracket, and close clearance with UTOF. | MIT & A. Alvino | 2007-06-06 | 2007-07-01 | X |  | Per M. Molina on 19 June: work ongoing with A. Alvino.
66 | Reroute Tracker cables near Star Tracker bracket to avoid interference. | S. Borsini | 2007-06-06 | 2007-07-01 | X
67 | Deliver FEM of PSS to MITeam | P. Mott | 2007-06-08 | 2007-06-15 | X |  | Wasn't this sent?
68 | Send current CAD PSS model to MIT & R. Mackay/SM. | J. Kastelic | 2007-06-06 | 2007-06-15 |  | X | Closed on 18-June. Provided PSS in the high, low and mid configurations. Wts of PSS in three configurations (+~200 lbs during shipping - see 19 June e-mail from J. Kastelic): 4907.982 lbs High Config, Empty, no panels, no lid. 4740.88 lbs Mid Config, Empty, no panels, no lid. 4237.34 lbs Low Config, Empty, no panels, no lid.
69 | Develop mod to PSS shipping panel to relieve interference with new location of BD07 on LSR at 349.6o. BD07 will be oriented in +Z direction. Also look at Cryocoolers (without balancer?) to determine if additional mods are required to PSS shipping panels. | MIT & R. Mackay | 2007-06-06 | 2008-06-01 | X |  | Cryocooler model was uploaded to the JSC file exchange website and are located in the Share Folder on 19 June.
70 | Determine if the normal helium main vent needs to be routed to a particular location/orientation inside or outside the AMS envelope to avoid a helium "cloud." (Consider corona conditions.) | T. Siedenburg, V. Choutko, S. Harrison | 2007-06-06 | 2007-07-01 | X? | X? | Per Prof. Ting & M. Capell, the main helium vent will be routed to a point above the upper VC to USS joint at the +X, -Y corner. Per M. Capell, corona will not be a problem (see 15 June e-mail exchange). However, see response from F. Palmonari dated 19-June at right: Angle toward +Y direction to aim away from EVA worksite for PVGF. Also attach to this vent at the TVT. | The TOF PMTs are inside an envelope light-tight with small vents, so one can expect the concentration of He inside TOF to increase with time, with respect to other molecules. I ask therefore to have the He vent as far as possible to the UTOF counters. Honestly I have no quantitative arguments to support my concern ( I have no idea how and where the magnet He will diffuse around AMS) so take this as a remark. Federico
71 | Move pilot valves for DV15A/B/C/D to eliminate interference with crates & VC shipping fixture | R. Mackay | 2007-06-06 | 2007-06-14 | X
72 | Define how we intend to test the O-ring test ports and when. | S. Harrison | 2007-06-06 | 2007-06-14 | X
73 | Shorten plumbing and bracket for BD11A/B to provide more clearance to TRD Gas Supply System Xenon Tank bracket. | R. Mackay | 2007-06-06 | 2007-06-14 |  | X | It now clears - its good enough.
74 | Locate and reorient DV20 outlet so it's accessible to CGSE at Pad | R. Mackay | 2007-06-06 | 2007-06-14 | X
75 | Send new DV20 outlet info to A. Grechko so he can design the CGSE connection at Pad | R. Mackay | 2007-06-06 | 2007-06-14 | X
76 | Reroute vacuum line from MV43 to DV 20ABCD to avoid interference with Tracker cables | R. Mackay | 2007-06-06 | 2007-06-14 | X
77 | Move PVVV lines on conical flange up to the top of the conical flange to avoid interference with cables and TTCS lines. | R. Mackay | 2007-06-06 | 2007-06-14 | X
78 | Reroute & reorient current lead exhaust vent to + or - X side of USS to allow connection to CGSE. | R. Mackay | 2007-06-07 | 2007-06-14 | X |  | MIT prefers the -X side because of less plumbing and free holes near strap port. However, -X side has several Magnet avionics cables not shown in the CAD models yet.
79 | Resolve CAB interfence with CAB triangular brackets and move heat pipe retainer bracket by 1-2 holes on underside of USS Upper Bridge Beam. Notch upper corner of CAB to accommodate Upper Tracker Radiator Screw - consider sharing bolt hole. Check shared bolt analysis and finalize assembly procedure with MIT. | C. Gargiulo, A. Assenza & CRISA | 2007-06-07 | 2007-06-22 | X |  | Corrado sent a proposal to CRISA - they have reviewed and are modifying their model. Marco accepts the mods to the sliding bracket. Expect to complete assessment and have new design finalized by 23-July. Corrado will present at TIM. See current details at right: | 1) "resolve CAB inteference with CAB triangular bracket": Interference already discussed and solved in the past between CRISA, Jacobs and CGS One of the beam profile, taking in place the USS Heat Pipes, is properly cut so to avoid interference with the brackets. 2)"and move heat pipe retainer bracket by 1-2 hole on underside of USS Upper bridge beam": CGS, responsible for all the CAB external thermal hardware, agreed in moving the retainer bracket by 1 hole as proposed by MITeam. CAD model retainer will be updated (new location)by MITeam and posted to AMS exchange directory by 26 June. 3)"Notch upper corner of CAB to accommodate Upper tracker radiator screw": CRISA agreed on the modification proposed by MITeam to add a chamfer in the CAB baseplate upper corner. CAD model will be modified (add a chamfer) and sent to MIT by CRISA (it was promised by Guillermo Munoz to be posted on AMS exchange/incoming CAD directory for the end of last week). CRISA will modify hardware (mechanical pieces) accordingly. 4)"consider sharing bolt hole, check shared bolt analysis": Jacobs (Carl Lauritzen) checked and confirmed CAB analysis is correct and bolt analysis has been performed with appropriate loads. Jacobs will procure bolts to fix the CAB to the USS and arrange to have the bolts shipped to CERN to be available for integration of the CAB to the USS. 5) "finalize assembly procedure of the CAB to the USS": MITeam will provide assembly procedure for CAB integration by 7 August
80 | Resolve interferencebetween TSPD to S & T Crates and UPD to U Crate. 70 mm maximum available from xPD wall to CAB wall. | M.Capell | 2007-06-07 | 2007-07-07 |  | X | M. Capell states they will remove the backshell and provide stress relief as required on a case-by-case basis.
81 | Schedule inputs: Line 57 should indicate June 1st since crates are already at CERN. Radiator flight brackets are installed before the sliding brackets Electronics Crates Jigs must be ready in the Cleanroom by July 16th CryoMagnet arrives at CERN NLT end of February, 2008 ECAL and stand must be ready in the Cleanroom by July 16th Line 206: Install ECAL thermostats offline before Setember 18th; 3 day activity LTOF will arrive at Cleanroom by July 1st. Offline testing through September. Incorporate updates from M. Molina's integration presentation. Swap lines 277 & 278 (Debris shields vs MLI on RICH). Add tracker feet metrology to schedule at CERN | J. Heilig | 2007-06-07 | 2007-06-15 |  | X | Closed June 15th!
82 | Develop CryoMagnet external hardware mockups with full size drawings to simulate hardware. | MIT Group | 2007-06-07 | 2007-08-31 | X
83 | Determine if HV bricks can be installed after cables | F. Cadoux | 2007-06-07 | 2007-06-30 | X |  | Meeting with RICH personnel in July to determine.
84 | Provide new delivery date for RICH/LTOF lateral MLI to J. Heilig | M. Molina | 2007-06-07 | 2007-07-02 | X |  | No news as of 19 June.
85 | Send PSS floor to VC dimension with PSS in mid & low configs to E. Perrin. | P. Mott | 2007-06-07 | 2007-06-15 |  | X | Provided 13 June.
86 | Update late electronics crates delivery dates & provide to J. Heilig | G. Ambrosi | 2007-06-07 | 2007-06-22 | X |  | Will require several iterations…
87 | Send LUSS lifting plate and LUSS shipping fixture modification designs to CGS | F. Cadoux | 2007-06-07 | 2007-06-15 |  | X | See AI # 26.
88 | Send LUSS FEM to CGS | C. Lauritzen | 2007-06-07 | 2007-06-15 |  | X | Sent zip file on 15-June with set of NASTRAN bulk data files for the lower USS, RICH, ECAL, and LTOF to assess the lifting configuration of this assembly.
89 | Perform analysis on LUSS with new lifting plates and LUSS shipping fixture | M.Molina | 2007-06-07 | 2007-07-15 | X
90 | Determine if we need to make a CGSE connection to flight helium vent at ESTEC for TVT to verify baro switch operation | M. Capell & S. Harrison | 2007-06-07 | 2007-06-11 |  | X | Yes, see very long e-mail chain titled "Main He flight vent and BSE during ESTEC TVT"
91 | Verify ECAL flight mounting bolts are ordered/delivered | P. Mott | 2007-06-07 | 2007-06-15 |  | X | The flight bolts are available at Jacobs and will be delivered to CERN in July.
92 | Evaluate use of RAS or PSS in TVT Chamber - or develop a new fixture | R. Becker. C. Gargiulo | 2007-06-08 | 2007-07-23 | X |  | Present results at July TIM.
93 | Resolve TAS fibre fixation interference with TRD MLI | F. Cadoux | 2007-06-07 | 2007-07-07 | X |  | Meeting with E. Perrin on 21 June
94 | Define PSS/USS movements into TVT and then to EMI Chambers | J. Burger | 2007-06-08 | 2007-07-23 | X |  | Received new floor plan from ESTEC - movement plan is in work. Present at next TIM
95 | Determine if PSS mod is required to accommodate height of Zenith Radiators | J. Kastelic | 2007-06-08 | 2007-07-23 | X |  | Currently, the Zenith radiators are .33 inches from the internal beams of the PSS cover per the models. CGS is building a ¼ zenith radiator mockup ready by Sept 2007. The height will be high fidelity. Joe Kastelic to present possible solutions at July TIM. | Currently, the Zenith radiators are .33 inches from the internal beams of the PSS cover. This is a nominal dimension so we could easily see an actual tolerance stream closing that gap but in any case too close for comfort. The top cover cannot be shimmed by any measurable amount due to maximum dimensions in the cargo bay of the 747. Suggested resolutions: 1. Acquire a high fidelity model of the Zenith Radiator. 2. Identify specific locations on the radiator at risk for interference with cover. 3. Assess and possibly modify the beams locally. 4. Or develop another workaround. | We are already building a ¼ zenith radiator for trial assemblying. It will be ready in September 2007. We will make sure it is high fidelity as far as the height is concerned - Marco
96 | Send E, R HV bricks integration schedule to J. Heilig | C. Ginzo | 2007-06-07 | 2007-06-22 | X |  | Discuss at meeting with MIT & CRISSA at July meeting
97 | Finalize TV test plan, test objectives, test configuration, & test specification and provide to ESTEC. | M. Molina | 2007-06-08 | 2007-07-23 | X |  | Inputs required from C. Clark
98 | Finalize EMI test plan, test objectives, test configuration, & test specification and provide to ESTEC. | T. Urban | 2007-06-08 | 2007-07-23 | X |  | Joe Burger will find out when ESTEC really needs what info. Preliminary answers are shown at right: | -Finalize EMI test plan, test objectives: We know this will happen later. -test configuration: The discussion that we’ve had in the last month re: the inability to perform magnet charging is the only matter that was un-resolved. I believe it to now be resolved. -test specification: We will test to the standard matrix of EMI spec.s that we’ve used all along.
99 | Define CGSE requirements for TVT & EMI test. | A. Grechko | 2007-06-08 | 2007-07-23 | X |  | Alexandre needs to be at TIM in July
100 | Define test harness and connector requirements for TVT & EMI test. | X. Cai | 2007-06-08 | 2007-07-23 | X |  | Per Mike on 19 June - Cai is on track for this
101 | Define TRD configuration with respect to how much Ar/Xe/CO2 gas will be needed and if any GSE piping will be required to fill and where. How will this be accomplished at KSC? Also define requirements to vent Ar/Xe/CO2 in TV Chamber and EMI Chamber. | T. Kirn | 2007-06-08 | 2007-07-23 | X
102 | Define access requirements inside the Large Space Simulator (LSS/TV Chamber) | R. Becker | 2007-06-08 | 2007-07-23 | X
103 | send cad models of PLF & MPLF to the MITeam | J. Kastelic | 2007-06-19 | 2007-06-26 | X
104 | Design additional small box close to the CAB needed to house the BaroSwitch Electronics (BSE). | MITeam | 2007-06-19 | 2007-07-23 | X |  | M. Capell inputs needed.
105 | Provide details on Helium Vent Pump mounted to USS. It is needed for Pre-integration to define routing of plumbing and cables. | M. Gallilee | 2007-06-26 |  | X
106 | Define mounting requirements for He Vent Pump | MITeam | 2007-06-26 |  | X
107
108
109
110