Version 1.4

October 29, 2007

Table of Contents

Section 1	Executive Summary	iii

Section 2	Introduction	1

2.1	Purpose	1

2.2	Legislative Background and Associated Guidance	2

2.3	Scope	2

2.4	Definitions	3

2.5	Thresholds for Real Property Investments	4

2.6	Document Structure	6

Section 3	Real Property CPIP Phases	8

3.1	Planning and Budgeting Phase	8

3.2	Acquisition Phase	9

3.3	Management-In-Use Phase	12

3.4	Disposition Phase	13

SECTION 4	 Non-Major Investment CPIP instructions	15

Section 5        Significant Investment CPIP instructions	22

Section 6	  Major Investment Process	34

Appendix A—Acronym List	A-1

Appendix B—Project Data Sheet	B-1

Appendix C—Real Property Investment Report	C-1

Appendix D—Capital Asset Plan	D-1

Appendix E—Asset Management Review Board Charter	E-1

Appendix F—Agriculture Acquisition Regulation (AGAR) Advisory - 83	F-1

Appendix G—U.S. Department of Agriculture Real Property Disposition Process, September 20, 2006	G-1

Document Revision History

| Version | Date | Revisions |
| --- | --- | --- |
| 1.0 | 1/29/07 | Initial Draft |
| 1.1 | 3/16/07 | Revisions from stakeholder comments |
| 1.2 | 4/5/07 | Internal revisions |
| 1.3 | 5/4/07 | Revisions from stakeholder comments |
| 1.4 | 10/29/07 | Final |

# Executive Summary

On February 4, 2004, President George W. Bush signed Executive Order (E.O.) 13327, Federal Real Property Asset Management, setting expectations and requirements to "promote the efficient and economical use of Federal real property resources in accordance with their value as national assets and in the best interests of the Nation.”  Later that year, the President's Management Agenda (PMA) was expanded to include a new initiative for improving federal real property asset management.

In order to achieve the goals mandated by E.O. 13327, the United States Department of Agriculture (USDA), has developed a real property Asset Management Plan (AMP).  The success of USDA’s AMP implementation directly influences the ability of organizations within the Department to execute business plans and fulfill their missions.  Recognizing both the importance and impact real property investments (and projects) have on the Department and its success attaining its strategic goals, the Secretary has authorized the establishment of an ongoing effort which supports a formal investment analysis and decision-making process.

USDA must have a disciplined capital programming process that addresses project prioritization between new assets and maintenance of existing assets, risk management, and cost estimating to improve the accuracy of cost, schedule and performance provided to management, and the other difficult challenges proposed by asset management and acquisition.  The purpose of the Capital Programming and Investment Process (CPIP) instructions, herein referred to as CPIP, is to provide guidance for a disciplined capital programming process, as well as techniques for planning and budgeting, acquisition, management-in-use and disposition of capital assets.  At the same time, agencies are provided flexibility in how they implement the key principles and concepts of capital programming.  CPIP is the primary process used to make decisions regarding the construction, consolidation/sharing, restoration and disposition of real property investments.

The CPIP instructions support the transition from a project-centric approach to a portfolio-centric approach to real property management.  CPIP is USDA’s primary process for (1) making decisions about initiatives in which USDA should invest and (2) creating and analyzing the associated rationale for these investments.

Effective capital programming uses long range planning and a disciplined, integrated budget process as the basis for managing a portfolio of capital assets to achieve performance goals with the lowest life-cycle costs and least risk.  This process should provide agency management with accurate information on acquisition and life-cycle costs, schedules, and performance of current and proposed capital assets.  Project Managers, when developing the costs, schedule and performance goals on developmental projects with significant risk must, therefore, provide the Agency Asset Management Review Board (AMRB) with risk adjusted, most likely cost, schedule, and performance goals.  Without the knowledge of the risks involved managers at all levels cannot make the best decisions for the allocation of resources among the competing investments.

Document Overview

These USDA Real Property Capital Programming and Investment Process (CPIP) instructions identify the processes and activities necessary to ensure the Department’s real property projects are well thought out, cost-effective, and support the missions and business goals of the organization.  It is based on guidance from both the Office of Management and Budget (OMB) and the Government Accountability Office (GAO).

At the highest level, the CPIP is a circular flow of USDA’s real property investments through four sequential phases and for the processes to follow through these phases for each of the defined real property investment thresholds in USDA.  As shown in Figure 1, these phases are:

Planning and Budgeting Phase—Executive decision-makers assess each proposed project’s support of USDA’s strategic and mission needs.  Project Managers compile the information necessary for supporting a detailed proposal assessment.

Acquisition Phase—Project analyses are conducted and the Agency decision-makers choose the real property projects that best support the mission of the organization and validate the planning and budgeting phase.  USDA ensures, through timely oversight, quality control, and executive review, that real property initiatives are executed or developed in a disciplined, well-managed, and consistent manner through the various acquisition steps.

Management-In-Use Phase—Actual results of the implemented projects are compared to expectations to assess investment performance.  This is done to assess the project’s impact on mission performance, identify any project changes or modifications that may be needed, and revise the investment management process based on lessons learned.  Real property investments are assessed to ascertain their continued effectiveness in supporting mission requirements, evaluate the cost of continued maintenance support, and consider replacement options.  Effective Management-In-Use requires the continuous monitoring of an Agency’s inventory of capital assets to ensure they are maintained at the right size, cost and condition to support the Agency mission and objectives.

Disposition Phase—Asset disposition is the culmination of previous planning, budgeting, acquisition, and Management-In-Use efforts and should follow established best practices in the disposition of capital assets.

Figure 1:  The Four CPIP Phases

# Introduction

## Purpose

The USDA plays a lead role in America’s food and agricultural system, helping the farm and food sectors operate in a highly competitive marketplace that must continuously respond to changing consumer demands for high quality, nutritious, and convenient food and agricultural products.  USDA carries out a wide variety of services and activities related to the management, research and conservation of the Nation’s agricultural resources.

Fulfilling its mission work is a paramount consideration throughout USDA.  For this reason, the land, facilities, and other real property held by USDA are an integral support component to its mission.  The strong relationship between USDA’s real property and its mission is the major reason why real property decisions are typically made at the agency and field levels.  This mission driven organizational structure has fostered a decentralized real property decision making environment that reflects a need to support a variety of missions across a wide variety of asset types in different geographic areas.

Federal agencies are facing increasing challenges in their efforts to manage their real property investments as they are operating in an age where the capability to deliver services to internal and external customers is essential to core business strategies.  Decreased funding and budget cuts have underscored the need for agencies to plan, allocate and manage funds based on sound investment strategies and to manage real property investments as capital assets.  Additionally, evolving Federal guidance has mandated the establishment and management of synergistic capital planning to ensure that investment decisions regarding the use and purchase of real property correlate with core business processes.

In response to E.O. 13327 and in conjunction with the PMA, USDA has emphasized the need to maximize and efficiently utilize its accessible resources to effectively manage its real property investments and to minimize redundancies.  This will be accomplished through a modification of the USDA real property portfolio management procedures to ensure that these more stringent real property governance practices are in place and followed.  To standardize the governance process, USDA will follow the USDA CPIP instructions.  The CPIP instructions provide USDA with a structured, performance-based, integrated approach to managing the risks and returns of capital assets for a given mission.  The CPIP instructions provides for the annual cycle of selection, and a continuous control, life cycle management, and evaluation of design and construction investments.

These instructions describe the USDA CPIP instructions including business cases as reflected in OMB Circular A-11 Exhibit 300s (Exhibit 300) and the Capital Programming Guide, supplement to OMB Circular A-11, Part 7:  Planning, Budgeting, and Acquisition of Capital Assets, June 2006.  It outlines a framework for USDA and its agencies to effectively manage its real property investment portfolio, which allows USDA to optimize the benefits of limited real property assets, ensure investments meet the strategic needs of the USDA and comply with applicable laws and regulations.  It also provides the framework within which USDA can formulate, justify, manage, and maintain a portfolio of design and construction investments.

These USDA Real Property CPIP Instructions are designed to supplement detailed formal project management training and general awareness training by providing managers and staff with practical information designed to help them better understand capital asset planning at USDA and meet the requirements set forth by Congress, OMB, and the Department.  This process provides a means for USDA to promote efficient and economical use of the Federal real property resources required to support the Department's missions and strategic goals.

## Legislative Background and Associated Guidance

The following statutes and guidance require Federal agencies to revise their operational and management practices to achieve greater mission efficiency and effectiveness.  They include:

- Federal Managers Financial Integrity Act of 1982

- The Chief Financial Officer (CFO) Act of 1990

- Federal Financial Management Improvement Act of 1996

- The Government Performance and Results Act of 1993 (GPRA)

- The Federal Acquisition Streamlining Act of 1994 (FASA)

- The Paperwork Reduction Act of 1995 (PRA)

- The Government Paperwork Elimination Act of 1998 (GPEA)

- The E-government Act of 2002 (P.L. 107-347)

- Executive Order 13327, Federal Real Property Asset Management (02/04)

- Executive Order 13423, Strengthening Federal Environment, Energy, and Transportation Management (01/07)

- Additional information related to USDA real property policy and procedures can be found on the real property website at http://www.usda.gov/da/pmd

.

## Scope

A formal capital asset management infrastructure is a best practice used throughout industry and by many government agencies to establish clear lines of authority, responsibility, and accountability for the management of capital assets.  Within USDA, an Agency Asset Management Review Board (AMRB) is responsible for reviewing its entire capital asset portfolio on a periodic basis and making decisions on the proper composition of the assets needed to achieve strategic goals and objectives within the budget limits.  In addition to the review by the Agency AMRB, each major project requires review by the Departmental AMRB.

In addition to a review by the Departmental or Agency AMRB, depending on the dollar threshold, each project should consider establishment of an Integrated Project Team (IPT) composed of a qualified Project Sponsor and necessary personnel from the user community, budget, accounting, procurement, value management, and other functions to be formed, as appropriate, to:

- Establish a baseline inventory of existing capital assets;

- Analyze and recommend alternative solutions;

- Manage the acquisition if approved; and

- Manage the asset once in use.

All real property projects within USDA must comply with these CPIP instructions and provide information to the applicable USDA agency for inclusion in the agency real property portfolio.  Exemptions to these instructions are granted only in exceptional circumstances.

Although all real property projects above the agency defined minimum thresholds must be reviewed by the Agency Asset Management Review Board (AMRB), not all real property projects must be reviewed by the Departmental AMRB.  Only those projects that are considered to be “major” and strategic investments for the Department are required to be included in the Departmental AMRB executive portfolio.  It is expected that each individual USDA agency will use the processes outlined in this instruction document or have a similar process, manage its own portfolio, and create associated thresholds.  Each agency is expected to use a process similar to the CPIP instructions to manage its “significant” investments.  For non-major investments agencies will determine what degree of project controls will be implemented based on scope, complexity and cost of the project.

## Definitions

Capital Assets:  Are land, buildings, and structures that are used by the Federal government and have an estimated useful life of two or more years.  Capital assets exclude items acquired for resale in the ordinary course of operations or held for the purpose of physical consumption such as operating materials and supplies.  The cost of a capital asset is its full life-cycle costs, including all direct and indirect costs for planning, acquisition, operations and maintenance (including service contracts), and disposal.  Capital assets may be acquired in different ways:  through purchase, construction, or manufacture; through a lease-purchase or other capital lease, regardless of whether title has passed to the Federal Government; through an operating lease for an asset with an estimated useful life or two year or more; or through exchange.  Capital assets include the environmental remediation of land to make it useful; leasehold improvements and land rights; assets owned by the Federal Government but located in a foreign country or held by others (such as federal contractors, state and local governments, or colleges and universities); and assets whose ownership is shared by the Federal Government with other entities.  Capital assets include not only the assets as initially acquired but also additions, improvements, modifications, replacements, rearrangements and reinstallations, and major improvements.  Examples include:  office buildings, hospitals, laboratories, schools, dams and water resources projects, and power plants.  Capital assets may or may not be capitalized under Federal accounting standards.  Examples included heritage assets and stewardship land.

Capital Programming:  Means an integrated process within an agency for planning, budgeting, procurement and management of the Department’s portfolio of capital assets to achieve agency strategic goals and objectives with the lowest life-cycle cost and least risk.

Capital Project (investment):  Means the acquisition of a capital asset and the management of that asset through its life-cycle after the initial acquisition.

Earned Value Management (EVM):  Is a project management tool that effectively integrates the investment scope of work with the schedule and cost elements for optimum investment planning and control.

Major Investment:  A capital project that requires special management attention because of its: (1) importance to the Department’s mission; (2) high development, operating, or maintenance costs; (3) high risk; (4) high return; or (5) significant role in the administration of a Department’s programs; (6) acquisition cost is equal to or exceeds $10M.  Major investments submit a Capital Asset Plan and Business Case and follow the Exhibit 300 process.

Significant Investment:  A capital project that is equal to or greater than the GSA prospectus level and less than $10M.

Non-Major Investment:  A capital project is less than the GSA Prospectus level.

Planning:  Preparing, developing or acquiring the information needed to design the investment, assess the benefits, risks, assess alternatives, establish costs, schedule and performance goals for the selected alternative.

Project Sponsor:  The Project Sponsor is an agency representative who is responsible for the overall management and performance of the project.  It should be a senior individual in the organization with requisite management and business skills to lead the capital asset investment and work with the Project Manager

Project Manager:  A Project Manager is the individual who is designated as responsible and accountable for the day-to-day performance of the project

## Thresholds for Real Property Investments

Major real property investments are considered to be strategic for the Department and, thus, have a greater documentation burden, including being individually reported to OMB on an Exhibit 300.  They are also included in the Departmental AMRB executive portfolio.  Major real property investments meet at least one of the following criteria:

- Total design and construction costs equal to or greater than $10 million

- Directly supports the President's Management Agenda items of "high executive visibility"

- Inter-agency project

Major investments are capital projects that require special management attention because of their importance to the agency mission; high development, operating, or maintenance costs; high risk; high return; or their significant role in the administration of agency programs, finances, property, or other resources.  Major investments should be separately identified in the agency’s budget.

Significant and non-major investments that do not meet the above criteria are to be managed by the capital programming functions within each individual agency.  As such, each managing agency is to have:

- A process for proposing, reviewing, and monitoring its real property investments

- An AMRB responsible for recommending final investment decisions to the Agency Head and overseeing the real property investment management process

- Relevant tools for supporting its real property investment management process

- Supporting documentation showing the ongoing operations of the process

For all investments, the Departmental AMRB primary responsibilities are to:

- Oversee a USDA real property portfolio that best supports the Department’s missions and program delivery processes through annual update of the Three-Year Rolling Timeline

- Assemble a consolidated USDA real property portfolio using a standard set of criteria

- Ensure the Department’s Asset Management Plan is followed by USDA agencies

- Ensure that the Department’s real property program remains in compliance with E.O.  13327 and implementing directives

- Ensure that the agencies’ projects are linked to strategic goals and performance measures

For major projects (equal to or greater than $10 million), the Departmental AMRB provides recommendations on agency proposed capital investments affecting the USDA portfolio to the Budget and Performance Integration Board (BPIB), which consists of the Deputy Secretary and Office of Budget and Program Analysis (OBPA).  It is also responsible for setting performance goals, assessing how well investments meet the goals, and how agencies are meeting performance measure targets.  The Departmental AMRB is chaired by the Assistant Secretary for Administration (ASA).

AMRB authorities for projects within the CPIP instructions are based upon the value of the project as shown in Table 1 below.

| Investment Type | Project Value | Required Review Documentation | Review Authority | Approval Authority |
| --- | --- | --- | --- | --- |
| Major | ≥ $10M or High Risk | Capital Asset Plan | Departmental Asset Management Review Board will review agency documentation and provide recommendations to the Budget and Performance Integration Board | Secretary |
| Significant | ≥ GSA prospectus level to < $10M | Real Property Investment Report | Agency Asset Management Review Board | Agency Headquarters |
| Non-Major | < GSA prospectus level | As determined by Agency Headquarters | Agency Headquarters will determine asset management review authority | Agency Headquarters may delegate approval authority |

Table 1:  Investment Review and Approval Levels of Authority for the Department

## Document Structure

This document is divided into six sections and seven appendices as described below:

- Executive Summary.  Provides an overview of the CPIP instructions.

- Introduction.  Describes the CPIP purpose, legislative background and associated guidance, scope, definitions, thresholds for real property investments and document structure.

- CPIP Phase Overview.  Provides a process and mechanism to assess an investment’s support of agency strategic and mission needs.

- Non-Major Investment CPIP instructions.  Provides processes to ensure that Non-Major real property investments are chosen that best support the agency’s mission and strategic goals that actual results are compared to expected results following project completion.

- Significant Investment CPIP instructions.  Provides processes to ensure that Significant real property investment initiatives are conducted in a disciplined, well-managed, and consistent manner, which promotes the delivery of quality products and results in projects that are completed within scope, on time, and within budget.

- Major Investment CPIP instructions.  Provides processes to ensure that Major real property initiatives are selected, executed and maintained to best support the agency’s mission and strategic goals.  It includes comparing actual to expected results once a project has been fully implemented.

Appendices:

- Appendix A.  Acronyms used throughout this document

- Appendix B.  A template for evaluating the mission need of a new real property investment proposal (Project Data Sheet)

- Appendix C.  A template and guidance to provide information related to the ongoing evaluation of the real property investment and projects (Real Property Investment Report)

- Appendix D.  The written template and guidance for the OMB Capital Asset Plan (CAP)/OMB Exhibit 300

- Appendix E.  The Departmental Real Property AMRB Charter and the associated operating procedures necessary to conduct investment reviews

- Appendix F.  A copy of the Agriculture Acquisition Regulation (AGAR) Advisory-83

- Appendix G.  U.S. Department of Agriculture Real Property Disposal Process

# Real Property CPIP Phases

The CPIP is an ongoing process in which proposed and ongoing projects are continually monitored throughout their lifecycle.  Successful investments and those that are terminated or delayed are evaluated both to assess the impact on future proposals and to benefit from any lessons learned.  The CPIP contains four Phases (Planning and Budgeting, Acquisition, Management-In-Use, and Disposition).  Additional guidance related to the investment thresholds is found in Section 2.4.  Specific agency steps to follow in the various phases are available for Non-Major Investments in Section 4, for Significant Investments in Section 5 and Major investments in Section 6.

Completing one Phase is necessary before beginning a subsequent phase.  This ensures that each investment receives the appropriate level of managerial review and that coordination and accountability exist.  Exceptions to CPIP requirements must be identified in the individual investment’s project plan.  A brief description of each phase follows.

## Planning and Budgeting Phase

The Planning and Budgeting Phase provides a process to:

- Assess a real property investment’s support of both departmental and agency’s strategic and mission needs

- Provide initial analysis to further support real property investments

- Submit agency portfolio thru agency/Departmental AMRB review process

Agency decision-makers assess each proposed investment’s support of USDA’s strategic and mission goals and incorporate it into a multi-year investment plan called the Three-Year Rolling Timeline.  Program/Project Managers compile the information necessary for developing preliminary business cases supporting multi-year plans.  These individual project proposals (Project Data Sheets) are assessed and prioritized in the Three-Year Rolling Timeline.

The Planning and Budgeting Phase of the real property investment management process determines priorities and makes decisions about which projects will be funded during the year.  The goal of the Planning and Budgeting Phase is to ensure that the Department’s real property investment portfolio is comprised of the appropriate range of investments that will best support its mission and strategic goals.  The Department has a real property project portfolio whose composition changes as investments are modified, added to, or deleted from the portfolio.  An analysis of the existing portfolio of real property investments, commonly done as part of a disposition process, helps to ensure that agency managers are informed of current costs, benefits, and risks associated with the existing portfolio.

The primary Planning and Budgeting Phase occurs annually when the Agency AMRB internally reviews, evaluates, and selects the real property investments to be included in the portfolio.  This process directly contributes to the Department’s budget request and submission process and results in the formulation of the real property portfolio for the current fiscal year (FY) and a projection for the following two fiscal years (FY+2 year).

The Planning and Budgeting Phase must also consider:

- How the investment supports the PMA, Secretarial priorities, Congressional mandates, and the Department’s and agency’s strategic goals and objectives;

- An alternatives analysis; Cost Benefit Analysis (CBA) and budget estimate, including risk-adjusted Return on Investment (ROI) and Net Present Value (NPV) calculations;

- Performance measures;

- How risks will be managed; and

- Agency investment review schedules.

Sustainability has become an overarching theme for incorporating the many Executive Order and statutory goals designed to protect the environment, conserve energy, minimize waste and promote federal leadership as good stewards of our natural resources in a cost-effective and sensible manner.  In January 2006, a Memorandum of Understanding (MOU) was signed by a majority of Federal agencies to consider sustainability in buildings.  The main objective of this MOU is that the Federal Government should plan, acquire, site, design, build, operate, maintain and ultimately dispose (or plan for reuse) of buildings and facilities in a manner that achieves agencies’ functional missions, uses sound financial practices, and provides a healthy and safe workplace, all while protecting and sustaining the environment.  Agencies need to consider all phases in the capital assets’ lifecycle, including deconstruction or reuse.  This MOU has been superseded and incorporated into Executive Order 13423, Strengthening Federal Environmental, Energy, and Transportation Management in addition to the requirements of the Energy Policy Act of 2005.  Sustainability should be considered for all projects.

Significant and Major investments should have completed Project Data Sheets (templates are in Appendix B).  Non-Major investments should consider the information requested in this documentation when selecting and reviewing investments.  At a minimum, agencies must take into consideration the applicable performance measures and how the project, regardless of cost, may affect the Department’s overall performance measures.  Agencies should have the capability to produce this information related to these investments.

Departmental decision-makers assess these investments in the following manner:

- Non-Major Investments:  Review of the compilation of the agency portfolio in the Three-Year Rolling Timeline

- Significant Investments:  Review of the individual projects in the Three-Year Rolling Timeline

- Major Investments:  Review of the individual Project Data Sheets for recommendations for agency approval and inclusion in the Three-Year Rolling Timeline

## Acquisition Phase

The CPIP Acquisition Phase begins once investments have been selected, budgeted, and have received funding.  The Acquisition Phase is characterized by decisions to continue, modify, or terminate a project.  Decisions are based on reviews at key milestones during the project’s development lifecycle.  The objective of the Acquisition Phase is to ensure, through timely oversight, quality control, and executive review, that capital investments are conducted (designed and constructed) in a disciplined, well-managed, and consistent manner.  Investments should be closely tracked against the performance measures and ensure that the project promotes the delivery of quality products and results in capital investments that are completed within scope, on time, and within budget.  During this process, senior managers should regularly monitor the progress/performance of ongoing capital investment projects against projected cost, schedule, performance, and delivered benefits.  Not every project will achieve the cost-benefit expectations of the Planning and Budgeting Phase.  If the Earned Value Measurement System and other management tools indicate that the planning expectations are not realized during the Acquisition Phase, agencies should undertake benefit-cost analysis, to evaluate whether the benefits of completing the project are worth the additional costs, schedule delays, or performance reductions that would be incurred.  Assuming the re-baselined project has an acceptable cost/benefit ratio, the agency must then compare that ratio with other projects within the agency’s portfolio to determine if the re-baselined project merits continued funding.  If not, agencies should concede the sunk-costs and terminate the project.

At the beginning of the Acquisition Phase, the IPT should re-examine the mission need.  The IPT should also re-examine the sustainable design principles and determine if new sustainability initiatives are available.  Furthermore, it should re-assess the market capabilities to verify the conclusions reached in the Planning and Budgeting Phase as to whether a commercially available asset can be acquired or limited (or full-scale) development work is needed.  The amount of development and complexity of integration are usually the greatest risk factor.  Therefore, this validation will have a significant impact on what types of risk treatment and mitigation will be necessary.  The IPT should review any prior decisions that development work would be necessary, because technical advances that have occurred since the Planning and Budgeting Phase could render development work unnecessary.  Alternatively, the IPT may determine that a decision in the Planning and Budgeting Phase for direct procurement is no longer valid and development is necessary.  When such a determination is made, the analysis and recommendations to change direction should be considered and approved through the portfolio planning process, before the IPT proceeds with the acquisition.

The most important aspect of the Acquisition Phase is managing the risk.  The Program/Project Manager must provide for continual risk management throughout the life of the project.  Risk management should be built into an agency’s Acquisition processes as a variety of risks may arise in each stage of the Acquisition process.  Agencies should also carefully monitor the terms and conditions, including pricing, on which risk allocations are determined to ensure that they reflect value for money.  To ensure that all the risk is identified by the Government and contractors, integrated baseline reviews are required either prior to award or as soon as possible after award, as appropriate and whenever there is a major modification to the program or a baseline change is requested.

Although USDA usually selects new investments annually, the Acquisition Phase is an ongoing activity.  It requires the continuous monitoring of ongoing capital investment projects through the design and construction or acquisition lifecycle.  USDA reviews occur before the annual budget preparation process.  Additionally, agencies will conduct periodic or quarterly summary reviews based on the review schedule that was outlined during the Acquisition Phase.

The Acquisition Phase is characterized by decisions to continue, modify, or terminate a project.  Decisions are based on reviews at key milestones during the project’s design and real property lifecycle.  The reviews focus on ensuring that projected benefits are being realized; cost, schedule and performance goals are being met; risks are minimized and managed; and the investment continues to meet strategic needs.  This phase also promotes the delivery of quality products and results in initiatives that are completed within scope, on time, and within budget.

Through the Acquisition Phase, Significant and Major investments continue to document relevant information in the Real Property Investment Report (RPIR) located in Appendix C.  Non-Major investments should consider the information requested in this documentation when selecting and reviewing investments.  If requested, agencies should have the capability to produce this information related to these investments.

Departmental decision-makers assess these investments in the following manner:

- Non-Major Investments:  Review of the compilation of the agency portfolio in the Three-Year Rolling Timeline

- Significant Investments:  Review of the individual projects in the Three-Year Rolling Timeline

- Major Investments:  Review of the individual PDSs for recommendations for agency approval and inclusion in the Three-Year Rolling Timeline

## Management-In-Use Phase

The Management-In-Use Phase begins after completion of the Acquisition Phase.  Effective Management-In-Use requires the continuous monitoring of an Agency’s inventory of capital assets to ensure they are maintained at the right size, cost and condition to support the Agency mission and objectives.  Management-In-Use is generally the longest phase of the investment or asset life-cycle.  Ownership costs, such as operations, maintenance (including service contracts), energy use and disposition can often consume more than 80 percent of the total life-cycle costs.  Agencies must review, properly plan for, and actively manage their investment during this phase and employ effective measures of an asset’s financial and physical condition, and its operations support for the agency mission.

Key objectives during the Management-In-Use Phase are:  1) to demonstrate that the existing investment is meeting the needs of the Agency, delivering expected value or that the investment is being modernized and replaced consistent with Agency’s mission and objectives; and 2) to identify smarter and more cost effective methods for delivering performance and value.

The purpose of the Management-In-Use Phase is to compare actual to expected results following completion.  This is done to assess the investment's impact on mission performance, identify deficiencies while the project is still under warranty, identify the level of customer satisfaction, and revise the investment management process based on lessons learned.

The Management-In-Use Phase provides the means to assess mature capital investments, ascertain their continued effectiveness in supporting mission requirements, evaluate the cost of ongoing maintenance requirements, and consider potential retirement or replacement of the capital investment.  The primary review focus during this Phase is on the mission support, cost, and condition assessment.  Process activities during the Management-In-Use Phase provide the foundation to ensure mission alignment and support for optimum facility operation and ongoing maintenance plans.

The outcomes are measured by collecting performance data and the comparison of actual to projected performance.  Any lessons-learned that are established should be reported to the Departmental AMRB to provide a better understanding of initiative performance and assist the Project Sponsor in directing any necessary initiative adjustments.

Additionally, results from the Management-In-Use Phase are fed back to the Planning and Budgeting and Acquisition Phases as lessons learned.  The Management-In-Use Phase focuses on outcomes, which include:

- Determining whether the capital real property investments have met their performance, cost, and schedule objectives

- Determining the extent to which the Capital Programming and Investment Process improved the outcome of the investment

## Disposition Phase

Asset Disposition is the culmination of previous planning, budgeting and acquisition efforts.  But, the determination to dispose of a capital asset should not be an afterthought once obsolesce is reached.  Projected costs of asset disposal are critical elements in the planning and budgeting for asset acquisition.  The decision to dispose of an asset may be triggered by any number of events; most will be part of a systematic plan formulated in advance that integrates the asset into the agency’s broader Capital Asset Plan.  Beginning with mission analysis and planning for the purpose of matching capabilities to mission requirements, and continuing with ongoing analysis, criteria are established and monitored to determine the condition of the asset and how well it is performing.  If an asset becomes uneconomical to keep in service or fails to meet performance criteria, the agency should critically assess the asset to determine whether it should be retired, replaced, enhanced or refurbished.  One of the tools available for use for this effort is the U.S. Department of Agriculture Real Property Disposition Process (Appendix G).  This document walks the agency through each step of the process to categorize USDA assets within the five categories identified on the Disposition Decision Tree and utilizing the Federal Real Property Profile Performance Assessment Tool (FRPP-PA).  It is critically important that all four performance measures are captured properly for each asset.

The following questions are a starting point to assist agencies in determining whether or not any type of capital asset is a candidate for disposition.  It is important that all appropriate agency management personnel are involved in the decision process.

- Does the capital asset still support the mission?

- Is the asset wholly or partly unneeded?

- Does the asset meet established performance measures (right size, cost and condition to support Department/Agency mission and objectives)?

- Will program changes alter asset requirements?  Is the asset used only irregularly for program use?  Would a portion of the asset satisfy program needs?

- Is continued Federal ownership and operation of the property justified in light of its current use?

- Can the asset be made available for use by others, within or outside the Federal community?

- Are there security or other considerations that outweigh disposition of the asset?

Recognizing long-standing concerns of the Federal Government in the disposition of excess and unneeded property, the Government Accountability Office (GAO) labeled Federal real property as high-risk in GAO Report Number GAO-03-122.  In the report, GAO highlighted that the Federal Government’s capital asset portfolio no longer effectively aligns with, or is responsive to, agencies’ changing missions.  Subsequently, GAO has updated the original report, GAO Report Number GAO-07,310, High-Risk Update, which acknowledges that progress has been made, but the problems that led to the designation of Federal real property as a high-risk area still exist.  In addition, deep-rooted obstacles, including competing stakeholder interest and legal and budgetary limitations, could significantly hamper a government-wide transformation.  As a result, this remains a high risk area.  After fully implementing E.O. 13327, Federal Real Property Asset Management, issued on February 6, 2004, and related PMA initiatives, agencies will need to show significant progress toward eliminating the problems that led to this area’s designation as high risk, such as reducing inventories of facilities to a minimum and making headway in addressing the repair backlog.  In addition, the OMB and agencies, through the Federal Real Property Council, will need to focus on developing strategies to address deep-rooted obstacles to a successful transformation, such as competing stakeholder interests.  Agencies are expected to dispose of unneeded assets, in accordance with applicable statutes, to ensure that the agency real property inventory of assets is maintained at the right size, cost, and condition.  Also, inventories should contain mission critical and mission dependent assets that are maintained in the appropriate condition and operated at the right cost.

Additional real property considerations to the above already stated should be considered when evaluating real property assets for disposition:

- Is the asset uneconomical to retain?  If so, could it be sold or exchanged for a more suitable asset with lower maintenance and operating costs, at a price roughly equivalent to the value of the present asset?

- Considering the cost of acquisition or lease, moving costs, preparation of the new space, operation and maintenance costs, and the increase in efficiency of operations, can net savings to the U.S. Government be realized by relocation?

- What effect does the availability of alternative facilities, if required, have on the foregoing?

# Non-Major Investment CPIP instructions

Agencies are responsible for determining the management process to be used in executing non-major projects.  The scope, level of complexity and cost should be considered when determining the level of detail the project will require.  Absent any agency specific guidance, project managers may choose to follow the CPIP instructions, again modifying it to meet individual project requirements.  This section outlines the step-by-step process agencies may choose to follow and is based on the CPIP Phases described in Section 3.  The thresholds and review criteria for this level of investment are defined in Table 2.

| Investment Type | Project Value | Required Review Documentation | Review Authority | Approval Authority |
| --- | --- | --- | --- | --- |
| Non-Major | < GSA prospectus level | As Determined by Agency Headquarters | Agency Headquarters will determine asset management review authority | Agency Headquarters may delegate approval authority |

Table 2:  Non-Major Investment Description

As depicted above, Non-Major investments (those below GSA Prospectus level) are not reviewed or approved by the Departmental AMRB.  Upon approval by the Agency AMRB or designated authority, these investments are compiled into the agency Three-Year Rolling Timeline.  The Departmental AMRB will review this collective representation of the agency’s Non-Major investments on an annual basis.  At a minimum, agencies must take into consideration the applicable performance measures and how the project, regardless of cost, may affect the Department’s overall performance measures.  Agencies should have the capability to produce such information related to these investments.  Examples of additional information agencies may require could include:

- Does the project support core/priority mission functions that need to be performed by the Federal government?

- Does the project support consolidation/sharing opportunities that would reduce costs, increase effectiveness, and improve customer service?

- Project alignment with USDA performance measures and strategic goals.

- A preliminary budget estimate providing an estimate of costs.

The following table outlines the specific step-by step CPIP instructions agencies may choose to follow for Non-Major Investments.  The table is structured to depict numerical process steps throughout each of the four CPIP Phases.  A detailed description and the associated responsible entity are also identified.

| NON-MAJOR INVESTMENT CPIP INSTRUCTIONS |
| --- |
| Step. | CPIP Phase | Process | Description | Responsible Individual(s) or Group(s) |
| 1 | Planning and Budgeting | Identify Mission/Business Needs | USDA agencies need to determine and prioritize the most critical capital investments that will be considered in the development of USDA’s real property project portfolio. These investments must support the departmental and agency missions and strategic goals. To effectively manage and optimize its real property assets, USDA agencies have closely integrated their investment, operational, and disposal decisions with their core mission activities. Consideration must be given to the following performance measure goals and objectives for real property investments when identifying a need for a real property project: Mission Dependency Utilization Condition Index (if existing) Annual Operating Costs | Agency Decision/Delegated Authority |
| 2 | Planning and Budgeting | Develop Project Information - Use Project Data Sheet or Agency Equivalent | Although Non-Major investments are not required to complete the Project Data Sheet, agencies should consider the information requested in this documentation when selecting and reviewing investments. At a minimum, agencies must take into consideration the applicable performance measures and how the project, regardless of cost, may affect the Department’s overall performance measures. Agencies should have the capability to produce such information related to these investments. The proposed project should be able to provide information in relation to these questions: Does the project support core/priority mission functions that need to be performed by the Federal government? Does the project support consolidation/sharing opportunities that would reduce costs, increase effectiveness, and improve customer service? Additionally, the following information should be available: High-level performance measures Project alignment with USDA Performance Objectives and Strategic Goals A preliminary budget estimate providing an estimate of costs necessary | Project Sponsor |
| 3 | Planning and Budgeting | Provide Information for Three Year Rolling Timeline | The Three-Year Rolling Timeline provides the necessary information to support an agency’s proposed real property investment portfolio. The Three-Year Rolling Timeline (agency project portfolio) outlines the entire set of projects for each fiscal year and identifies for each project a preliminary budget estimate, project score, and project composition based on the established Three-Year Timeline ranking categories. The Project Manager provides to the Agency data necessary to develop the Three Year Timeline. | Agency Decision/Delegated Authority |
| 1 | Acquisition | Finalize Project Proposal | The next step in the USDA Real Property CPIP instructions is to develop a specific project proposal. | Project Manager |
| 2 | Acquisition | Identify and Secure Project Development Funding | Once the project has been approved and funded, the Project Sponsor, with support from the budget analyst, will identify the funding source for support of the project during development. | Project Sponsor |
| 3 | Acquisition | Monitor Project Status | Investments should be reviewed during regular intervals throughout the project duration. Although Non-Major Investments are not required to submit a Project Data Sheet, the following project objectives should be considered: Introduction and brief overview of the investment Mission Needs Statement Acquisition strategy Initial project plan with estimated costs listed Project Risks Performance goal | Project Manager |
| 4 | Acquisition | Review Three-Year Rolling Timeline | The Departmental AMRB will continue to review the compilation of the agency Non-Major Investments as a part of the Three-Year Rolling Timeline | Departmental AMRB |
| 1 | Management-In-Use | Establish and Maintain Project Costs, Schedule, Risks and Performance Measure Baselines | The Project Manager collects actual information on the resources allocated and expended throughout the Management-In-Use Phase. The Project Manager compares the actual information collected to the estimated baselines developed during the Acquisition Phase and identifies root causes for any differences. Additionally, the Project Sponsor monitors operational, schedule, legal and contractual, and organizational risks during the Management-In-Use Phase. | Project Manager/Project Sponsor |
| 2 | Management-In-Use | Ensure Budget and Budget Documentation are Updated | The Project Sponsor and Agency Head ensures the budget and budget documentation are updated. The Project Sponsor monitors financial, operational, schedule, legal and contractual, and organizational risks. | Project Sponsor/Agency Head |
| 3 | Management-In-Use | Continue to Monitor Project Status | Investments should continue to be reviewed during regular intervals throughout the project’s duration. Although Non-Major Investments are not required to submit a RPIR, the project objectives should continually be considered. | Project Manager |
| 4 | Management-In-Use | Approve Agency Portfolio | The Agency decision maker approves or disapproves recommendations and if necessary asks for the plan to be revised. Finally, the Agency decision maker will forward proposed, aggregated projects to be in the Three-Year Rolling Timeline to the Departmental AMRB. | Agency Decision/Delegated Authority |
| 5 | Management-In-Use | Review Three-Year Rolling Timeline | The Departmental AMRB will continue to review the compilation of the agency Non-Major Investments as a part of the Three-Year Rolling Timeline | Departmental AMRB |
| 6 | Management-In-Use | Share Best Practices/Lessons Learned with Agency and Departmental AMRBs | To capture lessons learned, the Project Manager develops a Best Practices and Lessons Learned Report and submits it to the Project Sponsor, Agency Head and the Agency and Departmental AMRBs. All failures and successes are collected and shared to ensure that future initiatives can benefit from past experiences. A high-level assessment of management techniques, including organizational approaches, budgeting, acquisition strategies, tools and techniques, and testing methodologies is essential to establish realistic baselines and to ensure the future success of other real property initiatives. | Project Manager |
| 7 | Management-In-Use | Add Facility Information to the Corporate Property Automated Information System (CPAIS) | The Project Sponsor ensures that all of the required information related to the investment is entered into CPAIS following project completion for inventory and USDA real property portfolio purposes. | Project Sponsor |
| 8 | Management-In-Use | Continue Execution of Facility O & M | Facility Manager reviews the individual property item condition assessments and prioritizes deficiencies in alignment with overall mission needs. Identified projects are categorized as deferred maintenance projects and are submitted into the budget cycle. Project descriptions and justifications are prepared in anticipation of the initiation of a corrective action project. | Facility Manager |
| 1 | Disposition | Determine if the Asset Still Fits in the Agency’s Capital Asset Plan | The final determination to dispose of an asset must take into account a number of factors, including, but not limited to: Does the capital asset still support the mission? Is the asset wholly or partly unneeded? Does the asset meet established performance measures (right size, cost and condition to support Department/Agency mission and objectives)? Will program changes alter asset requirements? Is the asset used only irregularly for program use? Would a portion of the asset satisfy program needs? Is continued Federal ownership and operation of the property justified in light of its current use? Can the asset be made available for use by others, within or outside the Federal community? Are there security or other considerations that outweigh disposition of the asset? | Agency Decision/Delegated Authority |

Table 3:  Non-Major Investment CPIP instruction Steps

Non-Major Investment CPIP Checklist

PLANNING AND BUDGETING

- Agencies (if requested from the Departmental AMRB) should be able to provide information related to the individual project’s performance measures that are compiled in the Three-Year Rolling Timeline

- Prioritized Agency Investment List

ACQUISITION

- Agencies should be able to provide information related to the individual projects progress (i.e. Elements of the PDS - Performance goals and quantifiable performance measures, project costs, schedule, benefits, and risks etc.)

- A project plan which details quantifiable objectives including an acquisition schedule, project deliverables, and projected and actual costs

MANAGEMENT-IN-USE

- Completed project

- Share best practices/lessons learned with agency and Departmental AMRBs

- Add facility information to the Corporate Property Automated Information System (CPAIS)

DISPOSITION

- Determine if asset should be retired, replaced, enhanced or refurbished

# Significant Investment CPIP instructions

This section outlines the CPIP instructions, following the Phases described in Section 3 for Significant Real Property Investments.  The thresholds and review criteria for this level of investment are defined in Table 2.

| Investment Type | Project Value | Required Review Documentation | Review Authority | Approval Authority |
| --- | --- | --- | --- | --- |
| Significant | > GSA prospectus level to < $10M | Project Data Sheet And Real Property Investment Report | Agency Asset Management Review Board | Agency Headquarters |

Table 4:  Significant Investment Description

The following table outlines the CPIP instructions for Significant Investments.  The table is structured to depict numerical process steps throughout each of the four CPIP Phases.  A detailed description and the associated responsible entity are also identified.

| SIGNIFICANT INVESTMENT CPIP INSTRUCTIONS |
| --- |
| Step | CPIP Phase | Process | Description | Responsible Individual(s) or Group(s) |
| 1 | Planning and Budgeting | Identify Mission/Business Needs | USDA agencies need to determine and prioritize the most critical capital investments that will be considered in the development of USDA’s real property project portfolio. These investments must support the departmental and agency missions and strategic goals. To effectively manage and optimize its real property assets, USDA agencies have closely integrated their investment, operational, and disposal decisions with their core mission activities. Consideration must be given to the following performance measure goals and objectives for real property investments when identifying a need for a real property project: Mission Dependency Utilization Condition Index (if existing) Annual Operating Costs | Agency AMRB |
| 2 | Planning and Budgeting | Identify Project Sponsor | The Project Sponsor for each accepted project should be identified by Agency Management. The Project Sponsor should be a senior individual in the organization with requisite management and business skills to lead the capital asset investment and work with the Project Manager. The Project Sponsor is accountable to the Agency Head and Agency AMRB for the capital asset investment as it continues through the CPIP instructions. | Agency AMRB |
| 3 | Planning and Budgeting | Complete Project Data Sheet | The Project Data Sheet (PDS) (Appendix B) contains information which identifies the project (e.g. title, number, facility name, etc.). It also provides a brief description and justification of the project, as well as the project score/rank and preliminary cost estimate. Depending on the agency’s Asset Management Review Board (AMRB) process, the AMRBs may review projects more than once in the Planning and Budgeting Phase. The agency may determine what level of information is required on the PDS for alternatives and performance measures consistent with the decisions to be made by the AMRBs. Prior to the final review and ranking by the AMRB and moving to the Acquisition Phase, all required information should be available on the PDS for the AMRB to make an informed decision. Additionally, the Project Data Sheet allows for further examination of a proposed solution. It focuses on an analysis of alternatives to meet the mission need and initial planning for entering into the Acquisition Phase. The following activities are conducted during development of the Project Data Sheet: Discuss the proposed project in relation to these questions: Does the project support core/priority mission functions that need to be performed by the Federal government? Does the project support consolidation/sharing opportunities that would reduce costs, increase effectiveness, and improve customer service? Additional information captured in the Project Data Sheet includes: Identify high-level performance measures (Additional detailed performance measures will be developed as part of the Acquisition Phase.) Determine key selection criteria to evaluate concept alternatives that support high-level performance measures and business objectives Ensure project aligns with USDA and Agency Strategic Plans Prepare a preliminary budget estimate providing an estimate of costs necessary, and an order of magnitude estimate of budget requirements to support a three-year budget plan and lifecycle costing. If appropriate, full project funding should be requested. | Project Sponsor |
| 4 | Planning and Budgeting | Evaluate and Rank Project Requests into an Agency Portfolio | The next step in the CPIP instructions for the USDA agencies Asset Management Review Boards is to evaluate and rank real property assets based on the information provided in the Project Data Sheet. The project evaluation focuses on an analysis of alternatives to meet the mission need and initial planning for entering into the Planning and Budgeting Phase. In addition to other considerations, USDA agencies are to rank and prioritize projects taking into consideration critical deferred maintenance needs in health and safety, resource protection and mission. Projects are also reviewed, as applicable, against existing USDA and Agency priority lists, such as the USDA Dam Safety Technical Priority Rating List and the Seismic Safety Rehabilitation Priority List. | Agency AMRB |
| 5 | Planning and Budgeting | Provide Information for Three -Year Rolling Timeline | The Three-Year Rolling Timeline provides the necessary information to support an agency’s proposed real property investment portfolio. The Three-Year Rolling Timeline (Agency Project Portfolio) outlines the entire set of projects for each fiscal year and identifies for each project a preliminary budget estimate, project score, and project composition based on the established Three-Year Rolling Timeline ranking categories. The Project Manager and Project Sponsor provides the agency data necessary to develop the Three-Year Rolling Timeline for Agency AMRB Review and Agency Head approval. All data must be completed on the PDS at this point in the process. | Agency AMRB |
| 6 | Planning and Budgeting | Review of Agency Portfolios | Following incorporation into the Three-Year Rolling Timeline, the Agency AMRB reviews the agency portfolio in its entirety. Upon request, the agency should provide the PDS to the Departmental AMRB. | Agency Head |
| 1 | Acquisition | Obtain Approval to Enter Acquisition Phase | The Project Sponsor reviews the project data sheet submitted for the Three-Year Rolling Timeline and other documentation completed during the Planning and Budgeting Phase and makes any necessary changes. The Project Manager then develops quantifiable project outcomes with appropriate performance measures. These performance measures will form a basis for judging real property success and user satisfaction. | Agency Head/Project Sponsor/ Project Manager |
| 2 | Acquisition | Develop an Integrated Project Team (IPT) | The Project Manager coordinates the selection of the Integrated Project Team (IPT) members that will assist in the initiative’s development with concurrence from the Project Sponsor. The IPT brings together expertise from functional areas as required by the specifics of the initiative. The IPT normally involves functional experts in the following areas: Agency Budget Analyst Procurement/Contracting Specialist Project Manager Program or Facility Specialist Additional staff may be added from other functional areas as needed. Serving on the IPT will normally be an additional duty but initiative size or potential impact may increase commitment. | Project Manager |
| 3 | Acquisition | Identify and Secure Project Development Funding | The Project Sponsor, with support from the budget analyst, will identify the funding source for support of the project during development. The Project Sponsor will then get approval from the appropriate Agency management, as needed, depending upon the project’s characteristics. The members of the IPT should assist in coordinating these actions within their respective functional areas. | Project Sponsor/Agency Head |
| 4 | Acquisition | Develop Project Proposal | The next step in the USDA Real Property CPIP instructions is to develop a specific project proposal. The project proposal, generated by the Project Manager, should include the following information for review by the Agency AMRB: Information included in the Project Data Sheet to include: ROI and CBA Cost projections Alternatives analysis Funding source identification Acquisition Plan and strategy (Projects greater that $5M will require Chief Acquisition Officer approval). For additional guidance, AGAR guidance is found in Appendix F Project Plan and Milestones | Project Manager |
|  |  | Review Three-Year Timeline (see non-major for wording) |  |  |
| 5 | Acquisition | Monitor Project Status using RPIR | A review document should be created to accomplish the following project objectives: Introduction and brief overview of the investment Mission Needs Statement Acquisition strategy Initial project plan with estimated costs listed CBA and budget estimate, including risk-adjusted ROI and NPV calculations Risk Assessment Performance goals A detailed description and template for the RPIR is located in Appendix C. | Project Manager |
| 1 | Management-In-Use | Establish and Maintain Project Costs, Schedule, Risks and Performance Measure Baselines | The Project Manager collects actual information on the resources allocated and expended throughout the Management-In-Use Phase. The Project Manager compares the actual information collected to the estimated baselines developed during the Acquisition Phase and identifies root causes for any differences. Additionally, the Project Sponsor monitors operational, schedule, legal and contractual, and organizational risks during the Management-In-Use Process. | Project Manager |
| 2 | Management-In-Use | Ensure Budget and Budget Documentation are Updated | The Project Sponsor and Agency Head ensures the budget and budget documentation are updated. The Project Sponsor monitors financial, operational, schedule, legal and contractual, and organizational risks. The Project Sponsor also ensures that all budget documents remain current and final decisions are vetted through the Project Sponsor and Agency Head. | Project Sponsor/Agency Head |
| 3 | Management-In-Use | Assess Project Progress Against Performance Measures | The primary purpose of this assessment is to ensure the initiative is on schedule and to help identify issues or deficiencies that require corrective action. In some instances, where the business case may no longer exist or be as strong, or if significant changes to the cost and schedule baselines are required, it may also be necessary to terminate the project. | Project Manager/ Project Sponsors |
| 4 | Management-In-Use | Update RPIR (annually) | The review should incorporate the following information related to the real property project: Introduction and brief overview of the investment Cost vs. baseline Schedule vs. baseline Status of four performance measures Performance vs. baseline A validated/updated CBA Risk Management | Project Manager |
| 5 | Management-In-Use | Review/RPIRs | The Project Manager continues to update the RPIR on an annual basis throughout the duration of the project. It is forwarded to the Project Sponsor, and the Agency for review and evaluation. | Project Manager/Project Sponsor |
| 6 | Management-In-Use | Review/Approve RPIRs | On an annual basis, the Agency AMRB needs to review the projects that provide insufficient performance measure documentation which could be subject to reduced or delayed project funding. The AMRB will review the reports for the following criteria: Do the projects/ investments under review continue to support mission, business functions and the identified performance measures? To what extent do the projects/investments continue to meet planned cost and schedule baselines? Are there any identified deficiencies? If so, what progress has been made regarding corrective actions? Have performance gaps been identified and tracked, and has a mitigation plan been initiated to overcome the gaps? | Agency AMRB |
| 7 | Management-In-Use | Compile Agency Portfolio | The Agency AMRB compiles the Agency’s Project Portfolio for investments greater than the GSA prospectus level and sends it to the Agency Head for review. | Agency AMRB |
| 8 | Management-In-Use | Maintain Facility Operations & Maintenance | Facility Manager reviews the individual property item condition assessments and prioritizes deficiencies in alignment with overall mission needs. Identified projects are categorized as deferred maintenance projects and are submitted into the budget cycle. Project descriptions and justifications are prepared in anticipation of the initiation of a corrective action project. | Facility Manager |
| 9 | Management-In-Use | Share Best Practices/Lessons Learned with Agency and Departmental AMRBs | To capture lessons learned, the Project Manager develops a Best Practices and Lessons Learned Report and submits it to the Project Sponsor, Agency Head and the Agency and Departmental AMRBs. All failures and successes are collected and shared to ensure that future initiatives can benefit from past experiences. A high-level assessment of management techniques, including organizational approaches, budgeting, acquisition strategies, tools and techniques, and testing methodologies is essential to establish realistic baselines and to ensure the future success of other real property initiatives. | Project Manager |
| 10 | Management-In-Use | Add Facility Information to the Corporate Property Automated Information System (CPAIS) | The Program Sponsor ensures that all of the required information related to the investment is entered into CPAIS following project completion for inventory and USDA real property portfolio purposes. Continue execution of facility O&M. | Project Sponsor |
|  |  | Update Three-Year Timeline (see non-major projects for wording) |  |  |
| 1 | Disposition | Determine if the Asset Still Fits in the Agency’s Capital Asset Plan | The final determination to dispose of an asset must take into account a number of factors, including, but not limited to: Does the capital asset still support the mission? Is the asset wholly or partly unneeded? Does the asset meet established performance measures (right size, cost and condition to support Department/Agency mission and objectives)? Will program changes alter asset requirements? Is the asset used only irregularly for program use? Would a portion of the asset satisfy program needs? Is continued Federal ownership and operation of the property justified in light of its current use? Can the asset be made available for use by others, within or outside the Federal community? Are there security or other considerations that outweigh disposition of the asset? | Agency AMRB |

Table 5:  Significant Investment CPIP instructions Steps

Significant Investment CPIP Checklist

PLANNING AND BUDGETING

- Completed Project Data Sheet (see Appendix B)

- Agency approval for project incorporation into the Three-Year Rolling Timeline

- Prioritized Agency Investment List

ACQUISITION

- Performance goals and quantifiable performance measures

- A project plan which details quantifiable objectives including an acquisition schedule, project deliverables, and projected and actual costs

- Project costs, schedule, benefits, and risks

- Completed RPIR (see Appendix C)

- Chief Acquisition Officer approval for investments over $5M (see Appendix F for guidance)

- Update investment information on the 3-Year Rolling Timeline

MANAGEMENT-IN-USE

- Completed all project investments

- Updated RPIR

- Share best practices/lessons learned with agency and Departmental AMRBs

- Add facility information to the Corporate Property Automated Information System (CPAIS)

- Update investment information on the 3-Year Rolling Timeline

DISPOSITION

- Determine if asset should be retired, replaced, enhanced or refurbished

# Major Investment Process

This section outlines the CPIP instructions, following the phases described in Section 3 for Major Real Property Investments.  The thresholds and review criteria for this level of investment are defined in Table 2.

| Investment Type | Project Value | Required Review Documentation | Review Authority | Approval Authority |
| --- | --- | --- | --- | --- |
| Major | ≥ $10M or High Risk | Capital Asset Plan | Departmental Asset Management Review Board will review agency documentation and provide recommendations to the Budget and Performance Integration Board | Secretary |

Table 5:   Major Investment Description

The following table outlines the CPIP instructions for Major Investments.  The table is structured to depict numerical process steps throughout each of the four CPIP Phases.  A detailed description and the associated responsible entity are also identified.

| MAJOR INVESTMENT CPIP INSTRUCTIONS |
| --- |
| Step | CPIP Phase | Process | Description | Responsible Individual(s) or Group(s) |
| 1 | Planning and Budgeting | Identify Mission/Business Needs | USDA agencies need to determine and prioritize the most critical capital investments that will be considered in the development of USDA’s real property project portfolio. These investments must support the departmental and agency missions and strategic goals. To effectively manage and optimize its real property assets, USDA agencies have closely integrated their investment, operational, and disposal decisions with their core mission activities. Consideration must be given to the following performance measure goals and objectives for real property investments when identifying a need for a real property project: Mission Dependency Utilization Condition Index (if existing) Annual Operating Costs | Agency AMRB |
| 2 | Planning and Budgeting | Identify Project Sponsor | The Project Sponsor for each accepted project should be identified. The Project Sponsor should be a senior individual in the organization with requisite management and business skills to lead the capital asset investment and work with the Project Manager. The Project Sponsor is accountable to the Agency Head and Agency AMRB for the capital asset investment as it continues through the CPIP instructions. | Agency AMRB |
| 3 | Planning and Budgeting | Complete Project Data Sheet | The Project Data Sheet (Appendix B) contains information which identifies the project (e.g. title, number, facility name, etc.). It also provides a brief description and justification of the project, as well as the project score/rank and preliminary cost estimate. Depending on the agency’s Asset Management Review Board (AMRB) process, the AMRBs may review projects more than once in the Planning and Budgeting Phase. The agency may determine what level of information is required on the PDS for alternatives and performance measures consistent with the decisions to be made by the AMRBs. Prior to the final review and ranking by the AMRB and moving to the Acquisition Phase, all required information should be available on the PDS for the AMRB to make an informed decision. Additionally, the Project Data Sheet allows for further examination of a proposed solution. It focuses on an analysis of alternatives to meet the mission need and initial planning for entering into the Acquisition Phase. The following activities are conducted during development of the Project Data Sheet: Discuss the proposed project in relation to these questions: Does the project support core/priority mission functions that need to be performed by the Federal government? Does the project support consolidation/sharing opportunities that would reduce costs, increase effectiveness, and improve customer service? Additional information captured in the Project Data Sheet includes: Identify high-level performance measures (Additional detailed performance measures will be developed as part of the Acquisition Phase.) Determine key selection criteria to evaluate concept alternatives that support high-level performance measures and business objectives Ensure project aligns with USDA and Agency Strategic Plans Prepare a preliminary budget estimate providing an estimate of costs necessary, and an order of magnitude estimate of budget requirements to support a three-year budget plan and lifecycle costing. If appropriate, full project funding should be requested. | Project Sponsor |
| 4 | Planning and Budgeting | Evaluate and Rank Project Requests into an Agency Portfolio | The next step in the CPIP instructions for the agency’s Asset Management Review Board is to evaluate and rank real property assets based on the information provided in the Project Data Sheet. The project evaluation focuses on an analysis of alternatives to meet the mission need and initial planning for entering into the Acquisition Phase. In addition to other considerations, USDA agencies are to rank and prioritize projects taking into consideration critical deferred maintenance needs in health and safety, resource protection and mission. Projects are also reviewed, as applicable, against existing USDA and Agency priority lists, such as the USDA Dam Safety Technical Priority Rating List and the Seismic Safety Rehabilitation Priority List. Applicable agency approved Project Data Sheets are subsequently submitted to the Departmental AMRB. | Agency AMRB |
| 5 | Planning and Budgeting | Provide Information for Three-Year Rolling Timeline | The Three-Year Rolling Timeline provides the necessary information to support an agency’s proposed real property investment portfolio. The Three-Year Rolling Timeline (agency project portfolio) outlines the entire set of projects for each fiscal year and identifies for each project a preliminary budget estimate, project score, and project composition based on the established Three-Year Rolling Timeline ranking categories. The Project Manager and the Project Sponsor provides the necessary data to develop the Three-Year Rolling Timeline for Agency AMRB Review and Agency Head approval. All data must be completed on the PDS at this point in the process. | Agency Head |
| 6 | Planning and Budgeting | Review and Provide Recommendation to Agency Portfolios | Following incorporation into the Three-Year Rolling Timeline, the Departmental AMRB reviews the projects within their review scope and makes recommendations to the Agency Head. The Agency Head approves or disapproves recommendations and if necessary asks for the plan to be revised. Finally, the Agency Head will again forward proposed projects to be in the Three-Year Rolling Timeline to the Departmental AMRB. | Departmental AMRB |
| 7 | Planning and Budgeting | Provide Recommendation Regarding Agency Portfolios | The Departmental AMRB will review and the agencies would then make planning and budgeting investment recommendations and provide those recommendations and report those decisions to the USDA agencies. | Departmental AMRB |
| 1 | Acquisition | Obtain Approval to Enter Acquisition Phase | The Project Sponsor reviews the project data sheet submitted for the Three-Year Rolling Timeline and other documentation completed during the Planning and Budgeting Phase and makes any necessary changes. The Project Manager then develops quantifiable project outcomes with appropriate performance measures. These performance measures will form a basis for judging real property success and user satisfaction. | Project Sponsor/Project Manager |
| 2 | Acquisition | Develop an IPT | The Project Manager coordinates the selection of the IPT members that will assist in the initiative’s development with concurrence from the Project Sponsor. The IPT brings together expertise from functional areas as required by the specifics of the initiative. The IPT normally involves functional experts in the following areas: Agency Budget Analyst Procurement/Contracting Specialist Project Manager Program or Facility Specialist Additional staff may be added from other functional areas as needed. Serving on the IPT will normally be an additional duty but initiative size or potential impact may increase commitment. | Project Manager |
| 3 | Acquisition | Identify and Secure Project Development Funding | The Project Sponsor, with support from the budget analyst, will identify the funding source for support of the project during development. The Project Sponsor will then get approval from the appropriate Agency management, as needed, depending upon the project’s characteristics. The members of the IPT should assist in coordinating these actions within their respective functional areas. | Project Sponsor/Agency Head |
| 4 | Acquisition | Develop Project Proposal | The next step in the USDA Real Property CPIP instructions is to develop a specific project proposal. The project proposal, generated by the Project Manager, should include the following information for review by the Agency AMRB: Information included in the Project Data Sheet to include: ROI and CBA Cost projections Alternatives analysis Funding source identification Acquisition Plan and strategy Acquisition Plan and strategy (Projects greater that $5M will require Chief Acquisition Officer approval). For additional guidance, AGAR guidance is found in Appendix F Project Plan and Milestones | Project Manager |
| 5 | Acquisition | Monitor Project Status using CAP | This OMB standard form for reporting budget justification for major investments must be created to accomplish the following project objectives: Introduction and brief overview of the investment Mission Needs Statement Acquisition strategy Initial project plan with estimated costs listed CBA and budget estimate, including risk-adjusted ROI and NPV calculations Risk Assessment Performance goal A detailed description and template for the CAP is located in Appendix D | Project Manager |
| 6 | Acquisition | Review/Approve CAP | The investment’s CAP is sent to the Agency AMRB for review and approval based on OMB’s scoring criteria | Project Sponsor |
| 7 | Acquisition | Review/Approve CAP | The Agency AMRB reviews the CAP and forwards their finding to the Departmental AMRB. | Agency AMRB |
| 8 | Acquisition | Review/Approve Agency Project Portfolio | The Agency AMRB compiles the Agency Portfolio for investments equal to or greater than $10 million for headquarters review and approval. | Agency Head |
| 9 | Acquisition | Review and Provide Recommendations Regarding Departmental Portfolio for Investments Equal to or Greater than $10 million | The Departmental AMRB reviews and provides recommendations regarding the Department’s Portfolio for investments equal to or greater than $10 million for compliance with Departmental strategic, legislative, and budgetary goals using standard criteria to objectively compare projects based on the data presented. The Departmental AMRB validates and reviews the projects and their corresponding scores. The Departmental AMRB will then recommend approval, disapproval or other actions to the Budget and Performance Integration Board (BPIB). | Departmental AMRB |
| 10 | Acquisition | Approve Department Portfolio for Investments equal to or greater than $10M | The BPIB reviews and provides recommendations regarding the Department’s Portfolio for investments equal to or greater than $10M for compliance with Departmental strategic, legislative, and budgetary goals using OMB Exhibit 300 standard criteria. The Board then recommends approval, disapproval or other actions to the Secretary who makes the final investment decisions. | BPIB |
| 11 | Acquisition | Submit CAPs to OMB | The BPIB submits the CAPs for investments equal to or greater than $10M to OMB for approval. | BPIB |
| 1 | Management-In-Use | Establish and Maintain Project Costs, Schedule, Risks and Performance Measure Baselines | The Project Manager collects actual information on the resources allocated and expended throughout the Management-In-Use Phase. The Project Manager compares the actual information collected to the estimated baselines developed during the Acquisition Phase and identifies root causes for any differences. Additionally, the Project Sponsor monitors operational, schedule, legal and contractual, and organizational risks during the Management-In-Use Process. | Project Manager |
| 2 | Management-In-Use | Ensure Budget and Budget Documentation are Updated | The Project Sponsor and Agency Head ensures the budget and budget documentation are updated. The Project Sponsor monitors financial, operational, schedule, legal and contractual, and organizational risks. The Project Sponsor also ensures that all budget documents remain current and final decisions are vetted through the Project Sponsor and Agency Head. | Agency Head/ Project Sponsor |
| 3 | Management-In-Use | Assess Project Progress Against Performance Measures and Measure Earned Value | The Agency Head and Agency AMRB are not required to initiate actions on projects which have less than 10% variance from their original baselines for cost, schedule, or performance measures. On projects that have a 10% or greater variance, the Agency AMRB reviews the Corrective Action Plans and the Agency Head, based on the Agency AMRB recommendation will approve or disapprove the proposed mitigation measures and corrective actions proposed in the CAP. The primary purpose of this assessment is to ensure the initiative is on schedule and to help identify issues or deficiencies that require corrective action. In some instances, where the business case may no longer exist or be as strong, or if significant changes to the cost and schedule baselines are required, it may also be necessary to terminate the project. | Project Manager/ Project Sponsor |
| 4 | Management-In-Use | Update CAP (annually) | The review should incorporate the following information related to the real property project: Introduction and brief overview of the investment Cost vs. baseline Schedule vs. baseline Status of four performance measures Performance vs. baseline A validated/updated CBA Risk Management | Project Manager |
| 5 | Management-In-Use | Review CAP | The Project Manager continues to update the CAP on an annual basis throughout the duration of the project. It is forwarded to the Project Sponsor, and the Agency and Departmental AMRB for review and evaluation. | Project Sponsor |
| 6 | Management-In-Use | Review/Approve CAP | On an annual basis, both the Agency and Departmental AMRB need to review the projects that provide insufficient performance measure documentation which could be subject to reduced or delayed project funding. The AMRBs will review the reports for the following criteria: Do the projects/ investments under review continue to support mission, business functions and the identified performance measures? To what extent do the projects/investments continue to meet planned cost and schedule baselines? Are there any identified deficiencies? If so, what progress has been made regarding corrective actions? Have performance gaps been identified and tracked, and has a mitigation plan been initiated to overcome the gaps? | Agency AMRB/ Departmental AMRB |
| 7 | Management-In-Use | Compile Agency Portfolio | The Agency AMRB compiles the Agency’s Project Portfolio for investments equal to or greater than $10 million and sends it to the Agency Head for review. | Agency AMRB |
| 8 | Management-In-Use | Review/Approve Agency Project Portfolio | The Agency Head reviews the Agency Project Portfolio and makes a determination to approve, approve with recommended changes or reject the portfolio or projects within the portfolio. Once this determination is made, it is sent to the Departmental AMRB for review. | Agency Head |
| 9 | Management-In-Use | Review and Provide Recommendations regarding Department Portfolio for investments equal to or greater than $10 million | The Departmental AMRB assesses the investment’s progress and develops recommendations for the USDA agencies portfolio for significant investments. | Departmental AMRB |
| 10 | Management-In-Use | Maintain Facility Operations & Maintenance | Facility Manager reviews the individual property item condition assessments and prioritizes deficiencies in alignment with overall mission needs. Identified projects are categorized as deferred maintenance projects and are submitted into the budget cycle. Project descriptions and justifications are prepared in anticipation of the initiation of a corrective action project. | Facility Manager |
| 11 | Management-In-Use | Share Best Practices/Lessons Learned with Agency and Departmental AMRBs | To capture lessons learned, the Project Manager develops a Best Practices and Lessons Learned Report and submits it to the Project Sponsor, Agency Head and the Agency and Departmental AMRBs. All failures and successes are collected and shared to ensure that future initiatives can benefit from past experiences. A high-level assessment of management techniques, including organizational approaches, budgeting, acquisition strategies, tools and techniques, and testing methodologies is essential to establish realistic baselines and to ensure the future success of other real property initiatives. | Project Manager |
| 12 | Management-In-Use | Add Facility Information to the Corporate Property Automated Information System (CPAIS) | The Program Sponsor ensures that all of the required information related to the investment is entered into CPAIS following project completion for inventory and USDA real property portfolio purposes. | Project Sponsor |
| 1 | Disposition | Determine if the Asset Still Fits in the Agency’s Capital Asset Plan | The final determination to dispose of an asset must take into account a number of factors, including, but not limited to: Does the capital asset still support the mission? Is the asset wholly or partly unneeded? Does the asset meet established performance measures (right size, cost and condition to support Department/Agency mission and objectives)? Will program changes alter asset requirements? Is the asset used only irregularly for program use? Would a portion of the asset satisfy program needs? Is continued Federal ownership and operation of the property justified in light of its current use? Can the asset be made available for use by others, within or outside the Federal community? Are there security or other considerations that outweigh disposition of the asset? | Agency AMRB |

Table 7:  Major Investment CPIP instruction Steps

Major Investment CPIP Checklist

PLANNING AND BUDGETING

- Completed Project Data Sheet (see Appendix B)

- Agency approval for project incorporation into the Three-Year Rolling Timeline

- Prioritized Agency Investment List

ACQUISITION

- Performance goals and quantifiable performance measures

- A project plan which details quantifiable objectives including an acquisition schedule, project deliverables, and projected and actual costs

- Project costs, schedule, benefits, and risks

- Completed CAP (see Appendix D)

- Chief Acquisition Officer approval for investments over $5M (see Appendix F for guidance)

- Review/update investment on 3-Year Rolling Timeline

MANAGEMENT-IN-USE

- Completed all project investments

- Updated CAP

- Share best practices/lessons learned with agency and Departmental AMRBs

- Add facility information to the Corporate Property Automated Information System (CPAIS)

- Update investment information on the 3-Year Rolling Timeline

DISPOSITION

- Determine if asset should be retired, replaced, enhanced or refurbished

Appendix A – Acronym List

| ACRONYMS |
| --- |
| AMP | Asset Management Plan |
| AGAR | Agriculture Acquisition Regulation |
| AMRB | Asset Management Review Board |
| ASA | Assistant Secretary for Administration |
| BPIB | Budget and Performance Integration Board |
| CAP | Capital Asset Plan |
| CBA | Cost Benefit Analysis |
| CCA | The Clinger-Cohen Act of 1996 |
| CFO | Chief Financial Officer |
| CPAIS | Corporate Property Automated Information System |
| CPIP | Capital Programming and Investment Process |
| E.O. | Executive Order |
| EVMS | Earned Value Measurement System |
| FASA | The Federal Acquisition Streamlining Act of 1994 |
| FISMA | The Federal Information Security Management Act |
| FY | Fiscal Year |
| GAO | Government Accountability Office |
| GPEA | The Government Paperwork Elimination Act of 1998 |
| GPRA | The Government Performance and Results Act of 1993 |
| GSA | General Services Administration |
| IG | Inspector General |
| IPT | Integrated Project Team |
| NPV | Net Present Value |
| O&M | Operations and Maintenance |
| OBPA | Office of Budget and Program Analysis |
| OMB | Office of Management and Budget |
| OPPM | Office of Procurement and Property Management |
| PDS | Project Data Sheet |
| PIR | Post Implementation Review |
| PMA | President's Management Agenda |
| PMD | Property Management Division |
| PRA | The Paperwork Reduction Act of 1995 |
| ROI | Return on Investment |
| RPIR | Real Property Investment Report |
| SRPO | Senior Real Property Officer |
| USDA | United States Department of Agriculture |
| WBS | Work Breakdown Structure |

Appendix B--Project Data Sheet

The Project Data Sheet contains information that identifies the project (e.g. title, number, facility name, etc.).  It also provides a brief description and justification of the project, as well as the project score/rank and preliminary cost estimate.  Its use is mandatory for major and significant investment level projects.

Additionally, the Project Data Sheet allows for further examination of a proposed solution.  It focuses on an analysis of alternatives to meet the mission need and initial planning for entering into the Acquisition Phase.

Non-Major investments do not need to complete the Project Data Sheet for submission.  However,  agencies must take into consideration the applicable performance measures and how the project, regardless of cost, may affect the Department’s overall performance measures and should be prepared to provide the type of information included in this document to the Departmental AMRB during the review of the Three-Year Rolling Timeline.

The following activities are conducted during development of the Project Data Sheet:

- Identify business objectives based on mission analysis and Mission Needs Statement

- Discuss the proposed investment in relation to these questions:

  - Does the investment in major capital asset support core/priority mission functions that need to be performed by the Federal government?

  - Does it have to be undertaken by the requesting agency because no alternative private sector or government source can more efficiently support the function?

  - Does the investment support consolidation/sharing opportunities that would reduce costs, increase effectiveness, and improve customer service?

- Identify high-level performance measures (Additional detailed performance measures will be developed as part of the Acquisition Phase.)

- Determine key selection criteria to evaluate concept alternatives that support high-level performance measures and business objectives

- Ensure solution aligns with Department/Agency standards for health, safety, and security

- Identify alternatives that will be analyzed to support mission need and business objectives

- Determine whether the investment may incorporate components applicable to other mission needs and, if so, whether it may be appropriate to identify it as a key “line of business” for the development of a Modernization Blueprint.  If not, special care should be taken to determine and justify how the investment is truly unique and entails components that cannot be shared and reused for other purposes.

- Prepare a preliminary budget estimate providing an estimate of costs necessary to support more detailed planning and concept development prior to investment selection, and an order of magnitude estimate of budget requirements to support a three-year budget plan and lifecycle costing.  If appropriate, full project funding should be requested.

Project Data Sheet

<Agency Name>

| Project Information |
| --- |
| Project Title: | Project Score: | Rank: |
| Unique Asset ID | Agency/Facility Name |
| Region/Area/District | Congressional District | City | State |
| Project Classification: Capital Improvement, Repair and Maintenance, Purchase Land, Leases | Predominant Use Code: |
| Project Description: |
| Project Need/Benefit: |
| Alternative Analysis (Must be completed prior to entering the Acquisition Phase) |
| Alternative | Performance Measures |
|  | Utilization | Condition Index | Annual Operating Costs | Mission Dependency |
| Current Performance Measures (if existing) |  |  |  |  |
| Alternative 1 (Preferred) |  |  |  |  |
| Alternative 2 (second choice) |  |  |  |  |
| Alternative 3 (third choice) |  |  |  |  |
| Narrative Impact on Performance Measures: |

| Project Cost Estimate (This Request) | Project Funding History |
| --- | --- |
| Land Acquisition Cost | $ | Fiscal Year | Appropriation (Amount) | Source of Funds |
| Planning Cost | $ | FY XX |  | (B&F, MOD, R&M…) |
| Design Cost | $ | FY XX |  |  |
| Construction Cost | $ | FY XX |  |  |
| Total Project Cost |  | Appropriated to Date: $ |
|  |  | Future Funding to Complete Project: $ |
| Project Schedule | Support Documentation |
| Phase | Planned (Qtr/FY) | Actual (Qtr/FY) |  |
| Land Acquisition | (qtr/yyyy) |  | Capital Asset Plan (OMB 300) Yes No N/A |
| Planning | (qtr/yyyy) |  |  |
| Design | (qtr/yyyy) |  | Real Property Investment Report Yes No N/A |
| Construction | (qtr/yyyy) |  |  |
| Approvals | Preparation Information |
|  | Required | Approval Date | Not Approved with Remarks |  |
| Project Sponsor |  | mm/dd/yyyy |  | Prepared By |  |
| Area AMRB |  | mm/dd/yyyy |  | Office Phone |  |
| Agency AMRB |  | mm/dd/yyyy |  | Email |  |
| Agency Head |  | mm/dd/yyyy |  | Project Data Sheet Prepared/Last Updated | (mm/dd/yyyy) |
| Departmental AMRB |  | mm/dd/yyyy |  |  |  |

Appendix C—Real Property Investment Report

For projects requiring a RPIR (Non-Major and Significant Investments Only), the Project Manger prepares a RPIR in preparation for the annual investment review process by the Agency and/or Departmental AMRB.  The RPIR includes the following:

- Introduction and brief overview of the investment

- Mission Needs Statement

- Acquisition strategy

- Initial project plan with estimated costs listed

- CBA and budget estimate, including risk-adjusted ROI and NPV calculations

- Risk Assessment

- Performance goals

United States Department of Agriculture

Office of Procurement and Property Management

<Project Title>

Real Property Investment Report

Agency

Version 0.A (dd/mm/yyyy)

Document Acceptance and Release Notice

This is <release/version> <n.n> of the <Project Title> Real Property Investment Report (RPIR).  The RPIR is a managed document.  For identification of amendments each page contains a release number and a page number.  Recipients should remove superseded versions from circulation.

PREPARED:	DATE:___/___/___

(for acceptance)	(<Project Title> Project Manager, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(<Project Title> Project Sponsor, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Agency Head, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Agency Asset Management Review Board, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Departmental Asset Management Review Board, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Budget and Performance Integration Board, <name, title>)

Overview Information

Project Information

Input project information from the Project Data Sheet.

| Project Title: |
| --- |
| Project Number: | Department/Facility Name: |
| Region/Area/District: | Congressional District: | State: |
| Project Classification: New Construction, Renovation, Repair, Lease |

Purpose

Briefly describe the reasons for establishing the project and how it was initiated.

Background

Summarize the relevant background information that has lead to this project.

Business Need and Benefit

Clearly provide a description of the operational problem requiring this real property investment.  The description should include:

A summary of the business problem or need that requires a real property investment

The affect on your Agency/Program’s mission area/strategic goals this investment will have and how those goals relate to the overall USDA goals

The benefits to your Agency/Program

The criticality of this investment

The impact to your Agency/Program if the investment is not approved

Project Management Team

Identify the Project Management Team for this investment and their key responsibilities.

| Role | Name and Title | Project Responsibilities |
| --- | --- | --- |
| Project Sponsor |  |  |
| Project Manager |  |  |

Integrated Project Team

Describe the breakdown of the Integrated Project Team and the roles of personnel within the team.

| Role | Name and Title | Project Responsibilities |
| --- | --- | --- |
| Project Manager |  |  |
| Contracting Officer |  |  |

Reporting Requirements

Indicate the mechanism and frequency investment status is reported by the Project Manager to the Project Sponsor.

The Project Manager should report on the following:

    - Status of the project (milestones for the last reporting period, milestones for the next reporting period,	milestones for the remaining period of the project)

    - A budget report (with respect to planned expenditure, actual expenditure and the deficit/surplus)

    - An issues report (including areas of concern, specific problems, and any action that needs to be taken)

    - A risk management report (which will specify any changes to the major risks identified since the previous report and modification to the strategies put in place to manage them)

FRPC Performance Measures

- Utilization

Provide the Utilization.  The utilization is the percent utilized in relation to design capacity.

- Condition Index

Identify the Condition Index for the investment.

- Mission Dependency

Provide a short statement that describes how the investment is mission critical or mission dependent. If not, then explain why the investment must be approved (e.g., disposition costs).

- Annual Operating Costs

Insert the operating and maintenance costs for the investment. Identify whether there will be an increase or decrease in operating and maintenance costs with this investment.  Justify why the costs will increase if they will.

Summary of Funding

Funding Source

Describe in detail the funding source of all activities which require expenditures for this investment.

Funding Levels

Describe in detail the funding annually required to meet the investment needs, and breakdown the funding by Past Year (PY), Current Year (CY) and Budget Year, which is the future years’ budgets (BY).

| Year | Target | Actual |
| --- | --- | --- |
| 20XX (PY) |  |  |
| 20XX (CY) |  | N/A |
| 20XX (BY) |  | N/A |
| 20XX (BY) |  | N/A |
| Totals: |  |  |

Alternatives Analysis

Provide the high-level analysis information that was completed to determine this investment as the best option to meet the business need.  Provide a summary of the at least three options to meet the business need identified for the investment.  (The chosen option should be presented first.)  One option can be the “status quo.”  For each option include the benefits or advantages, disadvantages,

Preferred Option

Provide a summary of the investment as the chosen option. Include the four FRPC Performance Measures for that option.

| FRPC Performance Measures |
| --- |
| Utilization | Condition Index | Mission Dependency | Annual Operating Costs |

Alternative Option 1

Provide a summary of the second best option to meet the business need. Include the four FRPC Performance Measures for that option.

| FRPC Performance Measures |
| --- |
| Utilization | Condition Index | Mission Dependency | Annual Operating Costs |

Alternative Option 2

Provide a summary of the third option to meet the business need. Include the four FRPC Performance Measures for that option.

| FRPC Performance Measures |
| --- |
| Utilization | Condition Index | Mission Dependency | Annual Operating Costs |

Acquisition/Contract Strategy

Overview

Describe the overall strategy for acquiring the investment.  The type of contract vehicle, as well as any additional details, should be described here, which is required to support the investment.

Acquisition Breakdown

Insert all the acquisitions that are planned for this fiscal year in the table provided below.

| FY Planned Acquisitions |
| --- |
| Type (Good or Service) | Description | Contract Vehicle | Cost |
|  |  |  | $ |
|  |  |  | $ |
|  |  |  | $ |
| Total of Planned FY Acquisition | $ |

Contract Officer Technical Representative (COTR)

Provide the contact information for all COTRs associated with this investment.

Cost and Schedule Performance

Project Schedule

Identify and track the major milestones for the investment project.  Utilize the table below to summarize this data.  The project schedule should be attached to this report indicating two levels deep of tasking.

| <Project Title> Major Milestone Chart |
| --- |
| Milestone | Planned Completion Date | Actual Completion Date | Comment |

Performance Metrics

The following table provides examples of cost and schedule performance measures that are typical for many Real Property investment projects.

| Category | Focus | Purpose | Measure of Success |
| --- | --- | --- | --- |
| Schedule Performance | Tasks completed vs. tasks planned at a point in time | Assess project progress Apply project resources | 100% completion of tasks on critical path; 90% all others |
|  | Major milestones met vs. planned. | Measure time efficiency. | 90% of major milestones met |
|  | Revisions to approved plan | Understand and control project "churn" | All revisions reviewed and approved |
|  | Changes to customer requirements | Understand and manage scope and schedule | All changes managed through approved change process |
|  | Project completion date | Award/penalize (depending on contract type) | Project completed on schedule (per approved plan) |
| Cost Performance | Revisions to cost estimates | Assess and manage project cost | 100% of revisions are reviewed and approved |
|  | Dollars spent vs. dollars budgeted. | Measure cost efficiency | Project completed within approved cost parameters |
|  | Return on investment (ROI) | Track and assess performance of project investment portfolio | ROI (positive cash flow) begins according to plan |
|  | Acquisition cost control | Assess and manage acquisition dollars | All applicable acquisition guidelines followed |

Risk Management

Provide a summary of the Risk Management strategy being utilized throughout this project.  Utilize the table below to identify the all risks associated with the project and the status of those risks.

| <Project Title> Risks |
| --- |
| Date Identified | Area of Risk | Description | Probability of Occurrence | Mitigation Strategy | Current Status |

Appendix D—Capital Asset Plan

The Project Manager submits the CAP and their accompanying Project Data Sheet for Major Investments.  Key elements of the CAP submission include:

- Introduction and brief overview of the investment

- Mission Needs Statement

- Acquisition Strategy Statement

- Initial project plan with estimated costs listed for each Work Breakdown Structure (WBS)

- Performance goals

- Architecture and facility design, including accessibility for persons with disabilities

- Agency ranking and priority

- Alternative Analysis

- Risk Assessment and Mitigation Plans Statement

The Project Manager also reviews the project submission and requests the Project Sponsor to update the package or make changes as needed, including review and certification of the project budget/costs by the CFO.

The Agency Head then approves the investment submission and forwards the CAP to the Departmental AMRB.

United States Department of Agriculture

Office of Procurement and Property Management

<Project Title>

Real Property

Capital Asset Plan and Business Case Summary

Exhibit 300

Agency

Version 0.A (dd/mm/yyyy)

OMB Circular A-11 requires that the Capital Asset Plan (CAP) and Business Case Summary – Exhibit 300 must be completed for all Real Property investments that meet the following criteria:

- Total design and construction costs greater than $10 million

- Directly supports the President's Management Agenda Items of "high executive visibility"

- Multiple-bureau and/or agency projects

- Other significant projects requested by OMB

Document Acceptance and Release Notice

This is <release/version> <n.n> of the <Project Title> CAP and Business Case Summary Exhibit 300.  The CAP is a managed document.  For identification of amendments each page contains a release number and a page number.  Recipients should remove superseded versions from circulation.

PREPARED:	DATE:___/___/___

(for acceptance)	(<Project Title> Project Manager, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(<Project Title> Project Sponsor, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Agency Head, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Agency Asset Management Review Board, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Departmental Asset Management Review Board, <name, title>)

ACCEPTED:	DATE:___/___/___

(for release)	(Budget and Performance Integration Board, <name, title>)

PART I: SUMMARY INFORMATION AND JUSTIFICATION

Section A: Overview (All Capital Assets)

The following series of questions are to be completed for all investments.

Help OMB to identify which agency and bureau is responsible for managing each capital asset, which OMB MAX budget account funds the project, the kind of the project, who to contact with questions about the information provided in the exhibit 300, and whether or not it is an IT or a non-IT capital asset.

1.  Date of Submission:      (date)

2.  Agency:

3.  Bureau:

4.  Name of this Capital Asset:  (Short text)

5.  Unique ID: (For IT investments only, see section 53.  For all other, use agency ID system.)  (xxx-xx-xx-xx-xx-xxxx-xx)

6.  What kind of investment will this be in FY2008?
Planning  Acquisition  Operations and Maintenance   Mixed Life Cycle E-Gov/LoB Oversight

7.  What was the first budget year this investment was submitted to OMB?

(list “FY2001 or earlier” thru “FY2008”)

8.  Provide a brief summary of this investment:   (Long text)

9.  Did the Agency’s Executive/Investment Committee approve this request?  Yes   No

a.	If “yes,” what was the date of this approval?  (date)

10. Did the Project Manager review this Exhibit?  Yes    No

11. Contact information of Project Manager?

Name (short text)

Phone Number (xxx-xxx-xxxx)

E-mail (short text)

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

12. Has the agency developed and/or promoted cost effective, energy-efficient and environmentally sustainable techniques or practices for this project.  (Answer applicable to non-IT assets only)  Yes  No

a.	Will this investment include electronic assets (including computers)?  Yes    No

b.	Is this investment for new construction or major retrofit of a Federal building or facility?  (answer applicable to non-IT assets only)  Yes   No

1. If “yes,” is an ESPC or UESC being used to help fund this investment?  Yes   No

2. If “yes,” will this investment meet sustainable design principles?  Yes   No 	 
            3. If “yes,” is it designed to be 30% more energy efficient than relevant code?

Yes   No

13. Does this investment support one of the PMA initiatives?  Yes   No  
      If “yes,” check all that apply: 
       - Human Capital

- Budget Performance Integration

- Financial Performance

- Expanded E-Government

- Competitive Sourcing

- Faith Based and Community

- Real Property Asset Management

- Eliminating Improper Payments

- Privatization of Military Housing

- Research & Development Investment Criteria

- Housing & Urban Development Management & Performance

- Broadening Health Insurance Coverage through State Initiatives

-“Right Sized” Overseas Presence

- Coordination of VA & DoD Programs and Systems

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

14. Does this investment support a program assessed using OMB’s Program Assessment Rating Tool (PART)?  Yes  No  
a.	If “yes,” does this investment address a weakness found during the PART review?  Yes    No  
b.	If “yes,” what is the name of the PART program assessed by OMB’s Program Assessment Rating Tool?  
c.	If “yes,” what PART rating did it receive?

15. Is this investment for information technology?  (see section 53 for definition)  Yes  No   
If the answer to Question 16 was “Yes,” complete questions 16-23 below.  If the answer is “No,” do not answer questions 16-23.

16. Is this investment identified as “high risk” on the Q4 - FY 2006 agency high risk report (per OMB’s ‘high risk” memo)?  Yes  No

17.  If this project produces information dissemination products for the public, are these products published to the Internet in conformance with OMB Memorandum 05-04 and included in your agency inventory, schedules and priorities?  Yes  No  N/A 

18.  Are the records produced by this investment appropriately scheduled with the National Archives and Records Administration’s approval?  Yes  No

Section B: Summary of Funding (All Capital Assets)

- Provide the total estimated life-cycle cost for this investment by completing the following table.  All amounts represent budget authority in millions, and are rounded to three decimal places.  Federal personnel costs should be included only in the row designated “Government FTE Cost,” and should be excluded from the amounts shown for “Planning,” “Full Acquisition,” and “Operation/Maintenance.”  The total estimated annual cost of the investment is the sum of costs for “Planning,” “Full Acquisition,” and “Operation/Maintenance.”  For Federal buildings and facilities, life-cycle costs should include long term energy, environmental, decommissioning, and/or restoration costs.  The costs associated with the entire life-cycle of the investment should be included in this report.

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

| Table 1: SUMMARY OF SPENDING FOR PROJECT PHASES (REPORTED IN MILLIONS) All amounts represent Budget Authority (Estimates for BY+1 and beyond are for planning purposes only and do not represent budget decisions) |
| --- |
|  | PY-1 & Spending Prior to 2006 | PY 2006 | CY 2007 | BY 2008 | BY +1 2009 | BY+2 2010 | BY+3 2011 | BY+4 2012 and beyond | Total |
| Planning |  |  |  |  |  |  |  |  |  |
| Acquisition |  |  |  |  |  |  |  |  |  |
| Subtotal Planning & Acquisition |  |  |  |  |  |  |  |  |  |
| Operations & Maintenance |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |
| Government FTE Costs should not be included in the amounts provided above. |
| Government FTE Costs |  |  |  |  |  |  |  |  |  |
| Number of FTEs Represented by Cost |  |  |  |  |  |  |  |  |  |

Note: For the cross-agency investments, this table should include all funding (both managing partner and partner agencies).  Government FTE Costs should not be included as part of the TOTAL represented.

2.	Will this project require the agency to hire additional FTE’s?  Yes No

a.	How many and in what year?  (medium text)

3.	If the summary of spending has changed from the FY2007 President’s budget request, 
            briefly explain those changes.  (Long text)

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

Section C: Acquisition/Contract Strategy (All Capital Assets)

Complete the table for all contracts and/or task orders in place or planned for this investment:

| Contract or Task Order Number | Type of Contract/ Task Order | Has the contract been awarded, if so what is the date of the award? If not, what is the planned award date? | Start & end date of Cont ract/ Task Order r | Total Value of Contract/Task Order ($M) | Is this an Interagency Acquisition? (Y/N) | Is it perfor mance based? (Y/N) | Competitivel y awarded? (Y/N) | SIS, ESPC or UESC? (Y/N) | Is EVM in the contract t? (Y/N) | Does the contract include the required security & privacy clauses? (Y/N) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| (short text) | (short text) | (short text) | (sh ort text ) | (short text) |  |  |  |  |  |  |

2.   If earned value is not required or will not be a contract requirement for any of the contracts or task orders above, explain why: (long text) 
3.   Do the contracts ensure Section 508 compliance?  Yes  No  N/A 
4.  Is there an acquisition plan which has been approved in accordance with agency requirements?  Yes  No 
      a.	If “yes,” what is the date?  (date) 
      b.	If “no,” will an acquisition plan be developed?  Yes  No

- If “no,” briefly explain why: (medium text)

Section D: Performance Information (All Capital Assets)

- Agencies must use the Performance Goals and Measures Table below for reporting performance goals and measures for all investments.

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

| Table 1 |
| --- |
| Fiscal Year | Strategic Goal(s) Supported | Performance Measure | Actual/baseline (from Previous Year) | Planned Performance Metric (Target) | Performance Metric Results (Actual) |
| 2007 |  |  |  |  |  |
| 2007 |  |  |  |  |  |
| 2008 |  |  |  |  |  |
| 2008 |  |  |  |  |  |

| Table 2 |
| --- |
| Fiscal Year | Measurement Area | Measurement Grouping | Measurement Indicator | Baseline | Planned Improvement to the Baseline | Actual Results |
| 2007 | Mission & Business Results |  |  |  |  |  |
| 2007 | Customer Results |  |  |  |  |  |
| 2007 | Processes & Activities |  |  |  |  |  |
| 2007 | Technology |  |  |  |  |  |
| 2008 | Mission & Business Results |  |  |  |  |  |
| 2008 | Customer Results |  |  |  |  |  |
| 2008 | Processes & Activities |  |  |  |  |  |
| 2008 | Technology |  |  |  |  |  |
| 2009 | Mission & Business Results |  |  |  |  |  |
| 2009 | Customer Results |  |  |  |  |  |
| 2009 | Processes & Activities |  |  |  |  |  |
| 2009 | Technology |  |  |  |  |  |

PART II: 	PLANNING, ACQUISITION AND PERFORMANCE         INFORMATION

Part II should be completed only for investments which in FY2008 will be in “Planning” or “Full Acquisition,” or “Mixed Life-Cycle” investments, i.e., selected one of these three choices in response to Question 6 in Part I, Section A above.

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available

Section A: Alternatives Analysis (All Capital Assets)

In selecting the best capital asset, you should identify and consider at least three viable alternatives, in addition to the current baseline, i.e., the status quo.  Use OMB Circular A-94 for all investments, to determine the criteria you should use in your Benefit/Cost Analysis.

- Did you conduct an alternatives analysis for this project?  Yes  No 
a.  If “yes,” provide the date the analysis was completed?  (date) 
b. If “no,” what is the anticipated date this analysis will be completed? (date) 
c. If no analysis is planned, please briefly explain why not:  (long text)

- Use the results of your alternatives analysis to complete the following table:

| Alternative Analyzed | Description of Alternative | Lifecycle Costs estimate | Lifecycle Benefits estimate |
| --- | --- | --- | --- |
| Baseline | Status quo |  |  |
| 1 -(medium text) | (medium text) |  |  |
| 2 -(medium text) | (medium text) |  |  |
| 3 -(medium text) | (medium text) |  |  |

3.   Which alternative was selected by the Agency’s Executive/Investment Committee and

why was it chosen? (medium text)

4.   What specific qualitative benefits will be realized?  (long text)

Section B: Risk Management (All Capital Assets)

You should perform a risk assessment during the early planning and initial concept phase of the investment life-cycle.

Answer the following questions to describe how you are managing investment risks.

1.	Does the investment have a Risk Management Plan?  Yes  No 
a.	If “yes,” what is the date of the plan?  (date)

b.	Has the Risk Management Plan been significantly changed since last year’s
submission to OMB?  Yes No

- c. 	If “yes,” describe any significant changes: (long text)

2.	If there currently is no plan, will a plan be developed?  Yes  No

a. If “yes,” what is the planned completion date?  (date) 
            b.  If “no,” what is the strategy for managing the risks?  (long text)

3.	Briefly describe how investment risks are reflected in the life cycle cost estimate and investment schedule: (long text)

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

Section C: Cost and Schedule Performance (All Capital Assets)

1.  Does the earned value management system meet the criteria in ANSI/EIA 
Standard – 748?  Yes  No 
2.  Answer the following questions about current cumulative cost and schedule performance.  Indicate whether the information provided is contractor-only, or whether it includes both government and contractor costs.  “As of” date: date format (mm/dd/yyyy) 
     a.	What is the Planned Value (PV)?  (Positive dollar value with 3 decimals) 
        b.	What is the Earned Value (EV)?   (Positive dollar value with 3 decimals) 
        c.	What is the actual cost of work performed (AC)? (Positive dollar value with 3 decimals) 
3.  What is the calculated Schedule Performance Index (SPI= EV/PV)? 
Positive number with 2 decimal places 
4.  What is the schedule variance (SV = EV-PV)?  Positive or negative dollar value 
5.  What is the calculated Cost Performance Index (CPI = EV/AC)? 
Positive number with 2 decimal places 
6.  What is the cost variance (CV = EV–AC)? Positive or negative dollar value 
7.   Is the CV or SV greater than 10%? Yes  No 
     a.	If “yes,” was it the CV  or SV  or both  ? 
     b.    If “yes,” explain the variance:  (long text) 
     c.    If “yes,” what corrective actions are being taken? (long text) 
     d.   What is most current “Estimate at Completion”? (Positive dollar value with 3 decimals)   
8.  Is the department requesting a change in the performance baseline? Yes No 
9.  Complete the following table to compare actual performance against the current performance baseline and to the initial performance baseline.  In the Current Baseline section, for all milestones listed, you should provide both the baseline and actual completion dates (e.g., “03/23/2003”/ “04/28/2004”) and the baseline and actual total costs (in $ Millions).  Indicate if the information provided includes government and contractor costs: 
      a.	Government costs? Yes  No 
      b.	Contractor costs? Yes  No

|  | Comparison of Initial Baseline and Current Approved Baseline |  |
| --- | --- | --- |
|  | Initial Baseline | Current Baseline | Current Baseline Variance |  |
| Description of Milestone | Planned Completion Date (mm/dd/yyyy) | Total Cost ($M) Estimated | Completion Date (mm/dd/yyyy) Planned/Actual | Total Cost ($M) Planned/Actual | Schedule/Cost (# days/$M) | Percent Complete |
| (short text) | date | (Positive dollar value) | date | date | (Positive e dollar value) | (Positive e dollar value) | # days | +/- S | 0-100% |
| (short text) | date | (Positive dollar value) | date | date | (Positive e dollar value) | (Positive e dollar value) | # days | +/- $ | 0-100% |

Short text - 250 characters Medium text - 500 characters Long text - 2500 characters

All dollar amounts must be reported in millions with at least 3 decimals (6 decimals available)

Appendix E—Asset Management Review Board Charter

The following Appendix provides the Department Asset Management Review Board (AMRB) Charter.

The United States Department of Agriculture (USDA)

Departmental Real Property Asset Management Review Board (AMRB) Charter

Version 1.1

March 20, 2007

Table of Contents

1.0	Purpose	4

2.0	Background	4

3.0	Authority	4

4.0	Membership	5

5.0	Roles and Responsibilities	5

6.0	Meetings	6

7.0	Ratification	6

List of Tables

Table 1:  Investment Review and Approval Levels of Authority for the Department	5

# Purpose

The purpose of this Charter is to define the authority, membership, roles and responsibilities of the Departmental Real Property Asset Management Review Board (AMRB), and its relationships to other internal and external bodies.

# Background

USDA has recognized the need to adopt a more consistent, structured, performance-based, integrated planning process across all of its agencies to better enable the Department to oversee management of the extensive USDA asset portfolio. To meet this goal, USDA is building its process around the OMB Capital Planning and Investment Control (CPIP) guidance (See Capital Programming Guide, supplement to Part 7 of OMB Circular A-11). Utilizing the CPIP instructions to evaluate all real property investments will provide the Department and the agencies with the ability to manage risks and returns of real property assets throughout their lifecycle to ensure that USDA’s investments are well-conceived, cost-effective, and support strategic mission and business goals. All investments will be articulated in a business case, the requirements for which will be commensurate with the cost and impact of the investment on the organization.

The Departmental Real Property Asset Management Review Board is established pursuant to the requirements of Executive Order (E.O.) 13327, Federal Real Property Asset Management, which set expectations and requirements to “promote the efficient and economical use of Federal real property resources in accordance with their value as national assets and in the best interests of the Nation . . .” E.O. 13327 states that the executive branch departments and agencies of the Federal government “…shall recognize the importance of real property resources through increased management attention, the establishment of clear goals and objectives, improved policies and levels of accountability, and other appropriate action.”

To implement this initiative, the Department has included, as part of its Strategic Plan, a management initiative regarding Real Property.  This initiative, along with the Department’s Asset Management Plan (AMP), established the USDA Real Property Council (RPC), and appointed the USDA Senior Real Property Officer (SPRO).  Additionally, internal performance measures reflecting the President’s Management Agenda scorecard have been developed to evaluate compliance at the Departmental and Agency level. The AMRB is established as an integral component of USDA’s ongoing effort to implement E.O. 13327.

# Authority

The following directives authorize the establishment of this AMRB:

- E.O. 13327, Federal Real Property Asset Management, dated February 4, 2004.

- USDA Asset Management Plan (AMP), Version 6.1, dated April 14, 2006.

# Membership

The AMRB consists of the membership of the USDA Real Property Council.  The Assistant Secretary for Administration will serve as the Board chair and the USDA SRPO will serve as the Executive Secretary for the Board.

# Roles and Responsibilities

For all Major and Significant level investments, the Departmental Asset Management Review Board (AMRB) primary responsibilities are to:

- Evaluate and provide recommendations to agencies regarding Real Property projects above the GSA Prospectus level, which will create a USDA Real Property portfolio that best supports the Department’s missions and program delivery processes.

- Assemble a consolidated USDA Real Property portfolio using a standard set of criteria.

- Ensure the Department’s Asset Management Plan is followed by USDA agencies.

- Assure that the Department’s Real Property program remains in compliance with E.O. and implementing directives.

The Departmental AMRB provides recommendations on Agency proposed capital investments affecting the USDA portfolio to the Budget and Performance Integration Board (BPIB), which consists of the Deputy Secretary and Office of Budget and Policy Analysis (OBPA).  It is also responsible for setting performance goals, assessing how well investments meet the goals, and how agencies are meeting performance measure targets. The Departmental AMRB is chaired by ASA.

AMRB authorities for projects within the CPIP instructions are based upon the value of the project as shown in Table 1 below.

| Investment Type | Project Value | Required Review Documentation | Review Authority | Approval Authority |
| --- | --- | --- | --- | --- |
| Major | ≥ $10M or High Risk | Capital Asset Plan | Departmental Asset Management Review Board will review agency documentation and provide recommendations to the Budget and Performance Integration Board | Secretary |
| Significant | ≥ GSA prospectus level to < $10M | Real Property Investment Report | Agency Headquarters/Agency Asset Management Review Board | Agency Headquarters |
| Non-Major | < GSA prospectus level | As determined by Agency Headquarters | Agency Headquarters will determine asset management review authority | Agency Headquarters may delegate approval authority |

Table 6:  Investment Review and Approval Levels of Authority for the Department

# Meetings

The Departmental AMRB will hold meetings annually based on the reporting requirements of the USDA CPIP instructions or more frequently subject to the call of the Chair.  These meetings will be held in conjunction with the USDA budget submission process and schedule.

# Ratification

| Boyd K. Rutherford Assistant Secretary for Administration | DATE |  | Glenn D. Haggstrom Senior Real Property Officer | DATE |
| --- | --- | --- | --- | --- |

Appendix F—Agriculture Acquisition Regulation (AGAR) Advisory - 83

The following Appendix provides the AGAR Advisory 83: Acquisition Strategy Review and Approval Procedures

AGAR ADVISORY

##### UNITED STATES DEPARTMENT OF AGRICULTURE

##### OFFICE OF PROCUREMENT AND PROPERTY MANAGEMENT

AGAR ADVISORY NO. 83

Acquisition Strategy Review and Approval Procedures

INTRODUCTION:  The purpose of this Agriculture Acquisition Regulation (AGAR) Advisory is to establish interim policy and procedures for Chief Acquisition Officer (CAO) review of acquisition activities and programs of the Department of Agriculture (USDA).

SUMMARY:    Review of USDA’s acquisition activities is essential for effective management and to ensure that business approaches effectively support the USDA mission and program objectives.  Acquisition strategies for certain planned acquisitions based on dollar value, mission-impact, or as otherwise deemed appropriate by the CAO, will be submitted for review and approval in accordance with this AGAR Advisory.  This new process will be effective March 15, 2007.

SPECIFIC ISSUES:

- Background

  - Pursuant to 41 USC 414(a) the Secretary of Agriculture has designated the position of Assistant Secretary for Administration (ASA) as USDA’s CAO.

  - One of the primary duties of the CAO is to ensure, through proper management of USDA’s acquisition activities, that USDA mission objectives are achieved.  To support the CAO in fulfilling this responsibility and executing the functions delineated in 41 USC 414(b) and (c), agencies will submit written documentation concerning planned acquisition activities and provide necessary notifications in accordance with the acquisition strategy requirements in this AGAR Advisory.

  - The review and approval of acquisition strategies for significant planned acquisitions will provide the CAO one mechanism for reviewing the acquisition activities of the contracting agencies.  This process will accomplish the following results:

    - Provide a Departmental level review of the business approaches utilized by the contracting agencies in meeting USDA mission requirements,

    - Ensure that Federal and Departmental initiatives are being addressed,

    - And provide a regular venue for agencies to raise issues that may be of concern to the Department.

- CAO Review and Approval for Non-Commodity Acquisition Strategies

  - Review and Approval Thresholds

Pursuant to AGAR 407.103 the Head of the Contracting Activity (HCA) is responsible for developing procedures to comply with the acquisition planning requirements of FAR 7.103.  In conjunction with FAR planning requirements the CAO will review and approve the acquisition strategies for planned acquisitions meeting any of the following criteria:

- Acquisitions with an estimated value (inclusive of all option periods, quantities and items) of $5 million or greater, over the life of the contract.

- Acquisitions include contracts, letter contracts, blanket ordering agreements (BOAs), blanket purchase agreements (BPAs), delivery and task orders under Federal Supply Schedule Contracts, orders placed against indefinite delivery, indefinite quantity (IDIQ) contracts, all contracts awarded by other Federal agencies, exercise of unpriced options, and new work or scope modifications with an increase of $5 million or greater.

- For BOAs and BPAs the estimated value is the maximum value of all orders which may be placed under the agreement.

- Upon CAO review and approval of an initial planned acquisition, all associated options and orders over the life of the contract shall be covered up to the maximum estimated value of the original CAO approval.

- Acquisitions for major information technology (IT) investments in accordance with the criteria in (i)(A) through (C) below:

- Pursuant to the USDA Information Technology Capital Planning and Investment Control Guide, major IT investments are defined as investments which meet at least one of the following criteria:

  - Total lifecycle costs greater than $50 million or lifecycle Development/ Modernization/Enhancement (D/M/E) funding of $20 million or more, (Review and approval procedures for all contract actions $5 million and greater outlined in II(A)(1) apply)

  - Financial systems with costs greater than $500,000 per year in FY 2006 or later.

  - Identified by the USDA CIO as critical during the E-Board and IT Acquisition Approval process.  This may include systems that are

- Mandated by legislation or executive order, or

- Require a common infrastructure investment, or

- Are considered strategic or mandatory-use systems, or

- Significantly differ from or impact the Department infrastructure, architecture, or standards guidelines, or

- Receive significant multiple-agency funding.

- Planned acquisitions and contract actions for major IT investments are required to be included as part of the OMB Circular No. A-11, Part 7, Exhibit 300, for submission to OMB.

- Acquisitions identified by the HCA or Designee (HCAD) or CAO as significant because of cross-agency impact, their critical roles in mission accomplishment or to insure compliance with Presidential initiatives.

  - Requirements, Procedures and Submission Format

- Approval of the acquisition strategy by the CAO is required prior to issuance of the solicitation.  The Senior Procurement Executive (SPE) can review and approve in situations of CAO absence, unavailability, or emergency.  Agencies are encouraged to submit the required information for approval as early as possible in their schedule thereby limiting delay at the time of solicitation issuance.

- The acquisition strategy shall be submitted by the HCA or HCAD to the SPE via the Chief, Procurement Policy Division, Office of Procurement and Property Management (PPD/OPPM).  All agency acquisition strategy submissions shall be emailed to todd.repass@usda.gov, linda.persons@usda.gov and glenn.haggstrom@usda.gov.

- Attachment (1) is the acquisition strategy format required.

- Acquisition strategies shall be submitted, electronically to the Chief, OPPM/PPD, at least ten (10) working days prior to the bi-weekly CAO/SPE Acquisition Strategy Review Meetings (ASRMs.)  The CAO/SPE reserves the right to schedule additional ASRMs to accommodate initiatives or emergencies.

- ASRMs include the CAO, SPE, and Procurement Policy Division staff.  Other meeting participants may include on an as needed basis as requested by OPPM/PPD: Office of General Counsel, Office of Small and Disadvantaged Business Utilization, Agency representatives, and other subject matter experts.  The schedule for these meetings will be distributed by separate guidance to the HCAs/HCADs.

- Disposition (approval, disapproval, conditional approval) of the acquisition strategy submission will be provided at the ASRMs.  Notification of the disposition will be provided to the HCA/HCAD electronically within 2 business days of the ASRM disposition.

  - Changes in Acquisition Strategy Subsequent to Approval - Notifications

Agency updates involving significant changes to a strategy which has been already approved by the CAO must be described in a written notification to the CAO within three business days after the significant change occurs.  These updates include, but are not limited to, changes in the requirements, changes in strategy such as contract type, type of statement of work, small business approach to solicitation, or an increase of 10% or more in the total estimated value of the acquisition.  Agency notifications shall be submitted in accordance with the email distribution outlined in section II(B)(2) above.  Change notifications shall reference the Acquisition Strategy Identifier number, point of contact information, a detailed description of the significant change, and Agency HCAD approval.

  - Revision to CAO Review and Approval Threshold

This AGAR Advisory establishes an initial threshold of $5 million for CAO review and approval.  The CAO reserves the right to revise this initial threshold to a different dollar amount if considered appropriate and necessary for effective management of the USDA acquisition activities.  In situations of emergency or disaster, the CAO/SPE may temporarily waive the requirements of this advisory for identified acquisitions.

- HCA/HCAD Review and Approval of Non-Commodity Acquisition Strategies

(A) HCAs/HCADs shall develop a comparable acquisition strategy review process that requires HCA/HCAD review and approval of planned acquisitions (see paragraph II(A) above as a template for establishing your Agency $1 million to $5 million process) with an estimated value (inclusive of all option periods, quantities and items) between $1 million and $5 million, over the life of the contract.

(B) An Agency’s acquisition strategy review process shall be submitted by email to the Chief, OPPM/PPD for review and concurrence.  This process may include a request for consideration to delegate the review and approval authority of $1 million to $5 million to a level below the HCAD.  Upon approval and implementation, copies of all applicable Agency reviews and approvals shall be submitted to the Chief, OPPM/PPD upon request.

- HCA/HCAD Review and Approval of Contractual Commodity Acquisition Strategies

(A) Farm Service Agency Kansas City Commodity Office (FSA KCCO), and Agricultural Marketing Service (AMS) in coordination with the Animal and Plant Health Inspection Service (APHIS), HCAs/HCADs shall develop a comparable acquisition strategy review process that requires HCA/HCAD review and approval of planned acquisitions (see paragraph II(A) above as a template for establishing your Agency $1 million to $5 million process) with an estimated value (inclusive of all option periods, quantities and items) of $1 million or greater, over the life of the contract.

(B) An Agency’s acquisition strategy review process shall be submitted by email to the Chief, OPPM/PPD for review and concurrence.  This process may include a request for consideration to delegate the review and approval authority to a level below the HCAD.  Upon approval and implementation, copies of all applicable Agency reviews and approvals shall be submitted to the Chief, OPPM/PPD upon request.

- Implementation Requirements and Schedule

  - By March 12, 2007, the HCAs/HCADs shall submit to the Chief, OPPM/PPD, for review and concurrence, their agency/mission area Agency Strategy Review and Approval procedures that include, at minimum, procedures to comply with the HCA/HCAD acquisition strategy review and approval requirements established in paragraphs III or IV above.

  - The CAO and HCA/HCAD review and approval requirements and procedures established by this AGAR Advisory are effective March 15, 2007.

  - All planned acquisitions with an estimated value of $5 million or greater that have a documented issuance of the solicitation or publication of the FedBizOps solicitation notice prior to March 15, 2007 are exempt from this advisory.

This advisory is available on the USDA procurement homepage at http://www.usda.gov/procurement/policy/advisories.html.

EXPIRATION DATE:  Eighteen months from the date of this Advisory.

[END]

______________________________		      ______________

Chief Acquisition Officer	              Date

ACQUISITION STRATEGY

- Acquisition Strategy Identifier:

Agency Identifier - FY - Agency

(e.g., REE-06-0001, as determined by Agency)

- Contracting Agency Information

Agency Name and Address:

Agency Point of Contact:	    	Name:

Email Address:

Telephone Number:

Contracting Office Name and Address:

Contracting Officer:		Name:

Email Address:

Telephone Number:

- Please include a description of planned acquisition, including scope of work (attach), major deliverables/services, name of Agency Program/Project supported by the Acquisition.

- List the Estimated Dollar Amount (inclusive of all options).

- Provide the Period of Performance/Delivery Schedule.

- What funding method is planned? (proposed funding, include type and year of funds/no year)

- What is the Contracting Method?

  - Solicitation type (e.g., sealed bid (IFB), negotiated (RFP), request for proposals under a multiple award contract or Federal Supply Schedule, interagency agreements).

  - Small Business Program Considerations (e.g., 8(a) competitive, 8(a) non-competitive, small business set-aside, HubZone set-aside, Service Disabled Veteran owned small business, women-owned small business).

Provide a rationale and address market survey(s) conducted, if the planned acquisition will be unrestricted.

  - Extent of competition (e.g., full and open competition, competition after exclusion of sources, other than full and open competition pursuant to FAR 6.3, competition under Federal Supply Schedule, sole source set-aside, brand name specified under FSS, GWAC, multiple award or other indefinite delivery type contracts.

For brand name specific order, attach a copy of the justification as required by FAR 11.105 (See AGAR Advisory 75).

For other than full and competition pursuant to FAR Part 6.3, attach a copy of the approved justification for other than full and open competition.

  - For service contracts or task orders  -  if the contract or statement of work will not be performance based provide a rationale.

  - Source selection procedures

  - Contract Type (see FAR part 16) including pricing structure

  - Identify option periods, quantities or items

  - For indefinite delivery type contracts, identify the authorized users

- For major IT investments include a copy of OMB Circular A-11, Exhibit 300, Part I, Section A, Overview (All Capital Assets), Section B, Summary of Spending (All Capital Assets) and Section C, Acquisition/Contract Strategy (All Capital Assets).

- If the acquisition is a follow-on procurement, what is the current contract/order number(s), contractor(s) name and address and expiration date(s)?

10.  Does the scope include Biobased, BioPreferred products or other green purchasing initiatives?  What other acquisition issues of note should be provided?

SUBMITTED FOR REVIEW AND APPROVAL:

____________________________________	________________________

Project Manager	Date

____________________________________	________________________

Project Sponsor	Date

____________________________________	________________________

Contracting Officer	Date

HCA or HCAD					Date

---------------------------------------------------------------------------------------------------------

RECOMMENDATION TO THE CAO:

Approve				 _____________

Disapprove				 _____________

Approve Subject to listed conditions   _____________

Conditions:

Chief, Procurement Policy Division, OPPM		Date

Senior Procurement Executive			Date

---------------------------------------------------------------------------------------------------------

DECISION OF THE CAO:

Approved

Disapproved

Approved Subject to the listed conditions

Conditions:

Chief Acquisition Officer				Date

Appendix G—U.S. Department of Agriculture Real Property Disposition Process, September 20, 2006

The following Appendix provides the USDA process and reference guide for determining which assets should be disposed, retired, replaced, enhanced or refurbished.  It also lists actions agencies must take if assets with sub-standard performance measure scores are to be retained.

U. S. DEPARTMENT OF AGRICULTURE

REAL PROPERTY DISPOSITION PROCESS

September 20, 2006

Introduction

This document is a reference guide that discusses the U. S. Department of Agriculture’s (USDA) real property disposition process.  The process starts with incorporation of the Federal Real Property Asset Management Initiative Framework as outlined in the Office of Management and Budget’s (OMB) “Achieving Green in Federal Real Property Asset Management” (see below) as the formalized end target toward the goal of rightsizing USDA’s asset portfolio.  This guide will then discuss utilization of the General Services Administration’s (GSA), Federal Real Property Profile-Performance Assessment Tool (FRPP-PA) to identify USDA facilities within the six levels based on the Disposition Decision Tree developed by the Federal Real Property Council (FRPC), Performance Measures Committee.

References

For further guidance on the USDA disposition process, see the following references in the USDA Asset Management Plan (AMP):

- Section 1.2.3 		Six Areas of Focus (see #3-6)

- Section 4  		Operations and Maintenance of Real Property

- Section 5		Disposal of Unneeded Real Property

- Section 6		Performance Measures and Continuous Monitoring

The Disposition Process will be included in the next revision of the USDA AMP that is due in the second quarter of fiscal year 2007.

Background

One of the main goals in the President’s Management Initiative, as outlined in Executive Order (E.O.) 13327, Federal Real Property Asset Management, is to ensure that property inventories are maintained at the right size, cost, and condition to support agency missions and objectives.  While simple in construct, this task requires dedicated resources, effective coordination, and agency commitment to make tough decisions when needed.  Agencies were, therefore, charged with developing and implementing the necessary tools (planning documents, consistent recording of inventory, and utilization of government-wide performance measures) to improve management decision-making as identified in the OMB quarterly scorecards.  To begin this process, the FRPC developed the Federal Real Property Asset Management Initiative Framework discussed below.  In order to fully align its real property organization mission with the principles of E.O. 13327, USDA has embraced the real property initiative framework as reflected below and published in the document “Achieving Green in Federal Real Property Management.”

Federal Real Property Asset Management Initiative Framework

The Real Property initiative can be thought of as a layered pyramid, where each successful layer builds upon the developed tools and measures to create a rightsized Federal inventory.

Figure 2: Real Property Initiative Framework

Pictorially, as noted in Figure 1 above, the yellow foundation of the pyramid represents the basic tools needed to make decisions on asset management.  These tools are a complete and accurate inventory of all constructed assets; agency asset management plans which systematize agencies procedures and actions related to asset management; and performance metrics against which agencies can measure and evaluate asset management performance.

The second level of the yellow foundation of the pyramid represents the activities and tools needed for the government and agencies to enhance Federal asset management.  They are not dependent upon the foundation layer for execution, but would streamline government-wide asset management once implemented.  The disposition algorithm segment provides for the creation of a government-wide analytical formula to assist agencies in better identifying and ranking agency assets for possible disposal or rehabilitation.  The legislative proposal segment, once enacted, will help provide relief from barriers and process inefficiencies that agencies currently encounter when disposing, transferring, construction or renovating assets in the modern real estate market.

Once many of the tools are established, it will provide USDA with the foundation to develop a plan that addresses the specific actions that need to be taken in order to meet the goals and objectives of the real property asset management program.  This is a necessary step for demonstrating results toward rightsizing the agency asset portfolio.

With these tools and activities in place, and as we begin to implement the identified plan for meeting the goals and objectives, the final step is to move to the top, darker green portion, of the pyramid and produce measurable results.  The top of the pyramid highlights three targets for USDA to achieve in rightsizing its portfolio:

- Agencies must eliminate non-mission dependent inventory;

- Agencies must improve condition of its mission critical and mission dependent inventory; and

- Agencies must manage their inventory at the right cost.

With these targets in mind, agencies will make sound asset management decisions leading to a rightsized Federal inventory.

Disposition -Process Overview

USDA will utilize the Federal Real Property Profile Performance Assessment Tool (FRPP-PA) to segment all facilities/assets within the six levels based on the disposition decision tree as depicted on the following page.  This disposition decision tree will be followed by a discussion of each step of the process that must be completed to categorize USDA assets within the six categories.  It is critically important to ensure that all four performance measures are captured properly for each asset, as well as to ensure the status code (Active, Inactive, or Excess) is correct to get a true reflection of where each facility will fall in the six categories.

The following section explains the steps of the disposition process in detail as they relate to each of the categories outlined on the disposition algorithm tree.  For each general step, guidance is outlined as to procedures to follow.  These general steps are then followed by specific instructions for USDA assets.  For assets/properties that have fallen in categories 1a or 2a it will be imperative that each agency take a critical look at the asset.  If an agency decides against disposing of an asset, the agency must provide appropriate justification for retaining the asset and list what steps will be taken to improve the performance measures of each asset.  See the third series of boxes on the on the Decision Tree on page 5 and follow the procedures outlined below for actions that must be undertaken.

- Box 1 -   Determine asset status.  If the asset is declared Excess, proceed to Box 1a and the process ends for this asset.  If the status is declared Active or Inactive, proceed to Box 2 and determine if there is a Federal need for this asset based on Mission Dependency.

USDA Guidance:  1b) For properties that fall into the Excess Status (Level 5) report, follow the normal departmental internal screen process within 60 days of the results of the report.  If it is determined that there are no USDA agencies interested in the property, then declare the property excess to the Department and process the appropriate paperwork to submit the property to GSA for disposal by the end of the Fiscal Year (see AMP Section 5; FMR 102-75.115; AGPMR 110-75.115-5020 to 5045).

- Box 2 -   If no and the Mission Dependency is determined to be Not Mission Dependent, then proceed to Box 2a to ascertain if the asset or facility is still needed.  If the Mission Dependency is Mission Critical or Mission Dependent, then proceed to Box 3.

USDA Guidance: 2b) For properties that fall into the Mission Dependency (Level 4) report, if the property is determined to be “Not Mission Dependent” and the agency has no further use for the property, then follow the excess procedures outlined in 1b above.  However, if the agency determines that the property needs to be retained in its inventory for a future need, provide justification as to the retention of the property and indicate the intended future plans.  This property will require an approved waiver as part of the Department’s five-year certification process (See Request for Waiver to Retain Not Mission Dependent Asset at end of document).  Waivers are due to OPPM each July.

For the next three steps (Boxes 3-5), agencies with assets that do not meet the USDA performance measure targets for utilization, condition index and annual operating costs, but that the agency proposes to retain in an active or inactive status,  must submit to OPPM by the fourth quarter of the fiscal year a list that includes which performance measure is not met and when the facility will be brought into compliance.  Agencies must also ensure that corrective measures are included for the asset in the agency Facility Master Plans that will be developed as well as including initiatives addressing deficiencies as part of the agency’s three-year timeline.

- Box 3 -   To determine how the facility/asset falls in terms of Utilization, ask the question “Is the facility utilized?”  If the response is no, and the facility is determined to be under-utilized or not utilized, then a determination as to disposition or to look for sharing opportunities must be undertaken (Box 3a).  If the response is yes and the facility or over-utilized or utilized, then proceed to Box 4.

USDA Guidance: 3b) If there is no USDA need identified, submit the space to GSA for screening other Federal agency interest for sharing opportunities (see 1b).  For properties that fall into the Utilization (Level 3) report, if the property is determined to be “not utilized” or “under-utilized,” but program requirements preclude sharing with other agencies, a justification for continuing to retain the asset must be provided to OPPM stating reasons and rationale as part of the fourth quarter submission of underperforming assets.

- Box 4 -   To determine how the facility falls in terms of Condition Index, ask the question “Is the facility in good condition?”  If the response is no and the Condition Index is < 90%, then a determination as to disposition, replacement, or upgrade of the facility must be undertaken (Box 4a).  If the response is yes and the facility is > 90%, proceed to Box 5.

USDA Guidance: 4b) For properties that fall into the Condition Index (Level 2a) report, if the property is planned for disposal, outline the disposition timeframe (see 1b).  If retaining, submit as part of the fourth quarter submission of underperforming assets.

- Box 5 -   To determine how the facility falls in terms of operational efficiently, ask the question “Does the facility operate efficiently?”  If no and the ratio of Annual Operating Costs to the Square Footage of the facility is > the 75th percentile, then a determination as to the disposition, replacement or upgrade of the facility must be undertaken (Box 5a).  If the response is yes and the ratio of Annual Operating Costs to Square Footage is < the 75th percentile, proceed to Box 6.

USDA Guidance: 5b) For properties that fall into the Annual Operating Costs (Level 2b) report, if the operating and maintenance (O&M) costs of the asset exceeds USDA’s annual operating cost target and is to be retained, the agency must submit as part of the fourth quarter submission of underperforming assets.

This is the final categorization or segment of the disposition process resulting in retention of the asset.

PLEASE NOTE:  Box 3 is applicable only for buildings with predominant use of:  Office, Hospitals, Warehouses, Labs, and Housing.

Outcome

All assets reported to the FRPP will then be categorized in the six major categories on the disposition tree utilizing the Performance Assessment Tool:

- Keep the Asset

- Determine disposition, replacement or upgrade of the asset based on the annual operating costs

- Determine disposition, replacement or upgrade of the asset based on the condition index level

- Determine disposition or look for sharing opportunities based on utilization

- Determine disposition of the asset based on mission dependency

- Asset declared excess based on excess status code

REQUEST FOR WAIVER TO RETAIN

NON- MISSION DEPENDENT ASSETS

SECTION I: Asset Description

Data for 24 FRPC required Data Element:

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

SECTION II: Justification for Retaining Asset

a. Why does asset have to be retained: _____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

b. Alternative(s) considered:

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

c. Reason(s) alternatives not viable:

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

d. Economic analysis supporting retaining the facility vs. relocating to another mission

dependent or mission critical facility:

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

e. Historical property:

______________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

SECTION III: Performance Measures

a. Does the asset meet USDA performance measures target for utilization (as applicable), condition index, and annual operating and maintenance costs?

________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

b. IF NOT, provide plan and timeframe for meeting target.  Plan to include estimated cost of bringing the

asset up to standard, anticipated future operations and maintenance costs, fiscal year to be budgeted in,

and if fiscal year asset will meet performance measures targets.

____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

SECTION IV: Agency Asset Management Review Board Certificate

Date________________           ____________________________________

Agency Head

SECTION V: Department Asset Management Review Board Action

Recommend Approved____	Recommend Disapproved____

Comments:

____________________________________________________________________________________________________________________________________________________________________________________________________________________

Date________________            ____________________________________

Assistant Secretary for Administration

SECTION VI: Budget and Performance Integration Board

Approved____

Disapproved____

Date________________           __________________________________

Deputy Secretary

SECTION VII: Waiver Expiration date

Date__________________

# Text boxes

Real Property Capital Programming and Investment Process

FY2007