## Actions
AMS Integration Action Items Last Update: August 27, 2007
No. | Integration Actions | Responsible | Date assigned | Date Due | Open | Closed | Comments/Status NOTE! MIT stands for AMS Mechanical Integration Team
0 | Invite M.Molina to ALL integration meetings anywhere in the world. | A. Lebedev, S. Ting | Since the beginning of Time | Every Meeting | X |  | Will end when AMS re-enters the earth's atmosphere with ISS.
1 | Distribute weekly Integration telecon phone number to AMS Integration Team. Telecon at 3 PM Geneva every Tuesday. | K. Bollweg | 2007-03-12 | 2007-03-19 |  | X | Closed 19-Mar-07. Reopened & closed on 20-Mar with new toll-free numbers. K.Bollweg will report any major integration issue to Prof. Ting for a decision.
2 | Add Eric Perrin to Integration Team e-mail distribution. | K. Bollweg | 2007-03-12 | 2007-03-19 |  | X | Closed 19-Mar-07. Also added T. Martin & C. Clark.
3 | Add window for Magnet Field Mapping to schedule | J. Heilig, K. Bollweg | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Closed on 10-Apr.
4 | Setup FTP site for repository of AMS 3D CAD models | A. Eline | 2007-03-12 | 2007-03-19 |  | X | Closed 19-Mar-07. The FTP site was been set up - see e-mail from Mike Capell dated March 20th distributed with Revision 2 of this list.
5 | Establish system for dropping CAD models onto FTP site, tracking that includes a clear identification of the model date, who is responsible for delivering the model, and when an updated model is needed with a due date. | R. Becker | 2007-03-12 | 2007-03-19 |  | X | Use YYMMDD for date. Available CAD files are on site as of 6-Apr to close original action. Robert is updating the model status list. Some users are experiencing a read-write problem
6 | Verify CAD model interfaces and interferences, place checked models on server for access by integration team, and notify integration team members as required when conflicts exist. | R. Becker | 2007-03-12 | On-going | X |  | Robert is the official "Keeper of the Holes." He will use the naming convention in the AMS/USS ICD and will work with C. Cargiulo, F. Cadoux, & J. Kastelic. First release 13-Apr-07. Robert expects to have it done by May 4th. Robert said he would post by 22 June, 02 July.
7 | Establish integration team mailing list. | A. Eline | 2007-03-12 | 2007-03-19 |  | X | Received test e-mail on March 19th and the list was updated on the 20th. It will continue to be updated as required.
8 | Cable balcony common design to be proposed by AMS MITeam; reactions at bolt locations will provided to CGS for crates bolt analysis. Groups deviating from this common design have to send their balcony model with structural analysis to AMS MITeam for approval. | F. Cadoux | 2007-03-12 | 2007-04-23 |  | X | Close design by end of June. Proceed with production in July. Will focus on mods for Tracker balconies. Will meet E. Perrin on 6/21. Tracker - U balcony, J/ECAL balconies weight is still on the order of ~12.8 kg for all balconies. M. Molina needs to check masses of cables and balcony weights and their effect on the crate links. Franck presented status at July TIM. Still some details to be resolved. Each subdetector will produce these balconies. The action item for design is closed.
9 | Provide information on all MLI layout and fixation. Especially LUSS around RICH to Lower Support Ring of the VC and back of Main Radiators around electronics crates. Also for coverage of the TTCS condensor tubes (JvE to talk to MM). | M. Molina | 2007-03-12 | 2007-04-23 | X |  | Delays due to possible US vendor - some of these around the VC support rings are now provided by MIT. Finalize layout & fixation by end of June - same as action 11. | no update to RICH MLI. Early MLI for VC support rings is about to be contracted. Two proposals in hand. Main radiators & TTCS condensor tubes in September.
10 | Provide information U-TOF MLI fixation point for TRD MLI to K.Luebelsmeyer | G. Laurenti | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Giuliano recommends using X =0 & Y=0 with 2 " diameter velcro patch. Per Craig on 17-Apr, no velcro is needed. Closed May 8th - no velcro needed. | no update
11 | Define fixation of MLI/Beta cloth on Tracker planes and provide pins to Eric Perrin | M. Molina | 2007-03-12 | 2007-04-23 | X |  | CGS contractor will install pins in tracker. No update - part of early MLI.
12 | MLI fixation devices and pins will be delivered by MLI responsible to each sub-detector in time for the AMS pre integration in order to check any interference. Pre-installation of these devices will be made by MLI responsible. | Various | 2007-03-12 | As required | X
13 | Provide updated presentation on Clean Room space allocation with schedule. Also include plans for all storage outside Clean Room for flight & non-flight hardware, PSS, lifting fixtures, shipping crates, etc. | V. Plyaskine | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN.
14 | Clarify interface between MLI and Star Tracker Lens. | M.Molina & C. Gargiulo | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN. Corrado sent e-mail on 17-Apr outlining this interface. Will be discussed further at CERN during TIM.
15 | Presentation on clean room procedures. | K. Bollweg | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN. Deferred to next Integration meeting at CERN on June 7/8.
16 | Provide AMS Cleanroom Guidelines | K. Bollweg | 2007-03-13 | 2007-04-23 | X |  | Deferred to next Integration meeting at CERN on July 26/27.
17 | Check MLI or just Beta cloth on -Z surface of Tracker plane #5 and verify model thermal configuration. | M. Molina & C. Clark | 2007-03-12 | 2007-03-19 |  | X | Per Craig, there is nothing on the +Z plane #1 of the Tracker; the bottom has beta cloth + MLI. Marco confirmed this is correct on 21-Mar.
18 | Check low emmisivity surface(s) between Tracker & ACC and verify model thermal configuration. | M. Molina & C. Clark | 2007-03-12 | 2007-03-19 |  | X | Per Craig, the inner shell of the ACC as well as the Tracker are to have low emmissivity surfaces. Marco confirmed the ACC inner does have the low e coating on 21-Mar. On 3-Apr Marco said the low emmissivity coating is not needed on the Tracker.
19 | Add time to schedule to install MLI to back of Main Radiators between STA VC removal and Flt VC Installation. | J. Heilig | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. John has added two weeks - though he hasn't received any inputs from the collaboration.
20 | Send final drawings of TRD MLI to K. Luebelsmeyer. Not sure if these drawings have been sent. Trent will check on 19 June. | J. Cornwell | 2007-03-12 | 19-Mar-07; Closed 25 May - drawings received |  | X | Craig will check with John Cornwell; Klaus will send to Marco. As of 27-Mar, Craig will pester John again. Per Craig on 3-Apr, the design is being revised to reverse the MLI to improve static discharge. Final drawings to Klaus by 6-Apr. E-mail from Terry Wille/EC on 6-Apr indicated drawings were not ready. As of 27-Apr the drawings were still stuck in checking at NASA behind work for upcoming flight. As of 15-May, the drawings are released and C. Clark will send to R. Becker for AMS CAD ftp site.
21 | Inform AIDC during weekly videoconference of proposal to incorporate Main Radiator Linear Bearings & brackets into temporary mounting jigs. | R. Becker | 2007-03-13 | 2007-03-29 |  | X | AIDC was asked to modify a radius of one piece of hardware during telecon on 28-Mar. R. Becker notified AIDC at video con on 4-Apr of the linear bearing design. Robert presented the design at AIDC on 16-Apr. AIDC was asked to implement the linear bearing modification.
22 | CGS will provide +X, +Y corner Zenith Radiator mock-up for pre-integration in September 2007. This must include loop heat pipes to Cryocooler. | M. Molina | 2007-03-13 | 2007-09-01 | X |  | This is the corner that is most crowded.
23 | Coordinate TTCS plumbing lines rounting on wake VC rings with SCL. | R. Becker & J. van Es | 2007-03-13 | 2007-03-22 |  | X | Was completed at integration meeting at SCL on 23-Mar. New action items to be added - see AI #39.
24 | Verify if Main Radiators can be moved out with Tracker Radiator Jig and TTCS Boxes in place. | C. Gargiulo | 2007-03-13 | 2007-03-22 |  | X | Both ram & wake Main Radiators can be moved out. However, both of the upper radiator brackets must be dismounted at the crates & USS and removed. Linear bearings will be positioned so that the TRD Gas System box does not need to be moved or removed. Preliminary design scheduled to be ready by 29-Mar per AI #25.
25 | Develop preliminary design for Main Radiator Linear Bearings & brackets | C. Gargiulo | 2007-03-13 | 2007-03-22 |  | X | Preliminary design scheduled to be ready by 29-Mar; was presented during 27-Mar telecon.
26 | Develop design for new LUSS lifting brackets | F. Cadoux | 2007-03-13 | 2007-04-23 |  | X | By April TIM @ CERN. (Originally assigned during January TIM at JSC.) The preliminary design is done, drawings are in work. CGS needs funding to do this analysis. CAD model sent to CGS week of 11 June, 2007. Nastran model was sent by Jacobs to CGS. CGS is working out bugs in transmission.
27 | Develop design for modified LUSS shipping cover & verify clearance with RICH, ECAL & LTOF | F. Cadoux | 2007-03-13 | 2007-04-23 | X |  | By April TIM @ CERN. (Originally assigned during January TIM at JSC.) The preliminary design is done, drawings are in work and will be sent to Giuliano by July TIM. CGS still needs funding to do this analysis.
28 | Fabricate new LUSS lifting brackets | G. Laurenti | 2007-03-13 | 2007-09-01 | X |  | (Originally assigned during January TIM at JSC.) On 21-Aug Giuliano said he'd have these done by 30-Sep.
29 | Fabricate modified LUSS shipping cover | G. Laurenti | 2007-03-13 | 2008-07-01 | X |  | (Originally assigned during January TIM at JSC.) Since this will not be needed until shipping to ESTEC in 2008, a due date is moved to July, 2008.
30 | Verify usefulness of STA VC rotation device at SCL for Tracker & ACC deintegration at CERN off the RAS. Note: this device is also still expected to be required at SCL. | K. Bollweg | 2007-03-13 | 2007-03-23 |  | X | Closed 19-Mar-07: The rotation device at SCL can be used. However, modifications discussed at integration meeting still need to be done. Total weight carrying capability is 1875 kg X 2 = 3750 kg = 8267 lbs. A stand to temporarily set 2 of the 4 USS interface points is still needed while caster wheel brackets or acoustic stands are installed on the VC inteface points to the USS. See AI # 37.
31 | Routing on VC conical flanges of: Tracker Cables, TTCS pipes and wiring, AMSWire cables, TAS fibers, PDS cables, ACC Fiber & Cable Routing, etc. | F. Cadoux | 2007-03-12 | 2007-04-23 | X |  | Also see AI #152. Antonio needs to be located at CERN for a few weeks to complete this work. Design proposals will be tested during preintegration and then implemented in CAD for final production. Corrado will discuss with Roberto to arrange.
32 | UTOF Special rolling table dwg to be sent to Klaus | G. Laurenti | 2007-03-12 | 2007-03-19 |  | X | Giuliano will send revised drawings to Klaus on 4-Apr. Will incorporate TRD hardware while on UTOF special rolling table (new requirement). Klaus received drawings on 10-Apr. Giuliano will work with Klaus to implement mods.
33 | Send UTOF bracket to corner bracket to Aachen via CERN | G. Laurenti | 2007-03-12 | 2007-04-23 |  | X | There will be no fit check at Aachen - it will be done at CERN during preintegration.
34 | Find another integration secretary than Mike Capell | S. Ting | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Ken is the secretary!
35 | Lowest ECAL blanket fixation provided by C.Clark will not work with proposed cable routing. Work with Franck Cadoux to develop alternate. | C. Clark | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN. Joe Kastelic & Franck are exchanging CAD files. See presentation dated 27-Mar by Frank Cadoux. The strap from the lower ECAL bracket can be attached to the lower cable bracket with cable ties. Joe K. to define standard grounding wire existing design. Franck to decide which holes he wants the grounding wires attached to.
36 | Add schedule for TTCS pipework on naked flight VC | J. Heilig | 2007-03-12 | 2007-04-23 |  | X | By April TIM @ CERN (JH added two weeks in the schedule).
37 | Work out VC rotation sequence utilizing rotation device and caster wheels at SCL, acoustic test stands, and temporary stands. | K. Bollweg, P. Mott, & R. Stafford Allen | 2007-03-23 | 2007-04-23 |  | X | By April TIM @ CERN. Held telecon with Phil Mott & Ron Mackay on 29-Mar and worked out an acceptable procedure. Will present at April TIM.
38 | Resolve interferences between external Magnet hardware and the USS, VC Shipping Crate, & PSS in the low shipping configuration as well as access issues at the launch pad. | K. Bollweg, R. Mackay, & R. Becker | 2007-03-23 | 2007-04-23 | X |  | Robert & Corrado met with Ron @ SM on 20-Aug. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
39 | Add other new action items from integration meeting at SCL on 22/23-Mar. This involves the TTCS lines and interferences with cabling, crates, and other plumbing. | K. Bollweg, R. Mackay, A. Alvino, & R. Becker | 2007-03-23 | 2007-04-10 |  | X | Robert & Corrado met with Ron @ SM on 20-Aug. Robert will relocate to SM for several weeks begininng on 07-Sep to complete magnet external hardware integration. | Get with Ron Mackay to send robert & corrado back the new proposed routings of plumbing
40 | Identify all known Cable Balcony interferences for further discussion at April 3rd integration telecon - especially at the U Crates (request by K. Lubelsmeyer). | F. Cadoux | 2007-03-27 | 2007-04-03 |  | X | Robert & Corrado met with Ron @ SM on 20-Aug. Robert will relocate to SM for several weeks begininng on 07-Sep to complete magnet external hardware integration. | Get with Ron Mackay to send robert & corrado back the new proposed routings of plumbing
41 | Establish routing, locations, & orientations for all "normal" helium vents on the Magnet. (As opposed to "emergency" vents from BDs addressed in AI #38.) | K. Bollweg, R. Mackay, R. Becker, & K. Lubelsmeyer | 2007-04-03 | 2007-04-23 | X |  | Robert & Corrado met with Ron @ SM on 20-Aug. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
42 | Perform cable force test on TRD Cables and provide results. | K. Lubelsmeyer | 2007-04-10 | 2007-04-17 |  | X | Test performed and results provided on 13-Apr. Franck & Klaus to discuss test results at April TIM.
43 | Post AMS schedules on NASA AMS website. | J. Heilig | 2007-04-10 | 2007-04-23 |  | X | Posted on 12-Apr.
44 | Develop April TIM Integration Splinter Meeting schedule and preliminary agenda. | K. Bollweg | 2007-04-10 | 2007-04-17 |  | X | Preliminary schedule and agenda provided with this spreadsheet.
45 | Need details for GPS attachment to radiators. | C. Zurbach | 2007-04-27 | 2007-06-06 | X |  | Marco will send Claude the "thru hole" pattern on the radiator for confirmation. Also check bonding. See e-mail from Claude dated 28 June on integration plans & responsibilities. Per R. Becker, CGS is supplying GPS fasteners. GPS cable will be delivered in September to CERN.
46 | Can the PSS be used for the TV tests? Can the PSS support AMS when rotated 90 degrees? Does a new stand need to be developed? | C. Tutt, J. Burger, & K. Bollweg | 2007-04-27 | 2007-05-08 |  | X | Based on the ESTEC drawings provided to J. Burger, C. Tutt & K. Bollweg reviewed the operations required to rotate the USS in the PSS as well as putting the PSS on the 3.16m X 3.16m "Siesmic Structure" at the bottom of the TVT chamber. There would be significant modifications required to the PSS to adapt it to the Siesmic Structure. Thus, a new structure will be required...sorry Robert.
47 | Can the PSS be used for the EMI tests? Does a new stand need to be developed? | M. Capell & T. Urban | 2007-04-27 | 2007-05-15 |  | X | Per M. Capell at the 8-Jun-07 integeration meeting at CERN: The PSS will be used for the EMI tests.
48 | TVT Stand Design, Analysis, Fabrication, and Test. | MIT | 2007-04-27 | Various, see dates in comments | X |  | ESTEC needs design by 01-Sep-07. Stand needs to be delivered to ESTEC in August '08. Robert, Joe, & Corrado are working on a test stand design without the RAS but it will have a rotating mechanism in the TVT chamber. Corrado will send out conceptual design by 10 July and will present the plans at the integration meeting 26-27 July at CERN. As of 21-Aug, Corrado will need until end of Sep. to complete design.
49 | Determine how to rotate USS without keel attached for TVT. | J. Kastelic | 2007-04-27 | 6-Jun-07; see AI #48. |  | X | The USS can be rotated about the Y axis on the primary sill trunnions. A method of using the secondary sill trunnions to react the moment or some acceptable attachment to the lower USS needs to be developed.
50 | Lifting fixtures development for TVT test to rotate USS (in PSS?) with Z-axis horizontal. | MIT | 2007-04-27 | Various, see AI #48 |  | X | ESTEC needs design by 01-Sep-07. Lift hardware needs to be delivered to ESTEC in August '08. Need to decide if this is done inside or outside of TVT Chamber.
51 | Update the CGSE model at the launch pad. Also see AI #41. | A. Grechko | 2007-04-27 | 2007-07-01 | X |  | New vacuum line to evacuate PVVV identified on 04-Jun-07. A. Grechko needs drawings defining this connection from R. Mackay/SM.
52 | Determine requirements for shipping SFHe in cargo plane and trucks between ESTEC & KSC. | K. Lubelsmeyer & S. Harrison | 2007-05-15 | 2007-06-07 | X |  | Current plans are to ship cryostat with helium in superfluid state.
53 | Provide CAD model of AMS test beam area clearly identifying all ferrous metals in the area so that a loads assessment can be done on the magnet. | R. Becker | 28-Oct-05 & 2-May-07 | TBD* | X |  | This was transferred from the OPMT on 2-May-07 (#05-081). The due date is TBD because the location and availability of the Beam test has not been determined. As of 19 June, 2007 the location is known and a floor plan is being developed. As os of 21-Aug, this work is on hold until next week.
54 | Develop a risk mitigation plan for TTCS in-situ welding during flight integration. Relook at connections or welding at TTCB to TTCS tubing. Preintegration requires electronics to be nearby. Also considerpump controller inside TTCB. | M. Capell | 20-Feb-07 & 2-May-07 | 2008-03-01 | X |  | This was transferred from the OPMT on 2-May-07 (#05-081). Per M. Capell on 12-jun-07, this due date should be March, 2008. Mike plans to put a crate next to the welder and test in Feb '08.
55 | Confirm that the blankets for RICH and ECAL will be available for Pre-Integration activities at CERN. | M. Molina | 23-Feb-07 & 2-May-07 | 2007-04-23 | X |  | This was transferred from the OPMT on 2-May-07 (#05-106). Per M. Molina on 28-Jun-07, the RICH MLI will not be available on Sept 15th 2007, as originally scheduled, due to contractual reasons (ASI-CGS) and delayed payment issues. This includes the blanket between the RICH & ECAL and the big one wrapping RICH and LOWER TOF. Ameeting on this is planned at the July TIM.
56 | Make measurement of the amount of helium that is used during a quench and recharge a test objective. | S. Harrison | 9-Aug-06 & 2-May-07 | 2007-04-15 |  | X | This was transferred from the OPMT on 2-May-07 (#Mag-Review-01). Per telecon with B. Strauss/DOE on 12-Jul-07: This is still under review by SCL. There is no way to measure the helium used in the MATR due to its configuration. There are no plans to force a quench with the magnet in the flight VC since there is nothing that can be changed in the design at that point.
57 | Add at least one additional thermal cycle to the magnet testing in the MATF. For example: Step 7B - Warm the magnet system to room temperature and recool to 1.8K. | S. Harrison | 9-Aug-06 & 2-May-07 | 2007-03-23 |  | X | This was transferred from the OPMT on 2-May-07 (#Mag-Review-04). Per telecon with B. Strauss/DOE on 12-Jul-07: The warm-up cool-down cycles already planned are sufficient as long as the magnet does not experience significant training quenches as it run up to full field.
58 | Show how the resistance of the inter-coil joints is planned to be measured in the coming test program. (Related to magnetic field decay) | S. Milward | 9-Aug-06 & 2-May-07 | Was 15-Apr-07 Is 30-Sep-07 | X |  | This was transferred from the OPMT on 2-May-07 (#Mag-Review-05). Per telecon with B. Strauss/DOE on 12-Jul-07: This is being done in the MATR by measuring the persistence (rate of decay with the switch closed). If it is acceptable, this action will be closed.
59 | Present plans to measure the expected endurance on the system before flight. | S. Harrison | 9-Aug-06 & 2-May-07 | 15-Apr-07 |  | X | This was transferred from the OPMT on 2-May-07 (#Mag-Review-07). Per telecon with B. Strauss/DOE on 12-Jul-07: The boil off rate of helium will be measured in the flight cryostat which should be OK as a worst case estimate of the performance in zero-g. This measurement should be done with all systems operational, including the cryocoolers.
60 | Perform a Test Readiness Review with a committee of independent experts. Experts must have access to the full test plan. | S. Harrison | 9-Aug-06 & 2-May-07 | Was 15-Jan-07 Is 31-Dec-07 | X |  | This was transferred from the OPMT on 2-May-07 (#Mag-Review-11). Per telecon with B. Strauss/DOE on 12-Jul-07: The intent of this action was not a review by personnel already associated with the magnet development. Thus, the review performed by Mike Capell, Trent Martin, and Chris Tutt is not adequate. It should be performed as an "arms-length review" by experts in the fields of cryogenics and magnets, but not associated with AMS. It was also the intention of the committee that the review take place prior to operations in the flight cryostat. Bruce is a candidate for this committee and will suggest some others to participate in a review at SCL this fall. Potential candidates are Prof. Steve VanSciver of Florida State and Jim Kerby from Fermilab and CERN. (This action will be closed when the TRR is completed.)
61 | Turn/lay down the TTCS tubing loops/pigtails to resolve interference with UTOF. Check LTOF as well. | R. Becker to contact B. Verlatt | 2007-06-06 | 2007-06-15 | X |  | As of 21-Aug, tests are being done on sample tubes to see how much they can be moved to avoid the interference. They are being bent down and the pigtails are being "squashed" a bit to make room.
62 | CAD model needed for three vertical support beams (VSBs) for TTCS tubing, cryocooler tubing, and cables | CGS/G. Duchini | 2007-06-06 | 2007-06-20 | X |  | Received a new model at last TIM…not a final one. As of 21-Aug, we hope to finalize by beginning of Sep.
63 | Deliver FEM of VC shipping fixture to SCL/SM | P. Mott | 2007-06-08 | 2007-06-15 |  | X | Sent 18-June (a) SHIPFIXTURESTATIC – Full Shipping Fixture Model with LMSO VC (b) SHIPFIXTUREGAP – Full Shipping Fixture Model with CONM2 for VC (c) SHIPPINGFIXTURETOPPANEL- Simple Plate Model of Top Cover (d) SHIPPINGFIXTURESIDEPANEL- Simple Plate Model of Side Cover
64 | Modify Flight VC shipping fixture for SFHe top-off test at SM and to accommodate Magnet external hardware. | R. Mackay, K.Bollweg | 2007-06-06 | 2007-12-01 | X |  | Prof. Ting to make final decision on this test by mid-October. For now we are NOT planning to do the SFHe top-off test with the magnet Z-axis horizontal at SCL/SM. It will have to be done at CERN in the RAS.
65 | Reconfigure Tracker Cable Paddles to small panels to solve interference with Star Tracker bracket, and close clearance with UTOF. | MIT & A. Alvino | 2007-06-06 | 2007-07-01 | X |  | Small bridge design being developed as of 14-Aug - should be done by end of Aug.
66 | Reroute Tracker cables near Star Tracker bracket to avoid interference. | S. Borsini | 2007-06-06 | 2007-07-01 | X |  | Small bridge design being developed as of 14-Aug - should be done by end of Aug.
67 | Deliver FEM of PSS to MITeam | P. Mott | 2007-06-08 | 2007-06-15 |  | X | Wasn't this sent? Is it still needed now that we're not using the PSS in the TVT?
68 | Send current CAD PSS model to MIT & R. Mackay/SM. | J. Kastelic | 2007-06-06 | 2007-06-15 |  | X | Closed on 18-June. Provided PSS in the high, low and mid configurations. Wts of PSS in three configurations (+~200 lbs during shipping - see 19 June e-mail from J. Kastelic): 4907.982 lbs High Config, Empty, no panels, no lid. 4740.88 lbs Mid Config, Empty, no panels, no lid. 4237.34 lbs Low Config, Empty, no panels, no lid.
69 | Develop mod to PSS shipping panel to relieve interference with new location of BD07 on LSR at 349.6o. BD07 will be oriented in +Z direction. Also look at Cryocoolers (without balancer?) to determine if additional mods are required to PSS shipping panels. | MIT & R. Mackay | 2007-06-06 | 2008-06-01 | X |  | Cryocooler model was uploaded to the JSC file exchange website and are located in the Share Folder on 19 June. PSS will need to be modified at CERN. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
70 | Determine if the normal helium main vent needs to be routed to a particular location/orientation inside or outside the AMS envelope to avoid a helium "cloud." (Consider corona conditions.) | T. Siedenburg, V. Choutko, S. Harrison | 2007-06-06 | 2007-07-01 |  | X | Per Prof. Ting & M. Capell, the main helium vent will be routed to a point above the upper VC to USS joint at the +X, -Y corner. Per M. Capell, corona will not be a problem (see 15 June e-mail exchange). However, see response from F. Palmonari dated 19-June at right: Angle toward +Y direction to aim away from EVA worksite for PVGF. Also attach to this vent at the TVT. Closed during presentation at AMS TIM on 26-July. | The TOF PMTs are inside an envelope light-tight with small vents, so one can expect the concentration of He inside TOF to increase with time, with respect to other molecules. I ask therefore to have the He vent as far as possible to the UTOF counters. Honestly I have no quantitative arguments to support my concern ( I have no idea how and where the magnet He will diffuse around AMS) so take this as a remark. Federico
71 | Move pilot valves for DV15A/B/C/D to eliminate interference with crates & VC shipping fixture | R. Mackay | 2007-06-06 | 2007-06-14 |  | X | Valves have been moved. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
72 | Define how we intend to test the O-ring test ports and when. | S. Harrison | 2007-06-06 | 2007-06-14 | X |  | A new model was distributed by R. Mackay on 14 June and R. Becker responded with some concerns. This will be worked when Ron returns on 2 July. | STEVE TO DEFINE
73 | Shorten plumbing and bracket for BD11A/B to provide more clearance to TRD Gas Supply System Xenon Tank bracket. | R. Mackay | 2007-06-06 | 2007-06-14 |  | X | It now clears - its good enough.
74 | Locate and reorient DV20 outlet so it's accessible to CGSE at Pad | R. Mackay | 2007-06-06 | 2007-06-14 |  | X | A new model was disrtibuted by R. Mackay on 14 June and R. Becker responded with some concerns. This will be worked when Ron returns on 2 July.
75 | Send new DV20 outlet info to A. Grechko so he can design the CGSE connection at Pad | R. Mackay | 2007-06-06 | 2007-06-14 |  | X | A new model was disrtibuted by R. Mackay on 14 June and R. Becker responded with some concerns. This will be worked when Ron returns on 2 July.
76 | Reroute vacuum line from MV43 to DV 20ABCD to avoid interference with Tracker cables | R. Mackay | 2007-06-06 | 2007-06-14 | X |  | As of 7-Aug, this has been re-routed. Robert to send R. Mackay model of tracker cables in this area and Ron is to send Robert a new model of the pipe routing. Robert will specify elevation of pipe to clear cables. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
77 | Move PVVV lines on conical flange up to the top of the conical flange to avoid interference with cables and TTCS lines. | R. Mackay | 2007-06-06 | 2007-06-14 |  | X | A new model was disrtibuted by R. Mackay on 14 June and R. Becker responded with some concerns. This will be worked when Ron returns on 2 July.
78 | Reroute & reorient current lead exhaust vent to + or - X side of USS to allow connection to CGSE. | R. Mackay | 2007-06-07 | 2007-06-14 |  | X | MIT prefers the -X side because of less plumbing and free holes near strap port. However, -X side has several Magnet avionics cables not shown in the CAD models yet.
79 | Resolve CAB interfence with CAB triangular brackets and move heat pipe retainer bracket by 1-2 holes on underside of USS Upper Bridge Beam. Notch upper corner of CAB to accommodate Upper Tracker Radiator Screw - consider sharing bolt hole. Check shared bolt analysis and finalize assembly procedure with MIT. | C. Gargiulo, A. Assenza & CRISA | 2007-06-07 | 2007-06-22 | X |  | Corrado sent a proposal to CRISA - they have reviewed and are modifying their model. Marco accepts the mods to the sliding bracket. Expect to complete assessment and have new design finalized by 23-July. Corrado presented at July TIM. Jacobs to perform analysis of bolts fixing multiple components. | 1) "resolve CAB inteference with CAB triangular bracket": Interference already discussed and solved in the past between CRISA, Jacobs and CGS One of the beam profile, taking in place the USS Heat Pipes, is properly cut so to avoid interference with the brackets. 2)"and move heat pipe retainer bracket by 1-2 hole on underside of USS Upper bridge beam": CGS, responsible for all the CAB external thermal hardware, agreed in moving the retainer bracket by 1 hole as proposed by MITeam. CAD model retainer will be updated (new location)by MITeam and posted to AMS exchange directory by 26 June. 3)"Notch upper corner of CAB to accommodate Upper tracker radiator screw": CRISA agreed on the modification proposed by MITeam to add a chamfer in the CAB baseplate upper corner. CAD model will be modified (add a chamfer) and sent to MIT by CRISA (it was promised by Guillermo Munoz to be posted on AMS exchange/incoming CAD directory for the end of last week). CRISA will modify hardware (mechanical pieces) accordingly. 4)"consider sharing bolt hole, check shared bolt analysis": Jacobs (Carl Lauritzen) checked and confirmed CAB analysis is correct and bolt analysis has been performed with appropriate loads. Jacobs will procure bolts to fix the CAB to the USS and arrange to have the bolts shipped to CERN to be available for integration of the CAB to the USS. 5) "finalize assembly procedure of the CAB to the USS": MITeam will provide assembly procedure for CAB integration by 7 August | Shared bolt analyses needed by Jacobs
80 | Resolve interferencebetween TSPD to S & T Crates and UPD to U Crate. 70 mm maximum available from xPD wall to CAB wall. | M.Capell | 2007-06-07 | 2007-07-07 |  | X | M. Capell states they will remove the backshell and provide stress relief as required on a case-by-case basis.
81 | Schedule inputs: Line 57 should indicate June 1st since crates are already at CERN. Radiator flight brackets are installed before the sliding brackets Electronics Crates Jigs must be ready in the Cleanroom by July 16th CryoMagnet arrives at CERN NLT end of February, 2008 ECAL and stand must be ready in the Cleanroom by July 16th Line 206: Install ECAL thermostats offline before Setember 18th; 3 day activity LTOF will arrive at Cleanroom by July 1st. Offline testing through September. Incorporate updates from M. Molina's integration presentation. Swap lines 277 & 278 (Debris shields vs MLI on RICH). Add tracker feet metrology to schedule at CERN | J. Heilig | 2007-06-07 | 2007-06-15 |  | X | Closed June 15th!
82 | Develop CryoMagnet external hardware mockups with full size drawings to simulate hardware. | MIT Group | 2007-06-07 | 2007-08-31 | X
83 | Determine if HV bricks can be installed after cables | F. Cadoux | 2007-06-07 | 2007-06-30 |  | X | Meeting with RICH personnel in July to determine. Must wait for HV bricks to complete LUSS integration. Try to mount cables after bricks if at all possible.
84 | Provide new delivery date for RICH/LTOF lateral MLI to J. Heilig | M. Molina | 2007-06-07 | 2007-07-02 | X |  | See AI # 55. Delivery date is still TBD.
85 | Send PSS floor to VC dimension with PSS in mid & low configs to E. Perrin. | P. Mott | 2007-06-07 | 2007-06-15 |  | X | Provided 13 June.
86 | Update late electronics crates delivery dates & provide to J. Heilig | G. Ambrosi | 2007-06-07 | 2007-06-22 | X |  | Received latest info at July TIM...Will require several iterations…
87 | Send LUSS lifting plate and LUSS shipping fixture modification designs to CGS | F. Cadoux | 2007-06-07 | 2007-06-15 |  | X | See AI # 26.
88 | Send LUSS FEM to CGS | C. Lauritzen | 2007-06-07 | 2007-06-15 |  | X | Sent zip file on 15-June with set of NASTRAN bulk data files for the lower USS, RICH, ECAL, and LTOF to assess the lifting configuration of this assembly.
89 | Perform analysis on LUSS with new lifting plates and LUSS shipping fixture | M.Molina | 2007-06-07 | 2007-07-15 | X
90 | Determine if we need to make a CGSE connection to flight helium vent at ESTEC for TVT to verify baro switch operation | M. Capell & S. Harrison | 2007-06-07 | 2007-06-11 |  | X | Yes, see very long e-mail chain titled "Main He flight vent and BSE during ESTEC TVT"
91 | Verify ECAL flight mounting bolts are ordered/delivered | P. Mott | 2007-06-07 | 2007-06-15 |  | X | The flight bolts are available at Jacobs and will be delivered to CERN in July.
92 | Evaluate use of RAS or PSS in TVT Chamber - or develop a new fixture | R. Becker. C. Gargiulo | 2007-06-08 | 2007-07-23 |  | X | A new fixture is required in the TVT Chamber. Closed with presentation at TIM on 23-Jul.
93 | Resolve TAS fibre fixation interference with TRD MLI | F. Cadoux | 2007-06-07 | 2007-07-07 |  | X | TAS fixation will move to VC.
94 | Define PSS/USS movements into TVT and then to EMI Chambers | J. Burger | 2007-06-08 | 2007-07-23 |  | X | Received new floor plan from ESTEC - movement plan is in work. Joe will present at next TIM.
95 | Determine if PSS mod is required to accommodate height of Zenith Radiators | J. Kastelic | 2007-06-08 | 2007-07-23 | X |  | Currently, the Zenith radiators are .33 inches from the internal beams of the PSS cover per the models. CGS is building a ¼ zenith radiator mockup ready by Sept 2007. The height will be high fidelity. Joe Kastelic to present possible solutions at July TIM. J. Heilig sent e-mail to M. Molina on 3-Jul to confirm the final design of the zenith radiators, the glass rods, and all mounting brackets. Dynamic models of the PSS need to be run to verify relative movement of the PSS to the Zenith radiators. As of July TIM: The flight hardware will be measured at CERN and the PSS will modified in one area if required. | Currently, the Zenith radiators are .33 inches from the internal beams of the PSS cover. This is a nominal dimension so we could easily see an actual tolerance stream closing that gap but in any case too close for comfort. The top cover cannot be shimmed by any measurable amount due to maximum dimensions in the cargo bay of the 747. Suggested resolutions: 1. Acquire a high fidelity model of the Zenith Radiator. 2. Identify specific locations on the radiator at risk for interference with cover. 3. Assess and possibly modify the beams locally. 4. Or develop another workaround. | We are already building a ¼ zenith radiator for trial assemblying. It will be ready in September 2007. We will make sure it is high fidelity as far as the height is concerned - Marco
96 | Send E, R HV bricks integration schedule to J. Heilig | C. Ginzo | 2007-06-07 | 2007-06-22 |  | X | Discuss at meeting with MIT & CRISSA at July meeting this was updated at the July TIM.
97 | Finalize TV test plan, test objectives, test configuration, & test specification and provide to ESTEC. | M. Molina | 2007-06-08 | 2007-07-23 | X |  | Inputs required from C. Clark. ESTEC needs info by end of Sept.
98 | Finalize EMI test plan, test objectives, test configuration, & test specification and provide to ESTEC. | T. Urban | 2007-06-08 | 2007-07-23 | X |  | Joe Burger will find out when ESTEC really needs what info. Preliminary answers are shown at right: | -Finalize EMI test plan, test objectives: We know this will happen later. -test configuration: The discussion that we’ve had in the last month re: the inability to perform magnet charging is the only matter that was un-resolved. I believe it to now be resolved. -test specification: We will test to the standard matrix of EMI spec.s that we’ve used all along.
99 | Define CGSE requirements for TVT & EMI test. | A. Grechko | 2007-06-08 | 2007-07-23 | X |  | See e-mail from Alexandre to Steve Harrison dated 3-Aug.
100 | Define test harness and connector requirements for TVT & EMI test. | X. Cai | 2007-06-08 | 2007-07-23 |  | X | Closed per e-mail from X. Cai on 7-Aug.
101 | Define TRD configuration with respect to how much Ar/Xe/CO2 gas will be needed and if any GSE piping will be required to fill and where. How will this be accomplished at KSC? Also define requirements to vent Ar/Xe/CO2 in TV Chamber and EMI Chamber. | T. Siedenburg | 2007-06-08 | 2007-07-23 | X |  | Ops at CERN & ESTEC are defined and were presented at July TIM. KSC ops are still in work.
102 | Define access requirements inside the Large Space Simulator (LSS/TV Chamber) | R. Becker | 2007-06-08 | 2007-07-23 |  | X
103 | Send cad models of PLF & MPLF to the MITeam | J. Kastelic | 2007-06-19 | 2007-06-26 |  | X | Sent on 20 June.
104 | Design additional small box close to the CAB needed to house the BaroSwitch Electronics (BSE). | MITeam | 2007-06-19 | 2007-07-23 | X |  | M. Capell inputs provided. As of 14-Aug this work is being deferred until end of October.
105 | Provide details on Helium Vent Pump mounted to USS. It is needed for Pre-integration to define routing of plumbing and cables. | M. Gallilee | 2007-06-26 | 2007-07-10 | X |  | Vent Pump model received from vendor week of 30-Jul, new proposed location distributed to integration team on 7-Aug. R. Mackay to send vent pump model to R. Becker. Robert will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
106 | Define mounting requirements for He Vent Pump | R. Mackay | 2007-06-26 | 2007-07-17 | X |  | J. Kastelic to veruify new proposed location is OK on Lower Trunnion Bridge. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
107 | Define requirements and availability of vent holes for CGSE at SSPF | T. Martin | 2007-07-03 | 2007-07-17 |  | X
108 | Send latest VC Shipping fixture with proposed mods for Magnet external hardware to P. Mott, J. Kastelic, & R. Becker | R. Mackay | 2007-07-03 | 2007-07-17 | X |  | This was presented at July TIM. Prof. Ting has designated Prof. Lubesmeyer as responsible for shipping Flight Magnet from SCL to CERN. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
109 | Send latest PSS with proposed mods for Magnet external hardware to P. Mott, J. Kastelic, K. Lubelsmeyer & R. Becker | R. Mackay | 2007-07-03 | 2007-07-17 |  | X | These drawings are needed to initiate discussions with Luftansa.
The following actions (#110 thru 125) are from meeting with G. Piret/ESTEC at CERN on 24-July-2007:
110 | Update CGSE diagram to show the result of the discussion in the meeting: several labeled diagrams to show the different stages of piping and operations. Minimize the amount of CGSE whenever possible. Send to integration team. | A. Grechko | 2007-07-24 | 2007-08-14 | X
111 | Clearly state what parts of the piping and feedthroughs ESTEC is to provide. (Pumping down requires further discussion.) | A. Grechko | 2007-07-24 | 2007-08-14 | X
112 | Determine if the bipod fill port fitting will be required to pump on the SFHe Tank at ESTEC. (There are no plans to fill at ESTEC.) If needed, will this be in the TVT chamber or in the PSS? | S. Harrison | 2007-07-24 | 2007-08-07 | X |  | K. Bollweg to work with S. Harrison to define. Robert to show what portions of PSS need to be removed to use fill port with bipod. Robert Becker will temporarily relocate to SCL/SM on 7-Sep to complete external magnet hardware integration.
113 | Supply a list of sizes and weights of all CGSE equipment on the floors at ESTEC. Determine if the smaller heat exchanger at SCL can be used. | A. Grechko | 2007-07-24 | 2007-08-21 | X
114 | Provide information on kind of power connections needed for the vacuum pumps (German Schuko type) | A. Grechko | 2007-07-24 | 2007-08-21 | X
115 | Provide information on all other GSE power connections needed for the TVT & EMI tests. | T. Urban & M. Capell | 2007-07-24 | 2007-08-21 | X |  | In work.
116 | Investigate availability of 8 gauge Deutsch feedthroughs. | T. Urban | 2007-07-24 | 2007-08-14 |  | X | Deutsch DM5623 series feed-throughs are NOT available with inserts that carry 8 AWG contacts. The Interface Panel A and Test Connector Panel interfacing test cables that use 8 AWG wires will have to be “split-out” to be wired through 12 AWG contacts on the ESTEC available Deutsch connectors.
117 | Update X. Cai's table to show the number and sizes of the pins on the connectors, and also power supply capacities. | T. Urban | 2007-07-24 | 2007-08-21 | X |  | In work.
118 | Verify that the grounds are carried through on connector pins and not on the backshells. Verify that detector ground is not carried through on the trunnion pins and stand, and that we need separate ground straps. | T. Urban | 2007-07-24 | 2007-08-14 |  | X | Both items verified.
119 | Determine maximum and minimum design temperatures required for the new TVT stand. Define thermal isolation requirement between TVT Stand and USS. | C. Clark & M. Molina & C. Gargiulo | 2007-07-24 | 2007-08-28 | X
120 | Safety vents for the burst discs will be needed. Check requirements with ESTEC safety | G. Piret | 2007-07-24 | 2007-08-21 | X
121 | Define access points for AMS electrical power & data connections | X. Cai | 2007-07-24 | 2007-08-07 |  | X | Provided 7 August.
122 | Define access points for TRD gas connections | T. Siedenburg | 2007-07-24 | 2007-08-07 |  | X | Provided 7 August.
123 | Define access points for TVT instumentation | C. Clark & M. Molina | 2007-07-24 | 2007-08-07 | X
124 | Define access points for CGSE | K. Bollweg & A. Grechko | 2007-07-24 | 2007-08-14 | X
125 | Check the possibility of 3 shifts of ESTEC support for TVT setup & EMI tests. | G. Piret | 2007-07-24 | 2007-08-21 | X
The following actions (#126 thru 150) are from the integration meetings at CERN on 26&27-July-2007:
126 | Complete the silver Teflon TPS and submit to NASA/JS for review. | Marco Molina | 2007-07-26 | 2007-08-10 | X |  | C. Vettore is to deliver on August 20
127 | Provide Installation procedures for TRD and UTOF. | Arndt Schultz Von Dratzig | 2007-07-26 | 2007-10-09 | X
128 | Provide Installation procedures for the Tracker. | Eric Perrin & Maurice Bourquin | 2007-07-26 | 2007-09-01 | X
129 | Add dates to the schedule to identify integration paper delivery dates. Once complete, add the same list of documentation to build book. | John Heilig | 2007-07-26 | 2007-08-15 | X |  | John is working on it.
130 | Coordinate vertical support beams (VSBs!!!!) on outside of magnet with TTCS, CGS and SM. | Ken Bollweg | 2007-07-26 | 2007-08-15 | X
131 | Assess whether TTCS hardware will fit inside VC Shipping Fixture | Ken Bollweg & Johannes Van Es | 2007-07-26 | 2007-08-15 | X
132 | Adjust the schedule to allow the cooldown of the magnet once the Tracker is installed. | John Heilig | 2007-07-26 | 2007-08-05 |  | X
133 | Move GPS antennae off of the critical path. | John Heilig | 2007-07-26 | 2007-08-05 |  | X
134 | Go through the MLI requirements to identify which blankets need to be installed prior to the beam test, and how much after the beam test. | Marco Molina | 2007-07-26 | 2007-08-15 | X
135 | Must identify the amount of time required for each time segment. Include a review of the schedule for installing the radiators (should it be before or after the beam test). | Marco Molina | 2007-07-26 | Various through 15-Jan-08 | X
136 | Determine if the TTCS can be run during the beam test. Consider using expendable CO2 system (per Bart Verlatt). | J. Van Es | 2007-07-26 | 2007-08-31
137 | Add the Zenith Radiators on before the test beam. | John Heilig | 2007-07-26 | 2007-08-15 |  | X
138 | Determine if PDS can be built and delivered by 5/1/08. If not, what are the alternative approaches? | Marco Molina & Mike Capell | 2007-07-26 | 2007-08-05 | X
139 | Post the revised schedule based on the integration meetings at the July TIM and send an e-mail to the collaboration . | John Heilig | 2007-07-26 | ASAP |  | X
140 | Add action to OPMT about the 0.5 and 0.2 mm tolerance for 12 mm and 7 mm holes in the radiator face sheets. | Chris Tutt | 2007-07-26 | 2007-08-01 |  | X | This has been settled - AIDC will be able to use the new tolerances.
141 | Current lead exhaust position may need to be moved because Tracker cables may not be able to withstand the cold helium gas coming out. | Ken Bollweg | 2007-07-26 | 2007-08-15 |  | X | This has been moved and a permanent flight extension leading outside the USS has been added.
142 | Verify if the grapple fixtures can be installed without removing the brackets. | Joe Kastelic | 2007-07-26 | 2007-08-22 | X
143 | Get with UG reps to see if we can improve the speed on imports and integration tasks. Get better CAD systems for some of our guys so that we can open the models. | Joe Kastelic & Trent Martin | 2007-07-26 | 2007-08-22 | X
144 | Add columns into Holes database to show who is responsible for the analysis and ordering the bolts. Add grounding/bonding points. | Robert Becker | 2007-07-26 | 2007-08-31 | X
145 | List and locate all flaps, removable covers & permanent holes in thermal blankets required around the VC Support Rings for Magnet external hardware. (BDs, Fill ports, GSE pipe & electrical attachments, plumbing lines, etc.) Provide to M. Molina. | R. Mackay | 2007-07-27 | 2007-08-21 | X
146 | Deliver the latest Zenith Radiator model to J. Kastelic & Arndt Schultz Von Dratzig | M. Molina | 2007-07-27 | 2007-08-05 |  | X | Includes the Z brackets, spokes and GPS brackets. This model has been delivered - no changes to the spokes are required.
147 | Tolerance analysis from USS Trunnions to Zenith Radiator. | J. Kastelic | 2007-07-27 | 2007-08-28 |  | X | See AI #95 - this analysis is no longer required.
148 | Measure TRD M structure shear pins in corner brackets to "spoke" inserts for Zenith Radiator | T. Siedenburg | 2007-07-27 | 2007-08-21 |  | X
149 | Measure PSS cover to help determine clearance to Zenith Radiator "spokes.". | J. Heilig | 2007-07-27 | 2007-08-21 | X
150 | Determine if current MLI fixation design meets safety requirements -or- how to incorporate grommets into the thermal blankets | M. Molina | 2007-07-27 | 2007-08-07 | X
151 | Provide estimate of differential movement between VC and USS to VC joints to determine amount of compliance required for various helium vent pipe mounts. | C. Lauritzen | 2007-08-07 | 2007-08-21 | X
152 | Finalize TAS & ACC fibre fixation and routing on VC and send to AMS Integration team. Also the ACC signal cables from the PMTs to the Support Ring of the VC and then to the Electronics Crates. | F. Cadoux | 2007-08-14 | 2007-08-21 | X |  | Also see AI #31.