# DELETE THE FOLLOWING AFTER ADDED TO PROJECT SCRS

FEDERAL HIGHWAY ADMINISTRATION

EASTERN FEDERAL LANDS HIGHWAY DIVISION

LIBRARY OF SPECIFICATIONS (LOS)

TO

FP-03

LOS Version

30 January 2009

_____________________________________________________________________

_____________________________________________________________________

# INCLUDE THE FOLLOWING

$$000.00A

FEDERAL HIGHWAY ADMINISTRATION

EASTERN FEDERAL LANDS HIGHWAY DIVISION

SPECIAL CONTRACT REQUIREMENTS

Project INSERT PROJECT NAME AND NUMBER

INSERT PARK, FOREST, OR PARTNER AGENCY NAME

The following Special Contract Requirements amend and supplement the Standard Specifications for Construction of Roads and Bridges on Federal Highway Projects (FP-03) U.(S. Customary (Metric) Units, U. S. Department of Transportation, Federal Highway Administration.

$$101.00A

Section 101.—TERMS, FORMAT, AND DEFINITIONS

Revised 2 October 2005

INCLUDE THE FOLLOWING

$$101.01A

101.01.  Delete the last paragraph.

# INCLUDE THE FOLLOWING FOR LOOP DETECTORS

$$101.03A

101.03(a).	Add the following:

IPCEA - Insulated Power Cable Engineers Association

INCLUDE THE FOLLOWING WHEN THE FP DEFINITION IS INADEQUATE

$$101.04A

101.04.  Delete the definition for "Substantial Completion" and substitute the following:

Substantial Completion -- For conventional bridge and highway work, the point at which all bridge deck and parapet work is completed, all pavement structure and shoulder work is completed, and all permanent signing and striping is in place.  In addition, all guardrail, guardwalls, and safety appurtenances within (insert distance) feet (meters) of the traveled way is completed.  For all other work, the point at which the CO determines the project can be safely and effectively used by the public without further delays, disruption, or other impediments.

$$102.00A

Section 102.—BID, AWARD, AND EXECUTION OF CONTRACT

Revised 25 January 2005

INCLUDE THE FOLLOWING

$$102.04A

102.04.  Add the following:

Furnish documentary evidence as to the ownership and value of the assets pledged in support of the bond and details of the security interest in the assets by the individual sureties for the apparent low bidder within 14 calendar days after the opening of bids.  Failure to submit evidence within the time required will be grounds for declaring the surety unacceptable.

In addition, the CO may, after reviewing the Affidavit of Individual Surety and documentary information on the security interest and the assets pledged, by certified mail to the surety's business or residence address (as shown on the bond), request the surety to provide further information and/or documents with respect to any of the documents provided.  The CO may require such information to be furnished under oath.  Failure of the surety to accept such mail, or failure of the surety to respond with the requested information or documents within 7 business days of receipt of the request, will be cause for rejection of the surety.

These requirements are in addition to the requirements in FAR Subpart 28.203, except where in conflict with the requirements in the FAR, in which case the FAR controls.

$$102.06A

102.06.  Add the following after the last paragraph:

Submit the documentary evidence for individual sureties at the same time as the Affidavit of Individual Surety and security interest in assets pledged.  A Contractor submitting an unacceptable individual surety in satisfaction of a performance or payment bond before the issuance of the Notice to Proceed will be permitted one opportunity to substitute an acceptable surety or sureties within 7 business days of receipt of notification that the surety is unacceptable.

The Government's right to direct the substitution of sureties to ensure the continuing acceptability of the bonds during the performance of the Contract according to FAR Clause 52.228-2, Additional Bond Security, is not restricted.

These requirements are in addition to the requirements in FAR Subpart 28.203, except where in conflict with the requirements in the FAR, in which case the FAR controls.

$$104.00A

Section 104. — CONTROL OF WORK

Revised 1 November 2007

INCLUDE THE FOLLOWING

$$104.03A

104.03(a).  Add the following to the third paragraph:

Drawings will be reviewed in the order they are received.

INCLUDE THE FOLLOWING

$$104.03B

104.03(b).  Add the following after 104.03(b):

(c) As-built working drawings.  Furnish 2 sets of as-built working drawings.  The Government will provide 2 sets of contract drawings to be used exclusively for recording the as-built details of the project.

Keep the as-built working drawings current on a weekly basis and have at least 1 set available on the jobsite at all times.  Accurately and neatly record changes from the contract plans, which are made in the work, or additional information, which might be uncovered in the course of construction, as they occur by means of details and notes.  Maintain a log of all changes made to the as-built working drawings, and monthly, at the estimate cutoff date, make the as-built working drawings and log available for review by the CO.

Note all additions or revisions to the location, character, and dimensions of the prescribed work shown on the contract drawings.  Line out all details shown that are not applicable to the completed work.  Use the red-line process (red pencil or red ink) to record on the as-built working drawings and final as-built drawings, as a minimum, but not limited to, the information described below:

- Typical section(s)

- Revisions in dimensions; and

- Revisions in materials.

- Plan and profile

- Plan

- Revisions to the alignment;

- Changes in the construction limits;

- Revisions in location, type, and grade of road approaches;

- Location and type of utilities;

- Location, size, and type of underdrains;

- Skew of culverts;

- Channel changes;

- Location of monuments and permanent references;

- Elevations for all aerial and underground crossings of utilities; and

- Location, length, and type of fencing.

- Profile

- Revisions to grades, elevations, and stationing of intersection PIs;

- Equations;

- Culvert diameter, length, type, and stationing;

- Length of culvert extension, and length of existing culvert;

- Location, length, stationing, and type of retaining walls; and

- Location, length, stationing, and end treatment of guardrail.

- Bridge

- Stationing of bridge ends;

- Elevations including footing, bearing pads, deck, and top of walls;

- Pile driving record with pile length, size, type, and tip elevation;

- Post-tensioning records including stressing sequence, jacking force, and duct size and layout;

- Construction and concrete placement sequences;

- Bearing details with orientation;

- Expansion joints including actual clearance with atmospheric temperature; and

- Any changes in plan or dimensions including any major changes in reinforcing.

- Miscellaneous

- Revisions to parking areas or turnouts;

- Final location, type and length of curbs, sidewalks, etc.;

- Fencing type and limits; and

- Landscaping and planting.

- Special Contract Procedures

- Method of excavation, concrete placement, girder erection, structure repairs, etc.

Prepare final as-built drawings after the completion of each definable feature of work as listed in the Contractor Quality Control Plan (Foundations, Utilities, Structural Steel, etc., as appropriate for the project).  The as-built working drawings and final as-built drawings will be jointly reviewed for accuracy and completeness by the CO and the Contractor prior to submission of each monthly pay estimate.

If the monthly review finds that the Contractor is not maintaining the as-built working drawings, payment of the Contractor’s invoice will be withheld until the as-built working drawings are brought up to date.

Furnish the as-built working drawings to the CO before the final inspection.  Correct all details found during the final inspection that are not shown on the as-built working drawings and return to the CO within 5 working days for approval.

Once final as-built working drawings have been approved by the CO, provide final as-built drawings in the latest version of Adobe Acrobat (PDF) format (at the time of submission) on two sets of CD-R or DVD-R.  Include the latest version Adobe Acrobat reader on the CD-R or DVD-R.  Provide the final as-built drawings with a resolution quality such that the redlined drawings and notations are clearly discernable.  Final payment per Subsection 109.09 will not be made until the CD-R or DVD-R of the final as-built drawings have been reviewed and approved by the CO.

No direct payment will be made for maintaining and furnishing as-built working drawings.

INCLUDE THE FOLLOWING ON NPS PROJECTS

$$104.05A

104.05.  Add the following:

When hauling on National Park Service roads, do not exceed the following load restrictions:

| Single Units |  | Gross Vehicle Weight – pounds (kilograms) |
| --- | --- | --- |
| 2 axles |  | 40,000 (18,100) |
| 3 axles |  | 48,000 (21,800) |
| 4 or more axles |  | 52,000 (23,600) |
| Combination Units |  |  |
| 3 axles |  | 57,000 (25,900) |
| 4 axles |  | 62,000 (28,100) |
| 5 or more axles |  | 66,000 (29,900) |

Where the ground is saturated with water or during periods of freezing and thawing, the CO may impose further load restrictions or suspend hauling.

INCLUDE THE FOLLOWING

$$104.05B

104.05.  Add the following:

Operate loaded vehicles hauling material at speeds not exceeding 40 miles per hour (65 kilometers per hour), or the posted speed limit whichever is lower, and spaced at 500-foot (150-meter) minimum intervals.  Do not exceed 25 miles per hour (40 kilometers per hour), or the posted speed limit whichever is lower, or operate more than 1 loaded hauling vehicle at a time on a bridge.

$$105.00A

Section 105. — CONTROL OF MATERIAL

Revised 7 January 2009

INCLUDE THE FOLLOWING

$$105.02A

105.02(b).  Add the following:

If any material is to be excavated from any material source outside the construction limits, other than commercially operated sites, provide a certification from the State Historic Preservation Officer or Indian Tribal Council, if applicable, before work begins that states:

  - A cultural resource survey (a survey for historical sites and archeological remains) has been performed at the proposed site; and

  - No significant cultural resources exist in the area that will be disturbed by the Contractor.

$$106.00A

Section 106.—ACCEPTANCE OF WORK

Revised 2 October 2005

###### INCLUDE THE FOLLOWING

$$106.03A

106.03.  Delete the first sentence of the second paragraph and substitute the following:

Other than references in or to the FAR or Federal Law, when these Standard Specifications or Supplemental Contract Requirements reference certifications; certificates; or certified documents, equipment, or individuals, these references are not certifications under Section 4301 of Public Law 104-106, National Defense Authorization Act for Fiscal Year 1996.

INCLUDE THE FOLLOWING WHEN STATISTICAL SPECIFICATIONS (A.K.A. MATERIAL INCENTIVES) ARE USED

$$106.05A

106.05(a)  Add the following:

At the Preconstruction Conference, the Government will provide a copy of the computer program "QL-PAY," along with instructions.  QL-Pay is a Windows based program that computes the quality levels and pay factors as described in this Subsection.

$$107.00A

Section 107.—LEGAL RELATIONS AND RESPONSIBILITY TO THE PUBLIC

Revised 2 October 2005

INCLUDE THE FOLLOWING.  ADD ANY SPECIAL PERMITS REQUIRED BY THE PARTNERING AGENCY TO THE LIST.

$$107.01A

107.01.  Add the following:

The following permits may be required for this project:

(a)  (list only those permits required by the partnering agencies)

This list of permits may not be all inclusive of those required for construction.  No time or damages, including impact damages, will be allowed for failure to obtain necessary permits or agreements.  Provide copies of these permits and agreements upon request.

107.01.  Delete the second sentence of the third paragraph and substitute the following:

Obtain all additional permits or agreements and modifications to Government-obtained permits or agreements that are required.

INCLUDE THE FOLLOWING ON ALL NPS PROJECTS

$$107.02A

107.02.  Add the following after the third paragraph:

For the full duration of construction, protect the existing trees that are tagged by the CO in the following manner:

(a)  Install and maintain a 4-foot (1.2-meter) high wood slat fence with steel posts around the perimeter of the root protection area, per Subsection 619.06.  The root protection area is defined as an area equal to 10 feet (3 meters) outside the dripline.

(b)  All construction which takes place within the root protection area must be approved by the CO.  Do not store or locate construction materials, vehicles, staging areas, topsoil, disposal areas, or trailers within the root protection area.  Protect the area from flooding, erosion, sedimentation, and potentially harmful materials through run-off or spillage.

(c)  Remove all tree protection prior to final acceptance.

$$107.02B

107.02.  Add the following after the sixth paragraph:

Notify the CO in writing at least 48 hours in advance of any scheduled utility shutdown, investigation, and /or related work.

INCLUDE THE FOLLOWING WHEN THERE IS RAILROAD WORK

$$107.04A

107.04.  Add the following after the third paragraph:

The Railroad will, at all times, have jurisdiction over the safety of railroad operations, and the decision as to procedures which may affect the safety of railroad operations shall be final.

$$107.04B

107.04(a)(4).  Add the following:

The Railroad Protective Policy shall name the Railroad as the insured and contain an endorsement in the form prescribed for State or Federal highway projects for Railroad Protective Liability.

Title 23 CFR, paragraph 646, subpart A, as amended, is hereby incorporated by reference.  Form of policy shall be in accordance with that specified in Appendix A to Title 23 CFR, paragraph 646.

Furnish to the Railroad the Railroad Protective Policy and certificates evidencing the other insurance coverage required.  The Railroad Protective Policy and all insurance certificates will be subject to the Railroad's approval before any work can begin on the Railroad's property.  In addition, furnish evidence of commitment by the Insurance Company to notify the Railroad and the CO in writing of any material change, expiration, or cancellation of the policy not less than 30 calendar days before such change, expiration, or cancellation is effective.  Railroad Protective Liability and Property Damage Liability Insurance shall conform to the Federal-Aid Policy Guide, Chapter 1, Subchapter G, Part 646, issued by the U.S. Department of Transportation, FHWA, dated December 9, 1991, as supplemented and amended.

$$107.04C

107.04(e).  Add the following:

The current approximate wage rate is $(insert rate) per hour.  In addition, a surcharge of (insert percentage) percent computed on the actual payroll, will be included to cover the cost of overhead and fringe benefits.

INCLUDE THE FOLLOWING

$$107.05A

107.05.  Add the following after the second paragraph:

Submit all claims to the insurance company for investigation, regardless of deductible, unless the Contractor has chosen to pay the claim directly.  Provide the results of any investigations and subsequent actions to the CO within 1 week of receipt from the insurance company or of action.  Determination by the insurance company that the claim is not covered by the policy is not an adequate basis for the Contractor to fail to meet its obligations under the requirements of this Section.

$$108.00A

Section 108.—PROSECUTION AND PROGRESS

Revised 6 October 2006

INCLUDE THE FOLLOWING AS APPLICABLE

$$108.01A

108.01.  Add the following:

$$108.01B

Construction operations are limited as follows:

$$108.01C

No work will be permitted on Sundays or National legal holidays.

INCLUDE THE FOLLOWING FOR VIRGIN ISLANDS ONLY, THAT ARE NON-NPS & EFLHD ADMINISTERED

$$108.02A

108.02.  Add the following:

#### 108.02A  Disadvantaged Business Enterprise (DBE) Subcontracting Requirements.

# SELECTED DBE PROGRAM PROVISIONS FOR THE VIRGIN ISLANDS –

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PARTICIPATION IN USDOT ASSISTED CONTRACTS

(EFLHD – ADMINISTERED CONTRACTS)

Policy.  It is the policy of the United States that small business concerns, including small disadvantaged business concerns, shall have the maximum practicable opportunity to participate in performing contracts.  It is further the policy of the United States that its prime contractors establish procedures to ensure the timely payment of amounts due pursuant to the terms of their subcontracts with small business concerns, including small disadvantaged business concerns.

The Contractor hereby agrees, by signature on this Contract, to carry out this policy in the awarding of subcontracts to the fullest extent consistent with efficient contract performance.  The Contractor further agrees to cooperate in any studies or surveys as may be conducted by the United States Small Business Administration, the Federal Highway Administration (FHWA), or the Virgin Islands, as may be necessary to determine the extent of the Contractor’s compliance with this policy.

DBE Participation/Contract Goal And Good Faith Efforts.  For purposes of this Contract, the DBE subcontracting goal is (obtain percentage from PSERT) percent of the total contract amount, as determined by the Virgin Islands Department of Public Works with the concurrence of the Contracting Officer.  When the contract goal DBE participation is 0 percent, the contractor, if not an approved DBE, must still submit a small business subcontracting plan prior to award identifying all DBE’s which the contractor intends to use on the project.

This Contract will be awarded only to the low responsive and responsible bidder who meets this goal or who demonstrates good faith efforts to do so.  Failure to make a good faith effort is defined as willful or intentional failure to perform in accordance with the requirements of this Contract, or willful or intentional action to frustrate the achievement of the Subcontracting Plan, if applicable.  Guidance on what constitutes good faith efforts is described in the Virgin Islands Department of Public Works’ (VIDPW) approved DBE Program.  Bidders are required to obtain a current copy of the Disadvantaged Business Enterprise Program, Directory of Contractors from the VIDPW’s Civil Rights Program Manager.

All Business Concerns.  Prior to award, the successful bidder must submit a Subcontracting Plan, which shows a commitment to meet the goal. All DBEs must be certified by the VIDPW prior to submission of the Subcontracting Plan.  If the successful bidder is unable to meet the goal/DBE participation, it must demonstrate the good faith effort exerted to do so.  It is the Contracting Officer’s discretion to determine whether the good faith efforts exerted are acceptable. The following information must be included in the Subcontracting Plan:

(a)	The names and addresses of DBE subcontractors and suppliers that will participate in the contract;

(b)	A description of the work that each DBE will perform;

(c)	The dollar amount of the participation of each DBE firm listed;

(d)	Written documentation of the bidder’s commitment to use a DBE subcontractor/supplier whose participation it submits to meet the DBE contract goal; and

(e)	Written confirmation from the DBE that it is participating in the contract. The written confirmation shall describe the work to be performed and the dollar amount contracted consistent with (b) and (c) above.

The DBE contract goal/DBE participation committed to by the large business concern will become the established DBE subcontracting goal for the project as a contract requirement.  Compliance with the established goal will be determined by reviewing the required submissions, including Standard Form 1413 and FHWA Form 1775.  If, at the completion of the project, the prime contractor fails to meet its commitment, it will be required to document and justify why it failed to meet this commitment.  The Liquidated Damage Provision as stated below will apply if the contractor fails to meet the goal or demonstrate good faith efforts.

## Termination / Substitution / Replacement Of Listed DBE Firms.  The Prime contractor may not terminate for convenience a DBE subcontractor without the Contracting Officer’s prior written consent.  The prime contractor will be expected to identify an acceptable certified DBE subcontractor replacement in that event, or demonstrate good faith efforts to do so.  This restriction does not prohibit termination for default or for failure to perform adequately.  If a DBE subcontractor is unwilling or unable to perform the work of the commitment made to the prime contractor, the prime contractor shall immediately notify in writing the Contracting Officer, and request to be relieved of the commitment to use the named DBE.

### Counting DBE Participation.  When a DBE participates in a contract, only the value of the work actually performed by the DBE will be counted toward performance of the goal.  The entire amount of that portion of a construction contract or other contract that is performed by the DBE’s own forces will be credited.  Included are the costs of supplies and materials obtained by the DBE for the work of the contract (DBE manufacturer 100 percent of the cost of the materials or supplies may be counted & DBE regular dealer 60 percent of the cost of the materials or supplies), including supplies purchased or equipment leased by the DBE (except supplies and equipment the DBE subcontractor purchases or leases from the prime contractor or its affiliate).  Credit will be allowed for the entire amount of fees or commissions charged by a DBE firm for providing a bona fide service, such as professional, technical, consultant, or managerial services, or for providing bonds or insurance specifically required for the performance of a USDOT-assisted contract.  Credit will be allowed for fees considered reasonable and not excessive as compared with fees customarily allowed for similar services.

Credit to a DBE contractor will be allowed only if the DBE is performing a commercially useful function on the contract.  A DBE performs a commercially useful function when it is responsible for execution of the work of the contract and is carrying out its responsibilities by actually performing, managing, and supervising the work involved.

When a DBE subcontracts part of the work of its contract to another firm, the value of the subcontracted work may be counted only if the DBE’s subcontractor is itself a certified DBE.  Work that a DBE subcontracts to a non-DBE firm does not count.

When a DBE performs as a participant in a joint venture, credit for a portion of the total dollar value of the contract equal to the distinct, clearly defined portion of the work of the contract that the DBE performs with its own forces will be allowed.

The Prime Contractor may not count the participation of a DBE subcontractor toward its DBE achievements or the overall goal until the amount being counted toward the goal has been paid to the DBE.

Prompt Payment.  This Contract includes Prompt Payment for Construction Contracts, which requires payment to the subcontractor for satisfactory performance under its subcontract not later than 7 days from receipt of payment from the United States for work performed by the subcontractor. If retainage is withheld the prime contractor shall be required to release such retainage to subcontractors within 30 calendar days of satisfactory completion, i.e. according to the specifications, of the entire subcontractor’s work.

### Liquidated Damages.  If at the completion of the project, the prime contractor has failed to meet the established goal/commitment, or has not demonstrated good faith efforts to do so, the prime contractor shall be assessed liquidated damages for the difference between the established goal/commitment and the actual DBE participation achieved.

### Record Keeping Requirements.  The Prime Contractor shall keep such records as necessary to ensure compliance with its DBE utilization obligations.  The Prime contractor must retain all such records for at least 3 years after project acceptance by the Contracting Officer following the completion of the contract.  These records shall be available for inspection by the Virgin Islands Department of Public Works, the FHWA, the USDOT, or other appropriately sanctioned Virgin Islands State Agencies or Federal Agencies or Departments, to determine the Prime Contractor’s good faith effort to meet the established DBE subcontracting goal.  The prime contractor’s DBE liaison officer or designee shall complete the top half of Form A-644, Monthly Contractor DBE Participation, and submit the form or its facsimile to the Contracting Officer monthly.

### Compliance Procedures.  Whenever it appears that the Prime Contractor or any subcontractor or supplier may not be operating in compliance with the terms, conditions or requirements of this Contract, including but not limited to, encouraging fronting, brokering or the circumstance of a DBE not performing a commercially useful function as defined, an investigation will be conducted.  If it is found that the contractor or any subcontractor or supplier is not in compliance with these Special Provisions, the party in non-compliance will be notified in writing.

If the deficiencies are not corrected, the Contracting Officer reserves the right to initiate administrative action against the party or parties in non-compliance, which may include but not be limited to:

(a)	Termination of the contract for Default, which is a part of this Contract.

(b)	Withholding an appropriate percentage of partial payments pursuant to Section 109 of the Standard Specifications for Highway and Bridge Construction.  This appropriate percentage may be the amount of any proposed monetary sanction.

(c)	Initiation of appropriate debarment proceedings.

(d)	Referral of any unlawful actions to the appropriate enforcement agencies.

(e)	Other actions as appropriate, at the discretion of the Contracting Officer.

INCLUDE THE FOLLOWING FOR INCENTIVE / DISINCENTIVE CLAUSES

$$108.04A

108.04.  Delete the second and third paragraphs and substitute the following:

It is anticipated that multiple work shifts, weekend, and holiday work, will be required to complete the work within the contract time.  Therefore, because time is of the essence in completing the contract work, a monetary incentive is offered for early completion of the work as well as a disincentive assessment and/or liquidated damages for work being completed late.

(a)  For each calendar day prior to  (insert date)  by which Contract work is substantially complete, payment to the Contractor will be increased by an incentive of $  (insert I/D amount)  per day up to a maximum of $  (insert amount)

(b)  For each calendar day beyond  (insert same date)  which is required to achieve substantial completion, payment to the Contractor will be decreased by a disincentive of $  (insert I/D amount)  per day beginning the day after that date and ending with the day of substantial completion.

(c)  For each calendar day beyond  (insert same date)  which is required to achieve final completion and acceptance by the Government, payment to the Contractor will be decreased by liquidated damages of 20 percent of the amount specified in Table 108-1, beginning on the day after that date or the day after substantial completion, whichever occurs later, and ending with the day of final completion and acceptance by the Government.

$$109.00A

Section 109.—MEASUREMENT AND PAYMENT

Revised 2 October 2005

INCLUDE THE FOLLOWING

$$109.08A

109.08(b).  Add the following:

Submit invoices by the 7th day after the closing date.  Invoices received after the 16th day following the closing date will not be accepted for payment processing that month.  Include late, unprocessed invoice submittals in the following month’s invoice.

109.08(c).  Add the following:

The government’s designated billing office is:

Federal Highway Administration

Eastern Federal Lands Highway Division

Loudoun Tech Center

21400 Ridgetop Circle

Room 200

Sterling, Virginia 20166-6511

ATTN: CONSTRUCTION DIVISION

Section 109. — MEASUREMENT AND PAYMENT

Revised 23 September 2008

ASPHALT CEMENT Price Adjustment Provision Coordination on the use of this provision must be sought with Acquisitions, Construction, and Materials. The use of this price adjustment provision must be evaluated on a project-by-project basis and is only applicable when included by the Government for a specific project. Use this price adjustment provision on single or multiple season contracts/projects, when (1) the contract involves an extended period of performance with significant costs to be incurred beyond one year after performance begins, (2) the contract amount subject to adjustment is substantial, (3) the economic variables for materials and supplies are too unstable to permit a reasonable division of risk between the Government and the Contractor, without this type of provision; (4) the price of materials and/or supplies is extremely volatile, (5) suppliers are unable to provide price quotations for the usual term of the contract, (6) price quotes are based on the date of delivery or spot market conditions and (7) shortages are expected. The price adjustment provision should only be applied to the specific price volatile materials and/or supplies called out below.

109.06  Pricing of Adjustments.  Add the following:

ASPHALT CEMENT PRICE ADJUSTMENT PROVISION

GENERAL  The Asphalt Cement Price Adjustment Provision provides for a price adjustment in the form of a payment to the Contractor or a rebate to the Government for fluctuations in the cost of asphalt cement used in the performance of applicable construction work.  The price adjustment provisions are applicable only to the asphalt cement, as defined in Subsection 702.01, and incorporated in the following eligible contract pay items:

- 40101 Superpave pavement

- 40102 Superpave pavement, wedge and leveling course

- 40201 Hot asphalt concrete pavement, Marshall or Hveem test

- 40202 Hot asphalt concrete pavement, Marshall or Hveem test, wedge and leveling course

- 40301 Hot asphalt concrete pavement

- 40302 Hot asphalt concrete pavement, wedge and leveling course

- 40501 Open-graded asphalt friction course

Select appropriate eligible pay items and delete those that do not apply. For each of the eligible contract pay items chosen above, a corresponding statement should be added to the applicable SCR payment subsection, which indicates that “A price adjustment will be made for fluctuations in the cost of asphalt cement used in the performance of any eligible pay items according to Subsection 109.06 Pricing of Adjustments Asphalt Cement Price Adjustment Provision.” See end of provision for additional direction.

The price adjustment provisions are also applicable when the Government adds extra work to the eligible pay items already existing under the Contract.

The provision will remain in effect throughout the duration of the contract.  Enactment of the Asphalt Cement Price Adjustment Provision will only be considered when the increase or decrease in the price of asphalt cement as defined herein exceeds 10 percent.

The Asphalt Cement Price Adjustment Provision is intended to reduce but not eliminate the cost effects of price uncertainty to the Contractor and the Government for asphalt cement used in the construction of this contract.  It provides for sharing by the Government in a portion of the Contractor’s risk, which could result from unusual price fluctuations.  The provision is not intended to compensate the Contractor for normal day-to-day fluctuations and seasonal changes or to serve as a guarantee of full compensation for asphalt cement price fluctuations.

EFLHD will revise the following policy/procedures. The Construction Branch is responsible for (1) purchasing the Asphalt Weekly Monitor (AWM) newsletter; (2) selecting the applicable region and states; (3) calculating and posting price indexes on an accessible web page and; (4) calculating and paying price adjustment compensations. In order to establish a reference for the base and monthly performance price indexes, the Poten and Partners, Inc newsletter (i.e. Asphalt Weekly Monitor) should be surveyed and an applicable region and state inserted below. A website address must also be inserted below where the Contractor and other interested parties can check Government postings of monthly price indexes. There could potentially be one web page for each project unless projects are in the same state. The Base and Monthly Performance Price Indexes for Asphalt Cement must also be calculated using weekly high and low selling price data obtained from the Asphalt Weekly Monitor for the applicable state. Weekly high and low selling price data from four consecutive reports will be averaged to obtain a Base Price Index as well as a Monthly Performance Price Index. The Base Price Index (BPI) must be inserted below by Acquisitions in the conformed set. The Monthly Performance Price Index must be posted monthly by Construction on the website.

PRICE INDEXES  The Government will generate a monthly performance price index for asphalt cement using price data obtained from Poten and Partners, Inc. (PPI), which publishes a weekly report (Asphalt Weekly Monitor) on high and low selling prices for states in five regions throughout the United States including the East Coast/Northeast, the Mid-Continent/Midwest, the Gulf Coast/Mid South, the Rocky Mountains and the West Coast/Northwest.  Weekly high and low selling price data reported for (insert the applicable region and states) will be averaged and used to establish a base price index, BPI, for this project and a monthly performance price index, MPPI, for the duration of the contract.  These indexes are defined as follows:

- BASE PRICE INDEX  The base price index, BPI, is the price index determined by the arithmetic average, as specified above, shown in the four weekly publications immediately preceding the bid opening.  The BPI will be provided by the Government after contract award.  It is as follows:

BASE PRICE INDEX (BPI) FOR ASPHALT CEMENT

PER SHORT TON (TON) (or PER METRIC TON) = $

- MONTHLY PERFORMANCE PRICE INDEX  The monthly performance price index, MPPI, is the monthly price index at the time of performance of applicable work as determined by the arithmetic average, as specified above, shown in the four weekly publications issued prior to the last Wednesday of the month (i.e. the monthly performance price index during which asphalt cement is used in the performance of applicable construction work).

PRICE ADJUSTMENTS  Price adjustments are calculated by the Government for average conditions and are not intended to reflect the Contractor’s actual purchase price.  The ratio of the monthly performance price index and the base price index (MPPI/BPI) is calculated and used to determine price adjustments for eligible pay items as follows:

- No Price Adjustment – When the ratio MPPI/BPI falls within the range of 0.90 to 1.10, no price adjustment will be made for any asphalt cement used in construction work performed during the relevant month.

- Government Rebate – When the ratio MPPI/BPI is calculated to be less than 0.90, the Government is due a rebate determined in accordance with the following formula:

Government Rebate = [0.90 – (MPPI/BPI)] (BPI) (Q)

- Contractor Payment – When the ratio MPPI/BPI is calculated to be greater than 1.10, the Contractor is due additional payment determined in accordance with the following formula:

Contractor Payment = [(MPPI/BPI) – 1.10] (BPI) (Q)

The following definitions are applicable to both the Government Rebate and the Contractor Payment formulas:

MPPI	=	Monthly Performance Price Index for the month during which asphalt cement is used in the performance of applicable construction work.

BPI	=	Base Price Index that is established immediately preceding the bid opening.

Q	=	Quantity in tons of asphalt cement for eligible pay items that were used on the project during the progress payment period.  The quantity will be calculated using the asphalt content of the approved mix design and the following formula:

Q	=	Asphalt Concrete Pavement tons placed x (% Asphalt/100)

PRICE ADJUSTMENT COMPENSATION  Monthly adjustments will be accrued.  The final price adjustment will be paid, or rebated, after completion of all work for eligible pay items.  The Contractor may request in writing a partial price adjustment payment once every 12 months, or when the unpaid accrued increase exceeds $10,000.  The Government will take a rebate when the deductive accrual exceeds $10,000.

No price adjustments will be made for work performed beyond the Government-approved Contract completion date.

The maximum allowable monthly and final price adjustment to the Contractor or rebate to the Government is limited to a (MPPI/BPI) ratio of 1.6 and 0.4, respectively.

Cut and insert the following into the appropriate Section (delete the non-applicable Subsections):

401.19.  402.19.  403.19.  405.13.  Add the following:

A price adjustment will be made for fluctuations in the cost of asphalt cement used in the performance of any eligible pay items according to Subsection 109.06 Pricing of Adjustments Asphalt Cement Price Adjustment Provision.

Section 109. — MEASUREMENT AND PAYMENT

Revised 23 September 2008

FUeL Price Adjustment Provision Coordination on the use of this provision must be sought with Acquisitions, Construction, and Materials. The use of this price adjustment provision must be evaluated on a project-by-project basis and is only applicable when included by the Government for a specific project. Use this price adjustment provision on single or multiple season contracts/projects, when (1) the contract involves an extended period of performance with significant costs to be incurred beyond one year after performance begins, (2) the contract amount subject to adjustment is substantial, (3) the economic variables for materials and supplies are too unstable to permit a reasonable division of risk between the Government and the Contractor, without this type of provision; (4) the price of materials and/or supplies is extremely volatile, (5) suppliers are unable to provide price quotations for the usual term of the contract, (6) price quotes are based on the date of delivery or spot market conditions and (7) shortages are expected. The price adjustment provision should only be applied to the specific price volatile materials and/or supplies called out below.

109.06  Pricing of Adjustments.  Add the following:

FUEL PRICE ADJUSTMENT PROVISION

GENERAL  The Fuel Price Adjustment Provision provides for a price adjustment in the form of a payment to the Contractor or a rebate to the Government for fluctuations in the cost of diesel fuel consumed in the performance of applicable construction work.  The price adjustment provisions are applicable only to those contract items listed as eligible pay items in Table 1 below, if diesel is used as the primary fuel in the production of the affected items.

The price adjustment provisions are also applicable when the Government adds extra work to the eligible pay items already existing under the Contract.

The provision will remain in effect throughout the duration of the contract.  Enactment of the Fuel Price Adjustment Provision will only be considered when the increase or decrease in the price of diesel fuel as defined herein exceeds 10 percent.

The Fuel Price Adjustment Provision is intended to reduce but not eliminate the cost effects of price uncertainty to the Contractor and the Government for diesel fuel consumed in the construction of this contract.  It provides for sharing by the Government in a portion of the Contractor’s risk, which could result from unusual price fluctuations.  The provision is not intended to compensate the Contractor for normal day-to-day fluctuations and seasonal changes or to serve as a guarantee of full compensation for diesel fuel price fluctuations.

EFLHD will revise the following policy/procedures. The Construction Branch is responsible for (1) purchasing the Oil Price Information Service (OPIS) newsletter; (2) selecting the applicable region and city; (3) calculating and posting price indexes on an accessible web page and; (4) calculating and paying price adjustment compensations. In order to establish a reference for the base and monthly performance price indexes, the Oil Price Information Service (OPIS) newsletter should be surveyed and an applicable region and city inserted below. If possible, the city should be a large metropolitan area (i.e. a state capital) near the project site. A website address must also be inserted below where the Contractor and other interested parties can check Government postings of monthly price indexes. There could potentially be one web page for each project unless reference cities can be strategically selected to serve more than one project site. The Base and Monthly Performance Price Indexes for Low Sulfur No. 2 Diesel Fuel must also be calculated using weekly average rack price data obtained from OPIS for the applicable city. Weekly average rack price data from four consecutive reports will be averaged to obtain a Base Price Index as well as a Monthly Performance Price Index. The Base Price Index (BPI) must be inserted below by Acquisitions in the conformed set. The Monthly Performance Price Index must be posted monthly by Construction on the website.

PRICE INDEXES  The Government will generate a monthly performance price index for Ultra Low Sulfur, No. 2 Diesel Fuel using price data obtained from the Oil Price Information Service (OPIS), which publishes a weekly report on gasoline and distillate reseller prices for major cities in five regions throughout the United States including the East Coast (PADD 1), the Midwest (PADD 2), the Gulf Coast (PADD 3), the Rockies (PADD 4) and the West Coast (PADD 5).  Weekly average rack price data reported for (insert the applicable region and city) will be averaged and used to establish a base price index, BPI, for this project and a monthly performance price index, MPPI, for the duration of the contract.  These indexes are defined as follows:

- BASE PRICE INDEX  The base price index, BPI, is the price index determined by the arithmetic average, as specified above, shown in the four weekly publications immediately preceding the bid opening.  The BPI will be provided by the Government after contract award.  It is as follows:

BASE PRICE INDEX (BPI) FOR ULTRA LOW SULFUR, NO. 2 DIESEL FUEL

PER GALLON = $

- MONTHLY PERFORMANCE PRICE INDEX  The monthly performance price index, MPPI, is the monthly price index at the time of performance of applicable work as determined by the arithmetic average, as specified above, shown in the four weekly publications issued prior to the last Wednesday of the month (i.e. the monthly performance price index during which diesel fuel is consumed in the performance of applicable construction work).

PRICE ADJUSTMENTS  Price adjustments are calculated by the Government for average conditions and are not intended to reflect the Contractor’s actual purchase price.  The ratio of the monthly performance price index and the base price index (MPPI/BPI) is calculated and used to determine price adjustments for eligible pay items as follows:

- No Price Adjustment – When the ratio MPPI/BPI falls within the range of 0.90 to 1.10, no price adjustment will be made for any diesel fuel consumed in construction work performed during the relevant month.

- Government Rebate – When the ratio MPPI/BPI is calculated to be less than 0.90, the Government is due a rebate determined in accordance with the following formula:

Government Rebate = [0.90 – (MPPI/BPI)] (BPI) (Q) (FUF)

- Contractor Payment – When the ratio MPPI/BPI is calculated to be greater than 1.10, the Contractor is due additional payment determined in accordance with the following formula:

Contractor Payment = [(MPPI/BPI) – 1.10] (BPI) (Q) (FUF)

The following definitions are applicable to both the Government Rebate and the Contractor Payment formulas:

MPPI	=	Monthly Performance Price Index for the month during which diesel fuel is consumed in the performance of applicable construction work.

BPI	=	Base Price Index that is established immediately preceding the bid opening.

Q	=	Quantity of work on the project during the progress payment period for eligible pay items shown in Table 1 below.  The Government will convert work quantities, as necessary, to agree with the units associated with the applicable Fuel Usage Factor.

FUF	=	Fuel Usage Factor shown in Table 1 below applicable to both diesel and gasoline.

| Table 1 – Eligible Pay Items For Price Adjustments and Associated Fuel Usage Factors |
| --- |
| Eligible Pay Items | Fuel Usage Factor U.S. Customary Units | Fuel Usage Factor Metric Units |
| Earthwork: |
| Section 204 – Excavation and Embankment 20401 Roadway excavation 20402 Subexcavation 20403 Unclassified borrow 20410 Select borrow 20411 Select borrow 20415 Select topping 20416 Select topping 20420 Embankment construction 20421 Rock excavation | 0.30 gallons per cubic yard | 0.39 gallons per cubic meter |
| Aggregate Courses: |
| Section 301 – Untreated Aggregate Courses 30101 Aggregate base 30102 Aggregate base* 30103 Aggregate base* 30105 Subbase 30106 Subbase* 30107 Subbase* 30110 Aggregate Surface Course 30111 Aggregate Surface Course* | 0.70 gallons per ton | 0.77 gallons per metric ton |
| Section 302 – Treated Aggregate Courses 30201 Treated aggregate course 30202 Treated aggregate course* | 0.70 gallons per ton | 0.77 gallons per metric ton |
| Section 304 – Aggregate Stabilization 30401 Aggregate stabilization imported aggregate 30402 Aggregate stabilization imported aggregate* 30405 Aggregate stabilization in-place aggregate* 30410 Aggregate stabilization imported surface course aggregate* 30411 Aggregate stabilization imported surface course aggregate* | 0.70 gallons per ton | 0.77 gallons per metric ton |
| Section 309 – Emulsified Asphalt Treated Base Course 30901 Emulsified asphalt treated aggregate base 30902 Emulsified asphalt treated aggregate base* 30903 Emulsified asphalt treated aggregate base* | 0.70 gallons per ton | 0.77 gallons per metric ton |
| Asphalt Pavements: |
| Section 401 – Superpave Hot Asphalt Concrete Pavement 40101 Superpave pavement 40102 Superpave pavement wedge and leveling course | 2.40 gallons per ton | 2.65 gallons per metric ton |
| Section 402 – Hot Asphalt Concrete Pavement by Hveem or Marshall Mix Design Method 40201 Hot asphalt concrete pavement, Marshall or Hveem test 40202 Hot asphalt concrete pavement, Marshall or Hveem test, wedge and leveling course | 2.40 gallons per ton | 2.65 gallons per metric ton |
| Section 403 – Hot Asphalt Concrete Pavement 40301 Hot asphalt concrete pavement 40302 Hot asphalt concrete pavement, wedge and leveling course | 2.40 gallons per ton | 2.65 gallons per metric ton |
| Section 405 – Open-Graded Asphalt Friction Course 40501 Open-graded asphalt friction course | 2.40 gallons per ton | 2.65 gallons per metric ton |
| Section 408 – Cold Recycled Asphalt Base Course 40801 Cold recycled asphalt base course 40802 Cold recycled asphalt base course* | 0.70 gallons per ton | 0.77 gallons per metric ton |
| Section 416 – Continuous Cold Recycled Asphalt Base Course 41602 Continuous cold recycled asphalt base course | 0.15 gallons per square yard | 0.18 gallons per square meter |
| Section 418 – Foamed Asphalt Stabilized Base Course [not in FP - called out by Special Contract Requirements] 41801 Foamed asphalt stabilized base course | 0.30 gallons per square yard | 0.36 gallons per square meter |
| Concrete Pavements: |
| Section 501 – Rigid Pavement 50101 Reinforced rigid pavement 50102 Plain rigid pavement | 0.60 gallons per square yard | 0.72 gallons per square meter |
| * The Government will convert work quantities, as necessary, to agree with the units associated with the applicable Fuel Usage Factor. |

Select appropriate eligible pay items and delete those that do not apply. For each of the eligible contract pay items chosen above, a corresponding statement should be added to the applicable SCR payment subsection, which indicates that “A price adjustment will be made for fluctuations in the cost of diesel fuel consumed in the performance of any eligible pay items according to Subsection 109.06 Pricing of Adjustments Fuel Price Adjustment Provision.” See end of provision for additional direction.

PRICE ADJUSTMENT COMPENSATION  Monthly adjustments will be accrued.  The final price adjustment will be paid, or rebated, after completion of all work for eligible pay items.  The Contractor may request in writing a partial price adjustment payment once every 12 months, or when the unpaid accrued increase exceeds $10,000.  The Government will take a rebate when the deductive accrual exceeds $10,000.

No price adjustments will be made for work performed beyond the Government-approved Contract completion date.

The maximum allowable monthly and final price adjustment to the Contractor or rebate to the Government is limited to a (MPPI/BPI) ratio of 1.6 and 0.4, respectively.

Cut and insert the following into the appropriate Section (delete the non-applicable Subsections):

204.17.  301.10.  302.11.  304.12.  309.10.  401.19.  402.19.  403.19.  405.13.  408.10.  416.12.  418.xx.  501.17.  Add the following:

A price adjustment will be made for fluctuations in the cost of diesel fuel consumed in the performance of any eligible pay items according to Subsection 109.06 Pricing of Adjustments Fuel Price Adjustment Provision.

$$152.00A

Section 152. — CONSTRUCTION SURVEY AND STAKING

Revised 21 January 2009

INCLUDE THE FOLLOWING IF THE CONTRACTOR IS RESPONSIBLE FOR ESTABLISHING INITIAL REFERENCE POINTS AND HORZ/VERT CONTROL (CHECK WITH SURVEY)

$$152.02A

152.02.  Delete the first four paragraphs and substitute the following:

Include staking activities in the construction schedule submitted according to Section 155.  Include the dates and sequence of each staking activity.  Establish initial reference lines and control points, and horizontal and vertical control points as necessary to perform the construction survey and staking.

INCLUDE THE FOLLOWING IF THE CONTRACTOR IS RESPONSIBLE FOR REESTABLISHING THE INITIAL REFERENCE POINTS AND HORZ/VERT CONTROL SET BY THE GOV’T (CHECK WITH SURVEY)

$$152.02B

152.02.  Delete the second sentence of the second paragraph and substitute the following:

Reestablish any missing initial reference lines, control points, and stakes set by the Government.

INCLUDE THE FOLLOWING AS APPLICABLE BY INSERTING THE PARAGRAPHS THAT ARE NOT REQUIRED

$$152.03A

152.03.  Delete the text of paragraphs (_), (_), and (_).

INCLUDE THE FOLLOWING FOR ROADWAY PROJECTS GREATER THAN ½-MILE LONG

$$152.03B

152.03(a).  Add the following:

Set benchmarks a maximum spacing of 1,000 feet (300 meters) along the length of the roadway.

INCLUDE THE FOLLOWING FOR MONUMENTATION ALONG PRIVATE PROPERTY — DELETE THE HIGHLIGHTED TITLES THAT ARE NOT APPLICABLE

$$152.03C

152.03(k).  Add the following:

Perform the portion of the survey work required to establish permanent monuments and markers by a land surveyor registered in the State, Commonwealth, or Territory of (insert name).

INCLUDE THE FOLLOWING, IF APPLICABLE

$$152.03D

152.03(l)(9) and (10).  Delete the Subsections and substitute the following:

(9)  Permanent and temporary traffic control signs, signals, markings, delineators, object markers, etc.

INCLUDE THE FOLLOWING, IF APPLICABLE (IF $$152.03D IS INCLUDED, DO NOT INCLUDE $$152.03E; IF $$152.03D IS NOT INCLUDED, REVISE 10 AND 11 TO 11 AND 12)

$$152.03E

152.03(l).  Add the following:

$$152.03F

(10)  Excavation limits for various drainage, walls, structures, and other pertinent items.

(11)  Landscaping work.

$$154.00A

Section 154.—CONTRACTOR SAMPLING AND TESTING

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR CONTRACTOR TESTING

$$154.03A

154.03.  Add the following:

Furnish test results to the CO immediately after completing the test.  The requirements for furnishing test results do not include sample aging or curing time; therefore, reporting times will be extended accordingly.

Submit proposals for using alternate AASHTO or State approved test methods in writing for approval.  Alternate methods may be allowed based on documented equivalence to the method specified.

$$154.04A

154.04.  Add the following:

On a weekly basis, submit a copy of all current Contractor test results and pay factor calculations based on those tests for items accepted under Subsection 106.05.  When large quantities are produced, calculate pay factors as soon as possible.  Use this information to make any necessary adjustments to operations to achieve acceptable pay factors.  The Government may use the Contractor's test results to determine final pay factors for acceptance according to Subsection 154.05.

$$155.00A

Section 155.—SCHEDULES FOR CONSTRUCTION CONTRACTS

Revised 6 May 2005

INCLUDE THE FOLLOWING WHEN EE LESS THAN $3 MILLION, UNLESS LONG CPM CLAUSE APPLIES, SEE BELOW

$$155.02A

155.02. Add the following after the third paragraph:

155.02A  Weather Delays.

(a)  Weather Delay Definitions.

(1)  Reasonably Predictable Weather.  The number of workdays that can expected to be lost in any month due to rainfall based on 10-year historical weather data.

(2)  Rain Day.  A potentially lost workday on which rainfall is equal to or greater than 0.10 inches (2.5 millimeters).

(3)  Drying Day.  A work day(s) immediately following a rainfall equal to or greater than 1.00 inch (2.5 centimeters) which is potentially lost because of wet ground conditions.

(4)  Workday.  A day not excluded from work by Section 108 of the Special Contract Requirements.

(5)  Unusually Severe Weather.  When the number of Actual Workdays Lost is greater than the calculated Total Lost Days for the month in question.

(b)  Reasonably Predictable Weather.  Determine Reasonably Predictable Weather for this contract by completing Table 155-1.  Calculate data for Table 155-1 as follows:

(1)  Using the last 10 years of historical weather data from the nearest NOAA weather data collection station, compute the average number of workdays lost (rain days plus drying days) for each month and the standard deviation from the average.  Add the average number of workdays lost to the standard deviation.

(2)  The Total number of Lost Days (Average Workdays Lost plus 1 Standard Deviation, rounded to whole days) will be considered normal for each month.

(3)  Submit a completed Table 155-1 with the initial construction schedule.

(c)  Unusually Severe Weather  Under FAR Clause 52.249-10, Default (Fixed-Price Construction), the Contractor can request time for a delay due to Unusually Severe Weather.

The number of Actual Workdays Lost is calculated by first totaling the actual Rain Days plus the actual Drying Days occurring in the month in question.  From this total, deduct any workdays meeting the following conditions:

(1)  The Rain Day or Drying Day occurred on a non-work weekday such as a holiday.

(2)  Rainfall occurred at a time when no weather dependent work was in progress or occurred during planned or unplanned shutdowns due to other circumstances such as equipment failure, strikes, material supplies, delays, etc.

(3)  The Contractor was still working or able to work on weather dependent activities to the extent that less than 50 percent of the workday was lost due to weather.

If the net number of Actual Workdays Lost is greater than the Total Lost Days, then Unusually Severe Weather occurred during the month in question.

(d)  Time Adjustments for Rain Delays.  If the net number of Actual Workdays Lost to rain is less than the Total Lost Days for the month in question, no time adjustments will be made.  If the net number of Actual Workdays Lost is more, then an excusable time extension may be granted.  The Contractor must submit a Weather Time Impact Analysis supporting any alleged delays due to Unusually Severe Weather.

(e)  Delays Due To Other Weather Conditions.  Delays due to other unusually severe weather conditions (snow, extreme cold or heat, high winds, etc.) must be supported with a Weather Time Impact Analysis using historical weather data.

$$155.02B

155.02.  Delete the last paragraph and substitute the following:

The Construction Contract Time shown on the construction schedule for contract completion or for any interim completion dates shall be the calendar dates established in the contract.

$$155.04A

155.04. Add the following to the first paragraph:

For a computer-generated CPM, use Primavera software or software that is file-compatible with Primavera.

INCLUDE THE FOLLOWING (LONG CPM CLAUSE) WHEN EE EXCEEDS $3 MILLION OR THE PROJECT IS SENSITIVE (COMPLEX CONSTRUCTION OR POLITICALLY) TO THE TIMING OF CONSTRUCTION ACTIVITIES.  ALSO INCLUDE THE 15501-0000 CONSTRUCTION SCHEDULE IN THE EE.

$$155.02C

155.02 through 155.09.  Delete the Subsections and substitute the following:

## Construction Requirements

155.02  General

(a)  General format and purpose of the project schedule.

(1)  Develop a network plan and schedule, demonstrating fulfillment of the contract requirements.  Keep the network up to date and utilize the plan for scheduling, coordinating, and monitoring work under this contract. The network schedule shall be computer-generated using Primavera software or software that is file compatible with Primavera. The schedule shall be called the Critical Path Method - Project Schedule  (CPM-PS).

Use the principles and definitions of the terms in The Association of General Contractors in America (AGC) publication "Construction Planning & Scheduling", copyright January 1994, except that this specification shall govern in the case of conflicts.

(2)  Use the CPM-PS for coordination and monitoring of all work under this contract, including all subcontractors and suppliers. If a subcontract has not yet been awarded for a certain portion of the work, develop the schedule for that work.  After any subsequent subcontract award, propose a revision to the CPM-PS to reflect any changes resulting from this new contractual arrangement.

(3)  No construction work on the project (other than mobilization and traffic control) is allowed without an approved 60-day Preliminary Activity Schedule (PAS).

(4)  No progress payments will be made until the Initial CPM Progress Schedule (Initial CPM-PS) has been approved.

(b)  Contractor's Representative.  At or before the Preconstruction Conference, designate an individual in the Contractor's organization who shall be the Contractor's authorized representative responsible for the preparation, updating, and revision of the Project Schedule and who shall review and report progress of the project with and to the CO. This person shall be skilled in the application of computer network scheduling techniques on construction projects of the magnitude and complexity of this project.

(c)  Weather Delays.

(1)  Weather Delay Definitions.

(a)  Reasonably Predictable Weather.  The number of workdays that can expected to be lost in any month due to rainfall based on 10-year historical weather data.

(b)  Rain Day.  A potentially lost workday on which rainfall is equal to or greater than 0.10 inches (2.5 millimeters).

(c)  Drying Day.  A work day(s) immediately following a rainfall equal to or greater than 1.00 inch (2.5 centimeters) which is potentially lost because of wet ground conditions.

(d)  Workday.  A day not excluded from work by Section 108 of the Special Contract Requirements.

(e)  Unusually Severe Weather.  When the number of Actual Workdays Lost is greater than the calculated Total Lost Days for the month in question.

(2)  Reasonably Predictable Weather.  Determine Reasonably Predictable Weather for this contract by completing Table 155-1.  Calculate data for Table 155-1 as follows:

(a)  Using the last 10 years of historical weather data from the nearest NOAA weather data collection station, compute the average number of workdays lost (rain days plus drying days) for each month and the standard deviation from the average.  Add the average number of workdays lost to the standard deviation.

(b)  The Total number of Lost Days (Average Workdays Lost plus one Standard Deviation, rounded to whole days) will be considered normal for each month.

(c)  Submit a completed Table 155-1 with the initial construction schedule.

(3)  Unusually Severe Weather  Under FAR Clause 52.249-10, Default (Fixed-Price Construction), the Contractor can request time for a delay due to Unusually Severe Weather.

The number of Actual Workdays Lost is calculated by first totaling the actual Rain Days plus the actual Drying Days occurring in the month in question.  From this total, deduct any workdays meeting the following conditions:

(a)  The Rain Day or Drying Day occurred on a non-work weekday such as a holiday.

(b)  Rainfall occurred at a time when no weather dependent work was in progress or occurred during planned or unplanned shutdowns due to other circumstances such as equipment failure, strikes, material supplies, delays, etc.

(c)  The Contractor was still working or able to work on weather dependent activities to the extent that less than 50 percent of the workday was lost due to weather.

If the net number of Actual Workdays Lost is greater than the Total Lost Days, then Unusually Severe Weather occurred during the month in question.

(4)  Time Adjustments for Rain Delays.  If the net number of Actual Workdays Lost to rain is less than the Total Lost Days for the month in question, no time adjustments will be made.  If the net number of Actual Workdays Lost is more, then an excusable time extension may be granted.  The Contractor must submit a Weather Time Impact Analysis supporting any alleged delays due to Unusually Severe Weather.

(5)  Delays Due To Other Weather Conditions.  Delays due to other unusually severe weather conditions (snow, extreme cold or heat, high winds, etc.) must be supported with a Weather Time Impact Analysis using historical weather data.

155.03  60-DAY PRELIMINARY ACTIVITY SCHEDULE (PAS)

(a)  Requirement to Submit.  At least 5 working days before the Preconstruction Conference, submit 5 copies of a 60-Day Preliminary Activity Schedule (PAS) to the CO for review and approval.

(b)  Form.  Submit the PAS in written narrative form and include a detailed breakdown of all contract activities scheduled for the first 60 calendar days after Notice to Proceed.

Include an overall description of site mobilization, all shop drawing and sample submittals, and the fabrication and delivery of key and long-lead procurement activities.  Indicate intended submittal dates and realistic delivery dates for fabrication and delivery items.  Provide sufficient time, in accordance with Subsection 155.03(c) for the CO to review, approve and dispatch each shop drawing or submittal after its receipt with the required information.

(c)  Review and Approval of the PAS.  The CO will respond in 14 calendar days to the PAS submission and either approve the PAS or request revisions.  Provide the requested revisions in 7 calendar days.

(d)  Effect of the PAS.  Submission and use of an approved PAS does not relieve the Contractor from the requirement to provide and implement an approved Initial CPM-PS.

155.04  Initial (Baseline) CPM Project Schedule (Initial CPM-PS)

(a)  Submission.  Within 30 calendar days after the Notice to Proceed, develop a proposed initial CPM-PS and submit 5 hard copies of all CPM-PS documents and 2 copies of 3.5-inch high density computer diskettes containing the Primavera compatible files to the CO for review. The initial baseline CPM-PS shall reflect the Contractor's planned performance of the contract work including all contractual requirements (e.g. construction or traffic staging) and any physical constraints on the project. The initial baseline CPM-PS will be the basis on which any impacts from future contract modifications are determined.  Proposed changes to the contractual requirements must be submitted, approved, and then may be included in revisions to the CPM-PS.

(b)  Form and Requirements of the CPM-PS.  The CPM-PS shall consist of a schedule diagram and supporting documents.  The initial CPM-PS shall conform to the following:

(1)  Prepare the schedule diagram using the activity-on-arrow diagram method (ADM) or the precedence diagram method (PDM).  Depict the order and interdependence of all activities and the sequence of the work that will be accomplished by the Contractor in coordination with its subcontractors.  Show how the completion of predecessor activities restricts the start of successor activities.

(2)  Cover all activities required by the contract, including both construction and non-construction.  To the extent feasible, define and relate an activity (or groups of activities) to contract pay items.

(3)  The CO may require that unreflected items, or components of work within an item, be added to the diagram as separate activities, based on what the CO considers to be reasonable for a project of this scope and complexity.

(4)  Failure to include in the CPM-PS any elements of work required for performance of the contract will not excuse the Contractor from completing all work required by the contract by the contract completion date.

(5)  The CPM-PS shall begin with the date of issuance of the Notice to Proceed and conclude with the contract completion date established in the contract.  Float or slack time within the CPM-PS is not for use or benefit of either party, but is a jointly owned, expiring project resource available to both parties as needed to meet the completion date established in the contract.  No time extensions will be granted nor delay damages paid until a delay occurs which impacts the project's critical path, consumes all available float, and extends the work beyond the contract completion date.

(6)  Supporting documents shall include a submittal list, written narrative, tabulated schedule, and weather Table 155-1.

- A Time-Scaled Network Logic Diagram shall be submitted for the initial CPM-PS.  Include the following on the schedule diagram:

  - All activities including those covered by the PAS.  Include activities for correcting punchlist items and general cleanup.

  - Show all activity nodes or boxes, activity IDs, activity descriptions, and durations.

(3)  Group the activities independently by area (i.e. separate distinct bridges or roadways) and by type of work (e.g. submittals, utilities, roadway, bridge).

(4)  Include a concise description of the work represented by each activity, which shall be placed at or near the event node or box for each activity.  If the project is of sufficient complexity that the concise description cannot be legibly placed on the diagram, submit a tabulation of all activities by their event node or box numbering and description.

(5)  Code each subcontractors' activities so that their activities can be shown separately as well as cumulatively.

(6)  Construction activities shall have durations of whole working days, with a maximum duration of 25 working days each.  Divide activities with longer durations into subgroups of activities not exceeding 25 working days in duration.  Indicate logical start and end points (e.g. stationing, staging, etc.) for each subgroup.

(7)  Non-construction activities may have durations exceeding 25 working days consistent with the contract.  Non-construction activities include mobilization, all shop drawing and sample submittals, and the fabrication and delivery of key materials. Indicate intended submittal dates and realistic delivery dates for fabrication and delivery activities.  Provide the required times for CO review, approval, and dispatch of each submittal and resubmittals.  Where no times are specified, provide 14 calendar days for the review, approval, and dispatch of each submittal and resubmittals after receipt by the CO.

(8)  Indicate the total number of anticipated working days to complete each activity of work.

(9)  Identify the critical path on the diagram.

- Supporting documents

(1)  Submittal List.  Submit a list of all drawing and sample submittals required for the entire contract period.  Include:

(a)  Contractor Quality Control Plan;

(b)  Asphalt Mix Designs;

(c)  Concrete Mix Designs;

(d)  Bridge Falsework and Formwork Designs;

(e)  Manufactured Items;

(f)  Test Panels;

(g)  Contract Specialty Items.

- Include the following information for each submittal:

(a)  Bid Item Number;

(b)  Item Description;

(c)  Related Activity ID Number and Description from the CPM-PS;

(d)  Planned Date of Initial Submittal;

(e)  Planned Date of CO's Initial Response;

(f)  Comments.

(3)  Written Narrative.  Provide a written narrative describing the rationale and assumptions utilized in the development of the proposed CPM-PS schedule.  The narrative will serve, in conjunction with the diagram, as the basis for the CO's review and approval of the CPM-PS.  This narrative should use the schedule diagram as the basis of all schedule-related comments, referencing specific activities by number and description. Include the following in the written narrative:

(a)  A description of the planned critical path and the general sequence of work.

(b)  Information and references to adequately define the scope of work included in each major activity type (e.g. roadway excavation, aggregate base course).  This would include such information as station numbers, location, etc.

(c)  A description of the resource loading planned for use in the performance of the work for each major activity.  The Contractor's determination of major activities is subject to approval by the CO.  The description should include manpower allocation by types of labor and crew size, types and number of equipment and any special equipment, materials, and subcontractors involved.

(d)  A description of the basis (including the resource loading above) for the calculation of the duration for all major activities, to be stated as quantity production rates (e.g. cubic feet of excavation per day, etc).

(e)  A description of planned workdays per week (Monday through Friday, or Saturday), number of shifts per day, and number of hours per shift.

(f)  A description of the assumptions used in converting working days to calendar dates; including anticipated holidays, non-work (idle) days, Contractor scheduled winter shutdowns, contract constraints, and weather constraints as determined in Subsection 155.02(c).

(g)  Identify the subcontractor or supplier performing an activity and identify their activity codes used on the schedule diagram.  State all assumptions made in the scheduling of the subcontractor's or supplier's work.

(h)  Describe expected and critical delivery dates for equipment or material that can affect timely completion of the project.

(i)  Describe critical completion dates for maintaining the construction schedule.

(j)  A description of any organizational limitations such as resource constraints or subcontractor commitments, which limit scheduling flexibility.

(k)  Ensure that there is no conflict between the diagram and the narrative.  The CO's approval of the CPM-PS does not waive this responsibility.

(4)  Tabular schedule.  Provide a computer generated tabular schedule using the Classic Schedule Report format sorted by early start and total float.  The tabular schedule shall include the following data: activity ID, original and remaining duration, activity percent complete, subcontractors codes, activity description, early and late schedule dates, and total float. Two copies of the computer diskettes containing this data shall be submitted with the CPM-PS along with the hard copy printouts of this tabular schedule.

Other tabular schedule report formats may be requested to analyze CPM-PS revisions or time impacts.

(5)  Reasonably Predictable Weather.  Submit a completed Table 155-1 using 10-year historical weather data from the nearest NOAA weather data collection station (see Subsection 155.02(c)).

(e)  Review and Approval of the Initial CPM-PS

- Within 21 calendar days of receipt of the proposed CPM-PS, the CO will either approve the proposed CPM-PS or convene a Joint Review Conference at which the CO and the Contractor will discuss corrections and adjustments to the proposed CPM-PS.  If any corrections or adjustments to the proposed CPM-PS are agreed upon or directed by the CO based on this review, adjust the CPM-PS and submit to the CO for review and approval within 14 calendar days after the date of this meeting. No progress payment will be made until an initial baseline CPM-PS is approved.

(2)  When an initial baseline CPM-PS is approved, the CO will return an approved copy of the CPM-PS to the Contractor. This approved CPM-PS with its supporting documents becomes the CPM-PS of Record.  Thereafter, implement and execute the work under the contract in accordance with this schedule, unless, a revision to this schedule is approved by the CO.  An approved updated or revised CPM-PS becomes the current CPM-PS of Record.  The current CPM-PS of Record will be considered the Contractor's work plan for completing the entire contract.

155.05  CPM-PS Updates

(a)  Definition of a CPM-PS Update.  A CPM-PS Update is a normal monthly updating of the current CPM-PS of Record with no changes in the schedule logic or activities and no changes to the critical path.  An Update shall reflect work completed to date, as well as the Contractor's projection of work yet to be completed.  A normal Update should show the project being completed by the Contract Completion Date.

An Update may show negative float in the schedule (i.e. the actual completion occurs later than the Contract Completion Date).  Receipt of an Update with negative float does not constitute agreement by the Government with the revised completion schedule.  The reason for late completion (Government, weather, or Contractor caused delay) must be clearly explained in the written narrative.  Any change to the CPM-PS of Record regarding work that is still to be completed, can only be effected by a CPM-PS Revision, including a Time Impact Analysis.

Negative float due to Contractor caused delay may result in the following actions by the CO: a request for a revision to the schedule to meet the Contract Completion Date; retent withheld from progress payments; assessment of liquidated damages; issuance of a cure notice; or termination.

(b)  Timing of Updates.  Monthly job site meetings to review progress and payment quantities will be held on a date mutually agreed to by the CO and the Contractor.  Submit a CPM-PS Update to the CO 3 working days before the meeting date.

(c)  Form and Requirements of the CPM-PS Update.  Submit the following:

(1)  Tabular Schedule (Classic Schedule Report), updated as follows:

(a)  Actual finish dates for completed activities;

- Remaining duration required to complete each activity started, or scheduled to start, but not completed;

- Float remaining for each activity;

- Percentages for completed and partially completed activities;

- The CO may request additional tabular schedules using different sort parameters.

(2)	 The Submittal List updated as follows:

(a)  Actual date(s) of initial (and all subsequent) submittal(s);

- Actual date(s) of CO's initial (and subsequent) response(s);

- Status of CO's initial (and subsequent) response(s) (i.e. Approved, Rejected, Approved As Noted, etc.)

- Comments.

(3)	 Written narrative.  Identify all changes made to the schedule since the last update.  Describe any issues that occurred in the previous month impacting the schedule (e.g. delaying factors and their estimated impact on performance of other activities and completion dates; weather delays; and an explanation of corrective action taken or proposed).  Describe any changes in the resource loading.

(4)  Provide an updated Time-Scaled Logic Diagram when requested by the CO.

(d)  Review and Approval of the CPM-PS Update

(1)	 The CO will review and approve the CPM-PS Update within 7 calendar days or return it for corrections.  The approved CPM-PS Update shall become the current CPM-PS of Record.

(2)	 No monthly progress payment will be made until a CPM-PS Update is approved.

155.06  CPM-PS Revisions

(a)  Definition of a CPM-PS Revision.  A CPM-PS Revision reflects a significant change to the schedule logic, schedule activities, activity durations or some other modification to the schedule of planned work.  Activities performed out of sequence from the CPM-PS of Record affecting the critical path will require a CPM-PS Revision.

(b)  Timing of a Revision.  Submit proposed revisions to the CPM-PS in writing, as they are determined necessary by either party.  A revision shall be submitted in conjunction with any contract modification that affects the CPM-PS of Record. Submission of a proposed CPM-PS Revision will not in itself be considered to be Notice to the CO of a delay or disruption, or of any other basis for a change under the Contract.  Refer to the notice requirements in other sections of the Contract. Continue to submit monthly CPM-PS Updates to the current CPM-PS of Record until a CPM-PS Revision is approved.

(c)  Form and Requirements for Submitting a Proposed CPM-PS Revision.  Submit the following:

- Written narrative.  All proposals to revise the CPM-PS shall include a written narrative describing the changes to the critical path and any logic revisions or modifications to the schedule, including, but not limited to, changes in the resource loading, in durations, in specifications, in subcontractors, the addition or deletion of work, increased or decreased quantities, defective work, and acceleration of the work.

Delays and disruptions, which are ongoing and of uncertain duration as of the date of the proposed revision, shall be identified. When any delays or disruptions have occurred which are the contractual responsibility of the Contractor (i.e. which do not entitle the Contractor to a time extension under the terms of the Contract), advise the CO of the proposed efforts to return the project to a schedule consistent with the terms of the Contract--including the commitment of additional resources or other appropriate action.  If this is not possible, advise the CO of the extent to which completion dates or other terms of the Contract will not be met so the Government may evaluate its options under the terms of the Contract.

(2)  Time Impact Analysis.  Submit a Time Impact Analysis according to Subsection 155.07.

(d)  Execution of a Proposed CPM-PS Revision.  When the parties agree to a proposed CPM-PS Revision, submit 5 hard copies of the revised CPM-PS and 2 copies of the computer file diskettes within 7 calendar days after the parties reach agreement.  The revised CPM-PS shall include all of the items required by Subsection 155.04(b), plus a narrative description of the basis for the approved revisions to the CPM-PS.  The approved CPM-PS Revision shall become the current CPM-PS of Record.

155.07  Time Impact Analysis

(a)  General.  A Time Impact Analysis is the procedure by which the Contractor demonstrates the effect of specific time impacts on the overall project CPM-PS.  Time impacts may result in an increase or decrease in contract time.

If the Contractor does not submit a Time Impact Analysis, it is mutually agreed that the particular event does not require an extension of time to the Contract Completion Date, and the Contractor waives its right to subsequently request a time extension.

Once any Time Impact Analysis is approved by the CO, both parties agree to waive any rights to re-evaluate the impacts, evaluated therein, at a later date.

(b)  Situations Requiring a Time Impact Analysis

(1)  CO Requested Contract Modifications.  When requested by the CO in connection with a proposed contract modification, prepare a proposed revision to the CPM-PS of Record with a Time Impact Analysis reflecting, in detail, the anticipated impact of the contract modification.  This revised CPM-PS will be used as a basis to modify the contract time resulting from the contract modification.

(2)  Time Impacts of a Contractor Proposed Contract Modification.  When notification of a Contractor proposed contract modification is given which may result in a time impact under the terms of the contract, (see Subsection 155.07(d)), identify the events and provide written notice to the CO within 7 calendar days after the commencement of the alleged time impact.  This notice shall detail the contractual basis for the time impact.

Within 14 calendar days after the end of the time impact event, for which the Contractor has given notice, submit a Time Impact Analysis which reflects and analyzes the alleged event or contract modification.

(3)	  Weather Delays.  Submit a Weather Time Impact Analysis for alleged weather delays according to Subsection 155.02(c).

(c)  Form and Requirements of a Time Impact Analysis.  Consecutively number each Time Impact Analysis.  Include in each Time Impact Analysis, the following documents or information:

(1)  The CPM-PS of Record at the time of the alleged impact (Affected CPM-PS).

- Narrative Impact Analysis.  Provide a detailed narrative description of each alleged impact event.  The alleged impact to each and every specifically affected activity in the Affected CPM-PS shall be described in detail, including how each activity referenced in the Time Impact Analysis reflects the alleged impact.  This narrative shall describe:

  - The cause of the impact;

  - The start date of the impact;

  - The duration of the impact, specifically describing how Contractor caused delays were deleted from the analysis;

  - The activities affected; and

  - Whatever methods the Contractor can employ, at no or minimal cost to the Government, to re-sequence or reschedule the work to mitigate the delay.

(3)  As-Properly Impacted Schedule.  Revise the Affected CPM-PS to show the impact of the activities identified in Subsection 155.07(b), including any re-sequencing which would mitigate the delay.  If the contract completion date is delayed, note the amount of the requested time extension as a request for a delay to that date.

(d)  Analysis of a Time Impact

(1)  General.

- Any request for an extension of the contract time will be determined by the CO's review of the Time Impact Analysis' effect on the Affected CPM-PS;

- Activity delays will not automatically mean that an extension of the Final Contract Completion Date is warranted or due.  A Contract Modification or delay may not affect existing critical activities or cause non-critical activities to become critical, but may result in only absorbing a part of the available total float that may exist within an activity chain of the Network, thereby not causing any effect on the Final Contract Completion Date.

- Only delays to activities which affect the Contract Completion Date will be considered for a time extension.  The extension of the specified completion date will be based upon the actual number of calendar days the Contract Completion Date is adjusted.

- Extensions of time to the Contract Completion Date under the FAR Clauses 52.243-4, Changes; 52.236.2, Differing Site Conditions; or 52.212-12, Suspension of Work, will be granted only if requested in writing by the Contractor within the applicable notice period.

(2)  Float.  No extension to the Contract Completion Date will be issued for work performed on activities with available float.  Float is defined as the amount of time between when an activity "can start" (the early start) and when an activity "must start" (the late start).  Float is a shared commodity, not for the exclusive use or benefit of either party.  Either party has the full use of the float until it is depleted.  Float may be consumed by the Contractor through routine operational considerations; by the Government through contract modifications, or other actions, which are its responsibility; or by unusually severe weather, strikes or other actions which are the responsibility of neither the Contractor nor the Government.  Each updated or revised CPM-PS shall depict float as it is currently projected.  Once all or part of this float has been consumed, it will no longer be an issue with respect to subsequent events.

(3)  Contractor's Duty to Mitigate.  It is the Contractor's duty to attempt to mitigate delay.  Analyze and discuss what measures the Contractor plans to take to mitigate delay.  Include as a minimum those items of no cost to the Government.  Accompany any measures which are alleged to increase cost, such as additional staffing or equipment, by corresponding rationale and assumptions which analyze the additional requirements.  In addition, any Time Impact Analysis which does not include a discussion of the feasibility of re-sequencing future work to mitigate delay at no cost to the Government will be rejected.

(e)  Extensions to Contract Dates.  The Government desires all contract work (including all work associated with an approved time impact analysis) to be completed by the Contract Completion Date.  Therefore, any time extensions to the Contract Completion Date will require a contract modification.  In addition, no increased cost will be paid to the contractor to accelerate the work unless the Contractor has expressly notified the Government under FAR Clause 52.243-4, Changes, and a contract modification has been issued.

(f)  Execution of the Time Impact Analysis.  Incorporate approved logic changes or time extensions into the CPM-PS by or before the next monthly meeting.

155.08  Failure to Maintain Sufficient Progress.  The Contractor shall furnish sufficient forces, offices, facilities, and equipment, and work such hours, including multiple shift and overtime operations, as is necessary to ensure progress consistent with the requirements of the contract and the current CPM-PS of Record.

The currently approved CPM-PS of Record will be used to evaluate progress as required by FAR Clause 52.232-5, Payments Under Fixed-Price Construction Contracts.  If the Contractor's actual progress is less than that required by the currently approved CPM-PS of Record for completion by the Contract Completion Date, 10 percent of the amount of all progress payments will be withheld until completion, or until progress is improved for completion by the Contract Completion Date.

If the Contractor fails to improve progress for completion by the Contract Completion Date, the Government may exercise its rights and options pursuant to FAR Clause 52.249-10, Default (Fixed-Price Construction), including the issuance of a Termination for Default.

# Measurement

155.09  Measure the Section 155 items listed in the bid schedule according to Subsection 109.02.

# Payment

155.10  The accepted quantities will be paid at the contract price per unit of measurement for the Section 155 pay item listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Progress payments for construction schedule will be paid as follows:

(a)  25 percent of the unit bid price will be paid upon approval of the Initial CPM-PS, not to exceed 0.25 percent of the original contract bid amount.

(b)  The remaining portion will be paid in increments equal to the progress of the work, not to exceed 0.5 percent of the original contract bid amount.

(c)  Any portion of the lump sum in excess of 0.5 percent of the original contract amount will be paid after final acceptance.

INCLUDE THE FOLLOWING

$$155.00B

Add the following at the end of the Subsection:

TABLE 155-1

Project Number__________________________

Location of NOAA Data Collection Station__________________________

Data Years (10-year history):  19___ through 20___

REASONABLY PREDICTABLE WEATHER

| MONTH | AVERAGE WORKDAYS LOST | STANDARD DEVIATION | TOTAL LOST DAYS |
| --- | --- | --- | --- |
| JANUARY |  |  |  |
| FEBRUARY |  |  |  |
| MARCH |  |  |  |
| APRIL |  |  |  |
| MAY |  |  |  |
| JUNE |  |  |  |
| JULY |  |  |  |
| AUGUST |  |  |  |
| SEPTEMBER |  |  |  |
| OCTOBER |  |  |  |
| NOVEMBER |  |  |  |
| DECEMBER |  |  |  |

$$156.00A

Section 156. — PUBLIC TRAFFIC

Revised 25 September 2008

INCLUDE THE FOLLOWING FOR RUSH HOUR RESTRICTIONS

$$156.03A

156.03.  Add the following:

Rush hours are defined as:

(insert rush hours; use full time format, i.e. 5:00 a.m., 3:30 p.m., etc.)

Perform the work during the time periods specified.  Schedule and perform the work so as not to interfere with traffic during rush hours.  Installing traffic control devices before a rush hour is over, or failing to complete work and remove traffic control devices before a rush hour begins, will be considered Contractor noncompliance.  Noncompliance will result in a reduction in payment to the Contractor equal to $(insert amount) per hour, for each hour or portion thereof.  This reduction in payment will be subtracted from the Contractor’s progress payments and will be unrecoverable.

The CO reserves the right to review the Contractor’s progress before rush hour begins.  The CO may direct the Contractor to stop operations to ensure the Contractor completes all work, including the removal of all lane restriction traffic control devices and installation of rush hour traffic control devices before rush hour begins.

INCLUDE THE FOLLOWING FOR HIGH ADT OR URBAN AREAS

$$156.03B

156.03.  Add the following:

Comply with all of the requirements of the Traffic Control Plan and adequately maintain all of the devices required.  Clean, service, and replace all traffic control devices when they become inoperative, damaged, or when the specified reflectivity of the device is reduced by 50 percent.  The Contractor will be given written notice of those traffic control items not in compliance with the Contract.  Revise the identified items into compliance within 24 hours.  If the Contractor fails to bring the specified items into compliance within the 24-hour period, the CO may assess a daily reduction in payment to the Contractor of $(insert amount, typically ½ of the liquidated damages amount) per day.  The CO may continue to assess the daily reduction in payment for each additional 24-hour period until the items are corrected.  This reduction in payment will be subtracted from the Contractor’s progress payments and will be unrecoverable.  Use of this reduction in payment does not waive the CO’s right to suspend the work in whole or in part according to Subsection 108.05.

INCLUDE THE FOLLOWING, IF APPROPRIATE

$$156.03C

156.03.  Add the following:

Hauling will only be permitted from the nearest point of public access to the work site.  Minimize hauling over completed pavement.

INCLUDE THE FOLLOWING

$$156.04A

156.04.  Add the following:

(g)  Ensure that all drains and inlets within the project limits are fully functional throughout the duration of the project.

INCLUDE THE FOLLOWING

$$156.06A

156.06(b).  Delete the second sentence and substitute the following:

For shoulder drop-offs in excess of 3 inches (7.5 centimeters), provide a 1V:3H fillet with “Low Shoulder” warning signs.

INCLUDE THE FOLLOWING FOR URBAN AREAS

$$156.06B

156.06(i).  Delete the text and substitute the following:

(i)  Limit construction caused delays to public traffic to a maximum of 15 minutes per passage through the project.

INCLUDE THE FOLLOWING IF NIGHT OPERATIONS ARE NOT PERMITTED

$$156.07A

156.07.  Delete the Subsection and substitute the following:

156.07  Nighttime Operations.  Nighttime operations are not permitted.  Perform construction operations during the hours of daylight (½ hour after sunrise to ½ hour before sunset).

INCLUDE THE FOLLOWING FOR COMPLEX URBAN PROJECTS

$$156.08A

156.08.  Add the following:

Employ a full-time traffic safety supervisor, exclusively for this project, and designate the person in writing to the CO at the preconstruction conference.  The traffic safety supervisor will be on the site at all times when work is being performed and available during non-work hours.

INCLUDE THE FOLLOWING FOR RURAL OR UNCOMPLICATED PROJECTS

$$156.08B

156.08.  Delete the second sentence of the first paragraph and substitute the following:

The traffic safety supervisor may be the superintendent.

$$201.00A

Section 201.—CLEARING AND GRUBBING

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR USFS PROJECTS

$$201.03A

201.03.  Add the following:

Pay to the Forest Service within 30 calendar days after contract award or before the start of clearing and grubbing operations, the lump sum price of (obtain $ value from USFS) as payment in full for all merchantable timber involved in clearing and grubbing and individual removal of trees.

$$203.00A

Section 203.—REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Revised 6 May 2005

# INCLUDE THE FOLLOWING FOR BRIDGE CONCRETE REMOVAL

$$203.04A

  - Add the following:

(a)  Concrete Removal by Mechanical Impact Methods.  Furnish equipment that complies with the following:

(1)  Use power-driven hand tools for removal of existing concrete with the following restrictions:

(a)  Do not use jackhammers heavier than 30 pounds (13.6 kilograms).

(b)  Do not operate 30-pound (13.6 kilogram) jackhammers and mechanical chipping tools at an angle in excess of 45 degrees measured from the surface of the slab.

(c)  Do not use chipping hammers heavier than a nominal 15-pound (6.8-kilogram) class to remove concrete from beneath any reinforcing bar.

(2)  Use hand tools (hammers and chisels) for removal of final particles of concrete or to achieve the required depth.

(b)  Reinforcing Steel.  Clean all reinforcing steel that is to remain in place and has been exposed by removal operations.  Remove all rust and corrosive products, including oil, dirt, concrete fragments, laitance, loose scale, and other coating of any character that would destroy or inhibit the bond with the new concrete.

When cleaned reinforcing steel will be exposed for more than 7 calendar days before placing the concrete, protect the steel from corrosion and contamination.  Clean and/or replace all reinforcing steel corroded or contaminated because of the Contractor's failure to protect the steel.

Prevent cutting or damaging reinforcing steel designated to remain in place.  Repair or replace any damaged bars.

INCLUDE THE FOLLOWING, IF APPLICABLE

$$203.05A

203.05(b).  Delete the Subsection and substitute the following:

(b)  Burn.  Burning is prohibited.  Dispose of material according to Subsection 203.05(a).

$$203.05B

203.05(c).  Add the following after the first sentence of the first paragraph:

Bury debris beyond the toes of fills in areas authorized by the CO.

$$203.05C

203.05(c).  Delete the Subsection and substitute the following:

(c)  Bury.  Burying debris is prohibited.  Dispose of material according to Subsection 203.05(a).

$$204.00A

Section 204.—EXCAVATION AND EMBANKMENT

Revised 25 January 2005

# INCLUDE THE FOLLOWING

$$204.13A

204.13(d).  Add the following:

Flush the exposed faces of rock embankment with soil conserved from the excavation.

$$205.00A

Section 205.—ROCK BLASTING

Revised 6 May 2005

INCLUDE THE FOLLOWING FOR  NPS PROJECTS

$$205.08A

205.08(c)  Delete the first sentence of the sixth paragraph and substitute the following:

Allow a 2-foot (0.6-meter) offset for a working bench at the bottom of each lift for drilling the next lower controlled blasting hole pattern.

$$205.08B

205.08(c).  Delete the ninth paragraph and substitute the following:

Presplitting is not permitted.

$$212.00A

Section 212.—LINEAR GRADING

Revised 25 January 2005

# INCLUDE THE FOLLOWING

$$212.03A

212.03.  Delete the Subsection and substitute the following:

Construct the roadbeds according to Section 204.

$$212.04A

212.04.  Add the following after the second sentence:

Submit any deviations from the established vertical or horizontal alignment shown in the plans for approval.

$$251.00A

Section 251. — RIPRAP

Revised 30 January 2009

INCLUDE THE FOLLOWING (AND INCLUDE $$705.02A AND $$705.02B) FOR ALL RIPRAP APPLICATIONS

$$251.07A

251.07.  Delete the second sentence and substitute the following:

Rock for riprap will be evaluated under Subsections 106.02 and 106.04.

Verify that rock for riprap delivered to the placement site meets the applicable class size specified in Table 705-1 through sampling as specified in Table 251-1 and testing the size characteristic as follows:

The intermediate dimension of the largest accessible rock will be measured and must be greater than the upper limit of the D85 size range for the intermediate dimension specified in Table 705-1 for the applicable riprap class.  The intermediate dimension is defined as the shortest, straight-line distance from one side of the rock to the other on the maximum projection plane (plane of rock with the largest projected surface area).

Verify that production rock for riprap meets the applicable class gradation specified in Table 705-1 through sampling and testing the gradation characteristic as specified in Table 251-1.  Provide the CO a minimum 7-day advance notice of the sampling and testing schedule and location.

$$251.07B

251.07 Table 251-1.  Delete Table 251-1 and substitute the following:

| Table 251-1 Sampling and Testing Requirements | Reporting Time | Before using in work | “ | “ “ “ | Before using in work |
| --- | --- | --- | --- | --- | --- |
|  | Split Sample | Yes | “ | “ No No | Yes, when requested |
|  | Point of Sampling | Source of material | “ | “ Placement site Production stockpile | — |
|  | Sampling Frequency | 1 per material type | “ | “ One per 50 cubic yards (40 cubic meters) One per 1000 cubic yards (800 cubic meters) | 1 per mix design |
|  | Test Methods Specifications | AASHTO T 85 | AASHTO T 104 | AASHTO T 96 Subsection 251.07 FLH T 521-08 | AASHTO T 23 & T 22 |
|  | Category | — | — | — — — | — |
|  | Characteristic | Apparent specific gravity & absorption | Sodium sulfate soundness | LA abrasion Size Gradation | Making test specimens Compressive Strength |
|  | Type of Acceptance (Subsection) | Measured and tested for conformance (106.04) | Measured and tested for conformance (106.04) |
|  | Material or Product | Riprap Rock (705.02) | Grout |

$$253.00A

Section 253.--GABIONS AND REVET MATTRESSES

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR NPS PROJECTS AND OTHERS IF APPLICABLE

$$253.06A

253.06 Add the following after the second paragraph:

Hand place the rock for the visible faces of exterior basket cells to ensure an attractive appearance as directed by the CO.  Rock in other sections of baskets may be placed by mechanical equipment.

$$257.00A

Section 257.—ALTERNATE RETAINING WALLS

Revised 16 May 2005

INCLUDE THE FOLLOWING FOR ALTERNATE RETAINING WALLS

$$257.04A

257.04(i).  Add the following:

Design Criteria.  Consider the internal and the external stability of the wall.  For internal stability, the wall system must be coherent and self-supporting mass under the action of its own weight and any externally applied forces.  For external stability the wall system must be stable against sliding, overturning, foundation failure, and overall slope failure including failure of temporary construction slopes.

The CO will provide the angle of internal friction used for the computations of earth pressures in the reinforced and retained soil backfill.

The CO may reject any proposed wall alternate should the alternate present unreasonable slope stability risks at any individual site.

$$257.04B

Add the following after Subsection 257.04:

257.04A  Mechanically Stabilized Embankment Walls.  Construct mechanically stabilized embankment walls using either or both extensible and inextensible reinforcements conforming to Section 255 and to the following design criteria:

(a)  Structure Dimensions.  Dimension structures to satisfy the following minimum Factors of Safety:

(1)  Sliding > 1.5

(2)  Overturning > 2.0

(3)  Bearing Capacity > 2.5

(4)  Pullout Resistance > 1.5

(5)  Overall Stability > 1.3 (1.2 for temporary construction slopes)

Design the minimum reinforcement length to be 70 percent of the wall height (as measured from the back of the wall) and not less than 8 feet (2.4 meters) for wall heights up to 20 feet (6.1 meters).  For wall heights over 20 feet (6.1 meters), design the minimum reinforcement length to be 70 percent of the wall height (as measured from the back of the wall) and not less than 15 feet (4.6 meters), unless substantiating evidence is presented to indicate that shorter lengths are satisfactory.  Consider rock intrusion into the design of the embedment length design.  Include a minimum embedment length of 70 percent of the wall height (as measured from the back of the wall) if the design embedment length cannot be reached because of bedrock intrusion.  In addition, the reinforcement length must be sufficient to satisfy all external and internal stability considerations.

(b)  Wall Embedment Depth.  Design structures for the following minimum embedment unless constructed on rock foundations.  The minimum embedment is determined as a function of the height of structure (H) above the base of the wall.

| Slope in Front of Structure |  | Minimum Embedment |
| --- | --- | --- |
| Horizontal | walls |  | H/20 |
| 3H:1V | walls |  | H/10 |
| 2H:1V | walls |  | H/7 |
| 3H:2V | walls |  | H/5 |

Design the minimum embedment depth to the top of leveling pad to be 2 feet (0.6 meters) or below the prevailing depth of frost penetration.

INSERT THE FIGURE NUMBERS AND EARTH PRESSURE DIAGRAMS FROM GEOTECH

(c)  External Stability Computations.  Assume the stabilized earth mass to be a rigid body for stability computations.  Compute the coefficient of active earth pressure (Ka), used to compute the horizontal force resulting from the random backfill and other loads, based on the friction angle of the random backfill.

Compute the active earth pressure coefficients for random backfill as follows:

Where:	B  =  Slope angle above wall

  =  Internal angle of friction of random backfill

Figures (insert figure number) and (insert figure number) illustrate external stability equations for walls with horizontal backslope and inclined backslope respectively.  The resultant force acting on the base lies within the middle third of the base width.

(d)  Internal Stability.  Perform internal stability analyses to verify that the reinforcing material is not over-stressed and that the reinforcement embedment length beyond the failure surface is sufficient to prevent pullout.

(1)  Reinforcement Tension.  Use the tie-back wedge method of analysis for analysis of retaining walls reinforced with extensible reinforcement.

The required reinforcement tension to prevent rupture, Tr, calculated using the tie-back wedge method, is less than or equal to the allowable reinforcement tension, Ta, determined as outlined in Subsection 257.04A(f).

(2)  Reinforcement Length.  Design the reinforcement length to be the longer of the length required for external stability or internal stability.  Design the length required for external stability according to Subsection 257.04A(c).  Determine the length required for internal stability as follows:

At each reinforcement level, design the reinforcement length for a minimum factor of safety of 1.5 against pullout failure (i.e., at each reinforcement level the pullout resistance, Tp, is at least 1.5 times the required reinforcement tension, Tr).  Use only the effective pullout length extending beyond the Rankine failure surface into the resistant zone in the computation of the required pullout resistance.

The minimum reinforcement length in the resistant zone shall be 3 feet (0.9 meters).  The total reinforcement length at any level is equal to the sum of the lengths in the active and resistant zones.  Provide uniform reinforcement length throughout any section of the structure.

(e)  Reinforcement Pullout Resistance.  Evaluate the pullout resistance from the results of pullout tests.  The use of direct shear tests to determine the pullout resistance of reinforcement is not acceptable.  Base pullout resistance for design on a maximum elongation of the embedded reinforcement of ¾ inch (19 millimeters) as measured at the leading edge of the compressive zone within the soil mass and not the ultimate pullout capacity.

For geogrids, where insufficient data exists to evaluate pullout resistance as a function of soil type, pullout tests will be required on a project specific basis until such time that the engineering behavior of the soil-reinforcement system is clearly defined.  Perform the pullout tests using vertical stress (v) variations and reinforcement element configurations simulating the actual project conditions.

Perform the pullout tests on samples with a minimum embedded length of 2 feet (0.6 meters).  Perform the tests on samples with a minimum width of 1 foot (0.3 meters) or a width equal to a 4 longitudinal reinforcement element, whichever is greater.  Conduct tests at 70±2 oF (21±1 oC) at constant strain rates of 0.02 inches (0.5 millimeters) per minute.

Evaluate the pullout resistance for geogrids by the following relation:

Tp = 2 tan  v As fd

where:

Tp = Ultimate pullout capacity of tensile 	reinforcement (pounds (kilograms))

v = Vertical stress (pounds per square foot (kilograms per square meter))

As = Total plan area of geogrid beyond failure plans (square feet (square meters))

  = Internal angle of friction of backfill

fd = Equivalent coefficient of direct sliding derived from pullout tests

The equivalent coefficient of direct sliding is a function of the open area of the grid.  For preliminary analysis estimate from the following in the absence of product specific data tested with site-specific granular backfills:

| % Open Area of Grid | Equivalent Coefficient of Direct Sliding |
| --- | --- |
|  | 80 or more |  | 0.5 |
|  | 51 to 79 |  | 0.7 |
|  | 50 or less |  | 0.6 |

(f)  Reinforcement Properties and Allowable Stress.

(1)  General.  The long-term tension-strain characteristics of extensible reinforcements are influenced by:

(a)  Long-term polymer creep,

(b)  Long-term polymer degradation, and

(c)  Construction induced reinforcement damage as well as variations in the manufacturing process.

Account for and verify these factors by testing to determine the allowable long-term reinforcement tensions for design.

(2)  Creep.  Determine the long-term tension-strain-time behavior of polymeric reinforcement from results of controlled laboratory creep tests conducted for a minimum duration of 10,000 hours for a range of load levels on samples of the finished product to be used on the project.  Test samples in the direction in which the load will be applied in use in either a confined or unconfined mode.  Extrapolate results using a minimum design life of 100 years.

Determine the following from these tests:

(a)	 The highest tension level at which the accumulative creep strain-rate continues to decrease with Log-time within the required design lifetime and which would preclude brittle or ductile failures.  Term this value of load the limit state reinforcement tensile load and designate as T1.

(b) 	The tension level at which total strain is not expected to exceed 5 percent within the design lifetime.  Term this value of load the serviceability state reinforcement tension, and designate as Tw.

(3)  Polymer Durability.  Perform product specific studies to assess the effects on the reinforcement's durability in differing environments.  Include the effect on short-term and long-term mechanical properties as well as changes to the reinforcement microstructure, dimensional changes, changes in mass, oxidation, environmental stress cracking, hydrolysis, temperature, and plasticization in the studies.  Provide the test results for verification of product durability.  Investigate the full range of soil environments to which the reinforcements may be potentially exposed and the site-specific environment.  As a minimum include the following:

- The pH in the range of 3 to 9 - ASTM D 2165;

- Diesel oil - ASTM D 975;

- Fungi and Bacteria;

- U.V. exposure 500 hours. - ASTM D 4355;

- Solvents and agents that are site-specific.

Incorporate the results from these studies into durability reduction factors, (FD) and apply to the limit state tensile load T1.  Extrapolate results from short-term tests to the required design life of 100 years.

In the absence of site-specific product durability information, take FD as 2.0.  In no case shall FD be less than 1.10.

(4)  Construction Induced Damage.  Determine the effect of construction damage on the reinforcement from the results of full-scale construction damage tests on representative fill materials to be used in the construction of the reinforced backfill and according to construction procedures.  Incorporate the effect of construction damage tests into the construction damage factor (FC) that is applied to the limit and serviceability state reinforcement tensions.  In the absence of product specific construction damage tests on site-specific materials, take FC as 3.0.  Substantiate lower values by construction damage tests for the selected product with the specific backfill source from the project.

(5)  Allowable Reinforcement Tension.  The allowable reinforcement tension Ta, will be the lesser of the following 2 determinations:

(a)  Limit state determination.  The allowable long-term reinforcement tension based on a limit state criterion is given by:

where:	FS is an overall factor of safety to account for uncertainties in structure geometry, fill properties, reinforcement properties, and externally applied loads.  For permanent, vertically faced mechanically stabilized earth walls the minimum FS shall be 1.5 for overall stability.

(b)  Serviceability state determination.  The allowable long-term reinforcement tension based on a serviceability state criterion is given by:

For the serviceability state determination no overall factor of safety is required.

The allowable reinforcement tension, Ta, determined in this section shall be greater than the required reinforcement tension, Tr, calculated in Subsection 257.04A(d).

(6)  Geogrid Junction Strength.  For geogrids the summation of the shear strengths of the joints occurring in a 1-foot (0.3-meter) length of the grid sample shall be greater than the ultimate tensile strength of the grid element to which they are attached.  Otherwise, reduce the allowable reinforcement tensions in Subsection 257.04A(f)(5) by the ratio of the shear strengths to the ultimate strength.  Determine the ultimate tensile strength from the wide width tensile test, ASTM D 4595, and translate into an ultimate strength per element by dividing by the number of elements per foot (meter) of width.  Junction strength may be measured in accordance with Geosynthetic Research Institute (G.R.I.) Method GG-2-87.

(g)  Backfill Requirements.  Furnish backfill for embankments using inextensible metallic reinforcements meeting Subsection 255.06.

Furnish backfill for extensible reinforcements that has a nominal maximum particle size of 4 inches (10 centimeters), be reasonably free from organic or other deleterious materials, and have a pH between 3 and 9.  The shear strength parameters used for the computations of earth pressures in the reinforced and retained soil backfill will be provided on the plans.

(h)  Facing Connection Design.  Base the size of all structural facing elements so the design load stresses do not exceed the allowable stresses found in the AASHTO Standard Specifications for Highway Bridges.  Design extensible reinforcement connections to the facing to carry 100 percent of the maximum design tensile load at all levels.  Load test representative section of connection type with vertical stresses, ranging from minimum to maximum, to determine the allowable connection working load.  The reinforcement allowable strength may be no greater than the connection strength.

Conduct the load-test on samples at least 8 inches (20 centimeters) wide and at a rate of elongation not exceeding 0.5 inches (14 millimeters) per minute.

(i)  Corrosion Life.  The corrosion life of any metal components which are exposed to soil shall be 100 years.  Submit calculations concerning corrosion life to the CO for approval.

(j)  Miscellaneous.  If the wall designer/supplier needs additional information to complete its design, obtain the information.  Calculate the maximum bearing pressure under the stabilized mass using the Meyerhoff formula and clearly indicate on the plans.  Assume passive pressure in front of the wall mass to be 0 for design purposes.

Account for all appurtenances behind, in front of, under, mounted upon, or passing through the wall (such as the drainage structures, or other items shown on the plans) in the stability design of the wall.

$$257.04C

257.04B  Permanent Anchored Walls.  Design permanent anchored walls to conform to Sections 256, 551, 557, 601, and the following design criteria:

(a)  Design rock and soil anchors to conform to Section 256.

(b)  Design lagging by sound engineering principles.

(c)  Furnish a 1-foot (0.3-meter) reinforced concrete facing, designed according to AASHTO Standard and Interim Specifications for Highway Bridges.  Use Class A concrete, tested according to Subsection 552.19(a).  Extend the facing 2 feet (0.6 meters) below the gutter line or, if applicable, the ground line adjacent to the wall.  Finish concrete according to Subsection 552.16(a).

(d)  Design soldier piles for shear, bending, and axial stresses.  Design according to the latest AASHTO design criteria.  Soldier piles may be steel or concrete with a minimum yield strength for steel of 50,000 pounds per square inch (345 MegaPascals) and the minimum compressive strength of concrete of 3,000 pounds per square inch (20.7 MegaPascals), 28-day strength.

(e)  Design permanent drainage systems behind the wall.  Connect drainage systems to the nearest drop inlet by pipe or by free drainage.

INSERT THE FIGURE NUMBERS AND EARTH PRESSURE DIAGRAMS FROM GEOTECH

(f)  Show loading conditions for soldier piles, lagging, and anchors at critical stages of construction as indicated on Figures (insert figure numbers).

(g)  Ensure that the wall is compatible with horizontal and vertical alignment criteria indicated on the plans.

(h)  Size the tendon such that the design load does not exceed 53 percent of the guaranteed ultimate tensile strength of the tendon.

(i)  Analyze the anchor structure system to ensure long-term stability of both the anchors and the earth mass being retained.  Extend the free stressing length at least 5 feet (1.5 meters) beyond any critical failure surface but not less than 15 feet (4.6 meters) in soil or 10 feet (3 meters) in rock.  Account for the type of foundation, nearness, and susceptibility to movement of adjacent facilities in the design.

$$260.00A

Section 260.—ROCKBOLTS

Revised 25 January 2005

SECTION TO BE REVISED SHORTLY CONTACT PS&E REVIEW ENGINEER FOR FURTHER DETAILS

$$261.00A

Section 261.—ROCK DOWELS

Revised 25 January 2005

SECTION TO BE REVISED SHORTLY CONTACT PS&E REVIEW ENGINEER FOR FURTHER DETAILS

$$301.00A

Section 301.—UNTREATED AGGREGATE COURSES

Revised 6 May 2005

INCLUDE THE FOLLOWING FOR NEW OR RECONSTRUCTED CONCRETE PAVEMENT SLABS

$$301.01A

301.01.  Add the following:

Crushed recycled concrete may be used for aggregate courses under concrete pavements.

$$301.02A

301.02  Add the following:

Crushed recycled concrete						703.20

INCLUDE THE FOLLOWING

$$301.03A

301.03.  Add the following after the second paragraph:

Submit the representative 300-pound (150-kilogram) sample to the EFLHD Central Laboratory in Sevierville, Tennessee.

INCLUDE THE FOLLOWING IF ALLOWING AN ALTERNATE STATE GRADATION AND THE ALTERNATE STATE GRADATION INCLUDES SPECIFIED ALLOWABLE DEVIATIONS. ALSO INCLUDE APPLICABLE SCRS FROM SUBSECTION 703.05.

$$301.03B

301.03.  Add the following:

If an alternate State gradation is produced as provided in Subsection 703.05, notify the CO in writing.  If the target values with respect to the State gradation are not identified, they will be the midpoint of the allowable State specification band.

INCLUDE THE FOLLOWING IF ALLOWING AN ALTERNATE STATE GRADATION AND THE ALTERNATE STATE GRADATION DOES NOT INCLUDE SPECIFIED ALLOWABLE DEVIATIONS.  ALSO INCLUDE APPLICABLE SCRS FROM SUBSECTION 703.05.

$$301.03C

301.03.  Add the following:

If an alternate State gradation is produced as provided in Subsection 703.05, notify the CO in writing.  The target values with respect to the State gradation will be the midpoint of the allowable State specification band.  The allowable deviation (D) will be ½ the State specification band width, and the maximum allowable pay factor under subsection 301.08 will be 1.0.

INCLUDE THE FOLLOWING FOR NEW OR RECONSTRUCTED CONCRETE PAVEMENT SLABS

$$301.04A

301.04.  Add the following:

Remove and replace any layer of crushed recycled concrete material that exhibits heaving, pumping, rutting, or shearing under construction equipment even if the layer meets the density requirements in Subsection 301.05.

$$301.08A

301.08  Add the following:

Crushed recycled concrete for aggregate courses under concrete pavements will be evaluated under Subsections 106.02 and 106.04.

$$303.00A

Section 303.—ROAD RECONDITIONING

Revised 6 May 2005

INCLUDE  THE FOLLOWING WHEN STATIONING IS DONE OTHER THAN AT CL.  REVISE AS APPROPRIATE

$$303.10A

303.10.  Delete the second paragraph and substitute the following:

Measure ditch and shoulder reconditioning by the linear foot or mile (meter or kilometer), measured along the edge of pavement.

$$308.00A

Section 308.—MINOR CRUSHED AGGREGATE

Revised 6 May 2005

INCLUDE THE FOLLOWING WHEN CRUSHED RECYCLED CONCRETE IS PERMITTED IN TEMPORARY PAVEMENTS

$$308.02A

308.02.  Add the following:

Crushed recycled concrete				703.20

$$308.02B

Crushed recycled concrete may be used for aggregate courses in temporary pavements.

$$308.04A

308.04(a).  Add the following:

Remove and replace any layer of crushed recycled concrete material that exhibits heaving, pumping, rutting, or shearing under construction equipment even if the layer meets the density requirements in Subsection 308.05(a).

$$308.06A

308.06.  Add the following:

Crushed recycled concrete will be evaluated under Subsections 106.02 and 106.04.

INCLUDE THE FOLLOWING FOR A SMALL QUANTITY OF AGGREGATE FOR MINOR ROADS, PARKING LOTS AND FOR TEMPORARY PAVEMENTS (Quantity to be determined during the design and review process)

$$308.06B

  - Delete Table 308-1 and substitute the following:

Table 308-1

Sampling and Testing Requirements

| Material or Product | Type of Acceptance (Subsection) | Property or Characteristic | Test Methods Specifications | Sampling Frequency | Point of Sampling | Split Sample | Reporting Time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Crushed aggregate for roadway | Measured and tested for conformance (106.04) | Moisture-Density | AASHTO T 180 method D(2) | 1 for each aggregate supplied | Production output or stockpile | --- | Before using in work |
|  |  | Gradation(1) | AASHTO T 11 and T 27 | 1 for each 1000 tons | From windrow or roadbed after processing | --- | Before placing next layer |
|  |  | In-place density and moisture content | AASHTO T 310 or other approved procedures | 1 for each 500 tons | In-place | --- | Before placing next layer |
| Crushed aggregate for bedding and backfill | Measured and tested for conformance (106.04) | Moisture-Density | AASHTO T 99 method C(2) | 1 for each aggregate supplied | Production output or stockpile | --- | Before using in work |
|  |  | In-place density and moisture content | AASHTO T 310 or other approved procedures | 2 per lift | In-place | --- | Before placing next layer |

(1)Use only sieves indicated for the specified gradation.

(2)Minimum of 5 points per proctor.

$$308.06C

  - Delete the third and fourth paragraphs and substitute the following:

Construction of roadway aggregate courses, and bedding and backfill aggregate will be evaluated under Subsections 106.02 and 106.04.  Method 2 compaction will be evaluated under Section 106.04. Sample crushed aggregate for roadway according to Table 308-1.  Submit crushed aggregate for roadway samples to the CO for verification. Materials that do not meet the approved certification will be considered unacceptable.

INCLUDE THE FOLLOWING WHEN CRUSHED RECYCLED CONCRETE IS PERMITTED IN TEMPORARY PAVEMENTS

$$308.07A

308.07.  Add the following:

Measure crushed recycled concrete by the cubic yard (meter) in the hauling vehicle.

DO NOT USE SECTION 401 WHEN THE CONSTRUCTION CONTRACT WILL BE ADMINISTERED BY THE FOREST SERVICE, USE SECTION 403 INSTEAD (FS DOES NOT USE STATISTICAL ACCEPTANCE).

IF SECTION 403 IS USED, SECTION 401 AND SUBSECTION $$401.15A ONLY MUST BE INCLUDED.

$$401.00A

Section 401. — SUPERPAVE HOT ASPHALT CONCRETE PAVEMENT

Revised 1 October 2008

INCLUDE THE FOLLOWING

$$401.01A

401.01.  Add the following:

Asphalt binder is designated as performance grade PG (ASK MATERIALS ENGINEER FOR SPECIFIC GRADE).

INCLUDE THE FOLLOWING FOR PROJECTS IN STATES THAT HAVE CHANGED THE NATIONAL SUPERPAVE SPECIFICATION (CHECK WITH THE MATERIALS ENGINEER)

$$401.03A

401.03.  Add the following:

At the option of the Contractor, a State Department of Transportation Superpave hot asphalt concrete pavement mixture may be submitted for approval that has the same nominal maximum size aggregate, traffic level (design ESAL), and asphalt binder grade as specified.

INCLUDE THE FOLLOWING IF PROJECT HAS 401 OR 402 PAY ITEMS

$$401.03B

401.03(a).  Delete the first sentence and substitute the following:

Do not use mixes with over 15 percent recycled asphalt pavement in the top lift.

INCLUDE THE FOLLOWING

$$401.03F

401.03(b).  Add the following after the first sentence:

Submit all job-mix formula materials and information to the EFLHD Central Laboratory in Sevierville, Tennessee, with a copy to the CO as directed.

$$401.03C

401.03(b).  Add the following:

For State Department of Transportation mixes, submit a job-mix formula that is currently approved and has been tested by the State within a year of the date of intended use.  Include documentation from a State Department of Transportation official certifying that it is an approved State mix.

$$401.03D

For job-mix formulas with percentages of recycled asphalt pavement greater than 15 percent, submit a quality control plan showing sufficient control of the recycled asphalt pavement.

$$401.03E

401.03(c).  Add the following:

Allow a minimum of 21 calendar days for verification of each job-mix formula after receipt of all materials and information at the EFLHD Central Laboratory.

INCLUDE THE FOLLOWING IF PROJECT HAS 401 OR 402 PAY ITEMS

$$401.13A

401.13.  Add the following:

Begin paving operations at the furthest location from the asphalt plant and proceed towards the plant.

INCLUDE THE FOLLOWING IF PROJECT HAS 401, 402, OR 403 PAY ITEMS

$$401.15A

401.15.  Delete the second sentence of the first paragraph and substitute the following:

If drop-offs are left overnight, sign the drop-offs in excess of 2 inches (5 centimeters) with “Uneven Lanes” warning signs and provide a 1V:3H fillet for drop-offs in excess of 3 inches (7.5 centimeters).

DO NOT USE SECTION 402 WHEN THE CONSTRUCTION CONTRACT WILL BE ADMINISTERED BY THE FOREST SERVICE, USE SECTION 403 INSTEAD (FS DOES NOT USE STATISTICAL ACCEPTANCE).

IF SECTION 402 IS USED, ALSO INCLUDE SECTION 401 WITH SUBSECTIONS $$401.03B, $$401.13A, AND $$401.15A.

$$402.00A

Section 402. — HOT ASPHALT CONCRETE PAVEMENT BY HVEEM OR MARSHALL MIX DESIGN METHOD

Revised 1 October 2008

INCLUDE THE FOLLOWING

$$402.01A

402.01.  Add the following:

Asphalt binder is designated as performance grade PG (ASK MATERIALS ENGINEER FOR SPECIFIC GRADE).

INCLUDE THE FOLLOWING

$$401.03G

402.03(b).  Add the following after the first sentence:

Submit all job-mix formula materials and information to the EFLHD Central Laboratory in Sevierville, Tennessee, with a copy to the CO as directed.

$$402.03B

402.03(b).  Add the following:

For job-mix formulas with percentages of recycled asphalt pavement greater than 15 percent, submit a quality control plan showing sufficient control of the recycled asphalt pavement.

$$402.03C

402.03(c).  Add the following:

Allow a minimum of 21 calendar days for verification of each job-mix formula after receipt of all materials and information at the EFLHD Central Laboratory.

$$402.00B

THE FOLLOWING SPECIAL CONTRACT REQUIREMENTS ARE APPLICABLE TO THOSE 402 PAY ITEMS WITH BID SCHEDULE QUANTITIES GREATER THAN OR EQUAL TO 4000 TONS

Revised 1 October 2008

INCLUDE THE FOLLOWING WHEN THE PROJECT IS LOCATED IN A STATE WITH SIMILAR HACP SPECIFICATIONS.  GRADING C AND E SHOULD BE SPECIFIED IF ALLOWING A STATE OPTION (CHECK WITH THE MATERIALS ENGINEER)

$$402.03E

402.03.  Add the following:

At the option of the Contractor, a State Department of Transportation mixture gradation may be submitted which has the same maximum size aggregate as the specified grading and conforms to the aggregate quality requirements in Subsection 703.07, and design parameters (b); (c)(2) or (d); and (e) in Table 402-1 for the specified mix Class and the requirements of Table 402-2.

The allowable deviations for an optional State Department of Transportation gradation will be the allowable deviations as shown in Table 703-4 for the gradation specified.

$$402.03F

402.03(b).  Add the following:

For State Department of Transportation mixes, submit a job-mix formula that is currently approved and has been tested by the State within a year of the date of intended use.  Include documentation from a State Department of Transportation official certifying that it is an approved State mix.

USE FOR PAVEMENTS THAT DO NOT REQUIRE STATISTICAL EVALUATION (LESS THAN 4000 TONS) SUCH AS DRIVEWAYS, PULL-OFFS, AND PARKING AREAS BUT AREN’T MINOR ASPHALT (SECTION 404).

USE WHERE THE CONSTRUCTION CONTRACT WILL BE ADMINISTERED BY THE FOREST SERVICE (FS DOES NOT USE STATISTICAL ACCEPTANCE THEREFORE DO NOT USE SECTION 401 OR 402 EXCEPT FOR WHERE NOTED IN SECTION 401 INSTRUCTIONS).

IF SECTION 403 IS USED, ALSO INCLUDE SECTION 401 WITH SUBSECTION $$401.15A.

$$403.00A

Section 403. — HOT ASPHALT CONCRETE PAVEMENT

Revised 1 October 2008

INCLUDE THE FOLLOWING

$$403.01A

403.01.  Add the following:

Asphalt binder is designated as performance grade PG (ASK MATERIALS ENGINEER FOR SPECIFIC GRADE).

INCLUDE THE FOLLOWING FOR 401 SUPERPAVE HACP (DO NOT INCLUDE $$403.03B)

$$403.03A

403.03.  Delete the second and third bullet paragraphs and substitute the following:

(	State Department of Transportation Superpave hot asphalt concrete pavement mixture with the same nominal maximum size aggregate, traffic level (design ESAL), and asphalt binder grade as specified.  Meet the requirements for the location and type of facility being constructed as designated by the current State Department of Transportation specification.  Submit the aggregate quality, gradation requirements, and mixture criteria for the asphalt concrete mix.

INCLUDE THE FOLLOWING FOR 402 HACP BY HVEEM OR MARSHALL METHOD (DO NOT INCLUDE $$403.03A)

$$403.03B

403.03.  Delete the first and third bullet paragraphs and substitute the following:

(	State Department of Transportation Hveem or Marshall designed asphalt mixture with the same maximum size aggregate as the specified grading.  Meet the requirements for the location and type of facility being constructed as designated by the current State Department of Transportation specification.  Submit the aggregate quality, gradation requirements, and mixture criteria for the asphalt concrete mix.

INCLUDE THE FOLLOWING

$$403.03F

403.03(a).  Add the following:

Do not use mixes with over 15 percent recycled asphalt pavement in the top lift.

$$403.03D

403.03(b).  Add the following after the first sentence:

Submit all job-mix formula materials and information to the EFLHD Central Laboratory in Sevierville, Tennessee, with a copy to the CO as directed.

$$403.03C

403.03(b).  Add the following:

For State Department of Transportation mixes, submit a job-mix formula that is currently approved and has been tested by the State within a year of the date of intended use.  Include documentation from a State Department of Transportation official certifying that it is an approved State mix.

$$403.03E

403.03(c).  Add the following:

Allow a minimum of 21 calendar days for verification of each job-mix formula after receipt of all materials and information at the EFLHD Central Laboratory.

$$403.13A

403.13.  Add the following:

Begin paving operations at the furthest location from the asphalt plant and proceed towards the plant.

$$409.00A

Section 409.—ASPHALT SURFACE TREATMENT

Revised 2 October 2005

INCLUDE THE FOLLOWING

$$409.07A

  - Delete the subsection.

$$409.14A

409.14.  Delete the second paragraph and substitute the following:

Measure asphalt surface treatment (including both asphalt and aggregate) by the square yard (square meter).

$$412.00A

Section 412.—ASPHALT TACK COAT

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR CUT-BACKS

$$412.01A

412.01.  Add the following:

Tack coat rapid-curing cut-back asphalt grade is designated as shown in AASHTO M 81.

$$412.02A

412.02.  Add the following:

Cut-back asphalt							702.02

$$412.02B

412.02.  Add the following:

INCLUDE THE FOLLOWING FOR EMULSIFIEDS

$$412.02C

Tack coat emulsified asphalt grade is designated as (ASK MATERIALS ENGINEER FOR SPECIFIC GRADE)

INCLUDE THE FOLLOWING FOR CUT-BACKS

$$412.02D

Tack coat rapid-curing cut-back asphalt grade is designated as (ASK MATERIALS ENGINEER FOR SPECIFIC GRADE)

$$501.00A

Section 501.—RIGID PAVEMENT

Revised 8 May 2005

INCLUDE THE FOLLOWING FOR COLORED SEALANT, AS APPROPRIATE

$$501.02A

501.02.  Add the following:

$$501.02B

Furnish joint sealant material conforming to Subsection 712.01(e) that is a (insert color) color matching the color of the existing pavement.

$$501.02C

Furnish joint sealant material conforming to Subsection 712.01(f) that is a (insert color) color matching the color of the existing pavement.

INCLUDE THE FOLLOWING FOR STEEL PLATES, $$501.14B IS USED

$$501.02D

Furnish steel plates and keep available on the project for emergency use.

INCLUDE THE FOLLOWING FOR ACCELERATED FULL-DEPTH REPLACEMENT

$$501.03A

501.03.  Add the following:

Accelerated Full-depth Patching.  Design the concrete mix according to Subsection 552.03 and conform to Table 501-1a.  Make test specimens according to AASHTO T 23, except that specimens shall remain in molds until tests are conducted after a 7-hour cure.

Table 501-1a

Rigid Pavement Composition

| Water/Cement Ratio (maximum) | Temperature of Concrete | Slump | Air Content (%) | Aggregate Size (AASHTO M 43) | 7-Hour Minimum Compressive Strength |
| --- | --- | --- | --- | --- | --- |
| 0.42 | 70±20 oF (20±10 oC) | 5.0±0.75 inches (120±20 mm) | 5½±1½ | No. 57 | 1,200 psi (8 Mpa) |

INCLUDE THE FOLLOWING FOR COLORED PAVEMENT

$$501.03B

501.03 Add the following:

Pavement Containing Color. Prepare 6-foot by 6-foot by 4-inch (2 by 2-meter by 10 centimeter) test panels at an area near the project designated by the CO.  Do not begin concrete pavement work until the CO inspects and approves the appearance of the test panels and the concrete mix design 28 calendar days after the test panels are constructed.  The use of high range water reducer or accelerator in the test panel is prohibited.

INCLUDE THE FOLLOWING FOR FULL-DEPTH REPLACEMENT OR SMALL QUANTITY OF RIGID PAVEMENT (SEE $$501.12A)

$$501.11A

501.11.  Add the following to the first paragraph:

Seal joints within 5 calendar days after patching to prevent spalling.

$$501.12A

501.12.  Add the following:

For full depth replacement or small individual areas of rigid pavement (less than (insert quantity, to be determined during design & review) square yards (square meters)), meet the requirements of (c) below.

# INCLUDE THE FOLLOWING IF APPLICABLE

$$501.13A

501.13.  Add the following:

Schedule the patching operation so that all areas where the pavement has been removed are repaired during the same work period and the roadway opened to traffic according to Section 156.  Complete all concrete operations sufficiently before opening the lane to traffic to allow the concrete to have attained sufficient strength to support traffic according to Subsection 501.14.  In case of emergency, temporarily fill and plate the repair areas according to Subsection 501.14.

INCLUDE THE FOLLOWING FOR ACCELERATED FULL-DEPTH REPLACEMENT

$$501.14A

501.14.  Add the following:

For accelerated full-depth patches, do not allow traffic on new pavement until the minimum compressive strength has reached 1,200 pounds per square inch (8 MegaPascals) according to AASHTO T 22.

INCLUDE THE FOLLOWING, IF APPLICABLE

$$501.14B

501.14  Add the following:

If an emergency or unforeseen circumstance prevents the completion of a pavement patch before opening the roadway, backfill and compact the excavation with aggregate base and cover with a steel plate so that the lane can be immediately opened to traffic.  At the beginning of the next day's work, completely remove the aggregate, in a manner which will not disturb the subgrade or any dowels, load transfer tie bars, or load transfer assemblies which may have been previously placed.

Place steel plates over concrete patches only if the concrete has not developed sufficient strength as determined by the CO.

INCLUDE THE FOLLOWING FOR ACCELERATED FULL-DEPTH REPLACEMENT

$$501.15A

501.15.  Add the following:

Field Control for Accelerated Full-Depth Patching.  Conduct tests for concrete compressive strength, and gradation and moisture control of coarse and fine aggregate.  Should the mix be of a questionable nature or the previous patches show poor performance, the CO may require that test cylinders be made, cured according to Subsection 552.15, and tested for a 7-hour minimum compressive strength of 1,200 pounds per square inch (8 MegaPascals).  The minimum test frequency for slump and air content will be 1 per 20 cubic yards (15 cubic meters).  Conduct compressive strength tests as required by the CO.  Conduct tests for gradation and moisture content daily before production.  Concrete compressive strength will be evaluated under Subsection 106.05.  The maximum pay factor for concrete compressive strength will be 1.0.

INCLUDE THE FOLLOWING IF CONCRETE QUANTITY < 250 YD3 (190 m3)

$$501.15B

501.15.  Delete the third paragraph, the last sentence in both (a) and (b), and all of (c).  Substitute the following for the third paragraph:

Concrete compressive strength, pavement thickness, and pavement smoothness, will be evaluated under Subsection 106.04.  Determine pavement smoothness according to Subsection 501.12.  See Table 501-3 for minimum sampling and testing requirements for compressive strength and pavement thickness.

$$502.00A

Section 502.—RIGID PAVEMENT RESTORATION

Revised 8 May 2005

$$502.02A

502.02.  Add the following:

INCLUDE ONE OF THE FOLLOWING FOR COLORED SEALANT, AS APPROPRIATE

$$502.02B

Furnish joint sealant material conforming to Subsection 712.01(e) that is a insert color color matching the color of the existing pavement.

$$502.02C

Furnish joint sealant material conforming to Subsection 712.01(f) that is a insert color color matching the color of the existing pavement.

INCLUDE THE FOLLOWING IF PLATES ARE NEEDED

$$502.02D

Furnish steel plates and keep available on the project for emergency use.

$$502.05A

502.05.  Add the following:

Schedule the patching operation so that all areas where the pavement has been removed are repaired during the same work period and the roadway opened to traffic according to Section 156.  Complete all concrete operations sufficiently before opening the lane to traffic to allow the concrete to have attained sufficient strength to support traffic according to Subsection 502.11.  In case of emergency, temporarily plate the repair areas.

INCLUDE THE FOLLOWING FOR CRACK SEALING

$$502.06A

502.06(a).  Delete the first two sentences and substitute the following:

The CO will inspect joints in the existing concrete pavement after removal of the existing asphalt overlay and will designate those joints or cracks to be cleaned and sealed.

Clean expansion joints to a depth of 2 inches (5 centimeters).  Clean longitudinal joints and transverse joints to a depth of 1.5 inches (4 centimeters).

Fill designated joints and cracks 0.75 inches (2 centimeters) or less in width with a poured joint filler.  Fill joints and cracks over 0.75 inches (2 centimeters) in width with a sand-asphalt mixture.  Reseal joints immediately after cleaning.

INCLUDE THE FOLLOWING, IF APPLICABLE

$$502.11A

502.11  Add the following:

If an emergency or unforeseen circumstance prevents the completion of a pavement patch before opening the roadway, backfill and compact the excavation with aggregate base and cover with a steel plate so that the lane can be immediately opened to traffic.  At the beginning of the next day's work, completely remove the aggregate, in a manner which will not disturb the subgrade or any dowels, load transfer tie bars, or load transfer assemblies which may have been previously placed.

Place steel plates over concrete patches only if the concrete has not developed sufficient strength as determined by the CO.

$$551.00A

Section 551.—DRIVEN PILES

Revised 25 January 2005

INCLUDE THE FOLLOWING IF REQUIRED BY GEOTECH (ASK GEOTECH)

$$551.05A

551.05.  Add the following:

After completing the static load test, install instruments on the pile.  Strike the pile 50 to 100 blows with the driving hammer while the dynamic measurement is made.  Operate the pile hammer at normal operating temperature before it is used to restrike the pile.  After the dynamic measurement of pile capacity, the CO will remove the instruments from the pile.

$$551.08A

551.08.  Add the following:

Drive permanent piles a minimum of 40 calendar days after completion of the approach fills at the following locations:

1.	________________________________

2.	________________________________

3.	________________________________

$$551.11A

551.11. Delete the first paragraph and substitute the following:

Pile Load Tests.  Dynamic load testing is required.

$$552.00A

Section 552.—STRUCTURAL CONCRETE

Revised 2 October 2005

INCLUDE THE FOLLOWING FOR COLORED CONCRETE

$$552.02A

552.02.  Add the following:

Concrete coloring agents				711.05

$$552.03A

552.03.  Add the following:

All concrete in [insert item description] will be integrally colored by adding a concrete coloring agent.  The colored concrete after curing shall match as closely as practicable to Standard Color Chart Number [insert #] of Federal Specification 595B.

Prepare 5 square textured test panels with each panel being 1-foot (0.3 meters) square.  Determine coloring agent batch amounts by weight.  The maximum amount of coloring agent is not to exceed 10 percent of the weight of the cement. Use coarse and fine aggregates and cement as delivered on the project at the job mix rates with variable quantities of coloring agent as directed by the CO.   Provide additional mixing time as recommended by the manufacturer. Give the test panels a [insert type] finish in accordance with the contract requirements.

After the test panels have had at least 2 weeks exposure to sun, the CO will select a test panel to serve as a guide for the colored concrete.  Use the same rate of coloring agent used in the selected panel on all relative subsequent work.   Include the approved amount of coloring agent in the concrete mix design submittal.

Use an approved form release agent which will produce a minimum of staining, air holes, and hydration discoloration.

INCLUDE THE FOLLOWING IF APPLICABLE

$$552.03B

552.03(g).  Add the following:

$$552.03C

Use Type I or II portland cement in all concrete.

$$552.03D

Use Type I, II, or III portland cement in all Class P concrete.

INCLUDE THE FOLLOWING FOR BRIDGE DECK CONCRETE, EXCEPT WHEN REASONS ARE NOTED FOR EXCLUDING HIGH RANGE WATER REDUCERS

$$552.03F

552.03(v).  Add the following:

Provide Class (insert class) concrete with a minimum 28-day compressive strength of (insert strength) pounds per square inch (MegaPascals).

INCLUDE THE FOLLOWING IF APPLICABLE

$$552.09A

552.09(b)(4).  Add the following:

Provide for compressive strength testing of the concrete cylinders by an independent laboratory, qualified to perform the testing, and as approved by the CO.

INCLUDE THE FOLLOWING FOR CONCRETE REPAIRS

$$552.11A

552.11(a).  Add the following to the third paragraph:

Dispose of mortar, debris, foreign material and excess concrete according to Section 203.

552.11(a).  Add the following:

Before placing new concrete, clean the existing concrete surface and any exposed reinforcement of all loose material, dust, etc., by shotblasting and thoroughly flushing with clean water under pressure or compressed air.  If compressed air is used provide a filter in the air line to ensure that the air is oil-free.

If there is an interval of more than 24 hours between cleaning of the sound concrete surface and placement of new concrete, or there are previously prepared concrete surfaces that have been contaminated by any substance detrimental to good bonding, clean or remove the concrete.

Saw cut approximately 0.75 inches (2 centimeters) deep along all boundaries of the repair areas.  Point saw cuts, extending beyond the limits of repair areas, flush with the surface with portland cement or epoxy mortar.

Where the bond between existing concrete and reinforcing steel has been destroyed, remove the concrete adjacent to the steel to a depth that will permit new concrete to bond to the entire periphery of the exposed steel.  Provide a minimum of 0.75 inches (2 centimeters) clearance behind the steel.

Remove and replace all badly deteriorated reinforcing steel.

After removal of deteriorated or unsound concrete, shotblast exposed structural steel, reinforcing steel, and any concrete surfaces which will be in contact with repair material until free of rust and foreign material.  Clean the sound concrete surface by flushing with clean water from a high pressure water jet or compressed air.

INCLUDE THE FOLLOWING FOR CONCRETE REPAIRS PATCHES  < 5 inches (12.5 centimeters) DEEP

$$552.11B

For all vertical and overhead concrete repairs, and those horizontal repairs to areas less than 5 inches (12.5 centimeters)  in depth, use a high strength concrete patching compound placed according to the manufacturer's recommendations.

INCLUDE THE FOLLOWING FOR CONCRETE REPAIRS PATCHES > 5 inches (12.5 centimeters) DEEP, MUST SPECIFY CLASS

$$552.11C

For all other repairs, apply a bonding coat of a 2-component epoxy resin binder to the surfaces of the sound existing concrete immediately before placing new concrete against it.  Follow the manufacturer's recommendations for the epoxy resin binder.  Repair areas using Class (insert class) concrete.

INCLUDE THE FOLLOWING FOR CONCRETE CURBS ON THE STRUCTURE

$$552.11D

552.11(f).  Delete the first sentence and substitute the following:

(f)  Concrete railings, parapets, and curbs.

INCLUDE THE FOLLOWING FOR CONCRETE REPAIRS

$$552.19A

552.19.  Add the following:

Materials used for concrete repair will be evaluated under Subsection 106.03.

$$554.00A

Section 554.—REINFORCING STEEL

Revised 8 May 2005

INCLUDE THE FOLLOWING FOR REINFORCING STEEL

$$554.08A

554.08.  Delete the first sentence of the first paragraph and substitute the following:

Place, fasten, and support the bars according to the CRSI Manual of Standard Practice.  Use precast concrete blocks or metal supports.

INCLUDE THE FOLLOWING FOR MECHANICAL REBAR SPLICES

$$554.09A

554.09.  Add the following:

Mechanical splices, where allowed, may be made using the following coupler devices:  “Bar-Lock MBT” coupler, the “OS Splice Clip” as produced by Splice Sleeve North America, the   “Bar-Grip System” by AFC Dayton Barsplice, or the “Quick-Wedge” as produced by Erico Concrete Construction Products, or an approved alternative.  Approval by the CO of an alternate coupler design will be based upon technical data, including test results, and other necessary proof of satisfactory performance submitted by the manufacturer.

The criteria for acceptance of alternate coupler design is as follows: the total slip of the reinforcing bars within the splice sleeve after loading in tension to 30 pounds per square inch (MegaPascals) and relaxing to 3 pounds per square inch (MegaPascals) shall not exceed 0.01 inches (millimeters) for reinforcing bars No. 14 (43) or smaller as measured between gage points clear of the splice sleeve.  Mechanical couplers used in the superstructure slab must be butt type splices only.

Use only epoxy coated mechanical couplers for joining epoxy coated reinforcing.  Splice sleeves shall have a clear coverage of not less than 1.75 inches (centimeters) measured from the surface of the concrete to the outside face of the sleeve.  Do not place slab bar mechanical splices adjacent to each other.

All splicing procedures shall be in accordance with the manufacturer=s standard equipment, jigs, clamps, and other required accessories.  Use procedures in making mechanical butt splices as recommended by the manufacturer and approved by the CO.

$$555.00A

Section 555.—STEEL STRUCTURES

Revised 25 January 2005

INCLUDE THE FOLLOWING IF BEARINGS ARE PAID FOR SEPARATELY

$$555.21A

555.21.  Delete the second sentence and substitute the following:

The quantity of structural steel will include metal items incidental to the structure and required by the contract such as castings, steel plates, anchor bolts and nuts, pins and nuts, expansion dams, roadway drains and scuppers, weld metal, bolts embedded in concrete, cradles and brackets, posts, conduits and ducts, and structural shapes.

$$560.00A

Section 560.—REMOVAL OF CONCRETE BY HYDRODEMOLITION

Revised 8 May 2005

$$560.03A

560.03.  Add the following:

Lay out a grid and take elevations at each grid point according to Subsection 552.20.

$$560.09A

560.09.  Add the following:

Determine the volume of concrete required to overlay areas where hydrodemolition is used to remove the concrete as follows:

(a)  Establish a grid, measuring 3 feet (1 meter) on each side, over the entire area.  Lay out the grid as follows:

(1)  Establish transverse grid lines by placing the first grid line transverse to the structure centerline and placing the remaining transverse grid lines parallel to the first at a 3-foot (1-meter) spacing.

(2)  Establish longitudinal grid lines by placing the first longitudinal grid line parallel to the curb line and 1.5 feet (0.5 meters) from the face of the curb.  Place the remaining longitudinal grid lines parallel to the first line at 3-foot (1-meter) intervals.

(b)  Following concrete surface preparation, take elevations at each grid point in the presence of the CO.

(c)  Following concrete curing, reproduce the same grid and take elevations at each grid point.

(d)  The quantity of concrete will be determined from the following formula:

V = ATd in cubic yards (meters), where:

V  =	Quantity of concrete in cubic yards (meters).

AT =	Total deck area in square yards (meters).

d  =	Average depth, in yards (meters), of removal determined by calculating the difference in elevation at each grid point in the deck surface area.

$$562.00A

Section 562.—TEMPORARY WORKS

Revised 8 May 2005

INCLUDE THE FOLLOWING

$$562.02A

562.02.  Delete the second sentence and substitute the following:

Furnish factory fabricated components of vertical shoring towers complying with the Certification Program for Bridge Temporary Works (FHWA-RD-93-033).

$$562.03A

562.03.  Delete the third from the last paragraph and substitute the following:

Do not use deck overhang form brackets for girder bridges that require holes to be cast or drilled into the girder webs.

INCLUDE THE FOLLOWING IF STAY-IN-PLACE DECK FORMS ARE ALLOWED

$$562.06A

562.06.  Add the following:

Stay-in-place deck forms.  The use of metal stay-in-place deck forms is permitted.  Fabricate permanent steel bridge deck forms and supports from steel conforming to ASTM A 653 coating designation G165.

When metal stay-in-place forms are used to construct the deck slab, remove 2-foot by 2-foot  (0.6 by 0.6-meter) sections of the metal forms to create inspection ports.  Locate the inspection ports in accordance with the following or as directed by the CO:

(a)  Locate inspection ports transversely as close to the exterior beam as practical on the low side of the superelevation or on each side of a crown;

- Locate inspection ports longitudinally near each abutment, near each pier, and near the middle of each span.

INCLUDE THE FOLLOWING

$$562.07A

562.07.  Delete this Subsection and substitute the following:

562.07  Maintenance and Inspection.  Inspect and maintain temporary works in an acceptable condition throughout the period of use.

In the presence of the CO, perform an in-depth inspection of temporary works not more than 24 hours before beginning each concrete placement or before allowing people to enter a cofferdam or excavation support structure.  Inspect other temporary works at least once a month to ensure they are functioning properly.  Use a registered professional engineer to inspect cofferdams, shoring, support of excavation structures, and support systems for load tests before loading.

Furnish written results of the inspections to the CO before placing concrete, allowing people to enter a cofferdam or excavation support structure, or loading temporary works.  Include a certification that the system meets the requirements of the contract and drawings.

Clearly mark the capacity of factory fabricated components of vertical shoring towers according to the Certification Program for Bridge Temporary Works (FHWA-RD-93-033).  Make inspections and certifications for factory fabricated components of vertical shoring towers according to the Certification Program for Bridge Temporary Works (FHWA-RD-93-033).

$$563.00A

Section 563. – PAINTING

Revised 18 January 2006

$$563.03A

563.03.  Add the following:

SSPC Painting Contractor Certification Program (PCCP) Requirements.   All contractors and subcontractors that perform surface preparation, paint application, and any related work involving containment and collection of surface preparation debris, disposal of surface preparation debris, and a worker health protection program (including decontamination facilities) shall be certified by the Society for Protective Coatings (formerly Steel Structures Painting Council (SSPC)) to the requirements of SSPC-QP 1.  In addition, all contractors and subcontractors engaged in lead paint removal and any other related work shall be certified by the SSPC to the requirements of SSPC-QP 2.  Contractors and subcontractors shall be certified at time of bid, must remain certified for the respective work for the duration of the project and submit documentation of certification at time of bid.  If a contractor’s certification expires, the company will not be allowed to perform any work until the certification is reissued.  Requests for extension of time for any delay to the completion of the project due to inactive certification will not be considered and liquidated damages will apply.  Notify the CO of any change in contractor certification status.

$$601.00A

Section 601.—MINOR CONCRETE STRUCTURES

Revised 25 January 2005

INCLUDE THE FOLLOWING IF STATE MIXES ARE ALLOWED

$$601.03A

601.03.  Delete the first sentence and substitute the following:

Conform to Table 601-1 or furnish a concrete mix used locally by either a Federal or State agency for the construction of minor concrete structures, that also meets the minimum 28-day compressive strength requirement of Table 601-1.

$$602.00A

Section 602.—CULVERTS AND DRAINS

Revised 2 October 2005

INCLUDE THE FOLLOWING IF FLH PIPE POLICY, PDDM 7.3.C.14, REGARDING CORROSION AND ABRASION APPLIES.  DELETE PIPE MATERIALS THAT DO NOT MEET REQUIREMENTS FOR CORROSION AND ABRASION.

$$602.03A

602.03.  Add the following:

Furnish culvert pipe from the following groups:

Aluminum-alloy corrugated pipe, Type I or II, (insert gage from fill/height tables) gage minimum

Aluminum-alloy spiral rib pipe, Type I or II, (insert gage from fill/height tables) gage minimum

Asphalt–coated pipe (steel)

Concrete-lined corrugated steel pipe

Fiber-bonded asphalt coated steel pipe

Invert-paved corrugated steel pipe

Metallic coated corrugated steel pipe, Type I or II, (insert gage from fill/height tables) gage minimum

Metallic coated spiral rib pipe, Type I or II, (insert gage from fill/height tables) gage minimum

Polymer-coated steel pipe

Plastic pipe

Reinforced concrete pipe,	Class (insert class from fill/height tables, Class II minimum)

INCLUDE THE FOLLOWING FOR BOX CULVERTS

$$602.03B

602.03.  Add the following:

Construct either cast-in-place or precast concrete box culverts.  Construct cast-in-place box culverts according to Section 552.  Submit design drawings and details with supporting calculations for precast concrete box culverts to the CO according to Subsection 104.03.

$$604.00A

Section 604.—MANHOLES, INLETS, AND CATCH BASINS

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR INLET MODIFICATION

$$604.01A

604.01.  Add the following:

This work includes modifying existing inlets.

$$604.03A

604.03.  Add the following:

Adjusting is defined as raising, lowering or shifting the item to meet a new pavement elevation.  Modifying an item is defined as adding additional openings, partial reconstruction, or other structural modifications.

$$605.00A

Section 605.—UNDERDRAINS, SHEET DRAINS, AND PAVEMENT EDGE DRAINS

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR UNDERDRAIN

$$605.02A

605.02.  Delete the first and sixth materials and substitute the following:

Aluminum alloy corrugated pipe, Type III			707.03

Metallic coated corrugated steel pipe, Type III		707.02

$$605.02B

605.02.  Add the following:

Polymer-coated steel pipe					707.08

$$607.00A

Section 607.—CLEANING, RECONDITIONING, AND REPAIRING EXISTING DRAINAGE STRUCTURES

Revised 8 May 2005

# INCLUDE THE FOLLOWING FOR PIPE LINERS

$$607.01A

607.01.  Add the following:

This work includes of lining existing culverts.

# INCLUDE THE FOLLOWING FOR PIPE LINER MATERIALS

$$607.01B

607.01.  Add the following after Subsection 607.01:

607.01A.  Materials.  Conform to the following Sections and Subsections:

INCLUDE THE FOLLOWING FOR CEMENT MORTAR PIPE LINERS

$$607.01C

Portland cement	701.01

Water	725.01

# INCLUDE THE FOLLOWING FOR POLYURETHANE PIPE LINERS

$$607.01D

Furnish a polyurethane pipe liner conforming to:

###### INSERT THE SPECIFICATIONS FOR THE PIPE LINER

INCLUDE THE FOLLOWING FOR CEMENT MORTAR PIPE LINERS

$$607.01E

Furnish a cement mortar pipe lining conforming to AWWA C 602.

Furnish sand meeting the following gradation:

| Sieve Sizes | Percentage Passing |
| --- | --- |
|  | 14 (1.18 mm) | 100 |
|  | 20 (850 m) | 95-100 |
|  | 30 (600 m) | 85-95 |
|  | 40 (300 m) | 15-35 |
|  | 100 (150 m) | 1.5-5 |
|  | 200 (75 m) | 1-3 |
|  | 37.5µm | 0 |

$$607.02A

607.02.  Add the following:

The dry components of the cement mortar shall be 50 percent sand and 50 percent portland cement by weight.

After addition of the water, provide a mortar that is well mixed and will provide a dense, homogeneous lining that will hold firmly against the pipe surface.  Carefully control and keep the water-cement ratio to a minimum.  Allow for any existing moisture on the walls of the pipe.  Premix the mortar by machine for a sufficient length of time to obtain maximum plasticity, or 3 minutes minimum.

# INCLUDE THE FOLLOWING WHEN WATER IS BEING USED

$$607.02B

607.02.  Add the following:

Provide for the control and disposal of any accumulation of water that interferes with construction.

# INCLUDE THE FOLLOWING FOR PIPE LINERS

$$607.06A

607.06.  Add the following after Subsection 607.06:

607.06A.  Pipe Lining.  Remove and dispose all silt, sand, debris, detritus, or other sedimentation or foreign material from within pipe to be lined, and from inlet and outlet areas.  Remove all dirt, rust, tubercles, scale, loose or deteriorated remnants of old lining materials, accumulated water, and all other foreign materials from the interior surface of the pipe before lining.  After cleaning, the interior of the pipe shall present a surface free of all foreign material except nondeteriorated original coating.

Install pipe lining according to the manufacturer's recommendations.  Hand-place cement mortar lining only at sharp bends and special locations where machine placing is impracticable.

Patch holes in the existing pipe with cement mortar before the application of the lining.

Pave existing culvert inverts with cement mortar if they are deteriorated to the extent that an acceptable lining would not be achieved before centrifugal application of linings.  Fill cavities beneath badly deteriorated inverts with concrete, grout, or other method acceptable to the CO.

Close the pipe at both ends to prevent the circulation of air.  After the final pass with the machine, introduce water into the closed section to create a moist atmosphere and keep the lining damp.  Maintain curing for a minimum of 3 calendar days.

$$607.07A

607.07.  Add the following:

Lining materials will be evaluated under Subsection 106.03.  Lining construction will be evaluated under Subsection 106.04.  After curing, drill holes (1 per 50 feet (15 meters)) to verify lining thickness at random locations selected by the CO.  Patch the hole after thickness verification.

$$608.00A

Section 608.—PAVED WATERWAYS

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR DRAINAGE CHUTES

$$608.11A

608.11.  Add the following:

Measure drainage chutes by the foot from the front face of the curb along the flow line of the chute.

$$609.00A

Section 609.—CURB AND GUTTER

Revised 8 May 2005

# INCLUDE THE FOLLOWING FOR GRANITE BRIDGE CURB

$$609.02A

609.02.  Add the following:

Granite bridge curb					620.01(a)

Masonry anchors for bridge curb			717.18

INCLUDE THE FOLLOWING FOR STONE CURB ON DC PROJECTS

$$609.03A

609.03.  Add the following:

Furnish an air-entrained, portland cement concrete dry mix of 1 part cement, 2 parts sand, and 4 parts crushed stone, with just enough water added to the mix to make the mix adhesive.

$$609.04A

609.04.  Delete the second sentence of the first paragraph and substitute the following:

Set stone curb in dry-pack concrete so the curb face and top, are to line and grade.

INCLUDE THE FOLLOWING FOR GRANITE BRIDGE CURB

$$609.04B

609.04.  Add the following after Subsection 609.04:

609.04A.  Granite bridge curb.  On bridges, after the concrete base has set and before the concrete in back of the curb is placed, set the granite bridge curb to line and grade in full mortar beds and full mortar end joints with the anchors in the stone grouted in place.

Grout 2 0.5-inch (1.25-centimeter) diameter, stainless steel anchors into the back of each stone curb.  Pitch the anchor holes downward at approximately 45 degrees, and locate approximately 3 inches (7.5 centimeters) below the top and 12 inches (30 centimeters) from each end.  Furnish anchors with a 3-inch  (7.5-centimeter) square hook on one end and a 3–inch (7.5-centimeter) 45 degree bend on the other end, both pointing downward and separated by a minimum 6-inch (15-centimeter) straight shank.

Brush each stone curb clean and free from loose particles, and thoroughly wetted with clean water before setting.  Carefully lay the stone in a full bed of mortar.  Do not slide the stone on the mortar bed.  Set the curb with full mortar joints and leave all joints smooth and flush.  Hold each stone securely in position by 2 steel anchors.  Carefully place the concrete in back of the curb to avoid disturbing the line or grade of the curb.  Keep exposed faces of the curb free of mortar and cement stains.  Joints in granite bridge curb shall be raked out to a depth of 0.5 inches (1.25 centimeters) and sealed flush with the sealing material.

If a construction joint is required in the curb or sidewalk over a pier or bent, lay out the curb so that a joint in the curb will be opposite the joint in the sidewalk.

$$611.00A

Section 611.—WATER SYSTEMS

Revised 25 January 2005

# INCLUDE THE FOLLOWING FOR ADJUSTING VALVES

$$611.03A

611.03.  Add the following:

Adjust existing valves to the proposed grade.

$$612.00A

Section 612.—SANITARY SEWER SYSTEMS

Revised 25 January 2005

# INCLUDE THE FOLLOWING FOR ADJUSTING VALVES

$$612.03A

612.03.  Add the following:

Adjust existing valves to the proposed grade.

$$617.00A

Section 617.—GUARDRAIL

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR GUARDRAIL POSTS.  SELECT APPROPRIATE MATERIAL

$$617.03A

617.03.  Add the following:

Furnish steel or wood guardrail posts for use with W-beam type guardrail.

INCLUDE THE FOLLOWING FOR B-W PARKWAY GUARDWALLS

$$618.00A

Section 618.—CONCRETE BARRIERS AND PRECAST GUARDWALLS

Revised 8 May 2005

618.02.  Delete the text and substitute the following:

(a)  Portland cement according to Subsection 701.01, except that cement shall be Type I or Type III, AASHTO M85, both white and gray or mixtures of white and gray, including pure mineral oxide pigments for coloring.

(b)  Furnish fine and coarse aggregates according to Subsections 703.01 and 703.02, except that facing aggregates, including both fine and coarse aggregates of the artificial stone facing, shall consist of limestone, quartz, and mica, including silicious stones according to ASTM C 33.

(c)  Furnish a cold applied gray polyurethane sealant meeting the requirements of ASTM C 920, Type S, Grade NS, Class 25.  The joint sealants shall match the color of the false joints.  Furnish backer rod conforming to Subsection 712.01(g).

(d)  Furnish reinforcing steel conforming to Subsection 709.01, AASHTO 31 M, Grade 60 (AASHTO M 31M, Grade 420).  Reinforcing steel bars located less than 2 inches (5 centimeters) from an exposed face, shall be either epoxy coated or galvanized.  Furnish galvanized welded wire fabric.

(e)  Furnish Class A(AE) concrete with air entrained in the mix 6 percent ± 2 percent by volume.  In mixes containing coarse aggregates 0.4 inches or less in size, air entrained shall be 7 percent ± 2 percent by volume.  All concrete shall attain a 28-day minimum compressive strength of 4,000 pounds per square inch (27.6 MegaPascals) according to AASHTO T 22.  Take a sufficient number of concrete cylinder samples for 7, 14, and 28-day compressive strength tests.

(f)  Furnish non-corrosive (galvanized or epoxy coated) bolts, inserts, and ties.

(g)  Furnish bedding material conforming to Subsection 703.03 for AASHTO M 43, size No. 57.

618.05.  Add the following before the first paragraph:

Furnish a guardwall with a simulated stone surface on both sides and ends of the guardwall and with an integral coping.

Submit the supplier's qualifications and certifications according to Subsection 104.03.  Furnish a certification from the supplier stating that they have experienced personnel, physical facilities, established quality control procedures, and management capability to produce the required segments without delay to the project.  The precast guardwall supplier shall have a minimum of 5 years experience in manufacturing architectural and structural precast concrete units.

Construct precast concrete mowing strips and false joints that are uniform gray in color.

Provide capstones that span the entire width of the wall.

618.05(a).  Delete the first sentence and substitute the following:

A full size sample guardwall is located at (insert guardwall location).

618.05(c).  Delete the fourth sentence and substitute the following:

Prepare the foundation, compacting the bedding material with a minimum of 3 passes of a vibratory roller to ensure maximum consolidation, and place the sections.

618.08.  Add the following:

The CO will accept precast segments on the basis of material tests on the quality of the concrete and the CO's visual inspection.  Perform all necessary sampling and testing.

$$619.00A

Section 619.—FENCES, GATES, AND CATTLE GUARDS

Revised 8 May 2005

INCLUDE THE FOLLOWING FOR TEMPORARY FENCE

$$619.06A

619.06.  Delete the first paragraph and substitute the following:

When necessary, construct temporary fence to keep livestock, pedestrians and traffic off the road being constructed or away from trees requiring protection.  Temporary fence is intended to remain in place only during the construction of the project or until the fence is directed to be removed.  At the completion of the project, remove fence and dispose of legally off Government property.

619.06.  Add the following after the first paragraph:

Install fence as shown on the drawings or as directed by the CO.  Use a conventional metal "T" or "U" post spaced every 7 to 10 feet (2 to 3 meters).  Drive posts 12 to 18 inches (30 to 45 centimeters) into the ground.  Secure the fence to the post using 3 wire ties.

$$620.00A

Section 620.—STONE MASONRY

Revised 25 January 2005

# INCLUDE THE FOLLOWING FOR STONE MASONRY

$$620.03A

620.03.  Add the following:

Masonry is designated as Class (select from 620.01) masonry with a (select a finish) RF finish for stone masonry (item description).

$$622.00A

Section 622.—RENTAL EQUIPMENT

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR MOWING ON MAJOR GRADING PROJECTS

$$622.01A

622.01.  Add the following:

This work includes providing and operating equipment for mowing.

$$622.02A

622.02.  Add the following after the first paragraph:

Furnish mowers with a minimum rating of 12 Horsepower (9 kilowatts) and equipped with necessary accessories for mowing.

$$624.00A

Section 624.—TOPSOIL

Revised 25 January 2005

INCLUDE THE FOLLOWING ON NPS PROJECTS

$$624.04A

624.04.  Add the following after the second paragraph:

Where topsoil will be placed on slopes on which the character of the subsoil will not blend with the topsoil, work the topsoil into the subsoil to eliminate any slip-plane between the 2 materials and leave a sufficient cover of topsoil to ensure germination of the seed.

$$625.00A

Section 625.—TURF ESTABLISHMENT

Revised 8 May 2005

# INCLUDE THE FOLLOWING

$$625.01A

625.01.  Add the following:

The work does not include areas previously protected by soil erosion control measures according to Section 157, and upon which permanent suitable vegetation has started growth.

INCLUDE THE FOLLOWING ON NATCHEZ TRACE PROJECTS AND OTHER PROJECTS ONLY IF APPLICABLE.  ALSO INCLUDE SCRS FOR 713.19

$$625.02A

625.02.  Add the following:

Pesticide					713.19

INCLUDE THE FOLLOWING.  REVISE RATES

$$625.06A

625.06.  Add the following:

Apply limestone and fertilizer at the following rates:

Item	Rate (pounds per acre) (kilograms/hectare)

Agricultural Limestone (85 percent CaCO3)	704 (3470)

Fertilizer	3094 (790)

INCLUDE THE FOLLOWING FOR SEEDING.  REVISE SEED, AMOUNT AND SEASONS

$$625.07A

625.07.  Add the following:

Apply seed at the rates for each season as follows:

Seeding Seasons and

Name of Seed	Rates (pounds per acre) (kilograms/hectare)

March and April

Ryegrass, Italian, perennial	15 	(16.8)

Bermuda grass, common (hulled)	10	(11.2)

Fescue, Tall, Kentucky 31	25	(28)

Total Seed 	50	(56)

May through August

Ryegrass, Italian, perennial	25	(28)

Bermuda grass, common (hulled)	15	(16.8)

Total Seed	  40	(44.8)

September and October

Ryegrass, Italian, perennial	10	(11.2)

Fescue, Tall, Kentucky 31	25	(28)

Clover, Crimson, inoculate	15	(16.8)

Total Seed	50	(56)

November through February

Ryegrass, Italian, perennial	21	(23.5)

Bermuda grass, common (hulled)	21	(23.5)

Fescue, Tall, Kentucky 31	25	(28)

Clover, Crimson, inoculated	15	(16.8)

Total Seed	 82	(91.8)

INCLUDE THE FOLLOWING IF SPECIFIC MULCH TYPES ARE REQUIRED

$$625.08A

  - Add the following:

Use (insert type from 713.05) mulch.

INCLUDE THE FOLLOWING IF MULCH RATES OTHER THAN THE FP ARE REQUIRED.  REVISE MULCH TYPE AND RATES

$$625.08B

625.08.  Add the following:

Apply mulch at the following rates:

Mulch	Rate (pounds per acre) (kilograms/hectare)

Straw	4992 (5595)  (1 to 2 inch (2.5 to 5 centimeter) mat)

INCLUDE THE FOLLOWING FOR SUPPLEMENTAL FERTILIZER APPLICATIONS.  REVISE THE FERTILIZER RATE AS DICTATED BY THE MANUFACTURER OR REQUIRED BY SOIL ANALYSIS

$$625.09A

625.09.  Delete the last sentence and substitute the following:

Apply supplemental fertilizer at a rate of 401 pounds per acre (kilograms/hectare).  Apply supplemental seed at the same rate as the initial seeding.  Apply supplemental mulch at the same rate as the initial mulching and hold in place with a stabilizing emulsion tackifier.

INCLUDE THE FOLLOWING FOR PESTICIDE

$$625.09B

625.09.  Add the following:

Apply pesticide at the first sign of armyworm infestation.  Apply pesticide at the rate specified by the manufacturer by spraying with sufficient water for complete coverage.  Agitate the mixture while spraying.  Repeat application to control armyworms that reappear.

$$626.00A

Section 626.—PLANTS, TREES, SHRUBS, VINES, AND GROUND COVERS

Revised 8 May 2005

INCLUDE THE FOLLOWING IF REQUIRED

$$626.02A

626.02.  Add the following:

Agricultural limestone	713.02

Backfill	704.03

INCLUDE THE FOLLOWING FOR PLANTING SEASONS.  REVISE SEASONS

$$626.03A

626.03.  Add the following:

Plant material during the following planting seasons:

Deciduous Material:	October 15 to April 30

Evergreen Material:	Spring - March 15 to May 15

Fall - August 15 to November 15

The CO may extend or reduce the above periods according to weather and soil conditions.

INCLUDE THE FOLLOWING FOR PLANTS/TREES ON NPS PROJECTS

$$626.04A

626.04.  Add the following:

Submit the following for approval:

(a) Fertilizer.  1 sample packet of each type;

(c) Backfill.  1-cubic foot (0.03 cubic meter) sample, with testing certification that the  material is weed free.

The CO may substitute or delete specified material subject to the soil conditions encountered.

$$626.06A

626.06(b).  Delete the text and substitute the following:

Excavate planting pits to a depth such that the rootball rests on an undisturbed soil pedestal as shown on the plans and set so that the rootball is 2 to 3 inches (5 to 7.5 centimeters) above the grade for trees and 1 to 2 inches (2.5 to 5 centimeters) above grade for shrubs.  Crown the bottom so that the bottom slopes away from the roots in all directions.

Loosen soil at the sidewalls and bottom of the plant pit to a depth of 6 inches (15 centimeters) before setting the plant.

Do not leave any planting holes open overnight.

$$626.07A

626.07(b).  Delete the fourth and fifth sentences and substitute the following:

Backfill around the plant ball to half the depth of the ball, tamping at 6-inch (15-centimeter) intervals to fill voids around the ball and thoroughly water.

626.07(b).  Delete the last sentence and substitute the following:

Do not remove or pull the burlap and twine out from under the ball.  Backfill the remainder of the pit and tamp around the root ball.

626.07(c) Add the following after the first sentence:

Score the rootball to a depth of 1 inch (2.5 centimeters) along the entire side equally on 4 sides.

$$626.08A

626.08. Delete the Subsection and substitute the following:

626.08  Fertilizing.

Apply fertilizer at the following rates:

Trees	34 cubic inches (550 cubic centimeters) per tree

Shrubs	17 cubic inches (275 cubic centimeters)per shrub

Vine and Groundcovers	1.84 cubic inches (330 cubic centimeters) dry fertilizer per square foot (meter) of ground

When the pit is ½ full, place fertilizer according to the manufacturer’s recommendations.

$$626.09A

626.09.  Delete the first paragraph and substitute the following:

Saucer shape the backfill 3 inches (7.5 centimeters) above the existing grade for shrubs and 6 inches (15 centimeters) for trees, for a diameter equal to that of the planting pit, to catch and retain water.  Build up the backfill in holes on a slope on the lower side only to catch and hold water.  Do not cover the tops of the rootballs with backfill.

626.09.  Delete the last sentence of the first paragraph and substitute the following:

Saturate all backfill material in the pits at each watering.

Apply water only by open-end hose at a very low pressure to avoid creating air pockets in the soil and injuring the roots.

$$626.10A

626.10.  Delete the first sentence and substitute the following:

Support trees with stakes driven at equal spaces around the outside perimeter of the tree pit and to sufficient depth to hold trees firmly.  Do not drive stakes through the rootball.

Cut pieces of hose long enough to extend 2 inches (5 centimeters) past the trunk of the tree when wrapped around.  Place the hose around the trunk just below the first lateral branch for deciduous trees and halfway up the height of evergreen trees as shown on the plans.  Thread a double strand of wire through the hose and pull both ends horizontally beyond each stake by 3 feet (1 meter).

Provide approximately a 1 to 3-inches (2.5 to 7.5-centimeters) sway in the tree with the stakes in the vertical position after the guying is attached.

Stake trees no later than 48 hours after planting.

$$626.11A

626.11.  Delete the fourth sentence and substitute the following:

Do not cut the main leader.  All cuts to side branches are to be just outside the branch collar (the swollen base of the branch) to encourage wound closure.  Do not use tree wound dressing.

$$626.12A

626.12.  Add the following:

Apply mulch to cover the limits of the individual saucer areas of each individual plant to a loose measurement depth of 4 to 6 inches (10 to 15 centimeters) at the limits of the saucer area.  Feather the depth back to 0 inches (centimeters) at the trunk.

$$626.14A

626.14.  Add the following:

Replace plants that have died back in the crown 25 percent beyond the normal pruning line, or where the main leader has died back, with the same size and species as the original.

Final acceptance for trees and shrubs will be given by the CO at the end of the establishment period once the following items are completed:

(a)  All plant materials that have died or are determined to be unacceptable are replaced.

(b)  All deficiencies in work, and damage to structures and grounds, are corrected.

(c)  All stakes and guys are removed.

$$627.00A

Section 627.—SOD

Revised 8 May 2005

INCLUDE THE FOLLOWING.  SELECT ONE SOD TYPE OR INSERT TYPE REQUIRED.  ALSO $$713.10A OR B

$$627.03A

627.03.  Add the following:

$$627.03B

Furnish Bermuda grass or Tall Fescue, Kentucky 31 sod.

# INCLUDE THE FOLLOWING.  REVISE SOD SEASONS

$$627.03C

Lay sod between April 1 and September 30.

INCLUDE THE FOLLOWING

$$627.05A

627.05.  Delete the last sentence of the first paragraph and substitute the following:

Grade the finished surface of the sod bed to a smoothness comparable to results obtained by hand raking, leaving it clean and free of stones over 1 inch (2.5 centimeters)  in size, sticks, stumps, other debris and depressions that might interfere with proper placement or subsequent growth.

Apply fertilizer and agricultural limestone at the same rates specified in Section 625.

$$627.06A

627.06.  Add the following:

Thoroughly water the sod, immediately after installation, to a depth of 4 inches (10 centimeters).

$$628.00A

Section 628.—SPRIGGING

Revised 25 January 2005

# INCLUDE THE FOLLOWING.  REVISE THE SPRIG TYPE & SEASONS AS REQUIRED

$$628.03A

628.03.  Add the following:

Furnish Bermuda grass sprigs.

$$628.03B

Sprig between April 1 and August 31.

$$628.05A

628.05.  Add the following:

Apply fertilizer, mulch, and agricultural limestone at the same rates specified in Section 625.

$$633.00A

Section 633. — PERMANENT TRAFFIC CONTROL

Revised 10 December 2008

INCLUDE THE FOLLOWING FOR SIGN PANELS

$$633.01A

633.01.  Delete the second paragraph and substitute the following:

Sign panels are designated as plywood, aluminum, extruded aluminum, steel, plastic, or fiberglass reinforced plastic.

INCLUDE THE FOLLOWING FOR SIGNS ON NPS PROJECTS

$$633.03A

633.03.  Add the following after the first sentence:

Furnish signs also meeting the requirements of the National Park Service UniGuide Sign System Manual (see http://www.nps.gov/hfc/acquisition/uniguide.htm).

INCLUDE THE FOLLOWING FOR SIGNS AND/OR POSTS (AND INCLUDE $$633.03C AND/OR $$633.03D).  INCLUDE THE FOLLOWING IF $$633.03E IS USED.

$$633.03B

633.03.  Add the following:

INCLUDE THE FOLLOWING FOR SIGN PANELS IF A SPECIFIC SIGN PANEL MATERIAL IS REQUIRED — DELETE THE HIGHLIGHTED MATERIAL TYPES THAT ARE NOT ACCEPTABLE

$$633.03C

Furnish plywood, aluminum, extruded aluminum, steel, plastic, or fiberglass reinforced plastic sign panels.

INCLUDE THE FOLLOWING FOR POSTS IF A SPECIFIC POST MATERIAL IS REQUIRED — DELETE THE HIGHLIGHTED MATERIAL TYPES THAT ARE NOT ACCEPTABLE

$$633.03D

Furnish wood, aluminum, galvanized steel, or corrosion resistant steel posts.

INCLUDE THE FOLLOWING FOR SIGNS ON NPS PROJECTS

$$633.03E

Paint posts, sign supports, and sign panel backs and edges with Benjamin Moore, Moorgard, exterior latex low luster paint, Federal Standard 595B Color No. 20059 (brown), or approved equal.

INCLUDE THE FOLLOWING FOR SIGN PANELS

$$633.05A

633.05.  Add the following after the first sentence of the first paragraph:

For all legends on guide signs, use ASTM Type VIII, IX, X, or 3M DG3 retroreflective sheeting.

$$634.00A

Section 634.—PERMANENT PAVEMENT MARKINGS

Revised 25 January 2005

# INCLUDE THE FOLLOWING

$$634.03A

634.03.  Add the following to the first paragraph:

Place traffic markings before a winter suspension of paving operations.

$$635.00A

Section 635. — TEMPORARY TRAFFIC CONTROL

Revised 24 November 2008

INCLUDE THE FOLLOWING

$$635.02A

635.02.  Delete the Construction sign panels Section reference and substitute the following:

Construction sign panels							633.02

$$635.03A

635.03.  Add the following:

For all signs and other devices requiring orange color, use fluorescent orange, fluorescent red-orange, or fluorescent yellow-orange color.

$$635.03B

635.03(i).  Add the following:

Submit a certification that the devices have been successfully crash tested to meet the requirements of NCHRP Report 350 and/or have been accepted by the FHWA.

INCLUDE THE FOLLOWING FOR CONSTRUCTION SIGNS

$$635.07D

635.07.  Delete the last sentence of the first paragraph and substitute the following:

Remove or completely cover all unnecessary signs, or signs that conflict with the construction signing or Traffic Control Plan.  Cover signs that are not removed so that no part of the covered sign is visible to traffic.  Provide sign covers for temporary signs meeting the following requirements:

- Large enough to completely cover the sign.

- Easy to attach to and remove from the sign without damaging the sign face.  Do not use adhesives, glues, tapes, or mechanical fasteners that mar the sign face.

- Black, non-reflective, and opaque.

- Made of plywood (minimum of 3/8-inches (10 millimeters) thick), aluminum (minimum of 0.040 inches (1 millimeter) thick), or sheet metal of a sufficient thickness that the covering will not be lifted, bent, or damaged by wind.

- Durable enough to resist deterioration due to weathering and atmospheric conditions for the duration of the project.

INCLUDE THE FOLLOWING FOR HIGH LEVEL WARNING

$$635.07A

635.07.  Add the following:

Furnish 16-inch by 16-inch (40-centimeter by 40-centimeter) flags for high level warning devices that are fluorescent orange, fluorescent red-orange, or fluorescent yellow-orange in color.

INCLUDE THE FOLLOWING FOR CONCRETE BARRIERS

$$635.11B

635.11.  Add the following after the second sentence of the first paragraph:

Use temporary barriers that meet test level (select appropriate test level – use TL-2 for speeds less than or equal to 45 mph, or use TL-3 for speeds greater than 45 mph) criteria, per NCHRP Report 350 for crashworthiness standards.

$$635.11A

635.11.  Delete the second paragraph and substitute the following:

Mount flexible plastic 6-inch by 6-inch (15-centimeter by 15-centimeter) delineators with Type III or IV retroreflective sheeting to the top of concrete barriers on 25-foot (7.5-meter) centers.  Furnish white sheeting when the delineator is to the right of traffic and yellow when to the left.

INCLUDE THE FOLLOWING FOR SHADOW VEHICLES

$$635.16A

635.16.  Delete the first sentence of the first paragraph and substitute the following:

Use a shadow vehicle (17,600 to 19,800 pound gross vehicle mass) (8000 to 9000 kilogram gross vehicle mass) equipped with a truck-mounted attenuator (crash cushion) attached to the rear of the vehicle, exterior flashing yellow dome light, and an advance warning arrow panel.

INCLUDE THE FOLLOWING

$$635.17A

635.17.  Add the following:

Patch the travelway after milling to provide a smooth, uniform traveling surface before reopening travel lanes to traffic as directed by the CO.

INCLUDE THE FOLLOWING FOR TEMPORARY CRASH CUSHIONS

$$635.19A

635.19.  Delete the first sentence of the first paragraph and substitute the following:

Install an FHWA-approved temporary crash cushion conforming to test level (select appropriate test level – use TL-2 for speeds less than or equal to 45 mph, or use TL-3 for speeds greater than 45 mph) criteria, per NCHRP Report 350 for crashworthiness standards.

INCLUDE THE FOLLOWING AND SUBSECTION $$636.04B FOR TEMPORARY SIGNALS

$$635.20A

635.20.  Add the following:

Time the temporary signal system in accordance with the operating modes listed in Subsection 636.04.

$$636.00A

Section 636.—SIGNAL, LIGHTING, AND ELECTRICAL SYSTEMS

Revised 8 May 2005

INCLUDE THE FOLLOWING FOR TRAFFIC DETECTOR DEVICES

$$636.01A

636.01. Add the following:

This work includes the installation of traffic detector systems.

INCLUDE THE FOLLOWING FOR LIGHTING AND MISCELLANEOUS ELECTRICAL SYSTEMS, IF APPLICABLE

$$636.02A

636.02.  Add the following:

Conduits under the traveled way.	721.01(a)(2)

INCLUDE THE FOLLOWING FOR TRAFFIC DETECTOR DEVICES

$$636.02C

Granular Backfill	703.03

$$636.02G

Furnish type THWN Class B #14 AWG minimum, 600 Volt stranded single copper conductor, IPCEA Standard 861-401 with UL label.  Furnish wire with a uniform thickness of insulation which is moisture and heat resistant to 250 oF (120 oC).

$$636.02H

Furnish shielded twisted pair, size No. 14 minimum, lead-in cable.

$$636.02I

Furnish a traffic counter with the following characteristics:

OBTAIN SPECIFICS FROM DENVER SERVICE CENTER AND APPROVAL FROM DIRECTOR OF PROJECT DELIVERY, IF PRODUCT IS SOLE SOURCE

INCLUDE THE FOLLOWING FOR LIGHT POLES.  SELECT THE APPROPRIATE HIGHLIGHTED MATERIAL TYPE

$$636.04A

636.04.  Add the following:

Furnish steel or aluminum poles.

INCLUDE THE FOLLOWING AND $$635.20A FOR TEMPORARY SIGNAL SYSTEMS

$$636.04B

636.04.  Add the following:

Design and place the temporary signal system according to the MUTCD, Part IV.

Furnish a signal controller capable of operating in the following 3 modes:

|  | Signal Facing |
| --- | --- |
|  | Westbound Traffic | Eastbound Traffic |
| 1. Morning Rush |  | solid Red |  | solid Green |
| 2. Evening Rush |  | solid Green |  | solid Red |
| 3. Non-Rush |  | Red/Yellow/Green |  | Red/Yellow/Green |

INCLUDE ONE OF THE FOLLOWING CONCERNING COMMERCIAL ELECTRICITY

$$636.04C

Commercial electricity is available to power the temporary signal system at the (insert location).  Coordinate with the local electric company according to Subsection 107.02.

$$636.04D

Commercial electricity is not available at the project site.  Furnish a power source to operate the signal system.

# INCLUDE THE FOLLOWING FOR ALL CONDUIT PLACEMENTS

$$636.05A

636.05.  Add the following:

Install conduits a minimum of 3 feet (1 meter) below finished grade.  Replace pavement structure removed to install conduit in kind.

INCLUDE THE FOLLOWING FOR TRAFFIC DETECTOR DEVICES

$$636.05B

636.05.  Add the following:

Install pull boxes flush with the shoulder surface.  Restore the disturbed area around the pull box and conduit installations.

Complete the installation of all loops, conduits, and pull boxes at 1 location before moving to another location.

Install 1-inch (25-millimeter) conduit under the shoulder from the end of the saw cut to the pull box.  Do not drill or cut the part of the concrete encasement between the edge of the pavement and the pull box for conduit installation.  Install a bushing on the conduit stubout to prevent damage to loop lead-in wires.

Install the conduit in a direct line with the loop saw cut so that the wires entering the conduit will not be bent.  Construct the hole in the curb, if applicable, at a depth that will permit a minimum of 2 inches (5 centimeters) of cover on top of the conduit when installed.  The cover over the conduit shall be the same material used to seal the sawcut.

$$636.07A

636.07.  Add the following:

Furnish and install the lead-in cable in the conduit from the pull box with sufficient length to reach the future counter cabinet.  Secure the lead-in cable and cap the T-section end.  Splice each loop to an individual lead-in cable.

Install traffic counters and connect to loops according to the manufacturer's recommendations.

$$637.00A

Section 637. — FACILITIES AND SERVICES

Revised 24 September 2008

INCLUDE THE FOLLOWING FOR A FIELD OFFICE PROVIDED BY THE CONTRACTOR

$$637.02A

637.02.  Add the following:

SELECT ONE OF THE FOLLOWING CLAUSES ($$637.02B or $$637.02C) FOR THE FIELD OFFICE LOCATION

$$637.02B

Locate the Government field office at (insert location), as directed by the CO.  Provide high-speed Internet access, as described in Subsection 637.03(a)(7).

$$637.02C

Locate the Government field office where high-speed Internet access, as described in Subsection 637.03(a)(7), is available.  For urban projects locate the field office within 5 miles (8 kilometers) of the project site.  For rural projects locate the field office within 15 miles (24 kilometers) of the project site.  In remote locations where high-speed Internet service is not available, the field office distance range may be extended or waived by the CO.  All field office locations are subject to approval by the CO.

$$637.03A

637.03.  Delete the third and fourth sentences of the first paragraph and substitute the following:

Provide local and long distance telephone services.  The Government will be responsible for the cost of long distance calls made by Government employees for Government business and charged against this phone service.  Bill the Government separately for these charges.

637.03(a).  Add the following:

Divide the field office into 3 areas by permanent walls with hinged doors.  If window air conditioning is provided, provide a separate unit for each room.

Clean the field office weekly to the approval of the CO.

Supply the following equipment in the field office:

- Copy machine.  One self-feeding plain paper photo copying machine with the following minimum capabilities:

- Automatic document feeder capable of making at least 8 copies per minute;

- Reproducing copies at standard sizes up to and including 11 x 17 inches (297 x 420 millimeters); and

- Reducing 11 x 17 inches (297 x 420 millimeters) plan sheets to 8 ½ x 14 inches (210 x 358 millimeters) legal size and to 8 ½ x 11 inches (210 x 297 millimeters) letter size.

Furnish all necessary supplies, except paper.  Paper will be supplied by the Government.

- Printer.  One plain paper printing machine with printing capabilities of standard sizes up to and including 11 x 17 inches (297 x 420 millimeters).  The printer must be capable of printing from direct personal computer (PC) and local area network (LAN) hookups.  The printer may be one machine in combination with the copy machine.  Furnish all necessary supplies, except paper.  Paper will be supplied by the Government.

- Facsimile (FAX) machine.  One FAX machine with the following minimum capabilities:

- Automatic document feeder with a minimum capacity of 20 pages;

- Sending standard size documents up to and including 11 x 17 inches (297 x 420 millimeters);

- Printing on plain paper; and

- Automatic dial/redial.

The FAX machine may be one machine in combination with the copy machine.  Furnish all necessary supplies, except paper.  Paper will be supplied by the Government.

- Telephone.  Two dual line telephones (touch tone, hold button, intercom, and conference calling capabilities) with 2 separate lines, for the exclusive use of the CO.

- Answering machine.  One digital answering device capable of answering, recording, storing, and playing back messages at least 30 minutes in length.

- Cellular telephone.  (Specify number of phones as per the contract needs) durable, hand held digital/cellular wireless telephone(s) for the use of the CO.  Furnish cellular telephone(s) that are similar or compatible with the Contractor’s key field personnel (Project Superintendent, Traffic Control Supervisor, etc.) to enable the direct communication between the CO and the Contractor’s key field personnel.  Furnish each cellular telephone(s) with the following minimum capabilities:

- Direct Connect feature, or equivalent, to communicate onsite with Contractor’s key field personnel;

- Voicemail capable of answering, recording, storing, and playing back messages at least 30 minutes in length;

- Hands free device that can be used safely and effectively while driving, and is acceptable by the local law enforcement agencies;

- Customized communication configuration, independent of the other units, so that the CO may limit any features if necessary;

- Carrying case that can be worn on the belt and is appropriate for use on construction projects; and

- Other necessary cellular telephone accessories including a cigarette lighter power adapter/charger.

The cellular telephone plan shall provide the necessary amount of monthly Direct Connect airtime and monthly Digital/Cellular airtime for use on the project.  Ensure that each unit has unlimited Direct Connect capabilities and each unit is equipped with unlimited airtime, roaming, and local and long distance airtime necessary per month for official business only.  Provide phones that work properly at the project site and at the Contractor’s and Government field office locations.

- High-speed Internet access.  Provide, install, and maintain high-speed Internet access service having at least 768 kilobit per second download and 256 kilobit per second upload speed.  The high-speed Internet access service can be provided via DSL, FIOS, a dedicated T1 line, or cable.  Alternate Internet access service options may be submitted to the CO for approval.  The system must include a modem and a router with a firewall or a router and a firewall appliance.  The system must have the capability to support simultaneous Internet access of at least 3 workstations connected by Category 6 RJ45 LAN office drop cables.  If the router supports wireless Internet access, this feature must be disabled.  Wireless Internet access does not meet U.S. DOT security requirements and is not acceptable.  The firewall configuration must be submitted to the CO for approval and cannot be changed after it is approved, unless a change request is submitted and approved in advance.  Only U.S. DOT equipment is to be connected to the system.

If any equipment supplied becomes defective, is stolen, or for any other reason does not function as intended, replace the equipment with an equal or better unit at no additional cost to the Government.  Replace any defective equipment within eight hours after being notified by the CO.

The Contractor will retain ownership of all equipment supplied by the Contractor.  The CO will notify the Contractor when the equipment is no longer needed and request its removal.

INCLUDE THE FOLLOWING FOR LOCATING UTILITIES

Add the following after Section 637:

$$645.00A

Section 645.—LOCATING UTILITIES

Revised 25 January 2005

Description

645.01  This work consists of locating and marking existing utilities by excavating test pits to, or using electromagnetic devices, where a physical conflict with proposed construction is suspected and the location is ordered by the CO.

Material

645.02  Materials for restoring the test pit area to its original condition shall be replacement of the materials excavated or their equivalent in newly furnished materials meeting the various applicable sections of this specification.

Construction Requirements

645.03  General.  Notify (insert name of local locator service) 48 hours prior to any excavation, at (insert phone number) to have the utilities marked in the field.  Notify the CO 48 hours prior to any excavation.

Exercise special care and extreme caution in order to protect and avoid damage to any utility company facilities.  Existing utilities have been generally located and shown on the plans as they are believed to exist.  The Government assumes no responsibility for the accuracy of locations shown on the plans.  Locate and ensure the safety of all existing utilities.  Repair any damage resulting from Contractor’s operations at no additional expense to the Government.

Locate by test pit any utility that may be in conflict with the proposed work.  If a conflict appears to exist, then notify the CO in writing immediately and provide information on the location and elevation of the utility so that the CO can adjust the proposed work.

645.04  Locating Utility.  Use electromagnetic devices to establish alignment of utilities where applicable.  When necessary, thread a metal rod through non-metallic utility pipes to locate them.  Where neither method is feasible, locate the utility by perpendicular trench or test pits.

645.05  Excavation.  Excavate carefully so as not to disturb utility at it's assumed depth.  When excavating within roadway pavements where traffic is being maintained, excavate by air-vacuum methods or equivalent, keeping the area of disturbance to a minimum.  Uncover the utility sufficiently to make accurate measurements.

645.06  Record.  Describe the utility found (size, material, function), determine the elevation of the top of utility, and prepare a field sketch of the pit.  Indicate the date and the station and offset of the utility, noting whether the baseline or the centerline of proposed facility is being referenced.  Submit 1 copy to the CO within 24 hours.

645.07  Marking.  Mark the utility location by flags or paint.  Maintain the markings, including repainting faded or damaged markings as ordered by the CO, for the duration of the project, or until the CO determines that the markings are no longer needed.

645.08  Restoration.  Backfill with original material, thoroughly compacting the material with a mechanical tamper.  Restore aggregate base courses and pavement using equivalent materials and thicknesses.  For portland cement concrete pavements, use fast setting concrete.  For asphalt concrete pavements, cold patch, resurfacing of pit will be permitted so long as, in the opinion of the CO, it is thoroughly compacted.

645.09  Acceptance.  Locating utilities will be evaluated under Subsection 106.02.

Measurement

645.10  Measure the Section 645 items listed in the bid schedule according to Subsection 109.02.

For markings, do not measure maintaining the markings.

Payment

645.11  The accepted quantities will be paid at the contract price per unit of measurement for the Section 645 pay items listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

Section 647.— ENVIRONMENTAL MITIGATION

Revised 1 May 2006

Description

647.01  This work consists of --------------------------------.

Material

647.02  Conform to the following Subsections:

material name	7XX.XX

material name	7XX.XX

Construction Requirements

647.03

647.XX Acceptance.

Measurement

647.XX  Measure the Section 647 items listed in the bid schedule according to Subsection 109.02.

Payment

647.XX  The accepted quantities, measured as provided in Subsection 109.02 and above, will be paid at the contract price per unit of measurement for the Section 647 pay items listed in the bid schedule.  Payment will be full compensation for the work prescribed in this Section.  See Subsection 109.05.

$$701.00A

Section 701.—CEMENT

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR PROJECTS IN HIGH SULFIDE AREAS

$$701.01A

701.01(a).  Add the following:

Furnish portland cement with a maximum sulphate expansion of 0.040 percent when tested in accordance with ASTM C 452.

INCLUDE THE FOLLOWING FOR SHOTCRETE.  FOR COLORED SHOTCRETE, INCLUDE 711.05

$$701.01B

701.01.  Add the following:

For shotcrete, use low alkali portland cement.  Conform to AASHTO M 85, limiting alkalis according to Table 1A in AASHTO M 85.

$$703.00A

Section 703. — AGGREGATE

Revised 22 October 2008

INCLUDE THE FOLLOWING FOR COARSE AGGREGATE FOR CONCRETE DEPENDING ON STATE REQUIREMENTS

$$703.02A

703.02.  Add the following:

Gravel will not be permitted.

INCLUDE THE FOLLOWING FOR SUBBASE, BASE, AND SURFACE COURSES

$$703.05A

703.05(a).  Delete items (3) and (4).

INCLUDE THE FOLLOWING FOR AGGREGATE BASE

$$703.05B

703.05(b).  Add the following:

(3)  Plasticity index, AASHTO T 90					3 max.

$$703.05C

703.05(b).  Add the following:

Furnish material with a minimum California bearing ratio of (obtain CBR value from Materials Engineer or Pavements Section) percent, as determined by AASHTO T 193 at 95 percent of maximum dry density in accordance with AASHTO T 180 (Method D).

INCLUDE THE FOLLOWING (STATE GRADATION OPTIONS) FOR AGGREGATE BASE

$$703.05E

703.05(b)(1).  Add the following:

At the option of the Contractor, the gradation only of the aggregate base may conform to the requirements of (insert State, acceptable State aggregate, and State specification reference).

INCLUDE THE FOLLOWING FOR HACP AGGREGATE

$$703.07A

703.07(a).  Delete item (4).

703.07(b).  Delete item (1).

INCLUDE THE FOLLOWING FOR ASPHALT SURFACE TREATMENT AGGREGATE

$$703.10B

703.10.  Delete items (f) and (g).

INCLUDE THE FOLLOWING FOR AGGREGATE-TOPSOIL WHEN CRUSHED AGGREGATE IS SCARCE (VERIFY WITH MATERIALS ENGINEER)

$$703.14A

703.14.  Delete the Subsection and substitute the following:

703.14  Aggregate for Aggregate-Topsoil Course.  Furnish base or surface course aggregate meeting the gradation and quality requirements of Subsection 703.05.

INCLUDE THE FOLLOWING FOR AGGREGATE-TOPSOIL COURSES < 1 ½ inches (35 millimeters) THICK

$$703.14B

703.14.  Delete item (a) and substitute the following:

(a)  Gradation						AASHTO M 43, size number 67

INCLUDE THE FOLLOWING IF CRUSHED RECYCLED CONCRETE IS PERMITTED IN EITHER SECTION 301 OR 308

$$703.20A

Add the following after Subsection 703.19:

703.20  Crushed recycled concrete.  Furnish a recycled material consisting of crushed concrete.  A portion of the composite material may include recycled mortar or brick.  Furnish a recycled material free of reinforcing bars or wire, organic matter, lumps or balls of clay, and other deleterious matter.  Do not use material that breaks up when alternately frozen and thawed or wetted and dried.  Conform to the following:

(a)  Los Angeles abrasion, AASHTO T 96				50% max.

(b)  Liquid limit, AASHTO T 89						25 max.

(c)  Plasticity index, AASHTO T 90					6 max.

(d)  California bearing ratio, AASHTO T 193				55% min.

(e)  Gradation.  Furnish a gradation conforming to crushed recycled concrete material used locally in the construction and maintenance of highways by Federal or State agencies.  Furnish a well graded crushed recycled material with a maximum size of 2 inches (50 millimeters) and not more than 12 percent passing the No. 200 (75µm) sieve as determined by AASHTO T 27 and T 11.

$$705.00A

Section 705. — ROCK

Revised 30 January 2009

INCLUDE THE FOLLOWING (AND INCLUDE $$251.07A AND $$251.07B) FOR ALL RIPRAP APPLICATIONS

$$705.02A

705.02.  Delete the Subsection and substitute the following:

705.02  Riprap Rock.  Furnish hard, durable, angular rock that is resistant to weathering and water action and free of organic or other unsuitable material.  Angular rock is characterized by sharp, clean edges at the intersections of relatively flat surfaces.  Furnish rock with width and thickness of individual rock at least one-third its length (dimension of longest axis).  Do not use shale, rock with shale seams, or other fissile or fissured rock that may break into smaller pieces in the process of handling and placing.  Conform to the following:

(a)  Apparent Specific Gravity, AASHTO T 85				2.40 min.

(b)  Absorption, AASHTO T 85						4.0% max.

(c)  Sodium Sulfate Soundness Loss (5 cycles), AASHTO T 104	12% max.

(d)  Los Angeles Abrasion, AASHTO T 96				50% max.

(e)  Riprap Class								Table 705-1

$$705.02B

705.02 Table 705-1.  Delete Table 705-1 and substitute the following:

| Table 705-1 Size / Gradation Requirements for Riprap, CU (SI)(1) |
| --- |
| Class | Size Fraction, DX | Percent of Rock by Weight | Range of Intermediate Dimension(2), inches (millimeters) | Range of Rock Weight(3), pounds (kilograms) |
| 1 | 100 | 15 | 12.0 (300) | 140 (65) |
|  | 85 | 35 | 8.0 – 9.5 (200-240) | 39 – 64 (20-30) |
|  | 50 | 35 | 5.5 – 7.0 (140-180) | 15 – 27 (7-12) |
|  | 15 | 15 | 3.5 – 5.0 (90-130) | 4 – 12 (2-5) |
| 2 | 100 | 15 | 18.0 (460) | 470 (210) |
|  | 85 | 35 | 11.5 – 14.0 (290-360) | 130 – 220 (60-100) |
|  | 50 | 35 | 8.5 – 10.5 (220-270) | 51 – 90 (24-40) |
|  | 15 | 15 | 5.5 – 8.0 (140-200) | 13 – 39 (6-20) |
| 3 | 100 | 15 | 24.0 (610) | 1100 (500) |
|  | 85 | 35 | 15.5 – 18.5 (390-470) | 310 – 510 (140-230) |
|  | 50 | 35 | 11.5 – 14.0 (290-360) | 120 – 210 (55-95) |
|  | 15 | 15 | 7.5 – 10.5 (190-270) | 32 – 93 (15-42) |
| 4 | 100 | 15 | 30.0 (760) | 2200 (1000) |
|  | 85 | 35 | 19.5 – 23.0 (500-580) | 600 – 1000 (270-450) |
|  | 50 | 35 | 14.5 – 17.5 (370-440) | 240 – 420 (110-190) |
|  | 15 | 15 | 9.5 – 13.0 (240-330) | 62 – 180 (28-80) |
| 5 | 100 | 15 | 36.0 (910) | 3800 (1720) |
|  | 85 | 35 | 23.5 – 27.5 (600-700) | 1050 – 1750 (480-790) |
|  | 50 | 35 | 17.0 – 20.5 (430-520) | 410 – 720 (185-330) |
|  | 15 | 15 | 11.0 – 15.5 (280-390) | 110 – 310 (50-140) |
| 6 | 100 | 15 | 42.0 (1070) | 6000 (2720) |
|  | 85 | 35 | 27.5 – 32.5 (700-830) | 1650 – 2800 (750-1270) |
|  | 50 | 35 | 20.0 – 24.0 (510-610) | 650 – 1150 (290-520) |
|  | 15 | 15 | 13.0 – 18.5 (330-470) | 170 – 500 (75-225) |
| 7 | 100 | 15 | 48.0 (1220) | 9000 (4080) |
|  | 85 | 35 | 31.0 – 37.0 (790-940) | 2500 – 4100 (1130-1860) |
|  | 50 | 35 | 23.0 – 28.0 (580-710) | 950 – 1700 (430-770) |
|  | 15 | 15 | 15.0 – 21.0 (380-530) | 260 – 740 (120-340) |
| 8 | 100 | 15 | 60.0 (1520) | 17,600 (8000) |
|  | 85 | 35 | 39.0 – 46.0 (990-1170) | 4800 – 8000 (2180-3630) |
|  | 50 | 35 | 29.0 – 35.0 (740-890) | 1900 – 3300 (860-1500) |
|  | 15 | 15 | 19.0 – 26.0 (480-660) | 500 – 1450 (225-660) |
| 9 | 100 | 15 | 72.0 (1830) | 30,400 (13,800) |
|  | 85 | 35 | 47.0 – 56.0 (1190-1420) | 8300 – 13,900 (3760-6300) |
|  | 50 | 35 | 34.0 – 42.0 (860-1070) | 3300 – 5800 (1500-2630) |
|  | 15 | 15 | 22.0 – 32.0 (560-810) | 860 – 2500 (390-1130) |
| 10 | 100 | 15 | 84.0 (2130) | 48,200 (21,900) |
|  | 85 | 35 | 55.0 – 65.0 (1400-1650) | 13,200 – 22,000 (6000-10,000) |
|  | 50 | 35 | 40.0 – 49.0 (1020-1240) | 5200 – 9200 (2360-4170) |
|  | 15 | 15 | 26.0 – 37.0 (660-940) | 1350 – 4000 (610-1810) |

(1) Includes spalls and rock fragments to provide a stable, dense mass.

(2) Measured as the shortest, straight-line distance from one side of the rock or rock particle to the other on the maximum projection plane (plane of rock or rock particle with the largest projected surface area).

(3) Weights based on a specific gravity of 2.65.

INCLUDE THE FOLLOWING FOR STONE GUARDWALLS OR MASONRY, IF APPLICABLE

$$705.03A

705.03(a).  Delete the Subsection and substitute the following:

(a)  Sizes and shapes.  Do not use rock with depressions or projections that might weaken it or prevent it from being properly embedded.

On the wall face, furnish stone no less than 2 inches (5 centimeters) in vertical dimension, no less than 6 inches (15 centimeters) in horizontal dimension, and no less than 4 inches (10 centimeters) in depth dimension.

On the top of the wall, furnish stone no less than 4 inches (10 centimeters) in least dimension.

Submit stone samples representing every color to be used on the project to the CO for approval.

INCLUDE THE FOLLOWING FOR GRANITE CURB

$$705.06A

705.06.  Add the following:

(c)  Granite curb.  Furnish granite stone conforming to the following:

(1)  Top width.  5 inches (125 millimeters).

(2)  Bottom width.  5 inches (125 millimeters) minimum for two-thirds its length.

(3)  Depth.  9 ± 1/4 inch (225 ± 6 millimeters).

(4)  Length.  6 feet (1.8 meters) (except as noted).  Ten percent of the length of curb installed on the project may consist of stones no more than 6 inches (15 centimeters) shorter than the length specified, except as follows:

(a)  Stones used in making closures may be one-third shorter than specified.

(b)  On curves with radii greater than 160 feet (49 meters), but less than 492 feet (150 meters), stones may be from 4 to 6 feet (1.2 to 1.8 meters) in length.

(c)  Cut stones set on a radius of 160 feet (49 meters) or less to the required curvature and, except for making closures, may be the following minimum lengths:

| Radius (feet) (meters) | Minimum Length (feet) (meters) |
| --- | --- |
| 49 to 160 (15 to 49) | 6 (1.8) |
| 25 to less than 49 (7.6 to less than 15) | 5 (1.4) |
| Less than 25 (7.6) | 3 (0.9) |

Cut the ends of all curved stones on radial lines.

Furnish granite stone that is light gray in color, free from seams and other structural imperfections or flaws which would impair its structural integrity, and of a smooth splitting appearance.  Natural color variation characteristics of the deposit from which the granite stone is obtained will be permitted.

Whenever stone curb is sawed, clean all surfaces that will be exposed and remove any iron rust or iron particles by sandblasting or other approved method.  Remove saw marks in excess of 0.12 inches (3 millimeters).

Furnish either type A or type B stone curb, but use one type of stone throughout the project.

(d)  Stone curb, types A and B.

(1)  Type A.  Furnish curbstone that has been peen hammered or sawed to an approximately true plane, having no projections or depressions greater than 0.12 inches (3 millimeters) and has a top surface free from kerf.  The front and back arris lines shall be pitched straight and true and the back surface shall have no projection or depression greater than 1.5 inches (38 millimeters).

The front face shall have a batter of approximately 1H:12V and shall be hammered or sawed, free from drill holes and with no projection through the arris or pitch lines for the full depth of the face.  The front arris shall be a 1/4-inch (6-millimeter) bullnose.

(2)  Type B.  Furnish curbstone that has been peen hammered or sawed to an approximately true plane, having no projections or depressions greater than 0.12 inches (3 millimeters) and has a top surface free from kerf.  The front and back arris lines shall be pitched straight and true and the back surface shall have no projection or depression greater than 1.5 inches (38 millimeters).

The front face shall have a batter of approximately 3/4H:10V and shall be smooth quarry split, free from drill holes and with no projection of more than 3/4 inch (19 millimeters) and no depression of more than 1/2 inch (13 millimeters) measured from the plane of the face through the arris or pitch line for a distance down to within 1 inch (25 millimeters) of the bottom.  For the remaining distance there shall be no projection or depression greater than 1 inch (25 millimeters) measured in the same manner.

For both types of curb, furnish stone with ends that are square with the planes of the top and exposed faces so that when the stones are placed end to end as closely as possible, no space shall show in the joint at the top and exposed faces of more than 1/4 inch (6 millimeters) for the full width of the top and for the full depth, after which the end may break back not over 2 inches (50 millimeters) from the plane of the joint.  The arris formed by the intersection of the plane of the joint with the planes of the top and exposed faces shall have no variation from the plane of the top and exposed faces greater than 0.12 inches (3 millimeters).

$$710.00A

Section 710.—FENCE AND GUARDRAIL

Revised 25 January 2005

# INCLUDE THE FOLLOWING FOR BARBED WIRE FENCE

$$710.01A

710.01.  Add the following:

Furnish barbed wire with a Class 1 galvanized coating.

# INCLUDE THE FOLLOWING FOR WOVERN WIRE FENCE

$$710.02A

710.02.  Add the following:

Furnish woven wire with a Class 1 galvanized coating.

# INCLUDE THE FOLLOWING FOR CHAIN LINK FENCE

$$710.03A

710.03.  Add the following:

Furnish (insert gage) gage chain link fabric.

# INCLUDE THE FOLLOWING FOR FENCES, GATES OR BOLLARD POSTS

$$710.04A

710.04(a).  Add the following:

Treat fence, gate, and bollard posts according to 716.03.

INCLUDE THE FOLLOWING FOR STEEL-BACKED TIMBER GUARDRAIL

$$710.08A

710.08.  Add the following:

Rough sawn timber tolerance shall apply only to the timber cross section and post length.

$$711.00A

Section 711.—CONCRETE CURING MATERIAL AND ADMIXTURES

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR FIBER-REINFORCED CONCRETE

$$711.06A

Add the following after Subsection 711.05:

711.06.  Fiber Reinforcement.  Furnish a polypropylene fiber conforming to ASTM C 116, Type 3, and compatible with the constituents of the concrete mixture.  Furnish documentation of compatibility from the manufacturer.

$$713.00A

Section 713.—ROADSIDE IMPROVEMENT MATERIAL

Revised 8 May 2005

INCLUDE THE FOLLOWING FOR TOPSOIL

$$713.01A

713.01.  Add the following:

For furnished topsoil, submit a soil analysis report from the State University Agricultural Extension Service or other approved soil testing laboratory.  Include in the report the soil textural classification (percentage of sand, silt, clay and organic matter) and additive recommendations.

INCLUDE ONE OF THE FOLLOWING FOR STABILIZED SHOULDERS

$$713.01B

Furnish topsoil for aggregate-topsoil course from stockpiles conserved under Section 204, from stockpiles designated on the plans, or from Contractor sources.

$$713.01C

Furnish topsoil for aggregate-topsoil course from Contractor sources.

INCLUDE THE FOLLOWING ON NPS PROJECTS

$$713.02A

713.02. Add the following:

Use a maximum of 0.17 pounds (3 kilograms) of limestone per cubic foot (meter) of topsoil in order to adjust an acidic condition.

INCLUDE THE FOLLOWING FOR FERTILIZER FOR SEEDING

$$713.03A

713.03.  Add the following:

Furnish fertilizer containing the following minimum available nutrients, unless soil analysis indicates higher concentrations are required:

Total nitrogen					10 percent

Available phosphoric acid		10 percent

Water-soluble potash			10 percent

INCLUDE THE FOLLOWING ON NPS PROJECTS

$$713.05A

713.05.  Add the following after 713.05(h):

(i) Shredded Hardwood Mulch.  Furnish aged hardwood mulch, dark brown to black in color, with a particle size of less than 3 inches (75 millimeters or 80 per the FP96), a neutral pH, and free of sticks, stones, clay, or other matter which may injure plants.

$$713.06A

713.06(b).  Add the following:

The genus, species, and cultivar names shall agree with the nomenclature of the most current edition of “Hortus Third” by L.H. Bailey, Hortorium, Cornell University.

Provide durable tags, stating the date of installation, correct botanical name and size in weather-resistant ink or embossed letters.  Secure the tags to each tree, shrub, and other plant materials in a manner which will not restrict growth.  Leave the tags on all trees, shrubs, and other plant materials until final acceptance by the CO.

$$713.08A

713.08.  Add the following after 713.08(g):

(h) Tree protection.  Tree protection shall be a flexible PVC pipe 4 inches (10 centimeters) in diameter, 12 to 13 inches (30 to 32.5 centimeters or 35 per FP96) in height.

INCLUDE OF THE FOLLOWING, SELECT  THE TYPE OF SOD DESIGNATED IN 627.03

$$713.10A

713.10.  Add the following:

Cut Bermuda grass or Tall Fescue, Kentucky 31 sod to a depth equal to the growth of the roots, but not less than 1 inch (2.5 centimeters).

INCLUDE THE FOLLOWING FOR PESTICIDE

$$713.19A

Add the following after Subsection 713.18:

713.19.  Pesticide.  Pesticides to control armyworms are Bacillus Thuringiensis - Berliner, Bactospeine, Biotrol, BTB, BTV, Dipel, and Thuricide, as manufactured by Nutrilite Products, Inc., and Bioferm Corporation.

$$717.00A

Section 717.—STRUCTURAL METAL

Revised 18 May 2005

INCLUDE THE FOLLOWING FOR BRIDGE EXPANSION JOINTS

$$717.01A

717.01  Add the following after 717.01(e):

(f) Anchor bolts, nuts, and washers for expansion joints.  Stainless steel conforming to ASTM A 276, Type 304.

INCLUDE THE FOLLOWING FOR ELASTOMERIC EXPANSION JOINT SEALS

$$717.17A

Add the following after Subsection 717.16:

717.17.  Elastomeric Expansion Joint Seals.  Furnish synthetic, non-wicking, fabric-reinforced, neoprene elastomeric expansion joint seals.  Furnish neoprene elastomer conforming to ASTM D 2000 and to Table 717-4.

Table 717-4 - Neoprene

| Physical Property | ASTM Test Method | Requirement |
| --- | --- | --- |
|  | Hardness, Durometer A |  | D 2240 |  | 60±5 |
|  | Tensile Strength |  | D 412 |  | 2000 psi (13.8 MegaPascals) min |
|  | Elongation at Break |  | D 412 |  | 250% min |
|  | Low Temperature |  | D 746 |  | Not Brittle at -67 oF (-55 oC) |
|  | Weather Resistant |  | D 1171 |  | No Cracks |
|  | Ozone Cracking |  | D 1149 |  | No Cracks |
|  | 100 PPHM 70 hours |  |  |  |  |
|  | @ 100 oF (38 oC), 20% strain |  |  |  |  |
|  | Water Resistance |  | D 471 |  | 3% max. volume swell |
|  | Compression Set |  | D 395, Method B |  | 25% max |
|  | 22 hours @ 158 oF (70 oC) |  |  |  |  |

INCLUDE THE FOLLOWING FOR GRANITE BRIDGE CURB.

$$717.18A

Add the following after Subsection 717.16:

717.18.  Masonry Anchors for Granite Bridge Curb.  Stainless steel conforming to

ASTM A 276, Type 304.

$$718.00A

Section 718. — TRAFFIC SIGNING AND MARKING MATERIAL

Revised 10 December 2008

INCLUDE THE FOLLOWING FOR SIGN PANELS

$$718.01A

718.01.  Add the following:

For a list of acceptable manufacturers and products refer to the Sheeting Guide at:

http://safety.fhwa.dot.gov/roadway_dept/retro/sign/resource_mat.htm

$$721.00A

Section 721.—ELECTRICAL AND ILLUMINATION MATERIAL

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR LIGHTING

$$721.01A

721.01(c).  Add the following:

Furnish either ozone resistant cross-linked polyethylene (XLP) or polyvinyl chloride (PVC) insulated cable, with or without a nylon jacket, as applicable, conforming to the following:

(1)  XLP.  IPCEA S-66-524 and NEMA WC-7 (code type XHHW);

(2)  PVC.  UL 83, ANSI C33.80-1971, and Federal Specification J-C-304 (code types THWN or THW).

INCLUDE THE FOLLOWING FOR ELECTRICAL WORK

$$721.01B

721.01(c).  Add the following:

Furnish soft drawn or annealed copper conductors conforming to ASTM B 3, and stranding conforming to ASTM B 8.  Furnish 7 strand for #10 AWG through #2 AWG, and 17 strand for #1 AWG through #4/0 AWG.  Furnish #6 AWG minimum solid copper ground wires.

$$725.00A

Section 725.—MISCELLANEOUS MATERIAL

Revised 25 January 2005

INCLUDE THE FOLLOWING FOR EPOXY

$$725.21A

  - Add the following:

Furnish a 2-component epoxy resin binder mixed together at the site as prescribed by the manufacturer.  The pot life of the epoxy, mixing period, maximum time lapse between mixing and application, and the curing period are all dependent on the temperature, humidity, and wind conditions, and the proprietary product being used.

Package epoxy components in containers that are clearly marked with a warning of the hazards involved in handling the material.

Obtain technical assistance from the manufacturer of the epoxy binder and follow the manufacturer's recommendations concerning proper use and installation.  Submit the product proposed for use, manufacturer's name, and data concerning composition and application for approval before use on the project.