## Current Tasks
Updated 3/15/07
Task | Subtask | Who | Start | End | Completed
KEY:
Red: Highest Priority; Blue: Completed; Black: Upcoming
GEOS4-DAS Combo (Aura) Re-runs |  |  |  | 2007-03-31
Investigate array bounds problem in advection code |  | Jules | 2007-03-12 | 2007-03-19
Investigate floating point problem in convection |  | Jules | 2007-03-12 | 2007-03-19
Complete Aura re-run 2004-5 2x2.5 |  | Gary/Megan | 2007-03-19 | 2007-03-31
Validate Aura re-run data |  | Gary | 2007-03-19 | 2007-03-31
Incremental 1 year 4x5 FVGCM Combo Code Tests |  |  |  | 2007-04-06
Baseline w/new trop 124 sp & JPL06-2 & H2 fix FASTJX53c |  | Gary | 2007-04-05 | 2007-04-06
Test #3 but with a het rxn=0 |  | Gary | 2007-03-15 | 2007-03-17
HTAP simulations |  |  |  | 2007-05-11
Convert GMI output to HTAP format |  | Gary/Megan/Jules | 2007-03-12 | 2007-03-30
Assist with TP1 experiment runs |  | Gary/Megan | 2007-03-16 | 2007-03-30
Gather info on new runs to do |  | Gary | 2007-03-23 | 2007-04-16
Perform new runs |  | Gary/Megan | 2007-04-10 | 2007-05-11
Lightning Algorithm Runs (Trop Model 2x2.5) |  |  |  | 2007-04-18
Generate script to create restart file |  | Gary | 2007-02-23 | 2007-03-20
Perform 1 month test run and deliver to scientists |  | Megan | 2007-03-15 | 2007-03-22
FVGCM 1994-96 default lightning |  | Megan/Gary | 2007-03-23 | 2007-04-18
FVGCM 1994-96 new lightning |  | Megan/Gary | 2007-03-23 | 2007-04-18
GEOS4DAS 2004,2004-5 default lightning |  | Megan/Gary | 2007-03-23 | 2007-04-18
GEOS4DAS 2004,2004-5 new lightning |  | Megan/Gary | 2007-03-23 | 2007-04-18
Combo Integration with GEOS-5 |  |  |  | 2007-04-06
Convert ascii input files to netcdf |  | Jules | 2007-02-22 | 2007-03-28
Convert land fractions to LWI flags |  | Jules | 2007-02-22 | 2007-03-28
Remove mcor inside emission componen t |  | Jules | 2007-02-22 | 2007-03-28
Writing I/O modules for emiss/chem |  | Jules | 2007-02-22 | 2007-03-28
Assist GMAO as needed |  | Jules | 2007-02-22 | 2007-04-06
Other Code Updates/Model Runs/Issues |  |  |  | Varies
Diagnose strange "filename" problem (compiler?) |  | Jules et al. | 2007-02-16 | 2007-04-10
Identify reason Huisheng can't run multiple jobs |  | Jules/Hamid | 2007-03-22 | 2007-04-12
Fix qj problem in fastJX53c |  | Gary/Jules | 2007-03-30 | 2007-04-05
Continue code componentization
| Replace species number with name | Jules/Tom | 2007-02-16 | 2007-03-23
| Reorganize namelist file | Jules | 2007-02-16 | 2007-03-02 | 2007-03-04
| Remove default settings from code | Jules | 2007-03-26 | 2007-04-20
Help Rafaella with microaerosol code |  | Jules | 2007-01-15 | 2007-02-22
Help Yasuko/Bryan with Combo on discover |  | Megan/Jules | 2007-01-22 | 2007-03-23
Generate GMI model version numbers |  | Gary et al. | 2007-03-24 | 2007-04-06
Update GMI User's Guide |  | Gary/Megan/Jules | 2007-02-02 | 2007-06-01
Help develop NCCS data-sharing for GMI data |  | Gary | 2007-02-01 | 2007-05-01
Assist with implementation new GA Tech aerosol/cloud code segments |  | Jules | 2007-05-01 | 2007-05-21
Begin resolution doubling experiments |  | Gary/Megan/Jules | 2007-04-30 | 2007-05-30
Introduce aerosol/gas phase coupling |  | Gary/Megan/Jules | 2007-05-15 | 2007-06-20
Processing GEOS4-DAS Met Fields |  |  |  | 2007-04-20
Reprocess fields for slp Jan-Jun 2006 |  | Megan | 2007-04-02 | 2007-04-20
Investigate potential problems in 4x5 polar regions |  | Megan | 2007-03-27 | 2007-04-20
Create vertical regrid scripts for 1x1.25 |  | Megan | 2007-04-02 | 2007-04-20

## Completed Tasks
Task | Subtask | Who | Start | End | Completed
GEOS4-DAS/GEOS4 Forecast Combo Runs (AGU) |  |  |  | 2006-12-08 | 2006-11-30
Fix Soil NOx Problem |  | Jules/Bryan | 2006-11-02 | 2006-11-09 | 2006-11-09
Prepare code and namelist file for runs |  | Bigyani/Jules | 2006-11-02 | 2006-11-16 | 2006-11-17
Obtain/implement new emissions inventory from Bryan |  | Bigyani | 2006-11-13 | 2006-11-16 | 2006-11-14
Run Combo with GEOS4-DAS and Forecast fields |  | Bigyani | 2006-11-13 | 2006-11-16 | 2006-11-22
Validate output of Combo DAS and Forecast runs |  | Bigyani/Jules/Gary | 2006-11-22 | 2006-11-24 | 2006-11-24
Run Combo GEOS4DAS w/Harvard 2005 emissions Feb-Apr 2005 runs |  | Bigyani | 2006-11-24 | 2006-11-27 | 2006-11-27
Run Combo GEOS4DAS and Forecast fields, no fire |  | Bigyani | 2006-11-27 | 2006-11-28 | 2006-11-30
Other Code Updates/Model Runs/Issues |  |  |  | Varies
Investigate microphysical aerosol INF/NaN value problem |  | Bhat/Bigyani | 2006-11-22 | 2006-12-01 | 2006-11-29
Add aerosol components to FASTJX-53c |  | Jules | 2006-11-17 | 2006-12-01 | 2006-12-07
Re-run pre-ind microphysical aerosol model w/o FF |  | Bigyani | 2006-12-08 | 2006-12-20 | 2006-12-22
Run pre-ind aerosol model w/ present oxidant fields |  | Bigyani | 2006-12-29 | 2007-01-03 | 2007-01-03
Add capability to read in monthly photolysis rates |  | Jules | 2006-12-15 | 2007-01-08 | 2007-01-08
Provide AEROCOM emissions at 4x5 to GA Tech |  | Bigyani | 2007-01-09 | 2007-01-11 | 2007-01-11
Assist with implementation of GOCART aersol code |  | Jules | 2007-01-16 | 2007-01-17 | 2007-01-17
Provide MicroPhysical Code to GA Tech |  | Gary | 2007-01-18 | 2007-01-22 | 2007-01-19
Update code for daily emissions |  | Jules | 2007-01-09 | 2007-01-19 | 2007-01-19
Update code for Aerosol Dust emissions |  | Jules | 2007-01-09 | 2007-01-19 | 2007-01-19
Change station "column" files to "profile" files |  | Bigyani | 2007-01-26 | 2007-01-29 | 2007-01-29
Add code to output surface aerosol emissions |  | Jules | 2007-01-19 | 2007-01-25 | 2007-01-22
Obtain online storage for GMI input/output data |  | Gary | 2007-01-18 | 2007-02-01 | 2007-02-06
Generate up to 9 preliminary GMI slides for MAP conference |  | Gary/Jules/Bigyani | 2007-01-23 | 2007-02-06 | 2007-02-08
Develop directory structure on discover |  | Gary | 2007-02-02 | 2007-02-06 | 2007-02-10
Finalize slides for MAP conference |  | Gary | 2007-02-07 | 2007-03-02 | 2007-03-04
Add H2 fix |  | Jules | 2007-02-09 | 2007-02-09 | 2007-02-09
Continue learning how to run GMI models |  | Gary/Megan | 2006-12-18 | 2007-03-15
Help Boeing with Combo code |  | Jules | 2007-03-05 | 2007-03-06 | 2007-03-06
Propose New GMI Directory Structure |  |  |  | 2007-02-28 | 2007-03-07
Complete summary of directory structure on dirac and palm |  | Bigyani | 2006-11-08 | 2006-11-15 | 2006-11-14
Develop new input/output directory structures |  | Gary et al. | 2006-11-20 | 2006-12-20 | 2007-01-08
| Discuss first draft with SIVO | Gary et al. | 2007-01-18 | 2007-01-18 | 2007-01-18
| Edit new structure briefing | Gary | 2007-01-19 | 2007-01-25 | 2007-01-29
| Make final edits | Gary | 2007-01-31 | 2007-02-07 | 2007-02-08
Copy data to new directories and rename |  | Gary | 2007-02-07 | 2007-02-28 | 2007-03-07
GEOS4-DAS Combo (Aura) Re-runs
Update code to output potential vorticity |  | Jules | 2006-11-12 | 2006-11-15 | 2006-11-15
Fix truncated ozone profile problem |  | Bigyani | 2006-11-27 | 2006-12-13 | 2006-12-20
Generate Background Fields: 6 years spinup |  |  | 2006-11-24 | 2007-01-15
| Run 1998-2002 4x5 | Bigyani | 2006-11-29 | 2006-12-06 | 2006-12-04
| Regrid 2002 to 2x2.5 | Bigyani/Bhat | 2006-12-15 | 2006-12-18 | 2006-12-21
| Run 2003 2x2.5 | Bigyani | 2007-01-09 | 2007-01-15 | 2007-01-18
Complete evaluation of FASTJX-53c |  | Jules/others | 2006-11-09 | 2006-11-13 | 2006-11-13
Update code for new species output and output frequency |  | Jules | 2006-11-29 | 2006-12-05 | 2006-12-20
Update code for new noon_species (overpass1 and overpass2) |  | Jules | 2006-11-24 | 2006-11-29 | 2006-12-04
Update code to output cloud optical depth |  | Jules | 2006-12-04 | 2006-12-05 | 2006-12-05
Implement new qj_update.F |  | Jules | 2006-12-01 | 2006-12-04 | 2006-12-18
Add D. Considine's strat chem fix |  | Jules | 2006-12-13 | 2006-12-13 | 2006-12-13
Update code for new vort/trop pressure calc |  | Jules | 2006-11-20 | 2006-12-15 | 2006-12-18
Add code to fix shallow convection problem |  | Jules | 2006-12-14 | 2006-12-15 | 2006-12-18
Put flux diagnostics code in trunk version |  | Jules | 2006-12-11 | 2006-12-15 | 2006-12-18
Implement ozone column diagnostic from photolysis |  | Jules | 2006-12-13 | 2006-12-15 | 2006-12-18
Implement surface ozone output code |  | Bigyani | 2006-12-14 | 2006-12-15 | 2006-12-21
Generate output file names for Aura runs |  | Gary/Bigyani | 2007-01-04 | 2007-01-04 | 2007-01-08
Add code to output freq1 at specified time |  | Bigyani | 2007-01-18 | 2007-01-18 | 2007-01-18
Test emission code with ship emissions |  | Jules | 2007-01-23 | 2007-01-24 | 2007-01-24
Add code to read daily ship emissions |  | Jules | 2007-01-25 | 2007-01-26 | 2007-01-25
Output additional ship emissions diagnostics |  | Jules | 2007-01-25 | 2007-01-29 | 2007-01-29
Allow output of grid variables in necessary output files |  | Jules/Bigyani | 2007-01-29 | 2007-01-29 | 2007-01-29
Incremental 1 year 4x5 FVGCM Combo Code Tests
Perform Baseline run |  | Bigyani | 2007-02-21 | 2007-02-24 | 2007-02-24
Baseline with new tropopause definition |  | Bigyani | 2007-02-24 | 2007-02-26 | 2007-02-28
Baseline w/ new trop, 124 species |  | Bigyani | 2007-02-26 | 2007-02-28 | 2007-03-01
Baseline w/new trop 124 sp & JPL06-2 |  | Bigyani | 2007-03-01 | 2007-03-02 | 2007-03-02
Baseline w/new trop 124 sp & JPL06-2 & H2 fix |  | Bigyani | 2007-03-03 | 2007-03-03 | 2007-03-05
HTAP simulations
Meet with GMI Scientists to determine requirements |  | Gary | week of 1/15/07 | week of 1/15/07 | 2007-01-18
Add code for new emissions diagnostics |  | Jules | 2007-02-08 | 2007-02-16 | 2007-02-15
Help with code for regional emissions experiments |  | Jules | 2007-02-16 | 2007-02-16 | 2007-02-16
Assist Huisheng with runs |  | Jules | 2007-02-21 | 2007-03-01 | 2007-03-05
Lightning Algorithm Runs (Trop Model 2x2.5)
Determine which algorithm to use |  | Gary | 2007-01-19 | 2007-01-19 | 2007-01-19
Generate namelist files |  | Gary/Megan | 2007-03-01 | 2007-03-05 | 2007-03-12
Edit aura2 restart file for troposphere run |  | Bryan | 2007-02-23 | 2007-03-01 | 2007-03-01
Processing GEOS4-DAS Met Fields
Modify scripts to process data in near-realtime |  | Megan | 2006-11-02 | 2006-11-29 | 2006-12-08
Test operationally modified scripts for 2x2.5 |  | Megan | 2006-12-09 | 2007-01-18 | 2007-01-10
Fix slp problem in near realtime script |  | Megan | 2007-02-09 | 2007-02-16 | 2007-02-16
Fix tropopause units |  | Megan | 2007-02-20 | 2007-02-26 | 2007-03-05
Reprocess fields for slp (Jul-Dec 2006) and tropopause pressure |  | Megan | 2007-02-27 | 2007-03-15 | 2007-03-09
Process archived 2006 met fields |  | Megan | 2007-01-11 | 2007-03-20 | 2007-03-09