## WBS_Status_List_Spread
WBS Number: |  |  | Description: | Direct FY07$ | Risk | Consequence | Severity | Liklihood | Mitigation
1.02.05 |  |  | Conceptual Design - Conventional Facilities | 4233810 | Complete
1.05.01 |  |  | Conventional Facilities Management | 4216378 | Level of effort exceeds estimate | Cost | low | low | Ensure adequate staffing level
| 1.05.01.01 |  | CF Design Phase Management | 2108189 | NSLS II Engineering | Cost
| 1.05.01.02 |  | CF Construction Phase Management | 6111597 | NSLS II Engineering | Cost
[5 empty] | Project stretch-out increases costs | Cost | low | moderate | Not controllable
1.05.02 |  |  | Conventional Facilities Design | 18152501 | Changes in requirements delay design | Cost and Schedule | moderate | moderate | Ensure active interface management
|  | 1.05.02.01.01 | CF Title I A/E Design | 2391833
|  | 1.05.02.01.02 | CF Title I Design Coordination | 48902
|  | 1.05.02.01.03 | CF Title I Design C/M Support | 120000
|  | 1.05.02.02.01 | CF Title II A/E Design | 9975000
|  | 1.05.02.02.02 | CF Title II Design Coordination | 490246
|  | 1.05.02.02.03 | CF Title II Design C/M Support | 690000
|  | 1.05.02.03.01 | CF Construction Phase A/E Support | 3000000
|  | 1.05.02.03.02 | CF Construction Phase Coordination | 1436520
1.05.03 |  |  | Conventional Facilities Construction | 146419321.6704 | Bid prices exceed estimate beyond contingency | Cost and Schedule | high | low | Ensure accurate estimate and independent estimate
Risks common to all construction activities |  |  |  |  | Bid and award cycle delay of critical path task | Schedule | moderate | low | Perform advance procurement planning
[5 empty] | Delays due to extraordinary weather | Cost and Schedule | low | moderate | Identify workarounds and oversee construction planning/scheduling
[5 empty] | Contractor failure to perform | Cost,Schedule,Technical | moderate | low | Thorough evaluation & selection of qualified contractors
[5 empty] | Extraordinary errors & omissions in design | Cost,Schedule,Technical | moderate | low | Thorough design QA check& CM review process
[5 empty] | Safety related work stoppage | Schedule | moderate | low | Enforce vigorous const. safety program and offer incentives/penalties
[5 empty] | Funding stretch-out delays work | Cost and Schedule | moderate | moderate | Not controllable
[5 empty] | Change in market availability/price | Cost and Schedule | low | moderate | Thorough material /market analysis and use of commodity price protection clauses
[5 empty] | Delay in identifying nonconformance | Schedule and Technical | moderate | low | Enforce vigorous construction inspection program
| 1.05.03.01 |  | CF Construction Management | 5983608 | Level of effort exceeds estimate | Cost | low | moderate | Clearly define workscope required
| 1.05.03.02 |  | Improvements to Land | 6028242 | Differing site conditions | Cost,Schedule,Technical | moderate | moderate | Perform thorough early site investigation/sampling
|  | 1.05.03.02.01 | Site Preparation | 3200621 | HDR/VJ Assoc.
|  | 1.05.03.02.02 | Site Restoration and Landscaping | 2827621 | HDR/VJ Assoc.
[5 empty] | BNL fails to clear site on time | Cost and Schedule | moderate | moderate | Closely coordinate requirements with BNL and get written agreement
| 1.05.03.03 |  | Operations Center | 5004454.2 | Delay in 2 story/3 story decision | Cost and Schedule | low | low | Require decision at award
| 1.05.03.04 |  | Injection Building | 6285851.5 | Booster/LINAC design changes | Cost,Schedule,Technical | moderate | moderate | Ensure active interface management
| 1.05.03.05 |  | RF Building | 2485278 | Cryo system requirements change | Cost,Schedule,Technical | low | moderate | Ensure active interface management
| 1.05.03.06 |  | Ring Building | 77709862.9426 | Change in Beneficial Occupancy requirements | Cost and Schedule | moderate | low | Get confirmation of requirements during design and update and confirm regularly
|  | 1.05.03.06.01 | Pentant 1& Service Building | 15817795.1085 | HDR/VJ Assoc.
|  | 1.05.03.06.02 | Pentant 2 & Service Building | 15559266.9585 | HDR/VJ Assoc.
|  | 1.05.03.06.03 | Pentant 3 & Service Building | 15444266.9585 | HDR/VJ Assoc.
|  | 1.05.03.06.04 | Pentant 4 & Service Building | 15444266.9585 | HDR/VJ Assoc.
|  | 1.05.03.06.05 | Pentant 5 & Service Building | 15444266.9585 | HDR/VJ Assoc.
[5 empty] | Change in lattice design | Cost,Schedule,Technical | high | low | Ensure active interface management
[5 empty] | Change in User requirements | Cost and Schedule | low | high | Establish beamline design criteria
| 1.05.03.07 |  | Lab-Office Buildings | 19058732.0278 | Change in User requirements | Cost and Schedule | moderate | moderate | Ensure active interface management
|  | 1.05.03.07.01 | LOB 1 | 7536148 | HDR/VJ Assoc. | Cost and Schedule
|  | 1.05.03.07.02 | LOB 2 | 7536148 | HDR/VJ Assoc. | Cost and Schedule
|  | 1.05.03.07.03 | LOB 3 | 3986436.0278 | HDR/VJ Assoc. | Cost and Schedule
| 1.05.03.08 |  | Mechanical Utilities | 10471791 | Differing site conditions | Cost and Schedule | low | high | Field verification of tie-in points during design
[5 empty] | Unable to isolate utilities for tie in | Cost and Schedule | moderate | low | Consult with O&M staff on workarounds
| 1.05.03.09 |  | Electrical Utilities | 11991502 | Delay in receipt of equipment | Schedule | moderate | low | Early procurement of critical items
[5 empty] | Unable to perform shutdowns for tie in | Schedule | moderate | low | Schedule tie-ins eartly and consult with O&M staff on workarounds
| 1.05.03.10 |  | LN2 & GN2 Distribution System | 1400000 | Nonconforming material | Schedule | low | low | Select qualified contractor, perform off-site inspections
| 1.05.03.11 |  | Chilled Water | 6797490 | BNL fails to fund prorated share of CCWF | Cost and Schedule | high | moderate | Get written agreement
[5 empty] | Delay in receipt/start-up of chillers | Cost and Schedule | moderate | low | Early procurement of critical items
1.05.04 |  |  | Integrated Controls & Communications | 660000 | Requirements change as ASD control matures | Cost, Schedule, Technical | low | moderate | Ensure active interface management
1.05.05 |  |  | Standard Equipment | 1400000 | Requirements exceed estimate | Cost | low | low | Detail requirements during design
1.05.06 |  |  | Commissioning | 900000 | Construction delays delay equipment start-up | Cost and Schedule | low | moderate | Coordinate with contractor to minimize impact
[5 empty] | Scope of work changes | Cost | low | low | Ensure active interface management