Introduction

This Process Flowchart displays the activities typically associated with establishing or relocating a large facilitY. The activities are guide for planning an acquisition program that intends to: (1) establish or relocate a large facility; (2) acquire, integrate, and test equipment and systems to be housed in the facility; (3) acquire real estate where the facility will be located; (4) reconfigure the airspace; and (5) obtain, relocate, and train human resources. Over time, instructions, guidance, good examples, best practices, and other work-related aids will be attached to each activity in the process flowchart so that the best experience of the agency is available on-line for every acquisition program.

Work Activity Descriptions

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |

Identify Key Planning Elements

|  | Facility acquisition programs typically involve more than contracting for the construction or relocation of a facility. They may involve the identification, acquisition, test, and integration of systems and equipment to be housed in the facility; the reconfiguration of airspace when traffic control facilities are consolidated; the purchase of real estate where the facility will be built; and the identification, relocation, and training of human resources. These key planning elements provide the basis for establishing the facility management team, |
| --- | --- |

| ANS Division lead | Key planning elements |
| --- | --- |
| AMS Section 2.5.1 |

Establish Facility Management Team

The appropriate ANS Division lead identifies headquarters and regional personnel that must be on the facility management team. This management team then identifies and obtains representation from the equipment IPTs that will provide systems and equipment to be housed in the facility, as well as any other important players. All facility team members must be involved in planning and executing the facility program from the beginning.

ANS Division lead

Facility management team

AMS Section 2.5.1

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |

Develop Acquisition Strategy

Using the results of Investment Analysis, the facility management team develops the overall strategy for implementing the facilities program within the cost, schedule, performance, and benefit boundaries of the Acquisition Program Baseline. This strategy defines the inter- and infra-agency agreements and resource transfers required to implement the program, particularly those involving the electronic equipment products teams who will provide hardware for the program. The strategy establishes how each element of the facilities program will be implemented, including construction of the facility itself, associated equipment and physical requirements, the acquisition of needed real estate, and any relocation and retraining of human resources. The acquisition strategy is recorded in the Acquisition Strategy Paper which must be approved before releasing any screening information request to begin a source selection process.

Facility team leader

Acquisition Strategy Paper

ANS-1

Director(s) of IPTs supplying equipment

Appropriate Regional Managers

Instruction for the ASP

Template for the ASP

AMS Section 2.5.1

Develop Integrated Program Action Plan

The Integrated Program Plan consolidates into one planning document all the actions that will be accomplished to execute the program within approved cost, schedule, performance, and benefit baselines. It unifies planning previously contained in such documents as the AP, PMP, ILSP, TEMP, PIP, RMP, and HFP. Approval of the Integrated Program Plan authorizes the release of formal requests for offer, transfer of funds, and commitment of interagency agreements.

Facility team leader

Integrated Program Plan

ANS-1

Director(s) of IPTs supplying equipment

Appropriate Regional Managers

Instruction for the IPP

Template for the IPP

AMS Section 2.5.1

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |

Establish Metrics to Measure Performance

Metrics are used as a basis for evaluating and optimizing program performance. Metrics should be derived from requirements and benefits in the Acquisition Program Baseline, and should be imbedded as evaluation criteria for contract award, when appropriate. Actual performance and benefits are measured during operational usage to determine whether predicted values are achieved.

Facility team leader with support from the facility management team

Performance measures

Facility team leader

AMS Section 1.13

Prepare Air Traffic Operations Plan

The Air Traffic Operations Plan describes the means and methodology for establishing Air Traffic operations in the facility(s). The plan defines the organization, structure, and schedule for achieving Air Traffic operations. It also identifies the operational, training, equipment, staffing, and other actions required for operating the facility.

Air Traffic member of the facility management team

Air Traffic Operations Plan

| Air Traffic member of the facility management team |
| --- |
|  | Prepare Airway Facilities Operating Plan |

The Airway Facility Operating Plan defines the organization, structure, and schedule for establishing Airway Facilities operations at the facility. It also identifies training, equipment, staffing, and other actions required for maintaining the facility and its associated hardware.

Airway Facilities member of the Facility team

Airway Facilities Operating Plan

| Airway Facilities member of the Facility team |
| --- |
|  | Develop Airspace Implementation Plan |

When air traffic control is consolidated as part of establishing or relocating a facility, an Airspace Implementation Plan is prepared which defines the airspace configuration and traffic control procedures that will be implemented. Typically, these changes are determined during Investment Analysis from simulations and modeling of the airspace. The Airspace Implementation Plan also sets out a schedule for implementing airspace reconfiguration, and defines roles and responsibilities for achieving the changes.

Air Traffic Management member of the facility management team

Airspace Implementation Plan

Air Traffic Management member of the facility management team

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| Reconfigure Airspace and Change Procedures |

The airspace is reconfigured and procedures are changed according to the Airspace Implementation Plan. Dual operations are typically run during the changeover until all new procedures are validated and verified as operationally safe.

Facility Air Traffic operators

Reconfigured airspace and changed operational procedures

| Air Traffic Management member of the facility management team |
| --- |
|  | Prepare Human Resources Management Plan |

The Human Resources Management Plan identifies the site-specific actions and activities that must be executed to establish needed human resources at each new facility. The plan defines the schedule, milestones, data sources, resources, and responsible organizations for all aspects of human resource transition planning. It is compatible with and supplemental to the Integrated Program Plan.

Regional member of the facility management team

Site-specific Human Resources Management Plan

| Leader of the facility management team |
| --- |
|  | Implement Permanent Change of Station |

All human resources necessary for implementing the Air Traffic and Airways Facilities operating plans are relocated to the new facility. Typically, this involves identifying and reassigning personnel, transferring job positions, and moving employees along with their families and household belongings.

Site or regional member of the facility management team working with appropriate personnel offices

Relocated human resources

|  | Prepare Human Resources Training Plan |
| --- | --- |

Program-wide training actions are contained in the Integrated Program Plan. Detailed, site-specific training plans may be required when additional human resources are needed at the site or when job responsibilities change substantially. Site-specific training plans are consistent with and supplemental to the Integrated Program Plan

Regional or site member of the facility management team

Site-specific Human Resource Training Plan(s)

Regional or site member of the facility management team

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| Train Human Resources |

The actions and products in the Human Resources Training Plan are obtained via contractor support, through the FAA Training Center in Oklahoma City, or by other means. Human resource training must be complete before the beginning of operational testing at the site.

Regional or site member of the facility management team

Human resource training

Prepare Systems Architecture Document

The Systems Architecture Document identifies the systems, subsystems, equipment, and their interfaces that will be resident in the facility. It also identifies the interfaces required to interconnect the facility with all satellite and remote facilities from which information is received or to which it is transmitted. The Systems Architecture Document should be consistent with the overall NAS Architecture.

Systems engineering member of the facility management team

Systems Architecture Document

| Facility team leader |
| --- |
|  | Obtain Agreements With Equipment IPTs |

These agreements define the specific responsibilities of the acquiring organization (facility program) and the organizations providing the equipment and systems to be housed in the facility. They define delivery quantities, delivery dates, funding, and services to be provided by each equipment IPT. Services include all actions necessary to acquire, transport, deliver, integrate, and test individual equipments and systems.

Facility management team and equipment IPTs

Agreements for all equipment and systems to be resident in the facility(s)

Leader of the facility team

| Leaders of equipment PTs and IPTs providing products to the facility program |
| --- |
|  | Define Equipment-Related Facility Requirements |

Equipment-related facility requirements include power, heating, ventilation, air-conditioning, space, weight, grounding, bonding, shielding, and lightning protection. These facility requirements should be attachments to the agreements with the equipment IPTs. They should be determined before initiating the facility A&E design.

Members of the facility management team representing equipment PTs and IPTs

Facility requirements related to support of housed equipment

Facility team leader

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| Define Equipment Delivery Dates |

Working closely with system and equipment IPTs, the Facility Management Team develops a schedule that defines when new and systems and equipment will be delivered for residence in the facility. The equipment delivery schedule provides the foundation for planning the facility program. Equipment IPTs are responsible for immediately notifying the Facility Management Team of any change in equipment delivery schedules.

Facility Management Team

Equipment IPTs

Consolidated equipment delivery schedule for all equipments to be resident in the facility

|  | Acquire Systems and Equipment |
| --- | --- |

Equipment IPTs/PTs acquire the systems, equipment, and interfaces that will be resident within the facility. These may involve procurement of nondevelopmental products and services or may require development. Agreements with IPTs/PTs must include sufficient time to implement all necessary actions. In cases of substantial developmental risk, agreements with IPTs may require contingency options for delivery of alternative equipment until developmental capability is available. IPTs/PTs are responsible for delivering products and services at the time and within the cost specified in their agreement. All contracts and contract modifications for any design, development, test, manufacture, delivery, and installation of systems and equipment are managed by the responsible PTs or IPTs. Any delays or problems must be identified early to the Facility Management Team so work arounds can occur.

Equipment PTs and IPTs

Systems and equipment as per agreement

Update Material Delivery Forecast Model

The Material Delivery Forecast Model specifies when electronic equipment and systems will be delivered to the facility. This forecast model must be current at all times since it dictates the capability the facility must provide over time to meet the requirements of resident systems and equipment. As delivery dates change, system and equipment IPTs are responsible for ensuring the changes are reflected in the forecast model.

Oklahoma Cite maintains the forecast model

System//equipment IPTs keep delivery dates current

Material Delivery Forecast Model

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| Develop Real Estate Evaluation Criteria |

A site evaluation team is formed to develop criteria that depict a preferred site location for the facility. These criteria include “Quality of Life” issues in addition to size, location, access, zoning, utilities, and environment.

Site Evaluation Team

Site selection criteria and desirable site locations

| Facility team leader |
| --- |
|  | Advertise Market Survey |

The regional office issues a market survey with the evaluation criteria developed by the site evaluation team. The market survey notifies land owners of the FAA’s intention to acquire real estate that is affordable and best satisfies the agency’s evaluation criteria.

Regional contracting officer

Market survey

Evaluate Candidate Sites

The team evaluates candidate sites for the facility, identifies the most desirable locations, determines right-of-entry, and performs title searches. It also contracts for engineering studies, EDDAs, and preparation of Environmental Impact Statements or Finding of No Impact Statements, as appropriate.

Site evaluation team

Candidate sites

| Facility team leader |
| --- |
|  | Evaluate Lease Versus Purchase |

The site evaluation team determines the costs and benefits associated with leasing or purchase of candidate sites. This information is used by the source selection official as a basis for deciding how to obtain the best site for the facility

Site evaluation team

Lease versus Purchase Decision Paper

| Facility team leader |
| --- |
|  | Negotiate and Obtain Real Estate |

Real estate may be obtained competitively or sole source. When obtained competitively, the regional contracting officer negotiates with each offeror and recommends award to the one offering best value to the government. When negotiating with a single source, the property may be obtained by award when a reasonable price can be agreed to or by condemnation when agreement cannot be reached on a price.

Regional contracting officer

Acquired real estate

Regional contracting officer

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| Develop Facility Design Criteria |

Design criteria for the facility are derived from the facility, infrastructure, and equipment requirements in the Acquisition Program. The design criteria are the basis for obtaining the National facility design.

Facifity Management Team

Facility design criteria

Facility Management Team leader

Obtain National Facility Design

When a new class of facility is required, a national facility design is developed in accordance with the facility design criteria. Typically, national designs are developed by a headquarters program office using the national omnibus A&E contract. The national design becomes the basis for all facilities of a particular class that are constructed as part of the National Airspace System.

Facility team

Bid-ready national design package

| Facility team leader |
| --- |
|  | Adapt National Design to Local Site |

Site-specific adaptations may be required for the unique environmental and land characteristics at each site. These adaptations are typically contracted by the regional office responsible for constructing the facility. Contracting options include a competitive request for offer, sole source, or use of the national omnibus A&E contract. The product is a bid-ready design package containing drawings, design data handbook, and construction cost estimate.

Regional contracting officer supported by the Facility team

Site-specific bid-ready design package

Facility team leader

Award Facility Construction Contract

The Facility Management Team prepares a Division One Specification, including an engineering procurement request, which is typically issued as a request for bid by the regional contracts division. The request for bid encompasses all physical needs of the facility program including telecommunications, roads, sewage, water, and power. A contract is awarded to the responsive bidder offering best value to the government.

Regional contracting officer supported by the Facility Management Team

Contract for facility construction

Source selection official (usually the regional Administrator, unless otherwise specified by the JRC at the investment decision)

AMS section 3.2.2

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |

Construct Facility

Construction begins with issuance of a notice to proceed by the regional contracting officer, and ends when the responsible engineer notifies the regional contracts division that the contractor has fulfilled all contract responsibilities. The government monitors construction for conformance with the facility design.

Regional contracting officer and the responsible engineer with support from the Facility team

Constructed facility(s)

| Regional contracting officer(s), with support from the Facility team |
| --- |
|  | Develop Facility Test Plan and Procedures |

A test plan and procedures is developed for conducting the facility Contract Acceptance Inspection. It identifies test resources, personnel, and training; defines test requirements, objectives, and criteria; and establishes test schedules.

Perform Facility Contract Acceptance Inspection

The regional office assigns a responsible engineer to the construction project who coordinates with the contractor, and ensures the contractor performs according to the terms of the contract. The responsible engineer coordinates and oversees the Contract Acceptance Inspection.

Regional responsible engineer

Accepted facility

| Regional responsible engineer or designated AF official |
| --- |
|  | Install Systems and Equipment | The appropriate PT or IPT deliver and install systems and equipment, as per agreements established early in the facility program. The process begins with notification by the equipment provider of equipment delivery, and concludes with equipment checkout. Equipment installation may require site preparation work by the region or installation contractor. |

Equipment PT or IPT

Installed systems and equipment

| Technical on-site representative |
| --- |
|  | Integrate and Test Systems and Equipment | Each system or piece of equipment is integrated with the facility and other interfacing systems/equipments, and then tested to ensure each element meets its performance requirements and works with all interfacing elements. Typically, this is the responsibility or the equipment PT or IPT. |

Equipment PTs and IPTs

Integrated and fully functional systems and equipment

Technical on-site representative

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| Conduct Operational Test and Evaluation | Fully integrated systems and equipment are tested by FAA operations and maintenance personnel using standard operational procedures to evaluate the effectiveness and suitability of the facility, including interoperability, survivability, maintainability. The principal objective of OT&E is to resolve critical operational issues, and to verify the adequacy of support material such as manuals, handbooks, and other documentation for operations and maintenance. |

Regional Air Traffic and Airway Facilities personnel

OT&E test report

| Regional Air Traffic and Airway Facilities personnel |
| --- |
|  | Conduct Joint Acceptance Inspection | The Joint Acceptance Inspection verifies the facility is able to perform its specified functions. |

Responsible engineer

Facility acceptance as ready to perform air traffic control functions

| Regional Air Traffic and Airway Facilities personnel |
| --- |
|  | Commission Facility | Commissioning is the formal placement of a facility into operational service in the National Airspace System. |

Regional Air Traffic and Airway Facilities representative

Commissioned facility

Designated regional Air Traffic person

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |

Assess Facility Condition

| The performance of the facility is monitored, tracked, and assessed on a continuing basis during the In-Service Management phase. Performance data is evaluated against performance metrics for the facility to determine whether it continues to meet mission requirements. The capability of the facility is also evaluated periodically against the projected demand for services to identify when new construction or an expansion in overall capability will be needed. This involves close and open communications with customers and users of the services. The intent is to plan for future requirements so necessary improvements and support will be in place to provide the additional service as it is needed. Requirements for facility modernization construction contracts are derived from the facility condition index. | Regional Airway Facilities and Air Traffic representatives |
| --- | --- |

Updated facility condition index

Appropriate ANS facility division manager

AMS section 1.13

New Construction Within Scope of Sustaining Engineering?

A determination is made whether needed modifications and improvements can be accomplished within approved sustainment engineering funding in the facility program Acquisition Program Baseline.

Regional Airway Facilities representative

Approved Regional sustaining projects

Appropriate ANS facility division manager

Implement Sustainment engineering

Improvements and corrective actions that can be accomplished within approved sustainment engineering budgets are implemented.

Regional responsible engineer

Complete facility sustaining projects

Designated regional Air Traffic and Airway Facilities personnel

AMS Section 2.6

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |

Prepare for Investment Decision

When the projection of needed services exceeds the capacity or life of the facility, an Investment Decision by the Joint Resources Council is required. The Facility Management Team prepares for an investment decision that will determine (1) whether mission need is still valid, (2) whether the need is best satisfied by a continuation or expansion of the existing program or by some other means, and (3) whether needed capabilities are affordable in competition with all other agency needs.

Facility team leader

Investment Analysis Report

Revised Acquisition Program Baseline

Re-validated or revised Mission Need Statement

Associate Administrator of the sponsoring organization and Acquisition Executive

Associate Administrator of the sponsoring organization

Instruction for the IAP

Template for  the IAP

Instruction for the APB

Template for  the APB

Instruction for the MNS

Template for  the MNS

AMS Section 2.7

Investment Decision Approved?

The Joint Resources Council decides whether to approve a service-life extension based on the Investment Analysis Report and affordability. If approved, the extension is fully funded according to the revised Acquisition Program Baseline.

JRC Decision Memorandum

JRC chaired by the Acquisition Executive

Template for the JRC Decision Memorandum

AMS section 2.7

Re-plan Within Budget

If the Joint Resources Council does not approve additional funding for the facility program, the Facility Management Team uses existing funding authority to make what ever improvements are most needed.

Facility Management Team

Affordable facility engineering projects

Facility Management Team leader

| Activity Title | Activity Description |
| --- | --- |

Responsible

| Agent | Product | Approving Agent | Acquisition Tools |
| --- | --- | --- | --- |
| New Facility Approved? |

An Investment Decision to increase capability may be satisfied by expanding or upgrading an existing facility or by constructing a new one

Joint Resources Council

Go to Modernize Flowchart

If the Joint Resources Council approves extension of the service-life of the existing facility, the program re-enters solution implementation for the planning and executing activities to achieve the extension capability. This activity is defined in the Modernize Facility Flowchart.

Facility team

Plan Facility Decommissioning

If the Joint Resources Council approves construction of a new facility, the existing facility may be decommissioned and dismantled when the new facility becomes operational. Planning for decommissioning and removal must encompass the transition of services to the new facility, as well as the removal and disposition of residual GFE/GFI and real and personal property from the existing facility. This may involve disposal, or it may involve transition to other uses and programs.

Facility team leader with support form the regional office

Integrated Program Plan modified to plan decommission

facility

Site-specific restoration plan

Instruction for the IPP

Template for the IPP

AMS Section 2.8

Remove and Dispose Residual Equipment

GFI/GFE and any other contract-related real or personal property are disposed according to the restoration plan for each site.

Regional contracting officer Facility team member representing each site

AMS Section 2.8

Restore Site(s)

Each site must be restored according to each site restoration plan.

Facility team member representing each site

Restored site(s)

Regional site manager

AMS Section 2.8