Module 15:  Business, Cost Estimating and Financial Management

Module Outline

| Topic | Time Frame |
| --- | --- |
| Introduction/Objectives | 10 minutes |
| Cost Estimating | 75 minutes |
| PPBE Process | 30 minutes |
| Performance Measurement Methods | 50 minutes |
| Review | 10 minutes |
| Estimated/Approximate Time for Module Completion | 3 hours |

Topic 1: Introduction/Objectives

Instructor Notes: Module 15 – Business, Cost Estimating and Financial Management describes the different processes for financial management and performance measurement used during the life-cycle of a system or product. These include: cost estimating, cost analysis, financial planning, budgeting, Benefit-Cost Analysis, and Earned Value Management.

| Topic 1: Introduction/Objectives (continued) |
| --- |
|  | Notes: Slide # HERE (Topic # - Slide #) |

CONTENT TO BE PRESENTED: Key Points: The Federal Government uses many different methods to measure performance and cost. They do this in order to tell whether or not a contractor is working in a satisfactory way and providing results in a timely fashion. Some of these important methods include: Cost Estimating Cost Analysis Benefit-cost Analysis Earned Value Management And many others We will be covering some of these methods throughout this module.

| Topic 1: Introduction/Objectives (continued) |
| --- |
|  | Notes: Slide # HERE (Topic # - Slide #) |

CONTENT TO BE PRESENTED: Key Points: Objectives At the end of this module, you will be able to: Describe the different practices associated with cost-estimating. The practices include cost-estimating, cost analysis, and reconciliation of cost estimates Discuss the elements of financial management in the federal government. You will learn about the extremely important function of budget planning and analysis.

| Topic 1: Introduction/Objectives (continued) |
| --- |
|  | Notes: Slide # HERE (Topic # - Slide #) |

CONTENT TO BE PRESENTED: Key Points: Objectives At the end of this module, you will be able to (continued): Identify the important forms of performance measurement including Earned Value Management and Benefit-Cost Analysis. You will learn how to use certain important performance measurement tools to track the success of a program or project. Define the different procedures included in budget analysis. You will learn how to analyze budgets for government acquisitions.

Topic 1: Introduction/Objectives (continued)

Instructor Notes: This concludes the topic on the introduction and objectives. After addressing any questions the participants may have, inform them that we will be moving on to the next topic: Cost Estimating.

What questions do you have regarding the Introduction/Objectives?

Topic 2: Cost Estimating

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Cost estimates are one of the fundamental building blocks of the acquisition process. Cost estimates and the supporting budget are a part of the baseline against which a program's progress and success are measured They evaluate whether a system is affordable and consistent with the guidelines set out for it and the overall long-range investment and force structure plans Cost estimates also form the basis for budget requests to Congress

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Life-Cycle Cost Estimates are a product of an estimating procedure that specifies the expected dollar cost to develop, procure, operate, support and dispose of a given system or product. Must identify all elements involved in the life-cycle of a system or product, regardless of funding source or management control The importance of Program Cost Estimates: Basis of program budgets and are also critical in the day-to-day management of a program. Current acquisition regulations require programs to maintain a program cost estimate. It is necessary to support headquarters-directed analyses, to defend program budget requirements, or to choose between potential contractors in source selection.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Let us discuss how to develop a Preliminary Cost Estimate. First you must define the Estimating task (Plan the work to be accomplished) Includes: Understanding the level of detail required Determining the accuracy of the estimate Outlining all characteristics of the system being estimated Establishing ground rules and assumptions Summarizing all of this information in an estimating plan Then define all work or activities Consists of data research, collection, and analysis Preliminary decision about which estimating techniques to use must also be made Work Breakdown Structure (WBS) contains a wealth of information regarding the scope of work upon which to base an estimate

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: There are three types of estimates: Preliminary, Budgetary and Definitive. The Preliminary estimate is performed early on in the life of the project without detailed data. This estimate is usually requested during the initial evaluation of a project and is often used to establish the initial funding level on both the resources and budget levels. It is also referred to as a rough order of magnitude, conceptual, or feasibility estimate. The Budgetary estimate is developed during planning from a more detailed project analysis. This estimate is generally required for budgeting. It is also referred to as a design, control or appropriation estimate. The Definitive estimate is a detailed, bottom-up estimate used for creating a cost estimate baseline and obtaining firm commitments. It is prepared from well-defined requirements and specifications. It occurs during the executing and monitoring & controlling phase, or possibly during detailed planning.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Then you must determine Estimating Methodology. Variety of techniques are available to develop a cost estimate One chosen depends on the adequacy of the program definition, the level of detail required, the availability for data, and time constraints Analyst must have an understanding of the available data models and techniques and their preferred applicability crucial that the cost analyst have a clear and complete understanding of the program requirements More than one technique may be used to estimate cost for a single program, depending upon the phase of work and the information available about the system

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Determining Estimating Methodologies (continued) In deciding which technique to use, it is important to consider several factors: Availability of historical data Level of detail required Adequacy of system description Time/Resource constraints Program and project managers must ensure the cost estimate completely defines the program and is technically sound and reasonable The Cost Estimate must be defensible with well-reasoned analysis.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: There are several methods for Cost Estimating. They are: Analogy Simplest form of estimating Uses historical information available for a similar program already completed to estimate cost for proposed program Estimator makes a subjective evaluation of the differences between the new system and historical systems Estimating the cost of a new model car based on what you paid for the same make and model five years ago. In many cases, it is necessary to compare subsystems of the new system or product to subsystems of several old systems or products in order to make the most accurate comparisons.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Analogy (continued) Engineer will typically be asked to make a technical evaluation of the difference between the new system and the old system Based on evaluation, cost estimator must assess the cost impact of the technical differences This method only appropriate very early in the program life cycle when the system is not yet fully defined. Important that differences between the existing system and the proposed system are identified and their impacts estimated Advantage Based on actual experience Disadvantage For the most part, no truly similar programs exist Subjective evaluations must be made when determining the cost impact

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Another method is engineering (Bottoms-up). Generally a very detailed, costly and time-consuming process for estimating costs Involves associating costs to the lowest levels of a definable work within the WBS Direct labor hours required to complete the work are estimated from engineering drawings and specifications Done by an industrial engineer using company or general industry standards Raw materials and purchase parts requirements are also estimated Remaining cost elements also must be factored in: tooling, quality control, other direct costs, and various overhead charges including systems engineering and project management

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Engineering (Bottoms-up) (continued) Most often used late in the development or early in the production phases Encourages the contractor to do his homework early on and define all work down to the lowest level of the WBS Also is a great process control technique at the production facility Advantage Provides a detailed cost estimate Can be more accurate than other methods Disadvantage Tends to be time and cost intensive Historical data not always available to support estimates Tendency to rely extensively on judgment

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Another method is using actual costs (Extrapolation). Using actual cost data from a system to extrapolate the future estimated costs of building the same system Probably most accurate cost estimating method Actual cost experience on prototype units, early engineering development hardware, and early production hardware for the program should be used as much as possible Usually used in the late phases of acquisition, such as production and for replenishment spares Advantage Based on actual costs Disadvantage Often do not have actual costs until late in the acquisition process

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: A fourth method is the parametric (Statistical) method. Uses a database of similar systems and generates an estimate based on the relationship between cost and system performance or design characteristics Assumes that there is a relationship between some system or product parameter and cost Appropriate early in the program life cycle when detailed design specifications are not available Database of like systems, performance specifications and costs must be available Often serves as a useful check of an estimate made using another method

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Parametric (Statistical) (continued) Advantage Fast and easy to use Easy to change to do what-if drills Disadvantage Relies heavily on the timeliness and accuracy of the database Must rely on correlations between cost and performance features/characteristics Historical data is not always available to support these estimates

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Parametric (Statistical) (continued) Use regression analysis to attempt to quantify the relationship between variables and then describe the accuracy of that relationship Has two parts: Quantifying the relationship between the variables using a mathematical expression Describing the accuracy of the relationship by computation of various statistics that indicate how well the mathematical expression describes the relationship between the variables Regression analysis can be very detailed and requires extensive training

Topic 2: Cost Estimating (continued)

Activity: Activity Purpose: This activity will help to reinforce the information presented on the different techniques for cost estimating. Activity Length: 10 minutes Activity Instructions: Read the following scenarios and through class discussion, determine the correct cost estimating method to use (a mention of the four possible answers may be provided to the participants as well: Analogy, Engineering, Actual, and Parametric). It is early in the program life cycle of new computer software that is being created for the Department of Justice. Since it just a newer version of the software, and not an entirely new product, there is historical data available. (Analogy or Engineering). New police headquarters are being designed for placement outside of Phoenix, Arizona. The headquarters will be almost identical to the police headquarters in Tempe, Arizona, which was recently constructed. (Analogy) The 101st system of its kind is being created by a group of scientists in Washington D.C. It is early in the program life-cycle. The changes from system to system are negligible. (Actual) The “first ever” matter-transporter has been in development for almost 18 months due to budget issues. There is no historical data that can be used. (Engineering)

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Escalation Program cost estimates are normally done in constant year dollars Ignoring effects of inflation and the budgeting implications of using various appropriations, or “colors of money” Allows you to make cost comparisons across the years, see where cost growth exists, and see the impact of the learning curve on production estimates Current-Year Dollars: include the effects of inflation or escalation over the time period that those funds will be expended (paid out)

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Escalation (continued) Constant Dollars: Method of relating dollars across the years of a program’s life-cycle by removing the effects of inflation and showing all dollars at the value they would have in a selected base year (BY) Base Year (BY): A reference period which determines a fixed price level for comparison in economic escalation calculations and cost estimates Price level index for the BY is 1.000. Constant dollars have the value they would have in a selected base year (BY)

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Escalation (continued) Life Cycle Cost Estimates (LCCEs) are prepared in terms of constant/base-year dollars, where the base year is usually the year of program initiation. In order to input estimates into PPBE process, must convert the constant dollars to “current” or “then-year” dollars to account for inflation Then-year dollars will be used as input to the POM (Program Objectives Memorandum), BES (Budget Estimate Submission), and the President’s Budget.

Topic 2: Cost Estimating (continued)

Activity Activity Purpose: This activity allows the participants to review an example and then practice cost estimating skills. Activity Length: 10-15 minutes Activity Instructions: Break down the class into groups of 4. Have each group read the following scenario and determine a cost estimation for the best possible alternative. Give the groups 5-10 minutes to discuss and determine the answer and then share answers from the group as part of a class discussion. The Slate Construction Company has been contracted to build a new office that will connect to a Federal Building in Washington D.C. The exact layout of the office has not been determined. Construction costs will be $350/square foot. The office will be in the shape of a circle with a diameter of 30 ft. The contractor has been allotted 2500 hours of labor for this project, which has not been considered for the cost of each square foot. There will be 10 construction workers that will be paid $10/hour, with a $12 base rate for each day worked (they receive this on top of their hourly wage). They can only work 8 hours a day. Determine a cost estimate for this project. Answer: Construction costs (apart from labor) = 15 x 15 x (x $350 = $247,275 Labor = (2500 x 10) + (12 x 31) = $25,372 Cost Estimate = $25,372 + $247,275 = $272,647 (To tie the activity a bit tighter into the topic, consider asking the participants once they have finished with the math, to report what estimating technique they used. The correct answer is Parametric.)

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: One way to distinguish between cost analyses and cost estimating is the way in which they are processed critically. Cost estimating is often times viewed as a forward looking process Cost analysis may be viewed as a backward looking process. Let us discuss Cost Analysis in greater detail.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Cost Analysis Review and evaluation of the separate cost elements and profit/fee in an offeror’s or contractor’s proposal Includes cost or pricing data or information other that cost or pricing data And, the application of Judgment Used to determine how well the proposed costs represent what the cost of the contract should be, assuming reasonable economy and efficiency You must use cost analysis to evaluate the reasonableness of cost elements when cost or pricing data are required. You may also use cost analysis to evaluate information other than cost or pricing data to determine cost reasonableness or cost realism.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Cost Analysis (continued) A cost is reasonable if, in its nature and amount, it does not exceed the cost which would be incurred by a prudent person in the conduct of competitive business. Costs in an offeror’s proposal must be: Realistic for the work to be performed under the contract Reflect a clear understanding of contract requirements Consistent with the various elements of the offeror's technical proposal Perform price analysis even when you perform cost analysis Assuring the reasonableness of individual elements of cost does not always assure overall price reasonableness

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Suppose that you wanted to acquire a custom-made car identical to a Pontiac Trans Am. Your neighborhood mechanic has agreed to build the car for you. Before building the car, the mechanic obtains competitive quotes on all the necessary parts and tooling, pays laborers only the minimum wage, and asks for a very meager profit. How will the newly assembled car compare to an actual Trans Am, built on the assembly line? Most likely, it will be about ten times as expensive. Parts alone may be five times more expensive. The entire cost of tooling will be charged to one car. Labor, although cheaper per hour, will likely not be as efficient as assembly-line labor. Is the price reasonable? That decision can only be made using a thorough price analysis, and is the reason why it is so important.

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Here are the Cost Analysis Techniques and Procedures as described in FAR 15.404. The following techniques should be used, as appropriate, for cost analysis Evaluate cost elements, including: The necessity for and reasonableness of proposed costs, including allowances for contingencies Projections of the offeror's cost trends, on the basis of current and historical cost or pricing data or information other than cost or pricing data A technical appraisal of the estimated labor, material, tooling, and facilities requirements, and scrap and spoilage factors The application of audited or negotiated indirect cost rates, labor rates, cost of money factors, and other factors

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Cost Analysis Techniques and Procedures as described in FAR 15.404 Evaluate the effect of the offeror's current practices on future costs. Ensure that the effects of inefficient or uneconomical past practices are not projected into the future In pricing production of recently developed complex equipment, perform a trend analysis of basic labor and materials even in periods of relative price stability

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Cost Analysis Techniques and Procedures as described in FAR 15.404 Compare costs proposed by the offeror for individual cost elements with: Actual costs previously incurred by the offeror Previous cost estimates from the offeror or from other offerors for the same or similar items Other cost estimates received in response to the Government's request Independent Government cost estimates by technical personnel Forecasts or planned expenditures

Topic 2: Cost Estimating (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Cost Analysis Techniques and Procedures as described in FAR 15.404 (continued): Verify that the offeror's cost submissions are in accordance with the contract cost principles and procedures in FAR Part 31 and any applicable Cost Accounting Standards Board Cost Accounting Standards. Determine whether any cost or pricing data necessary to make the contractor's proposal accurate, complete, and current have not been either submitted or identified in writing by the contractor. If there are such data: Attempt to obtain the data and negotiate using the data obtained Or, make satisfactory allowance for the incomplete data Analyze the results of any make-or-buy program reviews, in evaluating subcontract costs.

Topic 2: Cost Estimating (continued)

Instructor Notes: This concludes the topic on Cost Estimating. After addressing any questions the participants may have, inform them that we will be moving on to the next topic: Planning, Programming, Budgeting, and Execution Process.

What questions do you have regarding Cost Estimating?

Topic 3: PPBE Process for Federal Acquisitions

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The Planning, Programming, Budgeting, and Execution (PPBE) process is the Department of Defense (DoD) internal methodology used to allocate resources to capabilities deemed necessary to accomplish the Department’s missions. The PPBE is primarily used for two objectives: The PPBE outputs funding proposed to be included in the President’s Budget (PB) which is submitted to Congress. The PPBE provides Combatant Commanders (COCOMs) with the optimal mix of forces, equipment, and support attainable within established fiscal constraints.

Topic 3: PPBE Process for Federal Acquisitions (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The PPBE is a calendar-driven process. Therefore, it is important to view required actions, events and decisions along a timeline. There are four steps that make up the PPBE: Planning Programming Budgeting Execution

Topic 3: PPBE Process for Federal Acquisitions (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The first phase of the PPBE is called the Planning phase. The planning phase identifies the capabilities required to deter and defeat threats. It defines for the upcoming Programming Phase national defense policies, objectives, strategy, and guidance for resources and force requirements to meet the capabilities and objectives.

Topic 3: PPBE Process for Federal Acquisitions (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The second phase of the PPBE is called the Programming phase. The programming phase is designed to allocate resources in varying support roles. It is during this phase that previous planning decisions, programming guidance, and Congressional guidance are translated into detailed allocation of time-phased resource requirements which include forces, personnel, and funds.

Topic 3: PPBE Process for Federal Acquisitions (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The third phase is called the Budgeting Phase. This phase occurs concurrently with the Programming phase. After the submission of the Program Objectives Memorandum (POM) and the Budget Estimate Submission (BES), budget analysts from the Office of Management Budget (OMB) conducts a review of the BES portion of the Components’ submission.

Topic 3: PPBE Process for Federal Acquisitions (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The fourth and final phase is called the Execution Review phase. The Execution review phase is intended to prioritize the programs which best meet government strategies. The purpose of the Budget review is to decide how much to spend on each program while the purpose of the Execution Review is to assess what is received for the money spent.

Topic 3: PPBE Process for Federal Acquisitions (continued)

Instructor Notes: This concludes the topic on the PPBE Process for federal aquisitions. After addressing any questions the participants may have, inform them that we will be moving on to the next topic: Performance Measure Methods.

What questions do you have regarding the PPBE Process for federal acquisitions?

Topic 4: Performance Measurement Methods

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Three major performance measurement tools are as follows: Benefit Cost Analysis (BCA) Earned Value Management (EVM) and Return On Investment (ROI). Let us look at Benefit Cost Analysis first. Program and project managers must prepare, update, and submit to the office of Management and Budget representative a benefit cost analysis For each new, modified, or fully integrated program or project Level of detailed analysis in a BCA must be: Proportionate to the size of the investment and rely on systematic measures of mission performance Consistent with the methodology described in OMB Circular A-94, “Guidelines and Discount Rates for Benefit-Cost Analysis of Federal Programs.”

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Program/project managers must: Follow regulatory approval thresholds Apply the BCA process Determine BCA pitfalls and limitations OMB A-94 should be used for all investments Use the Clinger Cohen Act for information technology (IT) investments and criteria for BCA OMB A-11 and the FAR require that a BCA be included with the annual budget when: An IT initiative exceeds $30 M over the system’s life cycle Or exceeds $10 M in any one year If life cycle cost is below $10M, simplified BCA is required

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Another source for guidelines associated with BCA is OMB Circular A-94, “Guidelines and Discount Rates for Benefit-Cost Analysis for Federal Programs” BCA is required for development, integration or maintenance projects that exceed $100K. The BCA effort should be tailored to the size of the project.

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Let’s take a look at the BCA Process. As you know, the BCA process is a systematic methodology for comparing alternative means of meeting a specific objective It consists of eight steps One or more steps may be emphasized, depending on the stage of the project life cycle

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Steps: Establish and define the goals or objectives Formulate appropriate assumptions Identify alternatives for accomplishing the objective Determine the benefits and costs of each alternative Evaluate alternatives by comparing their benefits and costs Test the sensitivity of the analysis outcome to major uncertainties Present the results Recommend an alternative

Topic 4: Performance Measurement Methods (continued)

Activity: Activity Purpose: This activity will provide the participants with an example of Benefit-Cost Analysis. Activity Length: 10 minutes Activity Instructions: Discuss as a class. Use the following information to determine whether the purchase of a new stamping machine would be a wise investment for your department. (Costs shown are per month and amortized over four years.) Purchase of Machine = -$20,000 includes interest and taxes Installation of Machine = -$3,125 including screens & removal of existing stampers Increased Revenue = $27,520 net value of additional 100 units per hour, 1 shift/day, 5 days/week Quality Increase Revenue = $358 calculated at 75% of current reject rate Reduced material costs = $1,128 purchase of bulk supply reduces cost by $0.82 per hundred Reduced Labor Costs = $18,585 3 operators salary plus labor o/h New Operator = -$8,321 salary plus overhead. Includes training Utilities = -$250 power consumption increase for new machine

Topic 4: Performance Measurement Methods (continued)

Activity: (continued) Insurance = -$180 premiums increase Square footage = 0 no additional floor space is required Answer: Benefits total $47,591 and Costs total $31,876 Benefits – Costs = Net Savings per Month = $15,715 Your cost benefit analysis clearly shows the purchase of the stamping machine is justified. The machine will save your company over $15,000 per month, almost $190,000 a year.

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Program/project managers must demonstrate a projected Return of Investment on all investments. Must be clearly equal to or better than alternative uses of available public resources ROI must be evaluated on the following criteria: Improved mission performance in accordance with Government Performance Results Act (GPRA) measures Reduced cost Increased quality Improved speed and/or greater flexibility Increased customer and employee satisfaction

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Return of Investment (ROI) (continued) ROI analysis must provide a quantifiable method for assessing, justifying, and prioritizing project funding It also must, where appropriate, reflect actual returns observed through pilot projects and prototypes

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Earned Value Management (EVM) EVM is another important program/project management technique. Integrates technical performance requirements, resource planning, with schedules, while taking risk into consideration Major objectives: Encourage contractors to use effective internal technical, cost and schedule management control systems Permit the customer to rely on timely data produced by those systems for better management insight Data is then used for determining product-oriented contract status, and projecting future performance based on trends to date. Also, EVM allows better and more effective management decision making.

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: EVM and Management Needs A fundamental requirement for managing any major acquisition system is insight into the contractors' performance, specifically the management and control. Proper EVM implementation ensures that the PM is provided contractor performance data that: Properly relates cost, schedule, and technical accomplishment. Relates time-phased budgets to specific contract tasks and/or statements of work (SOW). Objectively measures work progress. Allows for informed decision making and corrective action. (continues on next slide)

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: EVM and Management Needs (continued) Is valid, timely, and able to be audited Allows for statistical estimation of future costs Supplies managers at all levels with status information at the appropriate level, and Is derived from the same EVM system used by the contractor to manage the contract.

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Components of program/project management: Technical Performance Cost Resources Schedule Time Risk EVM provides an objective measurement of how much work has been accomplished Management team can readily compare how much work has actually been completed against the amount of work planned to be accomplished All work is planned, budgeted, and scheduled in time-phased “planned value” increments constituting a Performance Measurement Baseline (PMB)

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Graph illustrates a task with a total budget amount of $240k, which is planned for accomplishment over 24-month time frame "Time-now" line shows that $100k of the project resources was planned to be completed at this point in the project Project was planned to be 41.6% complete ($100k / $240k) at this point in time As work is performed, it is "earned" on the same basis as it was planned, in dollars or other quantifiable units such as labor hours Comparing earned value with the planned value measures the dollar value of work accomplished versus the dollar value of work planned Difference is called a schedule Variance Earned Value – Planned Cost = Schedule Variance (SV)

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Task was planned to have accomplished $100k worth of work in twelve months Real accomplishment was only $60k Graph shows a "behind schedule" condition Schedule variance in dollars would be a negative $40k $60k - $100k = ($40k)

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: EVM (continued) Value for the work performed compared with the actual cost incurred for the work performed, provides an objective measure of cost efficiency Any difference called a cost variance Earned Value - Actual Costs = Cost Variance (CV) Negative variance means more money was spent for the work accomplished than was planned. Positive variance means less money was spent for the work accomplished than was planned to be spent

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: EVM (continued) From the performing organization's own accounting system, we determine the actual costs for performing the $60K work was $110K When actual costs are compared with the earned value of $60K, the difference is the cost variance Earned value of $60K less the actual cost of $110K, is a negative cost variance of $50K Our example shows an overrun condition of $50K $60k - $110k = ($50k) Analysis of these variances should reveal the factors causing the deviation from plan

Topic 4: Performance Measurement Methods

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: EVM (continued) Task Manager uses information in conjunction with his knowledge of the task, to project an estimate to complete for this task Task Manager analyzes variances resulting from comparisons of these five basic data elements: Planned work Work accomplished Actual costs Total budget at completion Estimate at completion Work breakdown structure provides a useful framework for summarizing this performance information for all levels of management

Topic 4: Performance Measurement Methods

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: EVM (continued) EV improves on the "normally used" spend plan concept (budget versus actual incurred cost) by requiring the work in process to be quantified Planned value, earned value, and actual cost data provide an objective, quantifiable measurement of performance Enables trend analysis and evaluation of any cost estimate at completion within multiple levels for the project EVM valuable tool in the program/project manager’s “toolbox” for gaining valuable insight into project performance Tool that integrates technical, cost, schedule and risk management Also provides valuable quantifiable performance metrics for forecasting at-completion cost and schedule for their project.

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Successful Government Implementation of EVM: Example Lawrence Livermore Labs (part of the Energy Department’s National Nuclear Security Administration) successfully uses EVM to support its mission: to ensure that nuclear weapons are safe, secure and reliable. Some information about this example include: EVM is used to manage about 20 projects with a total value of about $500 million. In August 2005, the lab transitioned from spreadsheets to commercial software (Primavera Systems’ EVM suite) to simplify and automate project management. EVM enhances the ability of lab managers to keep projects on schedule and on budget.

Topic 4: Performance Measurement Methods (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Successful Government Implementation of EVM: Example (continued) EVM data contributes to DOE’s planning and investment control efforts. Data about past trends is used to forecast the future, mitigate risk and increase the potential for program success. Management wants to expand the use of EVM at Lawrence Livermore in the future. More information about Lawrence Livermore Labs use of EVM is available online: http://www.fcw.com/print/13_36/management/150387-1.html

Topic 4: Performance Measurement Methods (continued)

Instructor Notes: This concludes the topic on the performance measurement methods. After addressing any questions the participants may have, inform them that we will be moving on to the next topic: the Review.

What questions do you have regarding the performance measurement methods?

Topic 5: Review

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Let’s review the learning objectives for this module on Business, Cost Estimating and Financial Management: Describe the different practices associated with cost-estimating. Discuss the elements of financial management in the federal government. Define the different procedures included in budget analysis. Identify the important forms of performance measurement including Earned Value Management and Benefit-Cost Analysis.

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: As you learned, the federal government uses several different methods for measuring performance and cost. Some of these important methods include: Cost Estimating Cost Analysis Benefit-cost Analysis Earned Value Management And many others

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: We learned that cost estimates are one of the fundamental building blocks of the acquisition process. Cost estimates and the supporting budget are a part of the baseline against which a program's progress and success are measured. They evaluate whether a system is affordable and consistent with the guidelines set out for it and the overall long-range investment and force structure plans. Cost estimates also form the basis for budget requests to Congress. We discussed Life Cycle Cost Estimates and said that they were a product of an estimating procedure that specifies the expected dollar cost to develop, procure, operate, support and dispose of a given system or product.

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: We also discussed how to develop a Preliminary Cost Estimate. The steps were to: Define the Estimating task (Plan the work to be accomplished) Define all the work or activities Determine an Estimating Methodology Remember, the Cost Estimate must be defensible with well-reasoned analysis.

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: The different methods for Cost Estimating are as follows: Analogy Another method is engineering (Bottoms-up). Another method is using actual costs (Extrapolation). A fourth method is the parametric (Statistical) method. Learning Curve Theory We also learned about escalation and how it is used in Cost Estimating.

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: We covered Cost Analysis, which is the Review and evaluation of the separate cost elements and profit/fee in an offeror’s or contractor’s proposal Includes cost or pricing data or information other that cost or pricing data We also went into three other major performance measurement tools: BCA EVM ROI

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Remember the steps for a BCA are as follows: Establish and define the goals or objectives Formulate appropriate assumptions Identify alternatives for accomplishing the objective Determine the benefits and costs of each alternative Evaluate alternatives by comparing their benefits and costs Test the sensitivity of the analysis outcome to major uncertainties Present the results Recommend an alternative

Topic 5: Review (continued)

|  | Notes: Slide # HERE (Topic # - Slide #) |
| --- | --- |

CONTENT TO BE PRESENTED: Key Points: Earned Value Management (EVM) Integrates technical performance requirements, resource planning, with schedules, while taking risk into consideration The major objectives of Earned Value Management are to: Encourage contractors to use effective internal technical, cost and schedule management control systems Permit the customer to rely on timely data produced by those systems for better management insight

Topic 5: Review (continued)

Instructor Notes: Address any questions the participants may have. Inform them that we are moving on to the next module, Course Review.

What questions do you have about Module 15: Business, Cost Estimating and Financial Management?