PMG-30

PRIORITIZATION GUIDE

(EXCERPTS on ES&H RISK BASED PRIORITY MODEL)

U.S. Department of Energy

## Office of Engineering and Construction Management

## September 2002

Preface

This guide was originally developed by the U.S.  Department of Energy (DOE) Office of Field Management now the Office of Engineering and Construction Management as part of a project to develop a series of instructional and source materials for better management of all projects undertaken by DOE. This updated guide provides information on the two most widely used prioritization methodologies that are commonly practiced in DOE to rate and rank projects to ensure proper allocation of limited resources. However, other prioritization methods can be used that perform to the criteria established within the Real Property Asset Management Order. It is important to note that the models discussed in this manual are only tools; they are not intended to replace management review and judgment.

The intended audience for this guide is field and headquarters program/project managers, engineers, design engineers, reviewing committees, and line managers. Personnel involved in facility maintenance and operations and decontamination and decommissioning may find applications of these models useful in allocating resources for these activities.

Suggestions or comments for improving this guide are welcome and should be sent to the following address.

Nestor Folta

U.S. Department of Energy

Office of Engineering and Construction Management

1000 Independence Ave.  S.W.

Washington, DC 20585

Phone:  (202) 586- 4554

FAX:  (202) 586-4500

E-mail:  nestor. folta@hq.doe.gov

### Office of Engineering and Construction Management

Prioritization Guide

Contents

Page

Preface	v

Acknowledgements	vi

Acronyms and Abbreviations 	x

Executive Summary	xii

1.	Introduction	1

2.	Capital Asset Management Process (CAMP)	2

2.1	CAMP Process Specification	2

2.1.1	Authority	2

2.1.2	Program Office Advocates/Assistance	2

2.2	Process Attributes/Applicability	2

2.2.1	Applicability	2

2.2.2	Development Status	3

2.3	Approach Summary	3

2.4	Process Principles	4

2.4.1	Problem/Project Assessment	4

2.4.2	Rating Process	4

2.4.3	Scoring Process	5

2.4.4	Ranking Process	6

2.4.5	Review and Adjustment	6

2.5	Approval Process	6

2.6	Real-Life Examples	8

2.6.1	Example 1:  Utility System Modernization	8

2.6.2	Example 2:  Central Supply Facility Construction	10

2.7	Measuring for Results	12

2.7.1	Performance Objectives	12

2.7.2	Performance Criteria	12

2.7.3	Performance Measures	13

2.8	References/Reading List	13

2.9	Definitions	13

3.	Environment, Safety and Health Risk Based Priority Model (RPM)	23

3.1	RPM Process Specification	23

3.1.1	Process Authority	23

3.1.2	Program Office Advocates/Assistance	23

3.2	Process Attributes/Applicability	24

3.2.1	Introduction	24

3.2.2	Applicability	28

3.2.3	Development Status	28

3.3	Approach Summary	29

3.4	Process Principles	31

3.4.1	ES&H Activity Scoring and Ranking with the ES&H RPM	31

3.4.2	ADS Ranking Steps	31

3.4.3	Resource Allocation	35

3.4.4	RPM Matrix Impacts and Scoring Examples	37

3.5	Measuring Results	45

3.6	References/Reading List	45

3.7	Definitions	46

3.8	Training Courses/Program Assistance	47

Acronyms and Abbreviations

ADS		Activity Data Sheet

ALARA	As low as reasonably achievable

ANSI		American National Standards Institute

CAA		Clean Air Act

#### CAMP		Capital Asset Management Process

CBR		Corporate Budget Review

CERCLA	Comprehensive Environmental Response, Compensation, and Liability Act

CSO		Cognizant Secretarial Officer

DNFSB	Defense Nuclear Facilities Safety Board

DOE		Department of Energy

DOT		U.S. Department of Transportation

E&WM	Environmental & Waste Management

EH		Office of Environment, Safety, and Health

EM		Office of Environmental Management

EMAB		Environmental Management Advisory Board

EPA		Environmental Protection Agency

ES&H		Environment, Safety and Health

FTE		Full time equivalent

G&A		General & Administrative

GPP		General Plant Project

H&S		Health & Safety

INEL		Idaho National Engineering Laboratory

IS		Information Systems

M&I		Mission & Investment

MC&A		Material control and accountability

MEM		Management Evaluation Matrix

MIS		Management Information System

MSSA		Master Safeguards and Security Agreement

MUA		Multiattribute utility analysis

NAS		National Academy of Sciences

NFPA		National Fire Protection Association

###### NNSA		National Nuclear Security Administration

NRC		National Research Council

OMB		Office of Management and Budget

OSHA		Occupational Safety and Health Administration

RBP		Risk-Based Prioritization

RCRA		Resource Conservation and Recovery Act

RDS		Risk Data Sheet

REM		Roentgen-equivalent-man

RPM		Risk-Based Priority Model

S&S		Safeguards & Security

##### SC		Office of Science

SNM		Special nuclear material

TRU		Transuranic waste

WBS		Work breakdown structure

3.	ENVIRONMENT, SAFETY AND HEALTH RISK-BASED PRIORITY MODEL (RPM)

The Environment, Safety and Health Risk-Based Priority Model (RPM) is available to facilitate ES&H activity ranking within the DOE ES&H Management Planning Process.

3.1	RPM Process Specification

3.1.1	Process Authority

In November 1991, the Secretary of Energy directed DOE Headquarters programs to develop a consistent Departmental methodology to identify and improve management of its environmental, safety, and health programs. It was recognized that within a tightly constrained budget environment "some activities will need to be eliminated, reduced in scope, or stretched out in time to accommodate new and higher priority initiatives and enhancements to ongoing programs." In response to the Secretary's direction, the Office of Environment, Safety, and Health (EH) coordinated the development and implementation of a risk-based DOE ES&H Management Planning Process that defines, prioritizes, and allocates budget resources to the most important ES&H activities.

The requirements for the ES&H Management Planning Process have evolved over the years.  The term “ES&H Management Plan” has evolved to mean the generic process by which each site conducts and reports on its ES&H planning, programming, budgeting, work commitment making/execution, and performance evaluation activities on an annual basis.  Most significantly, with the implementation of Integrated Safety Management (ISM), the process emphasis has shifted away from using a Headquarters specified data system, towards integration of ES&H planning, budgeting and work execution processes into the individual site business systems.  As a result, use of the implementing software for the ES&H Management Planning Process is now optional.  However, sites are still expected to provide risk-based ES&H planning, budgeting, and work commitment information during the annual Departmental budget process. Planning information generated through the process is used to support management decision-making during the Department's corporate budget review process, and ES&H "crosscut" budget information derived directly from the ES&H Management Plan is submitted to the Office of Management and Budget (OMB) and then to Congress in support of the Department's budget request. The ES&H Risk-Based Priority Model (RPM) is the management "tool" specifically developed to facilitate ES&H activity ranking within the DOE ES&H Management Planning Process.

3.1.2	Program Office Advocates/Assistance

The Office of Performance Assessment and Analysis of the Office of Environment, Safety and Health (EH-3), in its missions and functions, serves as the focal point for collection, analysis and dissemination of  environment, safety, and health program planning, budgeting, and execution information for the Department. The Environment, Safety, and Health Management Plan is a process that enables consistent identification of needed Departmental environment, safety and health activities; risk-based priority setting; effective budget decision-making and allocation of environment, safety and health resources; and improved accountability for environment, safety, and health performance on the part of DOE line programs and operating contractors.

Frank Tooper, of the Office of PerformanceAssessment and Analysis, is responsible for the ES&H component of Contract Reform and use of the ES&H Management Planning process as a critical part of the contract reform initiative.

The principal points-of-contact for obtaining assistance in the implementation of the ES&H Management Plan and prioritization using the ES&H RPM are Raymond W. Blowitski, EH-3, 301-903-9878 and Patricia Bean, EH-3, 301-903-3909.

3.2	Process Attributes/Applicability

3.2.1	Introduction

ES&H issues and the activities proposed to resolve these issues are evaluated and ranked using the DOE RPM. The RPM is a multi-attribute utility model designed to support DOE management decision-making. Issues can be ranked based on the risk associated with the current situation (i.e., the level of consequences that might occur if the identified problem is not mitigated and the likelihood of experiencing those consequences).  ES&H activities developed to address the issues are ranked based on their risk-reduction potential (i.e., the difference in expected risk before and after implementation of the activity).

ES&H planners use the RPM to derive an ES&H activity score by assessing the relative level of risk posed by current conditions (before the activities are performed), and the relative level of risk expected to remain after the activities are performed. The ES&H activity score is calculated by taking the difference between the risk score before performance of the activity and the risk score after performance of the activity. The figure-of-merit for ranking an ES&H activity using the RPM, therefore, is the risk reduction expected to be achieved by the activity. This ensures that the score assigned to an ES&H activity is a measure of the effectiveness of the work being performed in the activity in reducing risks, rather than a measure of the magnitude of current problems or issues that the activities are defined to correct.

"Risk" is defined as the product of consequence and probability. The scores assigned to risks by the RPM are derived from numerical weights that represent various levels of severity of adverse impacts (consequences). The impact weights are then multiplied by the likelihood of occurrence (probability) of the impact. Each risk score assigned by the RPM is, therefore, the product of an impact weight and impact likelihood.

The RPM matrix (depicted in Table I at the end of this process description) provides the structure for examining both impact and likelihood and combining them into a risk-based ES&H activity score. The rows of the matrix define impact levels; the columns define likelihood levels. Each matrix cell (row and column combination), therefore, defines a risk level. Each matrix cell contains a numeric weight corresponding to the product of impact weight and likelihood.

The RPM matrix includes impacts in six categories that represent the major types of risks important to ES&H activities.

(1)	Public Safety and Health addresses potential adverse impacts on the health and safety of the off-site population surrounding a site or facility.

(2)	Site Personnel Safety and Health addresses potential adverse impacts on the safety and health of individuals inside the site or facility boundary, i.e., site workers and visitors.

(3)	Compliance addresses failures to comply with laws, regulations, compliance agreements, Executive Orders, and DOE Orders related to Environment, Safety and Health. Such failures may adversely affect the confidence of DOE or other agencies in the ability of the site or facility to operate while protecting the public, workers, and the environment.

(4)	Mission Impact addresses potential adverse impacts on the ability to perform the research or production mission of the site or facility or the ability to carry out important parts of the mission.

(5)	Cost-Effective Risk Management addresses potential accidental losses to a site or facility's capital investment (buildings, equipment) or an existing opportunity for cost savings, such as infrastructure upgrades, management systems upgrades, or improved program development.

(6)	Environmental Protection addresses potential adverse harmful impact on natural resources (air, water, land, wildlife).

Each of the six categories includes two or more impacts representing different levels of impact severity. For example, the Site Personnel Safety category includes four impacts of decreasing severity: catastrophic, critical, marginal, and negligible. A detailed description of the RPM impacts with examples is included in Section 3.4.4.

The Cost-Effective Risk Management category differs from the other categories in that it allows managers to assess the benefits of an ES&H activity on the organization's ability to manage its risks efficiently, protect its capital investment, take preventive action before risks to the public, workers, or environment develop, and reduce overall costs/risks.

As shown in Table II at the end of this section, the columns of the RPM (A through D) represent four likelihood levels used in assessing the risk reduction benefit of activities. Each likelihood level has an associated numerical value, which is multiplied by the impact weights to derive the risk value for each matrix cell in the matrix column corresponding to the likelihood level. The likelihood levels are as follows.

(1)	A.  Very high likelihood indicates an impact already exists with certainty or is expected to occur at least once per year. For example, if a site or facility is known to be out of compliance with a DOE ES&H Order, the likelihood of this impact falls into the very high category.  If a condition at a site or facility has historically resulted in one or more lost-time worker injuries per year and the condition has not been corrected, the likelihood of this impact also fits this category.

(2)	B.  High likelihood indicates that an impact is expected less frequently than once per year, but more frequently than once every 10 years. Such impacts are expected to occur within the operating history of the site or facility, but have not occurred regularly every year.

(3)	C.  Medium likelihood indicates that an impact is expected less frequently than once every 10 years but more frequently than once every 100 years. Impacts with this likelihood are not expected frequently within the operating life of a site or facility, but may occur once in the site or facility's life.

(4)	D.  Low likelihood impacts are unlikely to occur within the operating life of a site or facility, but are not impossible. For example, impacts in this category may occur once in the operating life of one site or facility out of a population of 100 similar facilities. Impacts with this likelihood are expected to occur less frequently than once per 100 years, but more frequently than once per 10,000 years.

The RPM matrix includes discrete values for severity of impact (the rows of the matrix) and the likelihood of experiencing these impacts (the columns of the matrix). These discrete values should be adequate to support prioritization of ES&H activities in most instances. However, if more precise risk assessment information is available, the RPM can accommodate such information. More precise information can be incorporated in two ways.

•	Instead of using the discrete likelihood levels, the RPM can accept any likelihood between 0.0001 and 1.0, and

•	a consequence multiplier can be applied to each impact to interpolate between or extrapolate beyond the discrete impacts levels of the RPM.

Adjusting Likelihood Values. As noted, in addition to the four discrete likelihood levels included in the RPM, any likelihood value from 0.0001 to 1.0 may be assigned if sufficient information is available on which to base a more precise likelihood estimate.

Example:	A portion of a non-reactor nuclear facility Safety Analysis Report analyzes a scenario in which an extreme overexposure of workers could occur. The likelihood of this scenario is estimated to be 10-3 per year. A fix has been defined to remove the possibility of this scenario. In deriving the RPM score for an ES&H activity representing implementation of the fix, Impact 4 (extreme over-exposure of workers) applies.  Because the estimated likelihood of the scenario falls between the representative likelihoods for RPM columns C and D (10-2 and 10-4), this likelihood value may be entered directly in the Information System; the risk score for the impact-likelihood combination representing this scenario is 2 (=10-3 times 2000). Note that a likelihood value other than one of the RPM matrix column likelihoods was used in this case because specific information was available (i.e., part of a facility SAR) to support a different value.

Consequence Multiplier Adjustments. A consequence "multiplier" is also included in the RPM to allow a more precise assessment of impacts beyond that afforded by the discrete matrix row values. The consequence multiplier can be used to interpolate between (or extrapolate beyond) the discrete levels of the impacts defined in the RPM. For example, in scoring impacts in the Public Safety and Health and Site Personnel Safety and Health categories, the multiplier can be used to adjust for the number of persons affected by the impact.

The consequence multiplier should only be used when sufficient, documented analysis is available to justify more precise levels. The consequence multiplier is not intended for application to the "Compliance" category, because the impact scale in this category is not considered to be continuous.

For example, the consequence multiplier that can be applied to the Public Safety and Health or Site Personnel Safety and Health categories accounts for the size of the population impacted. The RPM weights in each RPM matrix cell in these categories have been assigned based on an assumption that each impact affects 10 persons. If a significantly higher or lower number of persons is expected to be affected by an impact, however, different weights are appropriate.  Specifically, the weight should vary proportionally to the number of affected persons.

The RPM cell weights may be used exactly as given in the matrix, without adjustment, if the ES&H activity scorers determine that the implicit assumption of ten persons being affected by the impact is sufficient to score an ES&H activity appropriately. If the number of persons expected to be affected by an impact diverges from this assumption significantly (either higher or lower), so that the RPM cell weights do not represent the risk benefits of the ES&H activity appropriately the ES&H Management Planning process allows for an additional adjustment factor to be specified to multiply by the RPM cell weights.

The appropriate adjustment factor equals the number of persons expected to be affected divided by ten. For example, if 100 persons are expected to be affected by an impact, the multiplier equals 10 (i.e., 100 persons affected, divided by 10 persons implicit in RPM weights). If no more than one person is expected to be affected, the multiplier equals 0.1 (i.e., 1 person affected, divided by 10 persons implicit in RPM weights).

The consequence multiplier can be applied for those impact categories with continuous impact scales (e.g., number of injuries, risk management investment dollars) and where additional quantitative risk assessment information is available to establish a basis for the more precise values. The multiplier should not be used to interpolate between levels of compliance.

Example:	A national laboratory plans a program to reduce lost time injuries to lab workers.  Currently, such injuries occur at a rate of 100 per year. The proposed program intends to reduce this rate significantly. An ES&H activity is prepared to represent this program. In scoring this ES&H activity, Impact 6 (lost-time worker injuries) applies with a RPM likelihood category of A (greater than once per year). In addition, the number of persons affected by the impact significantly exceeds the 10 per year assumption implicit in the RPM weight for Impact 6. The appropriate multiplier for 100 injury victims per year is 10 (=100/10). This results in a scaled weight for the Site Personnel category equal to 1000 (Impact 6, Likelihood A RPM weight equals 100, multiplied by a scaling factor of 10).

Through the combined use of the continuous likelihood scale and the consequence multiplier, site or facility scorers can fully use the results of any available information from detailed, quantitative risk assessments. The RPM can reflect the most detailed risk assessment information available, while still maintaining its simple matrix structure to facilitate discussion and communication of these risks.

3.2.2	Applicability

The RPM was specifically developed to support prioritization of ES&H issues and activities; accordingly, the categories and weights of the RPM are optimized to rank ES&H programs.  However, the RPM has been tailored to rank site-wide indirect activities at several DOE facilities, and is the model on which both the Surplus Facilities Inventory Assessment (SFIA) Threat-Based Priority Model and the Management Evaluation Process (MEP) that were once used by EM were developed. Coverage of the RPM includes ranking of ES&H issues and the proposed/actual work activities to address these issues. The RPM is used to rank all types of ES&H activities including those funded by direct funding sources: operating, capital equipment, general plant project, or line item project, and those funded by indirect or allocable cost arrangements.

The RPM can be used to evaluate site-wide ES&H risks, programs, and activities from initial issues/hazard ranking, through budget formulation and decision-making, and ES&H program execution, regardless of type or funding source. The RPM is used to evaluate issues and activities of many different types including occupational safety improvements, capital upgrade projects, infrastructure maintenance, improvements in conduct of operations, etc.

The RPM is used at several DOE facilities located throughout the United States and by several Headquarters Programs. Facilities using the process range from small solar energy laboratories and fossil energy facilities, to large nuclear weapons facilities.

3.2.3	Development Status

The ES&H Management Planning Process and the RPM are fully developed processes that have been used successfully through ten complete Departmental budget cycles.   Furthermore, an optional PC database system, the Environment, Safety and Health Management Plan Information System (ES&H MPIS), which includes a detailed User's Manual, has been available for over 10 years to support the production, analysis, and use of ES&H Management Plans and to conduct prioritization using the RPM. The ES&H MPIS was designed using FoxPro development software and is distributed to all DOE facilities via the internet as a run-time application. The user interface consists of menus, windows, dialogues, and other features that facilitate communication with the database system.  General information on the ES&H Management Plan can be obtained from the following URL:

http://tis.eh.doe.gov/bps/eshplan.htm.  The ES&H MPIS software can be downloaded from the following URL:   http://tis.eh.doe.gov/bps/eshplan/software.htm.  The ES&H MPIS users manual and other guidance can be downloaded from the following URL:

http://tis.eh.doe.gov/bps/eshplan/document.htm.

In addition to direct input and update of data, the MPIS provides powerful but easy-to-use filtering, indexing (sorting), and output reporting capabilities. The Database System includes an RPM  "Scoring Screen" for each issue or activity record and a "Resource Screen" that captures budget costs of an activity in a variety of resource categories. The ES&H MPIS supports efficient risk-management and resource allocation by presenting activities in risk-ranked order, displaying budget cut-off lines and scenarios, and allowing automatic deferral to later years of less important activities that fall "below the line." The database system is comprised of four major modules.

(1)	Assessments, in which users can enter records and provide information about specific assessments (evaluations, etc.) that spawn ES&H issues.

(2)	Issues, in which users can enter records and provide information about specific ES&H issues identified in the assessments. Many issues can be linked to an assessment in the database.

(3)	Activities, in which users can enter records and provide information about specific ES&H activities defined to resolve the identified issues. Activities can be linked to issues within the database and through issues to assessments.

(4)	Milestones, in which users can enter records and provide information about the specific tasks or deliverables associated with an Activity and the due dates for these accomplishments. By linking the Milestones to Activities (and thereby to Issues and Assessments), this module allows the MPIS to serve as a powerful, integrated commitment management and tracking system.

In addition, the ES&H MPIS database has an optional infrastructure module that can be activated to plan for either ES&H related infrastructure activities, or general (non-ES&H) infrastructure activities.

3.3	Approach Summary

A comparison of priority setting methods is best achieved within the context of their intended use or management processes. With regard to the RPM, the DOE ES&H Management Planning Process produces a plan through a combination of top-down guidance and bottom-up analysis and decision-making. It is a continuous, risk-based, resource-constrained, management process designed to improve DOE and contractor use of available resources to manage ES&H risks. The process is designed to help managers produce and communicate integrated information necessary for environment, safety and health strategic planning and operational management. Both the development and output of the ES&H Management Planning Information are required annually as part of the Departmental budgeting process. The major steps of the Plan development process are the following.

(1)	Strategic Planning Guidance is provided by the Secretary of Energy, and key ES&H issues are identified by Cognizant Secretarial Officers (CSOs), the National Nuclear Security Administration (NNSA), and the Assistant Secretary for Environment, Safety, and Health (EH).

(2)	Headquarters managers provide direction to operating facilities, including budget targets to be used in preparing field planning data.

(3)	Field Elements conduct a needs analysis to identify ES&H needs and risks, identify ES&H activities/programs to address the needs or risks, and document these ES&H activities.  If using the optional software, the ES&H activities are entered into the ES&H Management Plan Information System database.

(4)	ES&H activities are ranked using the DOE ES&H RPM. The ranking is reviewed by successive levels of management; other planning factors (such as precedence and coupling relationships between ES&H activities, strategic factors, etc.) are applied to adjust rankings. (A complete description of the RPM ranking process is provided in Section 3.2.1).

(5)	Available resources are allocated to the activities. The ranked listing of ES&H activities is used to support budget decision-making during the Department's Corporate Budget Review (CBR) process. Less important activities that cannot be accomplished within prescribed budget constraints are reduced in scope or deferred to subsequent years.

(6)	Corporate budget review decisions are reflected in the ES&H Management Plans, and an ES&H "crosscut budget" is prepared for OMB.

(7)	Final OMB allowances are reflected in the ES&H Management Plans, and a revised ES&H "crosscut budget" is prepared to accompany the Department's congressional budget request.

(8)	Budget decisions and planning implications are communicated back to the operating facilities, and the updated ES&H Management Plans provide the baseline for incorporation into the ES&H program executed during the budget year and for the next annual planning and budget formulation cycle.  The ES&H activities that complete the budget cycle and eventually receive funding and management approval will make up the execution work plans and become ES&H commitments.

The RPM supports but does not replace the expertise of field and headquarters staff and management. The RPM is viewed as one tool within an overall management process that structures and focuses management decision-making. The RPM does not attempt to encompass all factors or provide all information required to determine the ultimate priority of an issue or activity. The ES&H planning process is designed to allow various factors important to the setting of priorities to be incorporated into the final adjusted ranking. Such factors include strategic considerations concerning the expected lifetime of the site or facility, the level of uncertainty in the risk evaluation, or project management considerations such as precedence relationships among activities. The RPM is not intended to provide a concise quantification of risk, but to structure management experience and knowledge (and any available quantitative risk data) into a defensible and traceable relative ranking of ES&H issues and activities.

3.4	Process Principles

3.4.1	ES&H Activity Scoring and Ranking with the ES&H RPM

Available resources may not be adequate to allow full and immediate implementation of all proposed ES&H programs and activities. Risk-based ranking of ES&H activities supports management's ability to allocate resources to the set of activities that will most reduce risk during the planning period. ES&H managers and planners should assess the risk-reduction benefits of each ES&H activity and rank them accordingly.

The ES&H RPM is the tool provided to produce the initial activity rankings. Operating organization planners use the RPM to derive risk-reduction scores for each ES&H activity. This risk-reduction benefit score is the primary consideration for establishing the relative ranking of ES&H activities.  However, site or facility, Operations Office, and Headquarters management may adjust the ES&H activity rankings to account for additional planning factors not considered by the RPM. In addition, Operations Office and Cognizant Secretarial Officer (CSO) ES&H planners are responsible for reviewing priorities for consistent application of the RPM and may adjust ES&H activity scores to ensure consistency in Departmental prioritization and budgeting for ES&H activities. After the risk-based priorities are established and adjusted, management will use the ranked list of ES&H activities to allocate available resources to the most important activities.

3.4.2	ES&H Activity Ranking Steps

Three major steps are associated with ranking ES&H activities:

(1)	Use the RPM to characterize and score the existing risks addressed by the ES&H activity;

(2)	Characterize and score the risks that would remain after implementation of the ES&H activity;

(3)	Apply other planning factors to adjust ES&H activity scores and produce the ES&H activity rankings. The difference between the scores in the first two steps is the risk-reduction score. The last step also includes Operations Office and CSO adjustments to ensure consistent and correct application of the RPM.

The RPM provides a convenient framework for structuring risk information and focusing site or facility management and staff expertise on the assessment of risks related to ES&H issues and activities.  It is strongly recommended that ES&H activity scoring at a site or facility be performed by an evaluation group with expertise in diverse fields and extensive experience with a site or facility's operations, potential risks, and operating history. This enhances the quality of the information used in the activity risk scoring and the validity of the ES&H activity rankings.

The operating organization scoring group should provide documentation of the basis for RPM scoring as well as the basis for scoring adjustments by operating organization management, Operations Office reviewers, and CSO reviewers. Thorough and clear documentation is essential for effective review and use of the ES&H activity risk-based rankings by decision-makers as the ES&H planning information is rolled up. High-quality documentation of the ES&H activity ranking process is particularly important to support Headquarters budget deliberations and to provide feedback from Operations Office and CSO reviewers to operating organizations.

Step 1:	 Assess and score risks before ES&H activity implementation.

The ES&H activity scoring group will consider existing risks addressed by the discrete activities included in the ES&H activity. Each ES&H activity should include an appraisal section, in which the  ES&H activity preparer should document these risks. The scoring group will consider the risks documented in the ES&H activity along with any additional risks that apply.

For each RPM impact category, the scorers perform the following steps.

(1)	Identify all impact levels that could occur because of the current situation.

(2)	Estimate the likelihood for all impacts identified in (1) above. One of the likelihood levels represented by the RPM columns A-D may be chosen. Alternatively, if information is available to support a different likelihood value, that value may be specified.

(3)	If more detailed information is available on the estimated impacts, specify a consequence multiplier to interpolate between or extrapolate beyond the impact levels designated in the RPM rows.

(4)	Select the combination of impact, likelihood, and multiplier that produces the highest risk score to represent the category in the overall ES&H activity score.

The risk score before performance of the ES&H activities is the sum of the representative risk scores from all categories that are scored by the scoring team. For example, if the scoring team determined the “before” score of a hypothetical activity included:

- a very high likelihood for a worker overexposure to radiation (RPM Matrix 6.A. = score 100),

- A very high likelihood for a major noncompliance with 10 CFR 835 that could result in penalties  (RPM Matrix 8.A. = score 150), and

- A very high likelihood for serious negative impact on the mission, e.g., shut down special nuclear material processing  (RPM Matrix 12.A. = score 150)

The total before score would be the sum of these individual scores, e.g., 100 + 150 + 150 = 400.

If using the optional software, the risk score is calculated automatically in the ES&H Management Plan Information System upon entry of the selected matrix cells.

Step 2:	 Assess and score risks after ES&H activity implementation and calculate ES&H activity risk reduction score.

After using the RPM to determine the ES&H activity risk score for existing risks, the scoring group will consider the effect on site or facility risks of performing the activities defined by the ES&H activity and the level of risk remaining after performance of the activities. The group will consider risks documented in the ES&H activity appraisal section along with any additional applicable risks. The scorers will derive the risk scores for the expected condition after completion of the activities in the same manner as they determined the before risk scores before ES&H activity implementation in Step 1. The risk score for the ES&H activity after completion of the ES&H activities is the sum of the representative risk scores from all categories that are scored by the scoring team.  For example, if the scoring team determined the “after” score of the hypothetical activity provided in the previous example would include the following risk reduction benefits:

- a reduction of the likelihood for a worker overexposure to radiation from very high to low (RPM Matrix 6.D. = score 0.01),

- A reduction in the likelihood from very high to low for the major noncompliance with 10 CFR 835 that could result in penalties (RPM Matrix 8.D. = score 0.015), and

- A reduction in the likelihood for potential for serious negative impact on the mission,  from very high to low e.g., low likelihood for shut down special nuclear material processing  (RPM Matrix 12.D. = score 0.015)

The total after score would be the sum of these individual scores, e.g., 0.01 + 0.015 + 0.015 = 0.04.  Again, if using the optional software, risk score is calculated automatically in the ES&H Management Plan Information System.

The net ES&H activity risk reduction score is the difference between the before risk score, calculated in Step 1, and the after risk score, calculated in Step 2. Using the previous examples, the risk reduction score would be the before score, 400, minus the after score, 0.04,  = the net risk reduction score = 399.96.  The net risk reduction score would indicate a very effective ES&H activity with regards to risk reduction. This net risk reduction score is also calculated automatically within the ES&H Management Plan Information System, if used. Comparing these risk reduction scores for all ES&H activities at a site or facility offers a preliminary relative ranking of the ES&H activities.  ES&H activities with high scores represent activities that are most effective in reducing current risks at the site or facility, while ES&H activities with low scores offer low benefits in curbing risk.

Step 3:	 Adjust ranking according to other planning factors.

Other factors besides the risk reduction potential of activities may influence the ranking of ES&H activities.  These factors may include cost, precedence and coupling relationships, and other planning factors. After the scoring group completes the RPM scoring and ranking using the RPM, operating organization management and Operations Office and CSO reviewers may adjust the ES&H activity ranking to account for these factors. Scoring adjustments may be made by adding to or subtracting from an ES&H activity RPM score to achieve the desired relative ranking for the ES&H activity. Scoring adjustments should be thoroughly documented for the ES&H activity.  If using the optional software, this information is documented in the  "scoring comments" section in the ES&H Management Plan Information System.

Cost of Activities.  Although the primary objective of implementing ES&H activities is to remove or reduce major risks, an additional important objective is to achieve risk reduction as efficiently as possible. To promote the efficient use of ES&H resources and the cost-effective conduct of ES&H programs, managers may adjust the priorities of ES&H activities based on the cost of activities included in each ES&H activity. Following are examples of situations in which scoring adjustments based on ES&H activity cost may enhance the ES&H activity rankings.

•  	Managers should adjust upwards the ranking of low-cost ES&H activities with substantial risk reduction to ensure such activities are near the top of the ranked list of ES&H activities.

•	Managers should reassess each high-cost ES&H activity with a high or moderate risk reduction score to determine if some subset of activities in the ES&H activity or some alternative activities could provide comparable benefits for lower cost. This may require redefinition, reformulation, or repackaging of corrective actions included in the ES&H activity.

Precedence and Coupling Relationships. Implementation of activities in some ES&H activities may not be feasible without previous implementation of activities in other ES&H activities. If the prerequisite ES&H activity is ranked below the dependent ES&H activity, site or facility managers may want to adjust the ranking of the prerequisite ES&H activity to reflect a realistic priority of activities. Similarly, two or more activities in separate ES&H activities may require simultaneous implementation. In this case, ES&H activity rankings may be adjusted so that the priorities of the dependent activities allow them to be performed in the same budget period.

Other Practical Planning Factors. Practical constraints may change the relative desirability or practicality of certain activities beyond the rankings provided by the RPM scores. Examples of planning factors that may merit adjustments in ES&H activity priority include:

•	expected life of a site or facility;

•	changes to site or facility mission;

•	strategic goals of the Department, EH, or the Program Office;

•	management workloads and the ability to provide adequate management and oversight to the activity;

•	staff loads and ability to hire additional staff;

•	uncertainties in changing requirements;

•	uncertainties in obtaining project benefits; and

•	perception of site or facility risks by the public or other external stakeholders.

After each ES&H activity has received an RPM risk reduction score and the ranking has been adjusted, the result is a ranked list of site or facility ES&H activities for use in resource allocation.

Operations Office and CSO planners should review the results of operating organization ES&H activity scoring and ranking to ensure consistent application of the RPM and proper scoring adjustments.  This review may result in additional ranking adjustments at the Operations Office or CSO level.

As part of their review, responsible managers should assess those ES&H activities representing significant risks for which effective mitigating activities have not been identified. This may be the case if ES&H activity scoring results in both a high before and a high after score, indicating that the ES&H activity does not fully address some significant risk of concern. The low risk-reduction score, if viewed alone, may result in deferral of the activity. However, if this activity is deferred, the significant current risk would remain unmitigated. Such ES&H activities should be evaluated further to determine if alternative corrective activities would more successfully reduce the risks or if risk reduction is not practical due to other considerations. Compensatory actions, which reduce current risks in the near-term while longer-term solutions are being developed, should always be considered for high- or moderate-risk situations.

3.4.3	Resource Allocation

After the risk ranking of ES&H activities has been completed, the next step in the ES&H Management Planning Process is to allocate available resources to these activities. This process establishes which ES&H activities will be funded within target level budgets and the level of funding associated with each activity. This process also identifies ES&H activities that cannot be funded under current resource limitations.

The allocation of resources to ES&H activities is a multistep process that involves all levels of the Department. Allocation of available resources to ES&H activities requires that budget targets (or resource constraints) be established. Because there are often several different funding sources for ES&H activities, separate targets may be required to allocate resources to ES&H activities funded from these different sources. For example, one funding limitation would be needed for ES&H activities funded out of the site-wide overhead pool, and a separate target would be needed for ES&H General Plant Projects (GPPs), which are funded out of the site's GPP appropriation.

Targets for programmatic funding should be provided by each CSO as part of the Departmental budget process. In some instances, these budget targets are summary (decision unit) level values.  In such cases, targets for use in allocating resources to ES&H activities are derived from these summary level targets. For activities funded by allocable cost mechanisms, funding targets must also be derived by operating organization budget personnel. For example, operating organization management (with Operations Office approval) is responsible for determining the size of the overhead pool of resources, and the portion of the overhead funds that will be allocated to ES&H activities.

After targets have been defined, the following major steps should be followed in allocating resources to ES&H activities for each funding source.

(1)	Produce the ranked list of ES&H activities.  If using the optional ES&H Management Plan Information System software, this listing can be easily produced as a report. This list shows activities in order of priority and their cumulative cost.

(2)	Starting with the highest ranking activities on the list, determine which activities can be supported within the target funding level (i.e., draw a line on the ranked list where the cumulative cost of activities in the ranked list equals the target level of funding). This budget target can be input to, and shown on the output report from, the optional ES&H Management Plan Information System.

(3)	Operating organization financial management, ES&H, and senior management should assess the implications of this first cut at differentiating funded from unfunded activities.  This review should examine both the funded and unfunded activities. The following questions should be considered.

--	Are all essential ES&H programs covered within the current funding target?

--	Are any significant ES&H risks not being addressed because the proposed activity falls "below the funding line"?

--	Are any of the unfunded ES&H activities critical to achieving the Department's ES&H strategic goals or programmatic missions?

--	Do any of the unfunded ES&H activities represent sound risk management investments or provide important preventive benefits that will yield long term benefits?

--	Are certain ES&H programs, or parts of these programs no longer essential due to changing mission, program needs, etc.?

--	Could any activities "above the line" be done more cost effectively to free resources to fund some of the currently unfunded ES&H activities?

(4)	After this review, the ES&H activity rankings, funding levels, and target budgets should be adjusted to reflect management's final decisions. To ensure management's ES&H resource allocation decisions are consistently captured and communicated, the ES&H activities should be characterized as follows.

--	Management's relative priorities should be reflected by adjusting the relative ranking of the ES&H activities. As discussed in the previous section, this is accomplished by adding or subtracting points from the raw ES&H activity RPM score to move it up or down in the relative ranking. The justification for these changes should be documented as Scoring Comments.

--	Activities to be funded should be designated as "Target".  This designation is made in the Funding Case field of the optional ES&H Management Plan Information System.  Activities that management determines cannot be funded within the budget target should be designated as "Unfunded."

--	The ES&H activity annual cost profile for all funded ES&H activities should be consistent with funding decisions and budgets for the appropriate fiscal year.

3.4.4	RPM Matrix Impacts and Scoring Examples

Public Safety and Health

Impact 1:  Immediate or eventual loss of life/permanent disability

This impact should be chosen when a potential result of a condition being evaluated could lead to permanent disability (loss of limb, sight, hearing) or loss of life by one or more members of the off-site population. (It does not address impacts to site workers or visitors.) This impact includes immediate deaths and disabling injuries, as well as future cancer deaths or genetic damage and effects that might result from releases of hazardous or radioactive materials that breach the site boundaries. Such releases could be the result of accidents that release hazardous materials within a building combined with failures in building confinement or containment, accidents during off-site transportation, or catastrophic events resulting in direct release of materials (e.g., fire, explosion).

Example:	A site or facility has proposed a set of seismic safety improvement projects to correct structural and equipment deficiencies that could contribute to building failures during an earthquake. Under current conditions, there is a high likelihood of structural failure during a strong earthquake. Structural failure may result in a chemical release or fire that could spread off-site. Because a number of public facilities and private residences are close to the site boundary, public safety could be threatened and fatalities are possible.

Impact 2:  Excessive exposure and/or injury

This impact indicates the potential for excessive exposure or injury to the off-site population, but without the potential for death or permanent disabling injury (i.e., recovery from potential injuries is expected). Excessive exposures to radioactive or hazardous materials are those that exceed published acceptable limits.

Example:	The example given for Impact 1 could apply to this impact if the potential volume of chemicals released were reduced such that death or permanent injury was not expected.  However, public exposures to hazardous substances that exceed limits would still be expected.

Impact 3:  Moderate- to low-level exposure

This impact indicates the potential for exposure of  off-site population to hazardous or radioactive materials, but these exposures are no greater than published acceptable limits. Immediate deaths or injuries are not expected. Rates of cancer incidence in the population would not detectably increase.

Example:	A site or facility must purchase modern radiation survey equipment to comply with Title 10 Code of Federal Regulations, Part 835 Occupational Radiation Protection, DOE Order 231.1, DOE Policy 441.1, DOE Guide 441.1-1, and American National Standards Institute (ANSI) N323. Existing survey equipment does not meet requirements for lower limits of detection for release of equipment or materials from radioactive materials management areas at the site or facility. Because of this inadequacy in detection instrumentation, contaminated materials may be inadvertently released to uncontrolled areas and subsequently disperse off-site. Because of the nature and volume of the contaminated materials, however, the potential releases would not constitute a threat to public health, but could result in a minimal exposure of members of the public to radioactive material.

Impacts 1, 2, and 3 differ in the extent of potential off-site consequences. In considering the potential consequences of a condition at a site or facility, the following factors should be considered:

(1)	the nature of possible accidents that could occur at the site or facility;

(2)	the potential for off-site release of hazardous or radioactive material in case of an accident;

(3)	the amount and type of hazardous or radioactive material present; and

(4)	the potential for deaths, injuries, or exposures of the off-site population.

Site Personnel Safety and Health

Impact 4:  Catastrophic: Injuries/illnesses involving permanent total disability, chronic or irreversible illnesses, extreme overexposure (e.g., 1000 rem/yr), or death

This impact encompasses potential permanent effects among the site worker population. Such effects may result from industrial accidents or excessive exposures to hazardous or radioactive materials. This impact includes immediate deaths and disabling injuries, as well as future deaths from latent effects such as cancer.

Example:	A site or facility has proposed a set of seismic safety improvement projects to correct structural and equipment deficiencies that could contribute to building failures during an earthquake. Under current conditions, there is a high likelihood of structural failure during a strong earthquake. Persons inside the deficient buildings would be at risk and fatalities are possible.

Impact 5:  Critical: Injuries/illnesses resulting in permanent partial disability, temporary total disability (> 3 months), or serious overexposure (e.g., 100 rem/yr.)

This impact involves injuries, illnesses, or exposures that result in lengthy hospitalization and significant recuperation time, but are not expected to result in death or permanent total disability.  This impact includes exposures to radioactive or hazardous materials that may exceed published acceptable limits.

Impact 6:  Marginal: Injuries/illnesses resulting in hospitalization, temporary reversible illnesses with a variable but limited period of disability (<3 months), slight overexposure (e.g., 5-10 rem/yr.), or exposure near limits (20-100%)

This impact involves worker injuries, illnesses, or exposures that result in emergency room treatment, limited hospitalization, and lost work time. Time required for recuperation from these effects, however, is not extensive.

Example:	A site or facility proposes a Line Item Project to improve pedestrian and vehicular safety through roadway modifications. This project will improve sight lines at turns and intersections and widen narrow portions of site roadways. Under current conditions, the site or facility experiences about two road accidents per year. These accidents are typically minor, but do occasionally result in injuries requiring limited hospitalization.

Impact 7:  Negligible: Injuries/illnesses that do not result in hospitalization, temporary reversible illnesses that require minor supportive treatment, or exposures below 20% of limits (e.g., < 1 rem/yr)

This impact involves worker injuries, illnesses, and exposures that would be expected to result in no lost work time (unless the exposure resulted in a cumulative dose exceeding limits).  Standard first aid is expected to be adequate treatment.

Compliance

Impact 8:  Major noncompliance with Federal, state, or local laws; enforcement activities; or compliance agreements significant to environment, safety, or health and involving significant potential fines or penalties

This impact includes major violations of laws, regulations, codes, enforcement actions, compliance agreements, or standards. These non-compliances have the following characteristics.

(1)	Violation of the law, regulation, code, enforcement action, compliance agreement, or standard could result in the imposition of fines on DOE or the operating organization, imprisonment of DOE or operating organization personnel, liability for the payment of significant damages, or other legal penalties.

(2)	The existing situation must represent a major, substantive non-compliance with the law, regulation, code, or standard. If existing conditions are substantially in compliance with only minor exceptions, this impact does not pertain. (See definition of Impact 10 below.)

(3)	The violated law, regulation, code, or standard must be significant to environment, safety, or health.

If an ES&H activity addresses a major non-compliance with an environmental law or regulation, such as the Clean Air Act (CAA), the Resource Conservation and Recovery Act (RCRA), or the Comprehensive Environmental Response, Compensation, and Liability Act (CERCLA), or it addresses a major non-compliance with a rule subject to penalties under the Price-Anderson amendments act, Compliance Impact should be 8.

In general, non-compliance with a DOE Order should be scored using Impact 9 or 10 below because fines or criminal penalties do not typically result from DOE Order non-compliance.  Likewise, non-compliance with an Occupational Safety and Health Administration (OSHA) requirement or a DOE occupational safety and health Order should be scored using Impact 9 or 10 below unless OSHA has the force of law at a site or facility (which is currently not the case at most DOE facilities). If an ES&H activity addresses a major non-compliance with an environmental law and a DOE Order simultaneously, the applicable compliance impact with the highest potential risk reduction score should be chosen (in this case, Impact 8).

Example:	A site or facility has proposed a project to expand its hazardous waste storage and disposal capability.  Currently, hazardous waste handling capability is inadequate, so that waste remains in temporary storage locations for longer than 90 days.  This is a violation of RCRA and the site or facility may be fined by the EPA. Because this example involves non-compliance with an environmental law, it would be scored with Compliance Impact 8.

Impact 9:  Major noncompliance with Executive Orders, DOE Orders/Notices, or Secretary of Energy Policy Statements that are significant to environment, safety, or health but do not involve significant potential fines and penalties

This impact includes significant noncompliances with any DOE Order/Notice or policy statement that is significant to ES&H. To distinguish Impact 9 from Impact 8, noncompliances included under Impact 9 cannot result in fines, imprisonment, or other legal penalties. Impact 9 also includes site or facility noncompliance with laws, regulations, codes, and standards (e.g., OSHA, NFPA, ANSI, NEC, MSHA) that are referenced in DOE Orders, but do not have the force of law at the site or facility. As with noncompliance covered under Impact 8, conditions of noncompliance included in this impact must be major, substantive noncompliances and must relate to requirements that are significant to environment, safety, and health. The impact does not include marginal noncompliances, such as minor administrative discrepancies (see definition of Impact 10 below).

Example:	A recent audit finding indicated that the Hazards Communication Program at a site or facility is not in compliance with the requirements of DOE Order 440.1. All aspects of the program are lacking, including surveillance, communications, and recordkeeping. A site or facility proposes to add five full time equivalents (FTEs) to upgrade the Hazards Communication Program.

Impact 10:  Marginal noncompliance with Federal, State, and local laws; enforcement actions; compliance agreements; Executive Orders; DOE Orders; or that are significant to ES&H

This impact includes minor noncompliance with laws, regulations, codes, standards, Orders, or directives that are significant to ES&H (the same group of laws and orders that are included in Impacts 8 and 9). It is differentiated from Impacts 8 and 9, which cover major noncompliance conditions. This impact pertains to conditions in which current ES&H programs largely conform to the requirements of applicable laws and Orders, but do not fulfill certain marginal or administrative aspects of the requirements. For example, if a site or facility has fulfilled the actual substantive physical requirements of a law or Order, but has not completed all administrative requirements or paper work, Impact 10 applies.

Example:	A site or facility proposes to add one clerical employee to assist the Industrial Safety Manager in support of the Hazards Communication Program that was recently upgraded as required by DOE Order 440.1. The responsibilities of this new employee will be record keeping and clerical support for visiting assessment teams. Recent audits have indicated that the program is adequate, but to be in full compliance the site or facility must keep better records of communication activities and provide better clerical support for visiting assessment teams to allow them to obtain a more comprehensive picture of the state of the site or facility's compliance.

Impact 11:  Significant deviation from good management practices

This impact indicates a significant deviation from accepted industry or DOE standards for the performance of activities in a given area. Such directives or good practices do not have the weight of a law, DOE Order, or DOE Policy Statement issued by the Secretary of Energy.

Mission Impact

Impact 12:  Serious negative impact on ability to accomplish major program mission

This impact includes conditions that seriously curtail or prevent accomplishment of the mission of a major program at a site. The condition need not shut down the entire site, but must threaten continuation of at least one of the site or facility's major research or production missions. Under this impact, the interruption of the affected program mission must be of sufficient duration to pose serious doubts about the feasibility of accomplishing yearly goals or objectives set for the program.

The program mission impact may be due to regulatory or administrative shutdown of part of a site or facility, a catastrophic accident preventing continued activities, or the unavailability of equipment, staff, or other resources required by the program.

Example:	Radiological surveys of chemistry laboratories at a site have revealed previously unknown contamination outside of posted radiological areas. To fully comply with Title 10 Code of Federal Regulations, Part 835 Occupational Radiation Protection, DOE Policy 441.1, and DOE Guide 441.1-2 as low as reasonably achievable (ALARA) guidelines, the site or facility proposes to fund systematic, detailed surveys of the laboratories and management of any contamination discovered. If this work is not performed, all chemistry division laboratories could be zoned as radiation areas, which would result in loss of effective use of the laboratory facilities and prevent progress in major programs that rely on the facilities.

Impact 13:  Moderate negative impact on ability to accomplish major program mission

This impact includes conditions preventing accomplishment of major program missions at a site.  Program interruptions considered under this impact are shorter than those included under Impact 12 above. Interruptions included under Impact 13 may pose risks to the achievement of set program goals or objectives, but still allow the possibility that such goals or objectives may be met.

Example:	A site or facility must institute a site roadway safety and stabilization program to meet Federal and State safety standards. This project will stabilize landslides adjacent to roads at the site. Without this work, the landslides threaten to displace roadways and underground utilities. If this occurred, access and utility supplies to some site buildings could be disrupted, interrupting programs in these locations. Repairs to re-establish access and utilities are not expected to cause an excessive disruption of progress on these programs.

Cost-Effective Risk Management

Impact 14:  Significant avoidable cost due to degrading infrastructure, inefficient management systems or program implementation, accident-related capital loss (total cost > $25M or annual cost > $5M), or the opportunity for cost savings

Impacts 14 and 15 involve either the loss of DOE capital investment due to accidents or an existing opportunity for cost savings (such as infrastructure upgrades, management systems upgrades, or improved program development). The difference between Impacts 14 and 15 is the dollar value shown to be at risk or the dollar value of the cost savings opportunity.

For Impact 14, the loss of investment could include loss of buildings, equipment, materials, finished products, or supplies, in which DOE had invested greater than $25 million. Such loss could be incurred by events such as fire, explosion, human errors, or natural occurrences.

In addition to situations involving financial loss due to accidents, Impact 14 also includes opportunities for cost savings that would have a positive financial impact. Prominent among such opportunities are situations in which an immediate preventive investment can help avoid a potentially greater cost impact in the future. Examples include neglected site or facility infrastructure for which short-term expenditures on physical upgrades or increased maintenance or surveillance can help avoid increased long-term costs due to continued neglect or degradation or potential catastrophic damage. For Impact 14 to apply, the total cost savings must exceed $25 million.

Impact 14 also includes annual cost impacts greater than $5 million incurred as a result of a condition causing losses to a site or facility's capital stock. Similarly, Impact 14 includes opportunities for recurring annual preventive or other positive financial impacts exceeding $5 million. Examples include opportunities to develop improved ES&H management systems that increase the efficiency of managing ES&H issues, thereby promoting early identification of problems; setting appropriate priorities for addressing issues; and defining cost-effective activities for addressing issues.

Example:	A site contractor has proposed launching a behavior-based safety process to improve worker safety and decrease the frequency of on-the-job injuries. The process includes workplace observation and feedback to workers to improve the safety of workplace behaviors. In addition to substantial expected safety improvements, the process is expected to yield substantial annual cost savings through reduction of workman's compensation expenses. The avoided costs could exceed $5M per year.

Impact 15:  Moderate avoidable cost due to degrading infrastructure, inefficient management systems or program implementation, or accident-related capital loss (total cost <$25M or annual cost $1M-5M)

This impact is similar to Impact 14, with the exception of the dollar amounts, which  include smaller investment losses or cost savings opportunities.

Example:	A national laboratory and DOE Operations Office ES&H division propose to develop an integrated issue management and commitment tracking system to improve the efficiency of ES&H management at the lab, increase accountability, and allow the Operations Office to perform its oversight role more productively.  Implementation of such a system is expected to improve the cost-effectiveness of risk management activities with savings expected to approximate $1.5M per year.

Example:	A production site or facility plans to perform a pollution prevention/waste minimization opportunity assessment on one segment of the plant's process and to implement waste minimization activities based on the findings of the assessment. Preliminary evaluations indicated that the resulting waste reduction would substantially reduce disposal costs. It is estimated that costs could be reduced by around $3M per year.

Environmental Protection

Environmental impacts are defined as damage to a significant public resource such as: air, water, land, or wildlife. These impacts would primarily result from accidents involving the release or spill of radioactive or hazardous materials to the environment.

Impact 16:  Catastrophic damage to the environment (widespread and long-term or irreversible effects)

This impact includes the most severe environmental effects, those with both of the following characteristics.

•	The effects spread or may spread over a wide area and are not easily containable in a limited area, and

•	the effects are irreversible or may only be reversed over a period of several years.

Example:	A process at a site or facility involves the use of industrial solvents. The site or facility has proposed a project to improve the monitoring of releases from the process. Under current conditions, solvents may be released, disperse off-site, and contaminate groundwater that supplies the drinking water for a nearby community. The water supply would be unusable and an alternative supply would be needed. Cleanup of the groundwater is thought to require 30 years.

Impact 17:  Significant damage to the environment (widespread and short-term effects or localized and long-term or irreversible effects)

This impact includes serious environmental effects that are less severe than those considered under Impact 16 above. These impacts must have one of the following characteristics.

•	The effects spread or may spread over a wide area but may be reversed in no more than a year's time, or

•	the effects are confined to a limited area but are either irreversible or require several years to reverse.

Impact 18:  Minor to moderate damage to the environment (localized and short-term effects)

This impact includes less severe effects on the environment than those covered in Impacts 16 and 17 and include both of the following characteristics.

•	The effects are confined to a limited area, and

•	the effects may be reversed within a year's time.

Example:	A site or facility proposes a project to construct double containment of feed lines into a diesel fuel tank to help prevent leaks. Currently, the tank is vulnerable to leaks, which could spill fuel and contaminate the soil in the area surrounding the tank.  Because of the volume and location of the tank, however, the contamination will not spread off-site and will not contaminate any water sources. Clean-up should require only a few weeks.

3.5	Measuring Results

ES&H planning information developed and prioritized using the ES&H Management Planning Process can provide a basis for defining the ES&H performance measures, objectives and commitments, required annually by the Department of Energy Acquisition Regulations (DEAR) in Title 48 Code of Federal Regulations (CFR) Clause 970.5223-1 “integration of environment, safety and health into work planning and execution”, by which contractor ES&H performance will be evaluated and through which ES&H accountability will be established. Existing site processes should be used to propose, review, and establish contractually-binding performance measures. The ES&H Management Planning process does not mandate the specific performance objectives, criteria, and measures to be used, but instead is designed to communicate answers to basic risk-management questions concerning ES&H activities.

•	Who, specifically, is responsible and accountable for ES&H performance at each site, and how is this accountability enforced?

•	What specific performance measures will be used to evaluate progress and ensure accountability for ES&H performance?

•	What is the achieved level of ES&H performance?

Award/incentive fee criteria and performance milestones, based on the performance of ES&H activities, should be incorporated into existing site incentive systems for the execution year for use with the Department of Energy Acquisition Regulations (DEAR), Title 48 Code of Federal Regulations (CFR) Clause 970.5215-3 “conditional payment of fee, profit, or other incentives – facility management Contracts”.

3.6	References/Reading List

Department of Energy Acquisition Regulations (DEAR), Title 48 Code of Federal Regulations (CFR) Clause 970.5223-1 (formerly 970.5204-2) “Integration of Environment, Safety and Health into Work Planning and Execution”

Environment, Safety and Health Guidance for Fiscal Year (Budget Year) Budget Formulation and Execution

DOE Budget Formulation Handbook, Field Budget Process, Chapter IV, Section 1 “Environment, Safety and Health: Supplementary Budget Submission Guidance”

Department of Energy Acquisition Regulations (DEAR), Title 48 Code of Federal Regulations (CFR) Clause 970.5215-3 (formerly 970.5204-86) “Conditional Payment of Fee, Profit, or Other Incentives – Facility Management Contracts”

3.7	Definitions

Allocated (Indirect) Cost/Funding. A cost that is incurred by an organization for common objectives and that cannot be identified specifically with a particular project or activity.

Commitment. A written declaration by contractors to accomplish certain activities or meet certain conditions, as described in the ES&H Management Plan.

Direct Costs/Funding. Any costs that can be specifically identified with a particular cost objective that are directly related to and are being incurred principally for the benefit of the program receiving the charges.

ES&H Activities. Work conducted whose primary intent is to protect the health and safety of the public, workers, and the environment.

ES&H Management Plan.  The generic process by which each site conducts and reports the results of its annual ES&H planning, programming, budgeting, work commitment making, and performance evaluation to its Headquarters and Field Element Managers, the Chief Financial Officer, and EH in response to the annual budget call.

ES&H Management Plan Information System (MPIS). An optional computer-based system in which the information, obtained through the application of the ES&H Management Planning Process can be collected, analyzed, and reported.

Program Execution Guidance. Guidance developed jointly by DOE Headquarters and Operations/Field Offices and issued to contractors that provides programmatic assumptions, expected outcomes, milestones, performance measures, financial controls, and reporting requirements; to be used to develop, implement, and monitor fiscal year operations at a site.

Risk-Based Priority Model (RPM). A methodology for establishing risk rankings of the ES&H activities at DOE sites. The ranking method relates likelihood of occurrence of these risks and their adverse potential effects on the public, site personnel safety and health, compliance issues, program mission, management investment, and environmental protection. This method provides the essential information for deriving ES&H activity priorities.

Roll-up. The flow and integration of data at the contractor, Operations/Field Office, and Headquarters levels.

Target Funding Level. The total available funding specified in the Budget Control Tables provided by Headquarters.

Unfunded Activity. ES&H work that is desirable to conduct, but for which target funding is not anticipated to be provided, based on planned program direction and budget decision-making.

3.8	Training Courses/Program Assistance

Information concerning implementation of the ES&H Management Planning Process, including prioritization with the RPM, can be obtained from the following web site:  “http://tis.eh.doe.gov/bps/eshplan/index.htm”.

Questions concerning the ES&H Management Planning Process and the RPM should be directed to Raymond W.  Blowitski, EH-3, at 301-903-9878 or Patricia Bean, EH-3, at 301-903-3909.

TABLE I.

ES&H RISK-BASED PRIORITY MODEL (RPM)

|  | LIKELIHOOD OF OCCURRENCE |
| --- | --- |
| IMPACTS | A | B | C | D |
|  | VERY HIGH | HIGH | MEDIUM | LOW |
| CATEGORY: PUBLIC SAFETY & HEALTH | 3000 | 300 | 30 | 0.3 |
| 1. Immediate or eventual loss of life/permanent disability |  |  |  |  |
| 2. Excessive exposure and/or injury | 300 | 30 | 3 | 0.03 |
| 3. Moderate to low-level exposure | 30 | 3 | 0.3 | 0.003 |
| CATEGORY: SITE PERSONNEL SAFETY & HEALTH | 2000 | 200 | 20 | 0.2 |
| 4. Catastrophic - Injuries/illnesses involving permanent total disability, chronic or irreversible illnesses, extreme overexposure (e.g., 1000 rem), or death |  |  |  |  |
| 5. Critical - Injuries/illnesses resulting in permanent partial disability or temporary total disability >3 months, or serious overexposure (e.g., 100 rem) | 200 | 20 | 2 | 0.02 |
| 6. Marginal - Injuries/illnesses resulting in hospitalization, temporary, reversible illnesses with a variable but limited period of disability of < 3 months, slight overexposure (e.g., 5-10 rem), or exposure near limits (20-100%) | 100 | 10 | 1 | 0.01 |
| 7. Negligible - Injuries/illnesses not resulting in hospitalization, temporary reversible illnesses requiring minor supportive treatment, or exposures below 20% of limits (e.g., < 1 rem) | 10 | 1 | 0.1 | 0.001 |

TABLE I.

ES&H RISK-BASED PRIORITY MODEL (RPM) (Continued)

| CATEGORY: COMPLIANCE | 150 | 15 | 1.5 | 0.015 |
| --- | --- | --- | --- | --- |
| 8. Major noncompliance with Federal, state, or local laws; Enforcement Actions; or Compliance Agreements significant to ES&H and involving significant potential fines or penalties |  |  |  |  |
| 9. Major noncompliance with Executive Orders; DOE Orders; or Secretary of Energy Directives (Notices or Guidance Memoranda) significant to ES&H and not involving significant potential fines and penalties | 75 | 7.5 | 0.75 | 0.0075 |
| 10. Marginal noncompliance with Federal, State, Local Laws; Enforcement Actions; Compliance Agreements; Executive Orders; DOE Orders; or Secretary of Energy Directives significant to ES&H | 20 | 2 | 0.2 | 0.002 |
| 11. Significant deviation from good management practices | 1 | 0.1 | 0.01 | 0.0001 |
| CATEGORY: MISSION IMPACT | 150 | 15 | 1.5 | 0.015 |
| 12. Serious negative impact on ability to accomplish major program mission |  |  |  |  |
| 13. Moderate negative impact on ability to accomplish major program mission | 75 | 7.5 | 0.75 | 0.0075 |
| CATEGORY: COST EFFECTIVE RISK MANAGEMENT | 40 | 4 | 0.4 | 0.004 |
| 14. Significant avoidable cost due to degrading infrastructure, inefficient management systems or program implementation, or accident-related capital loss (total cost > $25M, or annual cost $1M-5M) |  |  |  |  |
| 15. Moderate avoidable cost due to degraded infrastructure, inefficient management systems or program implementation, or accident-related capital loss (total cost < $25M, or annual cost $1M-5M) | 15 | 1.5 | 0.15 | 0.0015 |

TABLE I.

ES&H RISK-BASED PRIORITY MODEL (RPM) (Continued)

| CATEGORY: ENVIRONMENTAL PROTECTION | 2000 | 200 | 20 | 0.2 |
| --- | --- | --- | --- | --- |
| 16. Catastrophic damage to the environment (widespread and long-term or irreversible effects) |  |  |  |  |
| 17. Significant damage to the environment (widespread and long-term or irreversible effects) | 200 | 20 | 2 | 0.02 |
| 18. Minor to moderate damage to the environment (localized and short-term effects) | 20 | 2 | 0.2 | 0.002 |

TABLE II.  RPM MATRIX LIKELIHOOD LEVELS

|  | A | B | C | D |
| --- | --- | --- | --- | --- |
| Likelihood | Very High | High | Medium | Low |
| Numerical Value | 1.0 | 0.1 | 0.01 | 0.0001 |
| Expectation |  1 in 1 Year | < 1 in 1 Year,  1 in 10 Years | < 1 in 10 Years,  1 in 100 Years | < 1 in 100 Years,  1 in 10,000 Years |

The likelihood levels are defined in section 3.2.1.

A.	Very high likelihood indicates an impact already exists with certainty or is expected to occur at least once per year. For example, if a site or facility is known to be out of compliance with a DOE ES&H Order, then the likelihood of this impact falls into the very high category. If a condition at a site or facility has historically resulted in one or more lost-time worker injuries per year and the condition has not been corrected, then the likelihood of this impact also fits this category.

B.	High likelihood indicates that an impact is expected less frequently than once per year, but more frequently than once every 10 years. Such impacts are expected to occur within the operating history of the site or facility, but have not occurred regularly every year.

C.	Medium likelihood indicates that an impact is expected less frequently than once every 10 years but more frequently than once every 100 years. Impacts with this likelihood are not expected frequently within the operating life of a site or facility, but may occur once in the site or facility's life.

D.	Low likelihood impacts are unlikely to occur within the operating life of a site or facility, but are not completely precluded from occurring. For example, impacts in this category may occur once in the operating life of one site or facility out of a population of 100 similar sites or facilities.  Impacts with this likelihood are expected to occur less frequently than once per 100 years, but more frequently than once per 10,000 years.

(This page intentionally left blank.)

# Footnotes

1OSHA may have the force of law at a minority of facilities. At these facilities, significant non-compliances with OSHA would be included under Impact 8.