Close-Out Report

on the

Department of Energy/

National Science Foundation

Committee

for the

Technical, Cost, Schedule, and

Management Review

of the

U.S. LHC CMS

DETECTOR

PROJECT

May 21, 2003

U.S. Department of Energy

and the

National Science Foundation

U.S. LHC JOINT OVERSIGHT GROUP

April 4, 2003

TO:	Mr. Daniel Lehman, Director, Construction Management Support Division, SC-81

DATE:	March 31, 2003

RE:	Request to Conduct a Review of the U.S. ATLAS and U.S. CMS Construction Projects During May 19-23, 2003

The Joint Oversight Group (JOG) for the U.S. LHC Program requests that you conduct a Review of the U.S. ATLAS and U.S. CMS Construction Projects at Brookhaven National Laboratory on May 19-23, 2003.

The charge for this review is to assess:

- Technical progress in each subsystem;

- Schedule progress on completing the U.S. deliverables including installation;

- Adequacy of the updated estimated cost to complete; and,

- Project contingency budgets.

Please provide a report on the review to this office by June 30, 2003.

Mini-reviews were conducted of the U.S. ATLAS and U.S. CMS Construction Projects in December 2002.  The review committees concluded that both projects were making good technical progress and costs were tracking close to plans, with no major schedule concerns.  These reviews also concluded that planning for transition from the construction projects to M&O is well underway.  The committee should assess progress on planning for this transition and consider the report from the U.S. LHC Detector M&O Evaluation Group, which will meet for the first time on April 8-10, 2003.

We appreciate your assistance in this matter.  As you know, these reviews are an important element of the Department of Energy/National Science Foundation (DOE/NSF) joint oversight of the U.S. LHC Program and help to ensure that the U.S. meets our commitments on cost and schedule.

[signed]					[signed]

John R. O’Fallon				John W. Lightbody, Jr.

Co-chair					Co-chair

U.S. LHC Joint Oversight Group		U.S. LHC Joint Oversight Group

Department of Energy				National Science Foundation

U.S. Department of Energy

and the

National Science Foundation

cc:

James Decker, SC-2	Ken Stanfield, Fermilab

Milton Johnson, SC-3	Thomas B.W. Kirk, BNL

S. Peter Rosen, SC-20	William Willis, Columbia University

Moishe Pripstein, SC-22	Dan Green, Fermilab

Aesook Byon-Wagner, SC-223	Jane Monhart, CH/Fermi Area Office

Marvin Goldberg, NSF	James Yeck, CH/Fermi Area Office

Jim Whitmore, NSF	Pepin Carolan, CH/Fermi Area Office

Steve Meador, SC-81

Department of Energy/National Science Foundation

Review Committee on the U.S. CMS Construction Project

CONTENTS/WRITING ASSIGNMENTS

Executive Summary	Meador/Yeck

1.	Introduction	Meador/Yeck

2.	Technical Systems Evaluations

2.1	End Cap Muon (WBS 1.1)	Foster/Subcommittee 1

2.1.1	Findings

2.1.2	Comments

2.1.3	Recommendations

2.2	Hadron Calorimeter (WBS 1.2)	Michael/Subcommittee 2

2.3	Trigger and Data Acquisition (WBS 1.3)	Haggerty/Subcommittee 3

2.4	Electromagnetic Calorimeter (WBS 1.4)	Schamberger/Subcommittee 4

2.5	Forward Pixels (WBS 1.5)	Nelson/Subcommittee 5

2.6	Common Projects (WBS 1.6)	Baltay/Subcommittee 6

2.7	Silicon Tracker (WBS 1.8)	Nelson/Subcommittee 5

3.	Cost Estimate	Kerby (with input from other subcommittees)

4.	Schedule and Funding	Kerby (with input from other subcommittees)

5.	Management (WBS 1.7)	Baltay (with input from other subcommittees)

Appendices

- Charge Memorandum

- Review Participants

- Review Agenda

- Cost Table

- Schedule and Funding Charts

- Management Chart

G.  Action Items

# 2.1	Endcap Muon (WBS 1.1)

(B. Foster)

2.1.1	Findings

The Endcap Muon (EMU) system is 77% complete and on schedule to perform above-ground system tests as per CERN’s V33 schedule.  The assigned contingency on the ETC remains 50 percent, which is adequate for this subproject.

Major production of the Cathode Strip Chambers (CSC) at Fermilab finished on the schedule originally established in 1998.  Production and testing of the full complement of CSCs for the baseline detector at the four Final Assembly and Test (FAST) sites should be completed by the end of calendar ’03.

An incoming test and storage facility has been successfully established in the CERN ISR tunnel, and a throughput of production chambers has been established sufficient to support the installation schedule.

Production of the on-chamber electronics has been completed and the integration and test of on-chamber electronics has gone relatively smoothly and on schedule.  The FAST sites have proven successful at identifying and correcting a number of issues with the on-chamber electronics.

The off-chamber electronics are in an advanced prototype stage.  A beam test is currently underway to validate the performance of the off-chamber EMU electronics in beam conditions and rates comparable to that expected at the LHC.  This effectively responds to a recommendation from last year’s review. Successful beam test results will permit a final design review and production start in November ‘03, slightly ahead of the December ’03 milestone.

Final chamber mounting on the muon steel structures should commence in mid-June.  This represents a slippage since the November ’02 date projected at last year’s review.  Roughly half of this slippage appears to have been due to factors outside of CMS’ control.

Detailed planning exists for cabling, gas installation, and other infrastructure.

Two workable alternatives have been developed for the HV system, with a decision scheduled for this summer following tests.

The alignment system design and production is well advanced.  The system is in production and on schedule to be available when the magnet test begins in early ‘05.

2.1.2   Comments

The EMU group continues to make excellent progress in all phases of the project.

The Scope addition of the ME4/1 CSCs chambers appears not to have adversely affected the project schedule. Production of these chambers is to be completed FY’04 and common electronics has been adopted for these additional chambers.

The group continues to exhibit due diligence to avoid major accidents which might derail the EMU project.  These include cooling water spillages,  “bad gas” incidents, large-scale mechanical or electrical mishaps, etc.

The M&O plans are well advanced and reasonable.  The question which arose at the April M&O review as to the adequacy of the Engineering and Technical manpower (1 vs. 8 FTEs) was resolved as having been due to miscommunication.

An excellent candidate for the on-site M&O manager has been identified.  It is important that this position be filled as proposed by summer ’04.

2.1.3   Recommendations

- Early warning systems such as the “wet wire” leak detection system and the gas-gain monitoring tubes used at CDF may be worth considering as modest scope increases.

- Redundant low-voltage power supplies should be considered for electronics in the collision hall.

- The EMU group should work with CMS management to ensure that the YE1 cabling design and procurement takes place on a schedule which does not impede the installation of the YE1 chambers

- It will be most efficient if the off-chamber electronics for the ME4/1 CSCs are incorporated in the main production run of off-chamber electronics.

2.2	HCAL (WBS 1.2)

(D. Michael)

### 2.2.1Findings

The U.S. HCAL sub-project is 82% complete on an updated estimate at completion of $42,891k EAC. Important progress has been made in the last year in all of the subsystems, especially on the HF, HPD acquisition and testing and electronics systems.

In the last year, a total of $1.1M of contingency was used. The main uses were:

- $360k increase for overruns in the optics production at Fermilab, $800k of which was already identified in a previous review.

- $250k increase for optical fiber cables and patch panel to connect the various segments of electronics.

- $267k engineering and $94k production costs for the  Gigabit Optical Links. This is a scope increase for the U.S. HCAL project which was undertaken to avoid possible delays in the previous U.S. responsibilities.

- -$170k for lower cost of production of HPDs

The current project schedule shows a negative 8 month variance, primarily for production of the HCAL electronics.  An additional negative variance exists for the HPD acquisition and testing. These variances are approximately the same as identified one year ago. However, we note that the planned HCAL vertical slice test has slipped from May 03 to Fall 03. The HCAL sub-project manager reports that they are working to a new schedule which reflects this variance but that U.S. CMS schedules have not yet reflected this new working schedule.

Following some additional delays in the last year in starting production, HPD deliveries from DEP now have reached the planned maximum of 40 units per month. The testing capabilities at Minnesota are matched to this production rate. At this point, the acceptance rate of delivered tubes is 62%. At this time, MMM tubes out of a required NNN have been accepted. The yield is smaller than nominally planned. About half of the HPDs which have not yet been accepted do not meet the contract specifications. The other half have some anomalies which may not disqualify them for use but which has kept these tubes from being declared accepted at this time. All HPDs undergo an important two-week burn-in period as part of the testing.

Good progress is being made on all of the electronics, including that to be installed in the readout boxes which represents the most critical path. It appears that the XXX ASIC fabrication has been successful after the “engineering” fabrication iteration and that the QIE ASIC is also working well. This will permit electronics fabrication to proceed soon. At this time, the group is waiting for additional assurance from test-beam operation this summer prior to proceeding with the final fabrication. Significant new results were presented on radiation and lifetime aging of the electronic boards and chips.

Important progress was shown on the HF systems. Some of the most important progress was in the fabrication of the large mechanical components which is not a direct U.S. responsibility. However, getting this moving forward helps to make the U.S. contribution in the design, fiber acquisition and readout systems a contribution towards a complete system. The new manager for the HF appears to be having a very positive impact. Almost all of the fiber has been acquired, the PMTs have all been purchased and tested and the complete readout system is advancing well.

The HCAL group is planning a vertical slice test/burn-in phase. Currently both are defined as part of M&O. Should delays occur in the critical path items the first impact will be a shortening of this test/burn-in phase.

The HO RBX still does not have a final design. Although some float remains in the demand for this system, its production is lingering well behind the original schedule.

Important progress from the 2002 test beam effort was shown. A 2003 testbeam effort is just now getting underway.  Performance from the 2002 running was consistent with expectations for resolution and uniformity for all systems. The measured resolution was roughly 120%/sqrt(E) with a 5-7% constant term. In addition to the measured calorimetry performance, these run periods are also demonstrating a considerable ability of the HCAL group as a whole to meet tight schedule objectives.

### Comments

Overall, the HCAL sub-project has made excellent progress in the last year. Particular highlights include successful test-beam operation, important progress on HF fabrication and important advances in design and testing and fabrication of readout box components, including ASIC fabrication and testing and HPD production and testing.

Progress in the last year was good but the schedule remains very tight. Importantly, the group appears sufficiently well staffed to succeed in the face of tight schedules and is focused on achieving their installation objective. The main risk is likely not that the group cannot meet the defined installation schedule but that the installed readout box devices (which are very difficult to access) will have had less opportunity for full system burn-in tests than desired given the stringent requirements on failure rates once installed. It is important that management fight slips in order to keep as much of this pre-operational testing phase intact as possible. It is advisable that the group continue to find additional means of increasing the testing, where possible, for the readout boxes as a system. In the last year, the U.S. group decided to take on additional scope for the Gigabit Optical Links. This was a wise use of contingency to avoid possible delays to the completion of the critical readout boxes.

The HCAL group is currently working to a schedule which is not represented in the main U.S. HCAL schedule. HCAL and U.S. CMS management should resolve this. The nominal working schedule is tight for completion of work for installation, but there is no action at this point which will significantly recover time from the HCAL working plan. At the same time, HCAL managers must work to avoid additional delays. Getting the electronics into full production is very important. Pushing forward with readout box assembly and testing is critical. Although HPD production and testing are now moving forward, it is possible that increasing the planned HPD “spares” pool to perhaps 20-25% of the total needed might be one way to mitigate risks of using “acceptable, but less than perfect” devices. More time would make such action unnecessary (or demonstrate it is necessary) but this would now delay the critical path.

The U.S. HCAL group is responsible for providing optical fiber cables to connect the readout boxes to the main electronics systems. These cables must go through some patch panels and must also have provision for dealing with extra lengths of cable. The definition of this system is the responsibility of the CMS integration group but no final action has been taken yet. This presents a schedule risk for the U.S. groups to provide these cables in time. Decisions must be taken soon.

### Recommendations

- U.S. CMS management should work with the CMS integration group  to define the readout optical cable system for HCAL by Sep. 1 2003.

- Plan as much burn-in testing time as possible for the completed readout boxes. Where possible, find ways to increase this time before boxes become too inaccessible.

2.3    Trigger and Data Acquisition (WBS 1.3)

(J. Haggerty)

72.3.1 Findings

Excellent progress has been made on both trigger and data acquisition systems since the last review.

The CMS management estimates that 65% of the trigger work is complete, which is consistent with information presented by the calorimeter and muon trigger groups.  Many of the final boards are complete in both the calorimeter and muon trigger systems, and design and prototyping is well under way for all of them.

The CMS management estimates that 24% of the data acquisition work is complete, consistent with the achievements presented.

The data acquisition group completed an extensive document describing the design in the Technical Design Report of December 20002.

2.3.2 Comments

The slice test is an important reality check for both the trigger and data acquisition systems, and CMS management is to be commended for recognizing its importance.  It is important that both trigger and data acquisition systems use this test to exercise their designs as thoroughly as possible.

Significant additions have been made to the Wisconsin, MIT, and UCSD groups, consistent with previous recommendations, and these new hires have filled some essential needs.

The data acquisition Technical Design Report describes a present state of the art data acquisition system that appears to be very well grounded in experience and prototyping.

2.3.3 Recommendation

Identify adequate manpower to work on the slice test at CERN while testing and production continue in the US, particularly on the muon trigger system.

2.4	Electromagnetic Calorimeter (WBS 1.4)

(D. Schanbergr, K. Lang)

2.4.1 Findings

The progress on the Electromagnetic Calorimeter (ECAL) of the U.S. CMS since

the June 2002 DOE/NSF review has been mixed and included changes in deliverables.

The US group is responsible for procurement of 1/3 of Avalanche Photodiodes (APDs) and providing about 4.5 FTEs for APD certification and characterization.

The group will also supply a laser-based monitoring system for PWO crystals. Within the last year the scope of the monitoring expanded  from using one blue laser to two blue lasers and one red laser as recommended by the 2002 DOE/NSF Review.  In addition, the U.S. ECAL has been participating in the development of the front-end FPPA chip for the APDs, but the circuit turned out to be very difficult to fabricate and has only 30% production yield. The collaboration chose to pursue in parallel a more promising multi-gain preamplifier (MGPA) integrated circuit to be fabricated in deep sub-micron (0.25 um) technology. U.S. ECAL will fund 50% of MGPAs and their neutron irradiation testing effort. MGPA is not a baseline chip yet and its certification is underway. The group is also responsible for the delivery of parts of the fiber optic link for the barrel section as well as for the design and delivery of  about 50% of the clock/control links. Finally, in response to general CMS needs, the group has recently taken up yet another responsibility of designing and fabricating parts of the low voltage power supply, and due to the early stages of the system specification the exact deliverables of this part are still not completely defined.

The US ECAL system has maintained a solid progress in procuring and certification of the Hamamatsu’s APDs. About 93,000 (out of 128,000) units have been delivered so far, testing is on schedule and projected to be complete in April 2004.

Fermilab’s electronics testing facility is being set up  to test the MGPA chips.

US ECAL would benefit from additional physicist manpower needed in the near future in the beam tests, system monitoring and calibration analysis, and the development of the low voltage power.

Production and delivery of the PWO crystals which are not a US ECAL responsibility has slipped about half a year in the past year and is on the critical path. However, US deliverables are mostly decoupled from this potentially serious delay.

Due to delays in the choice of preamps, the ADC purchase is still on hold.

No participation in the slice test is presently be considered for any ECAL modules.

2.4.2 Comments:

It is encouraging to observe that a lot of progress has been made on the front end preamplifier.  Both the original and backup plans have made significant progress.  While  the baseline design is still the original Floating Point Pre-Amp (FPPA) version, which now have working prototypes, it is clear that the system costs will be very high.  Every effort should be made to insure that the alternate Deep SubMicron (DSM) Multi-Gain Pre-Amp (MGPA) is made to work.  This is a significant change to be making this late in the project, but appears to be appropriate.  Having working electronics using this new design in time for next year’s beam test which starts in April 2004 is vital for calibrating some supermodules with beam.  Given less than a year, and still testing the first submission makes this a very aggressive schedule. Every effort should be made to meet this time scale and resources should be directed towards that end  to ensure reliability. The same level of testing and certification as in the APD must be maintained.

The low voltage system design for the ECAL is just getting started by a new group.  No bottoms up cost estimate is available.  It is not possible to evaluate if the contingency is adequate for the US deliverables part of this category.

It appears that the design, specification, and the procurement plan of the data and trigger fiber optic links to the outside of the detector is complete and production is ready to start. The 12x receiver module, which is part of the optical link, is not yet budgeted for the barrel ECAL by CMS.  The number of clock and control links has recently doubled and the US ECAL has not changed scope to instrument the entire barrel system.

The ECAL system will not be a part of the “slice test”.  This will probably delay the understanding of integration issues associated with running with other detector subsystems.

The laser calibration system is in good shape.  The expansion from 1 to 3 lasers seems prudent but costly in M&O.

In view of changes of US ECAL deliverables the M&O estimates should be re-evaluated.

2.4.3 Recommendations:

1) Make the MPGA decision no later than the end of Summer 2003.

2) Consider alternate voltage regulators (or more of the same) which are not run close to their maximum rated current.

3) Improve the project definition, and define a procedure for the end-game to maximize the use of available resources.

2.5 	Forward Pixels (WBS 1.5)

(H. Nelson, M. Crisler)

2.5.1 Findings

The Forward Pixel subproject is 35% complete, with a contingency of approximately $1.9M or 40% of the estimated cost to complete of $4.9M. This subproject is nearing the end of development, and is planned to transition to construction in 2004 or 2005.

The pixel cell size has been changed from 150(m by 150(m to 100(m by 150(m, corresponding to the change in the Read Out Chip (ROC) from the DMILL technology to ¼ (m technology.  The ROC is responsibility of PSI (the Paul Scherrer Institute) in Switzerland.

A set of sensors submitted by U.S. collaborators in 2001 was received in 2002. These sensors have been evaluated with 80% yield measured and radiation tests have been performed.  The sensor design for the pixel forward disks is distinct from the design for the barrel pixel.

About 300 ROC’s, produced in DMILL technology and known as the PSI43 design, have been received and tested, and a yield of about 50% has been measured.  These ROC’s have and will be used to characterize the detectors, bump bonds, and readout chain.

The new ROC design in ¼ (m, known as the PSI46 design, has been finalized at PSI and passed on (on 5/16/03) to CERN for checking and submission.  The pixel size for PSI46 was changed, the overall dimensions are smaller than PSI43, and the power consumption is substantially smaller for PSI46 than for PSI43.

The sensors are to be bump bonded to the ROC’s.  Three vendors (MCNC in the U.S., and IZM and VTT in Europe) are presently doing bump bonding.  Working sensors bonded to DMILL ROC’s are expected to arrive between August, 2003 and October, 2003.

The chip that controls the ROC is the Token Bit Manager (TBM).  All TBM’s, for both the barrel pixel system (mostly a European responsibility) and for the U.S. forward disk pixel system are a responsibility of the U.S.

Working TBM’s, designed by the U.S. forward pixel group and produced in DMILL technology, were available and characterized last year.  The TBM’s are now being translated to ¼ micron, with submissions planned in June of 2003 and again in October of 2003.

The ROC’s sit on a Very High Density Interconnection (VHDI) flexible circuit.  Tests of a VHDI populated with 5 ROCs, using one of 8 test stands produced by the forward pixel group, have been undertaken.

The test stands simulate the complete readout stream, and allow further design and characterization of the downstream data acquisition system.

Mechanical and thermal design and study has been advanced during the past year.

Project manpower (less faculty) has increased from 6 FTE in 2001 to 11 FTE in 2002 to 14 FTE in 2003.

2.5.2 Comments

This subproject remains on the cutting edge of technology advancement, with many associated risks.  This subproject has never been planned to be online when beams are first available at the LHC, which explains the fraction of work completed being small.  The pixel systems have been designed for relatively straightforward installation after first operation of the LHC.  The high level of contingency is appropriate for this subproject.

Communication between the U.S. forward pixel subsystem and European counterparts has improved over the past year.  There is particularly close communication between the U.S. chip designers and their counterparts at PSI.

The pixel dimensions changed from 150 (m by 150 (m to 150 (m by 100 (m, and the technology for all readout and data acquisition chips have been changed from DMILL to ¼ micron technology. There was no top-to-bottom evaluation of system consequences of these changes, as recommended in earlier reviews.  Some consequences identified at this review, include enhanced mechanical clearances, and a reduction in heat production in the detector, appear beneficial.  Essentially final mechanical and cooling designs can now be made.

The ROC’s and TBM’s delivered so far have been useful for the development of system aspects of the forward pixel project, but less so than were anticipated.  Many test stands are now able to read out a pixel slice, and soon sensors bump-bonded to ROC’s will be available.  Test beam work and a `two-blade’ system test are planned in the near future.  There appears to be adequate technical manpower support for these activities.

There is adequate scientific manpower, however, there is inadequate focus on certain tasks, including bump bonding and integration.  The success of the system tests over the next two years depends on an increased level or participation from scientists in the subproject.  We encourage the forward pixel scientists to exploit the test stands and detectors now available to characterize their systems.  This activity is crucial for the timely success of the project.

    - Recommendations

- Continue to improve communications between International CMS Management, US CMS Management, and the US Forward Pixel group.

- Focus, in the next year, scientific manpower on system integration activities.

2.6	COMMON PROJECTS (WBS 1.6)

(P. Carolan)

2.6.1 Findings and Comments

Common Projects is essentially (~99%) complete. Procurement of superconductor for the CMS magnet has been completed.  All Endcap Iron disks have been erected at the CERN CMS SX-5 surface building on budget and schedule. This accomplishment is due to good management, good design, and good workmanship from those who were involved.  Cathode Strip Chamber mounts have been located with acceptable accuracy, requiring no corrective adjustment for the CSC mount mechanism. The only remaining costs are for magnet field mapping tasks (design and M&S), and projected costs for this has been incorporated into the latest EAC. There is no need to revise the Common Projects budget figure.

2.6.2 Recommendations

None.

  - Silicon Tracker (WBS 1.7)

(H. Nelson, M. Crisler)

    - Findings

The Silicon Tracker subproject is 33% complete, with a contingency of approximately $1.2M or 53% of the estimated cost to complete of $2.3M. This subproject consists of assembly from parts produced outside the U.S., and testing, qualification and installation of the assembled modules.

Production facilities have been established at FNAL and UCSB, including functioning assembly robots (gantries), Model 8090 wirebonders, as well as burn-in and well advanced test procedures and facilities.  At each site, the planned production rate is about 10 Tracker Outer Barrel (TOB) modules per day.

New tasks undertaken include the assembly of hybrids with pitch adapters at UCSB; module diagnostics and repair at UCR, and sensor probing at Rochester.

Delays associated with the hybrids have consumed a total compared to the original baseline of 12-15 months, and left little schedule float relative to  the v33 schedule, although there is additional capacity that can in principal earn float back.

The wirebonds on modules have been damaged during transit.

Project manpower (less faculty) has increased from 1 FTE in 2001 to 11 FTE in 2002, to about 25 FTE in 2003. A further increase to 40 FTE is planned in 2004.

    - Comments

The consumption of most of the remaining schedule float by more delays in the hybrids is worrisome.   A delivery of hundreds of hybrids suitable for production is expected in the next few weeks.

We commend the reactions of the silicon tracker group, which include the shouldering of new tasks designed to minimize the impact of further delays, and we also commend them for their ramp-up in manpower.  The relationships of the U.S. CMS silicon tracker subgroup with International CMS are close, with good communication an well-coordinated efforts.

Nevertheless, the production task that the silicon group faces could prove daunting.  Continued adaptation to late arriving parts will be required, and a few delays due to peculiarities in delivered parts would push the project into multishift production to maintain the schedule.

At the mid-year review six months from now it will be possible to evaluate whether the delivery of parts and production have achieved the ramp-up needed for timely completion of the project.

    - Recommendations

Continue to develop and execute plans to handle the late arrival of parts, particularly the hybrids.

Cost, Schedule, Project Management (WBS 1.7)  & Common Projects (WBS 1.6)

Subcommittee 6: Charles Baltay, Jim Kerby,  Steve Meador

3.	COST ESTIMATE

3.1	Findings

The U.S. CMS total project cost remains at $167.25 million.  As reported at the end of March 2003, the project is 76 percent complete.  Contingency as a percentage of remaining work is 49 percent.  Table 3-1 compares the cost estimate from the June 2002 review to this review.

Table 3-1.     U. S. CMS Cost Estimate

|  |  | U.S. CMS Baseline Comparison |
| --- | --- | --- |
| WBS | System or Item | April 2002 Base Cost (AY$K) | March 2003 Base Cost (AY$K) | Difference |
| 1.1 | End Cap Muon (EMU) | 38,885 | 39,786 | 901 |
| 1.2 | Hadron Calorimeter (HCAL) | 41,082 | 42,111 | 1,029 |
| 1.3 | Trigger/Data Acquisition (Tridas) | 12,391 | 14,629 | 2,238 |
| 1.4 | Electromagnetic Calorimeter (ECAL) | 12,136 | 10,745 | -1,391 |
| 1.5 | Forward Pixels (FPIX) | 7,234 | 7,366 | 132 |
| 1.6 | Common Projects (CP) | 23,000 | 23,349 | 349 |
| 1.7 | Project Office (PO) | 6,642 | 7,047 | 405 |
| 1.8 | Silicon Tracker (SiTkr) | 3,353 | 3,382 | 29 |
| U.S. CMS Total Estimated Cost (AY$) | 144,723 | 148,415 | 3,692 |
| Contingency | 22,527 | 18,835 | -3,692 |
| U.S. CMS Total Project Cost (AY$) | 167,250 | 167,250 | 0 |

As of March 2003, the overall project cost variance is reported to be a positive 9,462M$.  At least 70% of this variance is understood by project management to be an artifact of the accounting system, and will be lowered as invoices for completed work are received.  The overall project schedule variance is reported as a negative 10,136M$.  Of this, U.S. CMS management recognizes that a small number of these variances are related to critical path items, while the remainder are to U.S. CMS internal milestones or in delays in formally reporting work as complete.

The funding profile for the construction project is adequate, and U.S. CMS has done an admirable job husbanding contingency such that it has remained around (or above) 50% of the remaining work for the past 5 years.

  - Comments

The U.S. CMS team is commended for their use of project management tools and their understanding of the information provided by those tools.

The U.S. CMS overall contingency situation is adequate to complete the project.  The first priority of the U.S. CMS project remains the completion of the US deliverables in a timely manner.  In the course of the next year, the U.S. CMS team may find itself in a position to use contingency to further assist the International CMS collaboration in completion of other portions of the detector.  The committee supports the U.S. CMS construction project in this secondary goal.

A contingency analysis was successfully completed by U.S. CMS and presented at the fall 2002 Quarterly Project Review.

  - Recommendation

- Continue to monitor the contingency situation such that a decision on additional scope may be made within the next year.

4.	SCHEDULE and FUNDING

4.1	Findings

In 2002 CMS adopted a new schedule, consistent with CERN Installation schedule v33, and U.S. CMS effort is well matched to the new schedule.  With the change in CERN schedule, DOE split the CD-4 completion date such that it is expected 95% of U.S. CMS will be complete at the end of FY2005, with the remaining 5% complete at the end of FY2007.  The portions moved beyond the original 2005 end date are those U.S. CMS components dependent on items in the CERN schedule.

4.2	Comments

Overall the U.S. CMS schedule is reasonable.  Frequent schedule updates provide planning and project execution information for U.S. CMS project and subproject teams.

The schedule revision has been well used by U.S. CMS to plan detector slice commissioning tests of components above ground at CERN before installation.

The current funding profile is provided in Figure 4-1.

Figure 4-1.     U.S. CMS Funding and Commitments (Needs UPDATE)

4.3	Recommendations

- Continue to work towards the CD-4A completion date, and closely monitor the CERN schedule for any further potential impacts.

- Resolve outstanding schedule variances due primarily to administrative issues by September 1, 2003.

5.	MANAGEMENT (WBS 1.7)

5.1 Findings

The U.S. CMS project is now 76% complete.   The completion of the project has been broken into two phases, CD-4a when the project is 95% complete by the end of FY 2005, and CD-4b for the remaining installation part up to FY 2008.

The construction project appears on schedule and well within budget to achieve its stated goals.  A total of $28.8M of contingency has been expended so far.  The estimate to complete the project is $36.0M with a remaining contingency of $18.8M.  Management has a plan to maintain this 50% contingency to the end of FY 2005, and to keep a 100% contingency of the remainder of the construction project to FY 2008.

The plan outlined by management for the next phase of the project, namely Pre-operations, Maintenance and Operations (M&O), Software and Computing (SWC), and R&D for the future LHC upgrades, seems fairly well advanced.

A plan was presented to use the period after FY 2005, when most of the detector components have been completed, and the installation on time, to carry out detector subsystem tests (“slice tests”) in the above ground buildings at the CERN site.  The purpose of these tests is to increase the probability of an early start of the productive physics program.

The Deputy Project Manager, who has been instrumental to keeping the construction project so well on track, is leaving the project in the very near future.

  - Comments

The Review Committee feels that the U.S. CMS management has done an excellent job in carrying the construction project close to completion.  Keeping such a complex enterprise on schedule and well within budget is a very significant achievement.

The Committee feels that separating the completion of the construction project into two parts was very wise in that it separates the construction completion of the project mostly under U.S. control (CD-4a) from the installation (CD-4b) that is much more correlated to the overall CERN schedules.

The U.S. CMS management should be given high accolades for their contingency experience of this project.  The committee endorses the plan to keep a 50% contingency to close to the end of FY 2005 and 100% beyond.

The U.S. CMS management should also be complimented for the initiation of the slice tests, which is a very sensible use of the time window opened up by the slippage of the overall LHC schedule.

The M&O Plan presented by the management team seems sensible and sufficiently well thought out for this stage of the procedure.  This is clearly a dynamic problem and flexibility should be allowed to adjust to needs and changes as they arise.  The plan to keep the Category B efforts and costs specific to the detector components built by the U.S. CMS seems appropriate and practical.

The Committee feels strongly that the departing Deputy Project Manager should be replaced by a professional, highly qualified in these areas.  Thinking on this issue is naturally coupled to plans of how to change the top level management from a construction project to one that includes completion of the construction as well as looking forward to M&O and the general CMS Research program.  An example of the future management structure might be:

In this plan the replacement of the Deputy Project Manager could serve as the Construction Project Manager as well as the M&O Manager since efforts on the first will be winding down as the second one builds up, and the two require similar skills.

  - Recommendations

- Replace the departing Deputy Project Manager with a strong professional by September 1, 2003.

- Work to maintain the 50% contingency up the end of FY 2005 and a 100% contingency of the remaining construction funds to FY 2008.

# Text boxes

U.S. CMS

Program Manager

Dan Green

Construction

Project Manager

X

M&O     Program Manager

X

Software and Computing

Project Manager

Lothar Bauerdick