PROPOSAL INSTRUCTIONS:  _X_ DRAFT -- COMMENTS DUE BY:  11/21/05

__ FINAL   -- PROPOSAL DUE BY:

DO TITLE:  Design and Certification of a Stabilization System to Support Shuttle Tile Repair

DO Type:  _X_ CPFF     ___ FFP

DO Contact Information in Addition to the CRAVE Contract Specialist or CO:

TMR:	Joe Gensler						Phone:  (281) 483-0025

DO Manager:  Lora Bailey/EC				Phone:  (281) 483-8893

DO Mgr. Alternate:    N/A                          			Phone:  (281) 483-

Concurrences:

(Original Signed)____	(Original Signed)____	(Original Signed)____

Lora Bailey	Harold Reimers	Joe Gensler

DO Manager			      DO Mgr. Management		COTR

(Original Signed)  ___	(Original Signed)_____	(Original Signed)___

Joe Gensler	Steve Miller	Mike Ballard

Division TMR		      S & MA				Contract Specialist

Task Contains Flight Hardware, Flight Software or GSE?   	_X_ Yes	___No

Program Supported:    	_X_Shuttle     __ISS	 _X_EVA    _ _Advanced

---------------------------------------------------------------------------------------------------------------

WBS:  _X_ 1.0 EVA  __ 2.0 FCE   __ 3.0 EVR   __ ECLSS   __ 5.0 ATCS   __ 6.0 CHeCS

For purposes of complying with FAR 52.232-22, Limitation of Funds, the total amount allotted by the Government to contract is specified in clause B.6, Contract Funding.  The funding listed in B.6 is the amount allotted for all Delivery Orders on the contract combined.

All terms and conditions of the contract apply to this Delivery Order.  In the event of a conflict between the contract and this Delivery Order, the contract shall prevail.

WBS reporting shall be done in accordance with applicable WBS reporting categories, as shown above and in the contract within Section C, Table 1.

# Narrative Task Description

## Background / Problem Description:

- Objective

The objective of this Delivery Order (DO) is to design and certify a portable EVA device that uses Hot Melt Adhesive (HMA) to attach an EVA handhold to Shuttle Reaction-cured Glass (RCG) thermal protection tiles.  The system shall also be able to be reconfigured to stabilize the Orbiter Boom Sensor System (OBSS) at a worksite.

- Need for Shuttle Worksite Stabilization

During Shuttle Flight STS-114, the crew relied upon the Space Station Remote Manipulator System (SSRMS) to remove gap fillers protruding from Shuttle RCG tiles.  The crew would have used the SSRMS, in conjunction with the Orbiter Repair Maneuver (ORM), to access any area of the Shuttle’s Thermal Protection System (TPS) that needed repair.  This procedure will not be possible during later flights when the ISS grapple fixture required to support the effort will be blocked.  As a result, a new method of accessing potential TPS worksites must be developed.  Ideally a new method would be independent of the SSRMS so that the crew could affect TPS repairs during Shuttle missions away from the International Space Station (ISS), such as on a Hubble Space Telescope servicing mission.

The Shuttle Remote Manipulator System (SRMS), in conjunction with the OBSS, could be used to access Shuttle TPS repair sites, in the absence of the SSRMS.  However, the OBSS on the end of the SRMS is not stiff enough in most required manipulator configurations to allow the EVA crewmember to perform useful work.  As a result, a system must be developed to stabilize the crewmember at the end of the OBSS when interacting with a worksite.  A method should also be developed to stabilize the OBSS itself when it has positioned the crewmember at the desired worksite.

The only available surface on which to stabilize, at most of the potential TPS worksites, is the TPS tile surface itself.  This surface is critical and can be easily damaged.  Therefore, any stabilization system must not only react the desired stabilization forces, but must also ensure the safety of the Shuttle tiles.

- Prior Work

NASA funded research on Pressure Sensitive Adhesive (PSA) and Hot Melt Adhesive based stabilization systems to support Shuttle Return to Flight (RTF) activities.  Highlights of this work are available in the CRAVE Technical Library.

This work resulted in the analysis and prototype testing of both a PSA and HMA system.  This testing indicated that a HMA based system provides much better adhesion to Shuttle tile surfaces than a PSA system and requires much smaller forces to apply.  Consequently, NASA has baselined a HMA system for stabilization.

## Task Description:

The contractor shall build upon previous work to design a self-contained, HMA based system that can be used to provide an EVA handhold to stabilize an EVA crewmember while performing TPS inspection and repairs.  The effort shall follow NASA standard procedures for developing flight hardware, as described in NASA document EA-WI-023.  The development and certification effort shall be a phased approach.  During the initial phase, the contractor shall develop the requirements and detailed design for the stabilization system.  During Option 1, the contractor shall build two protoflight units and perform the tests necessary to flight certify the units.  The contractor shall also refurbish the protoflight units, if required.

During the initial phase, the contractor shall develop, test, and deliver an Engineering Development Unit (EDU). The results of the EDU testing will be used to guide the detailed design.  These tasks are described in more detail in the following paragraphs.

- Requirements Development

The stabilization system shall meet the following functional requirements:

- Attach to Shuttle RCG and react expected EVA loads without damaging the Shuttle tiles

- Be capable of being attached and removed by a single, free-floating crewmember

- Require less than 5 minutes to install and create a rigid connection

- Require less than 5 minutes to be removed

- Leave residual adhesive, following removal, of less than 0.060” inches in height

- Allow a minimum of 3 attachment and detachment cycles during a single EVA

- Accommodate the following surface variations:

Maximum tile-to-tile step:		0.06”

Maximum tile-to-tile gap:		0.15”

Minimum radius of curvature:	40.0”

- Fit within a single middeck locker

- Be reconfigurable to provide OBSS stabilization

- Meet applicable EVA GDRD requirements

The contractor shall expand and refine these requirements, and use them to develop a Project Technical Requirements Specification (PTRS).  The contractor shall also develop preliminary Interface Control Documents (ICDs) for the unit.  The contractor shall present this information at a Systems Requirements Review (SRR), to be held at NASA.  The contractor shall track issues brought up during the SRR and work to resolve these issues by accepting, tracking, and processing Review Item Disposition (RIDs).

- Preliminary Design

Following completion of the Requirements Development process, the contractor shall develop a preliminary design for the stabilization system.   The preliminary design shall be documented in a Preliminary Data Package to be distributed to NASA 5 days prior to a Preliminary Design Review (PDR).  During the development of the preliminary design, the contractor shall develop models of the stabilization system, perform the necessary preliminary analyses, and perform any testing deemed necessary to develop the preliminary design.  As a minimum, the contractor shall develop and test an Engineering Development Unit (EDU) to help prove out and refine the design.  The contractor shall deliver the EDU, along with a User’s Manual, to NASA at the end of the preliminary design phase.  NASA intends to test the unit and provide feedback to the contractor.  The contractor shall use this feedback to drive the unit design during the detailed design phase.

The contractor shall host a PDR at NASA.  The contractor shall track issues brought up during the review and work to resolve these issues by accepting, tracking, and processing RIDs.

During the Preliminary Design Phase, the contractor shall also develop the necessary safety documents, and coordinate and support the appropriate safety reviews.

- Detailed Design

Following completion of the Preliminary Design Phase, the contractor shall develop a detailed design for the stabilization system.  The detailed design shall be documented in a Critical Data Package to be distributed to NASA 5 days prior to a Critical Design Review (CDR).  During the development of the detailed design, the contractor shall refine models of the stabilization system, complete the necessary detailed analyses, complete the drawings and procedures required to produce the unit, perform any additional testing deemed necessary to develop the detailed design, and develop the necessary test plans and procedures to certify a protoflight unit.

The contractor shall host a CDR at their facility.  The contractor shall track issues brought up during the review and work to resolve these issues by accepting, tracking, and processing Review Item Disposition (RIDs).

During the Critical Design Phase, the contractor shall also develop the necessary safety documents, and coordinate and support the appropriate safety reviews.

- Reporting

The contractor shall provide monthly status and financial management reports as directed in the data requirements table.

- Government Provided Equipment

NASA will assist the contractor in battery requirements definition from previously Flight Certified cells. This DO assumes NASA will provide Flight Certified cells to the contractor.

Deliverables/Products:

| Product | Description | Qty | Due | Class |
| --- | --- | --- | --- | --- |
| Hardware |  |  |  |  |
| Mock Up |  |  |  |  |
| Prototype | Functional Prototype for engineering testing | 1 | 07/17/06 | 3 |
| Certification |  |  |  |  |
| Flight |  |  |  |  |
| Training |  |  |  |  |
| Other |  |  |  |  |
| Test |  |  |  |  |
| Software |  |  |  |  |
| Other Products | User’s Manual for Prototype Units | 1 | 07/17/06 |  |

SCHEDULE

Start Date:  January 3, 2006			Finish Date:	September 29, 2006

| ITERIM MILESTONES | DUE DATES |
| --- | --- |
| System Requirements Review | January 26, 2006 |
| Preliminary Design Review | May 11, 2006 |
| Critical Design Review | September 14, 2006 |
| Milestones, along with subjective measurements, are to be used for measuring performance. For schedule detail see Microsoft Project file located on the CRAVE web site for this DO listed under the Government Cost Estimate below. |

Government Estimate Located in RFQ File in Microsoft Project File On CRAVE Web Site

The file is titled:  WS Stabilization (CRAVE)-1-3-06.mpp

Total Government Estimate for this DO: $1.4M

Option 1:  $611k   (See Attachment 1)

Option 2:  $           (See Attachment 2)

TOTAL COST ESTIMATE FOR THIS DO:  $(Contractor Complete)

FEE:  $  (If Applicable)

OPTION 1:  $ N/A   (See Attachment 1)

OPTION 2: $  N/A   (See Attachment 2)

DATA REQUIREMENTS

Notes:  1.   Grey Scaled Rows Need No Additional/Required Fill-ins.

2.  On all other rows, If Necessary, Fill in Additional

Rqmts/Deliveries in last Column.

| DRD # | DATA TYPE | DRD TITLE | DUE | FREQUENCY | REQUIRED FOR DO? Y/N | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Written Approval | FlightGFE Configuration Management Plan | With Proposal | Once | Attachment J-8 |  |
| 2 | Mandatory Submittal | Regular Status Report/ Summary Review | Thirty (30) days following contract start | Monthly | Y |  |
| 3 | Written Approval | Project Technical Requirements Specification | If Required for DO See Comments | Once with Revisions | Y |  |
| 4 | Mandatory Submittal if Flt H/W | GFE Systems Requirements Data Package | If Required for DO See Comments | Once with Revisions | Y |  |
| 5 | Written Approval | Flight GFE Projects Requirements & Verification Document | If Required for DO See Comments | Once with Revisions | N |  |
| 6 | Mandatory Submittal if Flt H/W | Preliminary Design Review Data Package | If Required for DO See Comments | Once with Revisions | Y |  |
| 7 | Written Approval | Flight GFE Workmanship Specifications List | If Required for DO See Comments | Once with Revisions | N |  |
| 8 | Written Approval | Project Schedule | PDR or 10% effort complete Milestone | Once w/Revisions (due w/DO proposal, updates & details provided as DO progresses) | Y |  |
| 9 | Written Approval | Flight GFE Interface Control Document | If Required for DO See Comments | Once with Revisions | Y |  |
| 10 | Written Approval | GFE End Item Specification | If Required for DO See Comments | Once with Revisions | N |  |
| 11 | Mandatory Submittal if Flt H/W | Flight GFE Failure Analysis Report | If Required for DO See Comments | As Required | Y |  |
| 12 | Written Approval | Flight GFE Verification and Validation Plan | As Specified in EA-023 | Once with Revisions | Y |  |
| 13 | Written Approval | GFE Software Requirements Specification | If Required for DO See Comments | Once with Revisions | Y If Applicable |  |
| 14 | Written Approval | GFE Software Development Plan | If Required for DO See Comments | Once with Revisions | Y If Applicable |  |
| 15 | Written Approval | GFE Software Design Document | If Required for DO See Comments | As Required | Y If Applicable |  |
| 16 | Written Approval | Engineering Drawings | If Required for DO See Comments | Once with Revisions | Y |  |
| 17 | Written Approval | EEE Parts Lists and Analysis Report | If Required for DO See Comments | As Required | Y |  |
| 18 | Mandatory Submittal if Flt H/W | Critical Design Review Data Package | If Required for DO See Comments | Once with Revisions | Y |  |
| 19 | Mandatory Submittal if Flt H/W | Engineering Drawing Change Proposal | If Required for DO See Comments | As Required | Y |  |
| 20 | Written Approval | GFE Qualification Test Procedure | If Required for DO See Comments | Once with Revisions | Y | Equivalent to TPSs |
| 21 | Written Approval | Flight Product User’s Guide | If Required for DO See Comments | Once with Revisions | Y | Option 1 Only |
| 22 | Mandatory Submittal if Flt H/W | Software Code | If Required for DO See Comments | As Required | Y If Applicable |  |
| 23 | Written Approval | Information Technology (IT) Security Program Plan and Reports | (30) days after DO award, and as specified in JPG 2810.1 | JPG 2810.1 | Attachment J-4 Due 30 days after DO award |  |
| 24 | Written Approval | Certification Plan | If Required for DO See Comments | Once with Revisions | Y | Option 1 Only |
| 25 | Mandatory Submittal if Flt H/W | Certification Report | If Required for DO See Comments | Once with Revisions | Y | Option 1 Only |
| 26 | Mandatory Submittal if Flt H/W | Engineering Analysis | If Required for DO See Comments | As Required | Y |  |
| 27 | Mandatory Submittal if Flt H/W | Acceptance Data Package | If Required for DO See Comments | One Time | Y | Supplied with protoflight hardware delivery Option 1 Only |
| 28 | Mandatory Submittal | Export Control Audit Results | After award of 1st DO, yearly on Sept. 30 thereafter | Yearly | Y |  |
| 29 | Written Approval | Quality Plan | With Proposal | Once with Revisions | Attachment J-11 | Only if contractor is using the R-Quality Plan template instead of ISO, and only if they need to make changes to it |
| 30 | Written Approval | Patent Rights-Retention | As Required | As Required | Y (If Applicable) |  |
| 31 | Written Approval | Shuttle/Station Payload Safety Data Package | If Required for DO See Comments | As Required | Y |  |
| 32 | Mandatory Submittal if Flt H/W | Limited Life Systems List | If Required for DO See Comments | As Required | Y |  |
| 33 | Written Approval | Space Station GFE Failure Modes and Effects Analysis and Critical Items List | If Required for DO See Comments | As Required | N |  |
| 34 | Written Approval | Space Shuttle GFE Safety and Analysis Report &Hazard Report | If Required for DO See Comments | As Required | Y |  |
| 35 | Written Approval | Software Quality Assurance Plan Report | 90 Days Prior to Software Development | Once with Revisions | Y (If Applicable) |  |
| 36 | Written Approval | ISS Hazard Report | If Required for DO See Comments | As Required | N |  |
| 37 | Upon Request | Reliability and Maintainability Plan | With Proposal | One Time | Attachment J-9 |  |
| 38 | Written Approval | Government Certification Approval Request (GCAR) | If Required for DO See Comments | As Required | Y | Option 1 Only |
| 39 | Written Approval | Risk Assessment Executive Summary Report (RAESR) | If Required for DO See Comments | As Required | Y |  |
| 40 | Written Approval | Problem Reporting and Corrective Action (PRACA) | 2 business days of problem isolation but no later than 10 days after detection | As Required | Y | Option 1 Only |
| 41 | Upon Request | Nonconformance Record | If Required for DO See Comments | As Required | Y | Option 1 Only |
| 42 | Mandatory Submittal | Government Industry Data Exchange Program and NASA Advisory Problem Data | Reported one time when discrepancy occurs | Once with Revisions | Y |  |
| 43 | Written Approval | Electrical, Electronic, and Electromechnical (EEE) Parts Control Plan | If Required for DO See Comments | Once with Revisions | Y |  |
| 44 | Mandatory Submittal if Flt H/W | Certification Data Package | If Required for DO See Comments | Once with Revisions | Y | Option 1 Only |
| 45 | Written Approval | Certification and Acceptance Requirements Document | At CDR | Once with Revisions | Y |  |
| 46 | Upon Request | Wage/Salary and Fringe Benefit Data | Thirty (30) days after issuance of each DO | Once | N |  |
| 47 | Written Approval | GFE Acceptance Test Procedure | If Required for DO See Comments | One Time | N |  |
| 48 | Mandatory Submittal if Flt H/W | Flight GFE Verification & Validation Report | If Required for DO See Comments | Once with Revisions | Y | Option 1 Only |
| 49 | Mandatory Submittal if Flt H/W | Space Shuttle GFE Failure Modes and Effects Analysis (FMEA) and Critical Items List | If Required for DO See Comments | As Required | Y |  |
| 50 |  | Reserved | --- | --- | --- | --- |
| 51 | Mandatory Submittal | NASA Contractor Financial Management Reporting | After Issuance of 1st DO | Monthly | Y |  |
| 52 | Written Approval | Government Property Management Plan | With Proposal | Once with Revisions | Attachment J-7 |  |
| 53 | Mandatory Submittal | System Safety Plan | With Proposal | One Time | Attachment J-10 |  |
| 54 | Written Approval | R-Quality Plan Template | With Proposal/ Revisions as Required | Only applicable to B-CRAVE contracts in accordance with the SOW and the DRD | N | Only if contractor is using the R-Quality Plan template instead of ISO, and only if they need to make changes to it |

Type 1 = Written Approval               Type 2 = Mandatory Submittal                Type 3 = Submittal Upon Request

GOVERNMENT FURNISHED PROPERTY  - The list of items below will be provided as Government Furnished Property.

| Item | Part Number | Quantity | Value |
| --- | --- | --- | --- |
| Pistol Grip Tool Battery | SED33110979-305 | 3 | $8,000 each |
|  | (available by May 2006) |  |  |

ATTACHMENT 1

The Government may exercise the option described below for the option value listed on the DO cover page by written notification to the contractor 15 days before the completion of the Basic delivery order requirement.

OPTION 1 TITLE:  Production and Flight Certification of a Stabilization System to Support Shuttle Tile Repair

## Background / Problem Description:

Following the detailed design of the stabilization system, the design must be certified for flight through the development, testing, and of refurbishment, if required, of 2 protoflight units.

## Task Description:

- Protoflight Unit Production

The contractor shall fabricate and integrate two (2) protoflight units per EVA GDRD protoflight requirements and as documented in the design phase.

- Flight Certification

The contractor shall flight certify the two (2) protoflight units per the EVA GDRD and V&V Plan developed in the initial phase.

- Reporting

The contractor shall provide monthly status and financial management reports as directed in the data requirements table.

Deliverables/Products:

| Product | Description | Qty | Due | Class |
| --- | --- | --- | --- | --- |
| Hardware |  |  |  |  |
| Mock Up |  |  |  |  |
| Prototype |  |  |  |  |
| Certification |  |  |  |  |
| Flight | Protoflight | 2 | 03/02/07 | 1 |
| Training |  |  |  |  |
| Other |  |  |  |  |
| Test |  |  |  |  |
| Software | If software/firmware is required, the software/firmware will be developed in accordance with NPR 7150.2, NASA Software Engineering Requirements |  |  |  |
| Other Products |  |  |  |  |
| Option 1 Report |  |  |  |  |

SCHEDULE

Start Date:  October 23, 2006				Finish Date:	March 22, 2007

| ITERIM MILESTONES | DUE DATES |
| --- | --- |
| Milestones, along with subjective measurements, are to be used for measuring performance. For schedule detail see Microsoft Project file located on the CRAVE web site for this DO listed under the Government Cost Estimate below. |

CHANGES TO DRDs:  NONE

CHANGES TO GOVERNMENT FURNISHED PROPERTY:  NONE

(IF YES, THEN INSERT GOVERNMENT FURNISHED PROPERTY TABLES)