An Integrated Roadmap for the Programmatic Resolution of Gas Generation Issues in Packages Containing Radioactive Waste/Materials

Final Report

Prepared by:

National Transportation Integration and Planning Program

Idaho National Engineering and Environmental Laboratory

Bechtel BWXT Idaho, LLC

P.O. Box 1625

Idaho Falls, ID 83415-1625

April 2001

EXECUTIVE SUMMARY

Gas generation, particularly hydrogen, is an area of significant concern for the transport and storage of radioactive materials in the Department of Energy (DOE). Because it appeared that this issue was being addressed independently by various research and development (R&D) programs within the DOE Complex, the Office of Integration and Disposition (EM-20) and the Office of Science and Technology (EM-50) established a Task Group to develop an integrated gas generation R&D plan.

This report contains the integrated gas generation R&D plan in a “roadmap” form. Attachment A is the summarized graphical depiction of the roadmap (hereafter called the ‘roadmap summary’).  This depiction is the heart of the report and it contains concise, useful information readable at a glance. The following figure from the roadmap summary is an example of what useful information can be viewed.  For example, Figure 1 shows the shipping function for plutonium oxides in jeopardy because of untimely certification of a transportation package, as indicated by the red coloration of the function coupled with red flags showing activities/functions in jeopardy. Section 5 and Attachment A contain a complete guide for reading the roadmap summary. To give supporting detail to the roadmap summary, an R&D activities matrix is located in Attachment B.  The matrix gives a summary statement, owner, and projected completion date for the R&D ‘issue resolution activities’ that are shown in the roadmap summary.

Figure 1. Example of the Integrated Hydrogen Gas R&D Plan Diagram showing the relation of R&D actions to functions over time. This view shows a function and a milestone in jeopardy.

From this planning effort the Task Group found the following:

- Overlaps: There are no significant overlaps in planned R&D activities, nor appreciable duplication of R&D already performed

- RFETS Closure: The de-inventory of nuclear materials and closure of Rocky Flats Environmental Technology Site (RFETS) may be in jeopardy because both the 9975 and SAFKEG shipping packages have encountered problems associated with certification due in part to gas generation issues

- Unclear NM disposition pathway: Orphan nuclear materials (those materials that cannot be treated/stabilized according to DOE-STD-3013-2000, Stabilization, Packaging, and Storage of Plutonium-Bearing Materials) need a clear disposition pathway.

The roadmap summary shows pathways that have significant risk, which may indicate more emphasis, should be placed on contingency planning. If an existing pathway proves unsuccessful, what is the backup plan? For example, getter development and shipping of sealed containers of oxides and some other nuclear materials are activities that may need some contingency planning due their moderate to high probability of failure. Continued use of roadmapping efforts will be useful in keeping focused on the efforts necessary to mitigate the risk in the disposition pathways and to respond to the specific needs of the sites.

The roadmapping effort further identified the following opportunities for sharing of information and collaboration (1) use of periodic symposium for sharing, (2) modeling of gas generation rates; (3) gas measurement methods; (4) use of getters; (5) inert atmosphere; (6) permeable membrane technology; and (7) drying/stabilization techniques.

Another aid to resolving gas generation issues is the establishment of an independent peer review group to address challenges of gas generation throughout the DOE Complex. This would assist in viewing the overall picture and keep R&D efforts in line with existing and forecasted needs.

In conclusion, it became apparent to the Task Group that gas generation issues can adversely affect DOE milestones in a number of programs and at a number of sites. The Task Group believes that gas generation issues may represent one of the greatest threats to timely accomplishment of DOE’s Environmental Management (EM) mission.

Contents

Acronyms	iv

1	INTRODUCTION	1

2	PURPOSE	2

3	ROADMAPPING APPROACH AND METHODOLOGY	2

3.1	Regulatory Background	2

3.2	Process Background	5

4	OVERVIEW OF PROGRAM APPROACHES	8

4.1	TRU Waste Program	8

4.2	NM Programs	8

4.3	SNF Program	10

4.4	Program Integration	10

5	USING THE ROADMAP SUMMARY AND MATRIX	10

5.1	Roadmap Summary Explanation	11

5.1.1	Overview	11

5.1.2	Colors	11

5.1.3	Legend	12

5.2	Detailed Matrix Explanation	12

6	FINDINGS, RECOMMENDATIONS, AND PATH FORWARD	12

6.1	Findings	12

6.2	Recommendations	13

6.2.1	Sharing of Information	13

6.2.2	Contingency Planning	15

6.2.3	Independent Peer Review Group	16

6.3	Path Forward / Assignment of Responsibilities	17

Acronyms

ANSI	American National Standards Institute

CFR	Code of Federal Regulations

CH	Contact-Handled (i.e. CH-TRU)

CoC	Certificate of Compliance

DOE	Department of Energy

DP	Defense Programs

EM	Environmental Management

EPA	Environmental Protection Agency

FRR	Foreign Research Reactor

H2	Hydrogen Gas

ICV	Inner Containment Vessel

IE	Inspection and Enforcement

HLW	High-Level Radioactive Waste

HVAC	Heating, Ventilation, and Air Conditioning

INEEL	Idaho National Engineering and Environmental Laboratory

LANL	Los Alamos National Laboratory

LLNL	Lawrence Livermore National Laboratory

LLW	Low-Level Radioactive Waste

LWA	Land Withdrawal Act

M/LLW	Mixed/Low-Level Radioactive Waste

NM	Nuclear Materials

NMFA	Nuclear Materials Focus Area

NN	Non-proliferation and National Security

NRC	Nuclear Regulatory Commission

NSNFP	National Spent Nuclear Fuel Program

NTP	National Transportation Program

NTWP	National TRU Waste Program

ORNL	Oak Ridge National Laboratory

Pu	Plutonium

R&D	Research and Development

RH	Remote-Handled

RFETS	Rocky Flats Environmental Technology Site

SAR	Safety Analysis Report

SARP	Safety Analysis Report for Packagings

SNF	Spent Nuclear Fuel

SRS	Savannah River Site

SQS	Small Quantity Sites

TFA	Tanks Focus Area

TMFA	TRU & Mixed Waste Focus Area

TRU	Transuranic

U	Uranium

WIPP	Waste Isolation Pilot Plant

# INTRODUCTION

Gas generation issues, particularly hydrogen, have been an area of concern for the transport and storage of radioactive materials and waste in the Department of Energy (DOE) Nuclear Complex for a number of years. Potentially combustible gases can be generated through a variety of reactions, including chemical reactions between water or organic compounds and the contained material and radiolytic decomposition of hydrogen-containing materials. At the same time, chemical reactions can remove hydrogen, and these reactions can be enhanced by the presence of radiation. The balance between these competing reactions is not well known at this time. This uncertainty in the potential for the generation of combustible quantities of hydrogen in containers of radioactive material is the essence of the problem in shipping or storage of those materials. Transportation regulations prohibit shipment of explosives and radioactive materials together. The regulator responsible for certifying packages for the shipment of radioactive waste, the Nuclear Regulatory Commission (NRC), has developed criteria to ensure packaging effectiveness when there is the potential for generation of combustible gas mixtures. The regulator responsible for certifying packages for the shipment of non-defense nuclear materials (DOE/EM-5) may adopt the same criteria, but has indicated a willingness to consider other criteria that will provide equivalent assurance that radioactive materials are not being shipped together with explosives, as required by the transportation regulations.

The gas generation issue is unlikely to have a single, generic answer suitable to all situations. That is because of the wide variety of wastes, residues, and nuclear materials that exist within the DOE Complex. To illustrate the problem, consider stabilized plutonium oxides – at this time we believe that the primary hydrogen generation mechanism is a reaction between “tightly bound” adsorbed water and the plutonium oxide. In unstabilized oxides, with higher water content, hydrogen production may also be possible through radiolytic decomposition of some of the less tightly bound water. Some residues contain unreacted materials, such as calcium, that can produce hydrogen through reactions with unbound water that may be present. Wastes may contain organic materials, which, in the presence of a radiation field, can decompose to produce hydrogen. In short, different materials produce hydrogen through different reactions, and some materials may involve several reactions. In the same manner, reactions that remove hydrogen can vary from material to material.

To ensure that the various gas generation activities within the Office of Environmental Management (EM) are properly integrated, Mr. David Huizenga, DOE EM-20 and Mr. Gerald Boyd, DOE EM-50, established a Task Group to develop an integrated gas generation research and development (R&D) plan (i.e., a program level ‘roadmap’).  Members of the Task Group included DOE and contractor representatives from: the Nuclear Materials (NM) programs, which includes the Nuclear Material Focus Area (NMFA), the Nuclear Materials Stewardship Program, and the 94-1 Program; the National Transportation Program (NTP); the Spent Nuclear Fuel (SNF) program; the TRU Waste program, including the Transuranic and Mixed Waste Focus Area (TMFA); and site personnel associated with these programs.

Gas generation data provided by the NM, SNF, and TRU Waste programs give focus to the activities needed to succeed in proper storage and shipment.  Also, site subject matter experts, Focus Area representatives, and national program personnel provided additional information and clarification about the site and R&D baselines. Future assessments will integrate data from the high-level radioactive waste (HLW) and mixed/low-level radioactive waste M/LLW programs to better determine if those programs also have gas generation issues.

This report identifies the major gas generation programmatic issues within the DOE Complex and the research that has been and is being conducted to address gas generation concerns. This document is a report on the work of the Task Group in developing the integrated R&D plan (roadmap). The report also presents a “program level” roadmap that links technology development to program needs and identifies the probability of success in an effort to understand the programmatic risk associated with the issue of gas generation.

# PURPOSE

This “program level” roadmapping is meant to focus needed technical support to the baselines (and to alternatives to the baselines) where the probability of success is low (high uncertainty) and the consequences of failure are relatively high (high programmatic risk).  Emphasis should be directed to areas where investments are large, the return on investment is high, or the timing is crucial for dispositioning the waste or material. A second purpose of this document is to provide the basis for coordinating sharing of “lessons learned” from R&D efforts across DOE programs to increase efficiency and effectiveness in addressing gas generation issues.

# ROADMAPPING APPROACH AND METHODOLOGY

The approach is to use “roadmapping” methodology to link technology development (and deployment) efforts to the programs’ needs and requirements for dispositioning the material/waste that generates gas through radiolysis and chemical decomposition.  Development of this roadmap involved identifying the major steps needed for disposition (or for storage pending disposition) and the associated R&D and certification activities required to ensure the viability of each step. In a generic disposition pathway, four major functions are needed: (1) treatment, (2) packaging, (3) transportation, and (4) disposal/storage. Issues or challenges arise because of uncertainty in completing a function. In addition, there are regulatory activities that are required to demonstrate to an independent third party that a function can be completed adequately and safely. The independent third party then, in part, uses the technical information provided by R&D activities as referenceable material proving adequacy and safety in a disposition pathway function.

The following subsections (3.1 and 3.2) describe the regulatory background for each of the three-waste/material programs and the process used in developing the roadmap.

## Regulatory Background

The potential for gas generation in packages containing nuclear material or waste has been a growing regulatory concern.  In part, the growth of the gas generation issue is because the scope of work within the DOE complex has changed.  As sites change from production mode to environmental remediation and facility closure, a wider variety of materials are being shipped for testing, process, or final storage than has been shipped in the past.  This section discusses the current regulatory requirements pertaining to gas generation for transportation and storage of nuclear materials and waste.

The Nuclear Regulatory Commission (NRC) has the responsibility to issue certificates of compliance for transport packages containing radioactive materials. The Code of Federal Regulation, at 10 CFR 71, provides the necessary regulations. DOE has been authorized (49 CFR 173.7) to issue certificates for DOE transportation packagings, provided that DOE use the same or comparable regulations. DOE exercises its authority as a regulator only for shipments of nuclear materials. The NRC regulates (certifies packages for) transportation of TRU, LLW, and SNF.

The NRC first established basic guidelines for hydrogen gas generation in the Inspection and Enforcement (IE) Information Notice No. 84-72: Clarification of Conditions for Waste Shipments Subject to Hydrogen Gas Generation, published by the NRC Office of Inspection and Enforcement in 1984. The memo required that in twice the expected shipping time, hydrogen gas be limited to a molar quantity that is no more than 5% by volume of the secondary container gas free volume at a standard temperature and pressure.  Failing that, the secondary container can be inerted to ensure that oxygen is limited to 5% by volume in the portions of the package that could have hydrogen greater than 5%.  The Standard Review Plan for Transportation Packages for Radioactive Material, NUREG-1609 published in November 1999, has superceded the earlier Information Notice for Type B packages.  It requires that an applicant for a Certificate of Compliance (CoC) for a package demonstrate in a Safety Analysis Report for Packaging that hydrogen and other flammable gases comprise less than 5% by volume of the total gas inventory within any confined volume.  It also requires that the maximum normal operating pressure within the vessel be appropriately evaluated. The DOE has not restricted itself to the NRC criteria, and may adopt other equally effective criteria, perhaps more similar to those in the earlier IE Bulletin.

Storage of potentially gas-generating materials is another subset of the gas generation issue.  However, regulation of this function differs from that of transportation in several ways. Perhaps foremost is the fact that the regulatory interest is in the storage facility, and not just the materials container. The container is just one element in a system intended to isolate the radioactive materials from workers, the public, and the environment. Similar to transportation, however, regulation is accomplished through preparation, review, and approval of safety analysis reports, control of operations processes and procedures, and training of involved workers. These aspects prevail whether the facility is a storage vault or a materials repository, and whether the regulator is the NRC or is internal to DOE.

Guidance for the non-facility aspects of long-term storage of plutonium metals and oxides is contained in DOE Standard 3013, originally published in 1994. The standard requires that oxides be stabilized by heating for at least two hours at 950°C in an oxidizing atmosphere and that the moisture content of the stabilized material be less than 0.5% by weight. Metals must have no liquids present, contain no pyrophoric compounds, and be in sufficiently large pieces to preclude spontaneous combustion.  The materials are doubly encapsulated in leak-tight, welded metal cans that may contain a maximum 4.4 kilograms of plutonium (or 5.0 kg of plutonium-bearing material). The standard conservatively assumes that all of the hydrogen in the water adsorbed on oxides is decomposed to generate hydrogen gas. The mass-loading may be reduced to ensure that internal pressure from hydrogen generation remains within the design parameters of the container for a minimum of 50 years. The body of analytical and theoretical work that supports this standard indicates that stabilized oxides provide an oxygen “sink” that precludes a combustible atmosphere within the container, even though it may be rich in hydrogen. It should be noted that gas generation issues generally do not affect current storage. That is because current practice is to not contain the hydrogen source, thereby allowing the generated gases to be diluted and swept out of the storage facility through the heating, ventilation, and air conditioning (HVAC) system. Although there have been some instances in which gas generation has contributed to unexpected occurrences in storage vaults, it has generally not been a problem for the vast majority of nuclear materials that have been or are being stored - some of which have been in storage for decades.  An extensive review of storage "events" showed that all had involved unstabilized materials, implying that stabilization effectively limited pressurization.

In summary, different government bodies may regulate shipment and storage of wastes and materials at different points in time or location. DOE and EPA primarily regulate TRU waste, while activities to disposition NM are governed by DOE. NRC sets forth the regulations and procedures for SNF dispositioning.

## Process Background

In January 2000, the National Transportation Program (NTP) sponsored a Hydrogen Gas Generation Workshop in Albuquerque, New Mexico.  The goal of the workshop was to promote the integration of DOE gas generation activities across DOE programs.

As a result of the workshop, it became apparent that gas generation issues were being addressed independently by a number of different organizations.  Therefore, David Huizenga, Deputy Assistant Secretary, Office of Integration and Planning (EM-20) in coordination with Gerald Boyd, Deputy Assistant Secretary, Office of Science and Technology (EM-50) decided to establish a Task Group responsible for development of a report that would help integrate resolution of gas generation programmatic issues.  The Task Group was assigned to develop a strategic approach for addressing gas generation issues, develop a roadmap to solutions, and establish an integrated group within EM-20 that will review progress on R&D activities.  The National Transportation Program (NTP) of EM-20 was asked to lead the planning effort in coordination with the Science and Technology Integration Program at the INEEL.  Other members of the Task Group consisted of cross-program DOE representatives and contractors from 1) the Nuclear Materials Programs, 2) the Spent Fuel Program, 3) Waste Management, and 4) the TRU Waste Program.  In addition, the Task Group coordinated with both the TRU and Mixed Waste and Nuclear Material Focus Areas under EM-50.

The roadmapping effort began with a kick-off meeting held in May 2000. Representatives from the Task Group plus subject matter experts from DOE sites that have potential gas generation problems were invited. The purpose of the working session was to address the R&D activities, the needs and requirements, and the programmatic and regulatory issues associated with storage, packaging, and shipping waste/materials that generate hydrogen gas (and possibly other gases) within the DOE complex.  Figure 2 shows the process used during the “roadmapping” effort. A two-toned status bar indicates how far in the process this document describes. The lighter tone indicates that a start has occurred but that more effort and detail ought to be done in subsequent efforts. The kick-off meeting was used as the first method to address the first two functions indicated in the figure.

Figure 2. Roadmapping Process for the Integrated Hydrogen Gas Generation R&D Plan

It was determined at the kick-off session that the programs that have, or potentially have, gas generation issues include the NM programs, the TRU waste program, the SNF program, the nuclear material programs in NN-60 and DP, the high-level radioactive waste program, and potentially the mixed and low-level radioactive waste program (for high activity waste). The nuclear material programs in NN-60 and DP appear to have mostly metallic or low alpha activity (e.g., uranium) materials; these programs do not appear to have serious gas generation issues, primarily because metals do not pose a gas generation problem, and there will be very little shipment of oxides. The solutions for excess EM oxides are directly applicable to the National Nuclear Security Administration oxides.  Table 1 shows the sites/programs having gas generation issues and those entities that are seeking resolution to those issues.

Table 1. Sites with potential gas generation issues and programs seeking resolution.

| Program with Waste/Material Stream | NM | TRU | SNF | HLW | M/LLW | Other |
| --- | --- | --- | --- | --- | --- | --- |
| Sites with Gas Generation Issues: |  |  |  |  |  |  |
| Hanford | X | X | X | X |  |  |
| INEEL | X | X | X | X |  |  |
| LANL | X | X |  |  |  |  |
| ORNL | X | X |  |  |  |  |
| RFETS | X | X |  |  |  |  |
| SRS | X | X | X | X |  |  |
| SQS/Other Sites | X | X | X | X |  |  |
| FRR |  |  | X |  |  |  |
| Universities |  |  | X |  |  |  |
| Other Gov’t Agencies |  |  | X |  |  |  |
| DP | X |  |  |  |  |  |
| NN-60 | X |  |  |  |  |  |
| Programs Working on Solutions to Issues: |  |  |  |  |  | Point of Contact |
| TMFA |  | X |  |  |  | Whitney St. Michel or Sheila Lott |
| NTWP |  | X |  |  |  | Phil Gregory |
| NTP | X | X | X |  |  | Steven Hamp |
| 94-1 R&D | X |  |  |  |  | Richard Mason or Sharon Arp |
| NMFA | X |  | X |  |  | Gary Roberson |
| NSNFP |  |  | X |  |  | Gregg Wachs |
| TFA |  |  |  | X |  | Tom Brouns |

Gas generation issues are found across the DOE Complex. The severity of the impact, however, depends on the material in question. For example, many of the issues associated with transportation of TRU waste have been solved. Methods to predict gas generation have been expanded to include most of the waste materials destined for WIPP. Further, the methods have been refined to account for reduced gas generation in certain wastes, thereby allowing a larger payload. Current issues deal mainly with a small portion of the wastes that cannot yet be shipped and the desire to improve efficiency and cost effectiveness.

With respect to nuclear materials, the situation is quite different. Shipments of plutonium oxide and other related materials from Rocky Flats are currently precluded because there is no certified transportation package. One of the major impediments to certification is the inability to realistically predict gas pressure and composition within the sealed transportation container. Resolution of this matter is on the critical path for de-inventory of nuclear materials from Rocky Flats Environmental Technology Site (RFETS). As the site attempts to maintain its schedule, delays are creating a “bow wave” of shipments that threatens to exceed the capacity of the transportation system. A complicating factor at RFETS, Savannah River Site (SRS) and Hanford is the requirement in the “3013 Standard” that oxides packaged according to the standard must be represented by materials in a surveillance program currently underway at Los Alamos National Laboratory (LANL). The current inability to ship such materials precludes their inclusion in the surveillance program, thereby delaying their packaging for storage.

With respect to spent nuclear fuel, the problem is not so immediate. However, the ability to predict gas generation to the satisfaction of regulatory and safety officials is a critical factor in designing systems to store and transport SNF. It is important that these matters are resolved in the near future so that shipping and facility deactivation schedules will not be adversely impacted.

The HLW program has gas generation issues ranging from gas generation in liquid waste storage tanks to transport of the liquid waste in pipes (pre-vitrification). The Tanks Focus Area (TFA) is doing some work on defining mechanisms for gas generation due to gamma- and beta-ray impinging on hydrogenous material (i.e., high-level waste). This work may be useful to other DOE programs. It may also be useful to explore other opportunities to share R&D activities with the HLW program in the future.

The M/LLW program was identified as potentially having a gas generation issue due to high activity waste. However, no information could be obtained to determine if there are any issues or not. All people contacted so far were not aware of any problems (or at least of any actions being taken to determine if there is an issue).

The National Transportation Program (NTP) has been providing support to the various programs in helping determine or develop the shipping packages that could be used for transporting the waste and materials.  NTP also provides support by funding some R&D efforts and evaluation of R&D efforts that could improve transportability of nuclear waste and materials.

In summary, it is apparent that gas generation issues can adversely affect DOE milestones in a number of programs at several sites. The Task Group believes that gas generation issues may represent one of the greatest threats to timely accomplishment of DOE’s Environmental Management (EM) mission.

# OVERVIEW OF PROGRAM APPROACHES

Each of the programs (NM, TRU, SNF) has different, yet related approaches to solve gas generation issues. In terms of maturity of shipment campaigns, the programs are at different levels; therefore each program has a different focus. The TRU waste program currently focusing on ways to speed up the process and to include a greater portion of the TRU waste that can be disposed at WIPP; the NM program is at the threshold of shipping, while the SNF is looking at a future time for shipping to a national repository. The following is a summary of each program’s approach.

## TRU Waste Program

The TRU waste program addresses the shipment of defense-related TRU waste throughout the DOE complex and the disposal of TRU waste at WIPP.  The TRU waste program focuses on the use of the TRUPACT-II, HalfPACT, and 72-B cask packagings, each with an approved Certificate of Compliance (CoC) from the NRC, based on a satisfactory review of the applicable Safety Analysis Report for Packagings (SARP).  The SARP is intended to demonstrate compliance with all applicable transportation requirements.  Of particular interest is the requirement that concentrations of hydrogen gas may not exceed 5% (by volume) of the free gas volume in any confined region of the package during the maximum allowable transportation period. Many forms of TRU waste can generate hydrogen gas and this requirement can often limit the amount of waste that may be transported within a single package.

Payload expansion initiatives, intended to increase the envelope of shippable waste in the three approved packagings, are submitted to the NRC for review and approval.  These expansion initiatives build on analytical methods used to estimate flammable gas concentrations and use the best available information about the waste and the waste packaging.  This information is used to provide an accurate model for flammable gas generation and release.  Through the payload expansion initiatives included in 19 revisions of the TRUPACT-II SAR, approximately 97% of the contact-handled waste inventory in approved payload containers (e.g., 55-gallon drums) may be shipped to the WIPP site for disposal.  Future work in the TRU waste program will focus on making the remaining 3% of the waste shippable, developing a packaging for the shipment of waste in large payload containers, and increasing the envelope of shippable remote-handled waste in the 72-B cask.

## NM Programs

It appears that the NM program currently has the most serious issues and the most pressing drivers to solve the gas generation issue due primarily to not having a certified shipping container.  One of the major impediments to certification is the inability to realistically predict the extent of hydrogen generation within the sealed transportation container.  Resolution of this matter is on the critical path for de-inventory of nuclear material from RFETS, and has already delayed shipments. In fact, RFETS de-inventory is the critical driver for the schedule information shown on the roadmap summary chart. Savannah River Site (SRS) will be the likely recipient of the RFETS 3013-compliant materials while most of the non-compliant materials are expected to go to WIPP. Each of these sites has a vested interest in how the materials will be packaged, shipped and stored (dispositioned).

Gas generation issues also impact other DOE sites that have nuclear materials including Hanford, INEEL, LANL, LLNL and Oak Ridge. Other DOE programs like NN-60 and DP are also impacted. Some of these sites (e.g., INEEL and Oak Ridge) have mostly uranium materials that do not typically have a serious issue with gas generation.

The NM approach to solving the gas generation issue is to develop empirical data in the 94-1 Program demonstrating overall gas generation rates (including gas recombination rates).  These empirical data are then used in analytical models being developed by the NMFA that can predict or bound gas pressure and composition in a sealed container. Two types of models are under development: one would be used to predict or bound gas pressure and composition for materials meeting certain specifications, while the other would be used to extrapolate gas generation measurements on less well characterized materials. The first type of model allows safe storage or transport to be assured through characterization of the materials, ensuring that they meet the required specifications. The second type of model requires a gas generation measurement on each container of material, although it may be possible to use statistical methods to reduce the number of measurements made. In either case, failure to meet the requirements, i.e., to be within the material characterization criteria or to have an acceptable measured gas generation rate, would require treatment (repackaging and/or stabilization) of the materials to meet the shipping/storage requirements.

In regards to the two shipping packagings slated for immediate use pending certification (namely 9975 and SAFEKEG) the SARP for the 9975 has been submitted using current information. There is no assurance a certificate will be granted based on that information. In fact, current, on-going R&D is proving helpful in answering some of the regulator’s questions. The SARP for SAFEKEG is under review. It is likely, but not certain, that information for the 9975 will be satisfactory for the SAFEKEG. The SAFEKEG is needed a) because of its lesser weight more can be included in the weight-limited DOE Transport Safeguard System which will allow for quicker de-inventory of RFETS and b) as a backup to the 9975 should a design flaw or other systemic problem be identified. On longer term schedule shipments, as the case for de-inventory of Hanford, additional R&D could prove helpful depending on what restrictions are placed on the 9975 and/or SAFEKEG. Further R&D could be useful for some materials, those that are outside of the current 3013 scope (generally <30% Pu plus U) and currently appear to be orphans, to permit the 3013 scope to be expanded to accommodate these materials.

R&D performed for gas generation is also done for economic reasons. For example, R&D on moisture measurements could result in a system that is less expensive in terms of both cost and personnel exposure. However, there is no clear “deadline” for those benefits so the urgency is much less and no attempt has been made to show it on the roadmap summary chart, but it is worthwhile R&D nevertheless.

A major unknown at this time is whether DOE/EM-5 will accept hydrogen concentrations greater than 5%. Even if it can be shown that hydrogen concentrations greater than 5% do not produce a flammable mixture in the container, there may be a concern regarding behavior during an accident involving some breach of the package. In such an event, the gas escaping into the oxygen-containing ambient environment might reach flammable concentrations and produce an unacceptable result. One possibility for stabilized materials may be to rely on the robust design of the 3013 specified container inside the 9975 transportation package to survive an accident and preclude release of any contained hydrogen. Another possibility may be the development and incorporation of getter materials within the package to mitigate or control the hydrogen concentration. These concepts, coupled with additional empirical data and improved predictive models, currently appear to be the most promising solution(s) to the gas generation issue for the NM program.

## SNF Program

The SNF program’s approach is much like that of the NM program.  It plans to use the modeling of gas generation rates for traceable proof for certified packaging.  Coupled with modeling, the strategy also includes drying of spent fuel elements (treatment) to reduce a potential hydrogen gas source.  Additionally, work is being performed to look at a permeable membrane technology to prevent excessive gas buildup during long-term storage. The sites having SNF assume that their efforts to solve the generation issue will be timely and successful. This is based in part on the fact that the schedule to disposition the fuel is at least 5-10 years in the future. Driving this schedule is the future opening of a geologic repository for SNF.

## Program Integration

Overall there do not appear to be many overlaps of ongoing or planned R&D efforts related to gas generation issues among DOE EM programs. There are many reasons for this. One reason is simply the differing situations that exist for the different materials. For example, because shipments of SNF are not contemplated for several years, currently SNF only needs gas generation data to support design of storage and transportation containers. However, shipments of nuclear materials are already delayed and a transportation container has been designed and is nearing certification. What is needed at this time is a predictive model that is sufficiently robust in its theoretical and experimental basis to satisfy a regulator. Such a model for TRU waste has been developed, approved, and is currently in use. R&D on gas generation from TRU waste is focused on increasing the amount of material that can be put into a container. It should be noted that the approach taken in construction of a TRU waste gas generation model and its justification to the regulator is now being applied to certain nuclear materials. Similarly, approaches being taken to measure and model gas generation in nuclear materials may be applied to SNF. In this way, lessons learned are applied to later endeavors.

Another reason for the apparent absence of overlaps is the differing nature of the materials and the consequent differences in gas generation mechanisms. For example, gas generation in a nuclear material, “stabilized oxides”, is dominated by its greatest source of hydrogen: water, and a mechanism that includes potentially both surface catalysis and radiation-induced reactions. Gas generation in another nuclear material, unstabilized oxides, still considers only a single source of hydrogen, but radiolysis appears to dominate over other types of reactions. However, TRU waste has many sources of hydrogen. Also, TRU waste has a significant, though finite, source of hydrogen and the rate of gas generation is dependent in part on the radiation field. In stabilized oxides, the situation is reversed, with only a limited source of hydrogen. Thus, R&D on gas generation mechanisms for TRU waste is not particularly applicable to stabilized oxides.

Programs have started to share and integrate information and expertise.  For example, the 94-1 R&D program, which has extensive experience measuring gas evolution in dry oxides, and the NMFA are applying their expertise to the measurement of gas evolution from “dried” SNF.  Another positive development is the integration of SNF into the NMFA R&D activities.

# USING THE ROADMAP SUMMARY AND MATRIX

A simplifying visual depiction assists decision-makers to readily identify how R&D and key programmatic efforts link to the gas generation issues in the DOE Complex. This section contains two products: (1) the summarized graphical depiction of the roadmap summary. (Attachment A), and (2) a matrix (Attachment B) containing in depth information including points of contacts and projected completion date for each of the R&D issue resolution activities included on the roadmap summary. Roadmap summary site milestones and agreements were taken from The DOE Plan in Response to DNFSB Recommendation 2000-1 Revision 1, entitled An Implementation Plan for Stabilization and Storage of Nuclear Material dated January 2001.

## Roadmap Summary Explanation

The gas generation roadmap summary shows at a glance the functions involved to disposition a waste/material type, the R&D and regulatory activities associated with successfully completing a function, and the current condition of the functions and activities. This roadmap summary is designed to assist decision-makers by quickly showing how issue resolution activities are logically related to disposition functions and to direct decision-maker focus towards resolution of the issues.

### Overview

Starting left to right on the roadmap summary (Attachment A) are four columns: (1) program name, (2) waste/material type, (3) issues and resolution activities, and (4) a timeline of functions and activities. To get a material/waste positioned for disposition/disposal, functions, like those defined on the roadmap summary, are needed (namely, treat, package, ship, and store). These functions are shown as bars and are labeled on the far right of the roadmap summary. The roadmap summary is designed to focus on how resolution activities enable a function to begin or improve. The activities do this is by producing deliverables (for example, regulator approval of a package type or gas generation rate data that helps prove the safety of a container) that provide a basis to begin performing or improving a function. The timeline column then identifies four dimensions for an activity: (1) risk, (2) time, (3) type of activity, and (4) possibility for sharing across programs. Risk is depicted by the colors (section 5.1.2) and time is shown by the location of an icon in relation to the timeline. The shape of the icon, as defined in the legend (section 5.1.3), shows the activity type and the possibility for sharing is defined by a purple diamond surrounding an icon.

### Colors

It is essential the roadmap summary be colored. This added dimension provides significant information by identifying where emphasis and management involvement is needed. The colors indicate a level of risk as described by the following color definitions:

- Red indicates there is significant risk to achieving success. For example, the activity lacks funding, basic assumptions that provide the foundation for the activity or function are wrong, the regulator indicates that activity may be unacceptable, or the critical path appears to be unachievable unless heroic efforts are made.

- Yellow designates moderate risk. For example, the activity is behind schedule, the success of the activity is suspect (funding, schedule, regulatory approval, politics), an aggressive assumption has not been proven, or some combination of factors.

- Green indicates low risk. For example, an activity/function has funding, priority, and expects to meet its milestones and goals.

- Blue describes where a process improvement happens. Examples are: an increase in process efficiency, reduction in cost, schedule improvements, and increased safety.

- Striping shows that the function is ‘at risk’ unless, and until, the resolution activity is successfully completed. The color of the striping is indicative of the coloring of the resolution activity (indicating level of risk) feeding into the function.

### Legend

The Legend is located at the bottom of the roadmap summary. It shows symbols for milestones, completion times for R&D activities, regulator approval times, and “at risk” activity flags. The flags are meant to be an added guide to direct decision-makers to focus on specific areas. The first row continues by showing if an activity extends beyond the timeline shown on the roadmap summary. An important symbol is the purple diamond surrounding an R&D icon. It designates a possible opportunity for programs to share information by virtue that they may be similar enough or have lessons-learned that another program can use for assistance. On the bottom row with the color definitions is a two-tier, two colored icon showing a performance improvement area. When a function has an increase in productivity or throughput because of an R&D activity, this icon shows it.

## Detailed Matrix Explanation

The roadmap summary provides a broad overview of the issues within the DOE Complex. Because of the brevity, Attachment B of the report contains more detail of each of the resolution activities shown on the roadmap summary. Only R&D resolution activities are enumerated along with detail concerning activity objectives, responsible group and individual, and the expected deliverable format and content. The activities are cross-referenced to the roadmap summary by the material/waste letter coupled with the number of the activity. For example, on the first page of summaries labeled “TRU Gas Generation Roadmap Summary,” the first waste/material is called Non-Type IV and it is labeled with the letter ‘A’. If  activity 2 ‘Reduce layers of confinement R&D’ is chosen then further information about the activity can be found in the matrix labeled TRU A-2.

# FINDINGS, RECOMMENDATIONS, AND PATH FORWARD

The Task Group purposely kept this roadmapping effort and analysis at a fairly high level rather than going into great detail.  In doing so, some of the findings and recommendations may be somewhat subjective based on high level analysis and may have precluded inclusion of some important lower level critical activities.

By reviewing the report, the roadmap summary (Attachment A), and the matrix (Attachment B), the Task Group makes the following findings, recommendations, and suggested path forward:

## Findings

- No duplication of efforts - There are no significant overlaps in planned R&D activities, nor appreciable duplication of R&D already performed.  The reason for this is that shipping program maturity levels are staggered. TRU waste shipping is the most mature with shipments currently taking place, whereas NM is at the threshold of shipping from RFETS. Shipping of SNF to a repository is scheduled to start a decade from now.

- NM shipping packages - For the RFETS shipping schedule to be met, both the SAFKEG and 9975 packagings must be certified for transportation campaigns of nuclear material. Both the SAFKEG and the 9975 packages are needed to ensure the maximum amount of material can be shipped in the narrow window of opportunity. There is a moderate probability with high consequence of failure to give a moderate level of risk tending to high because problems are being encountered with certification of both packages.  It is essential that the 94-1 R&D efforts to understand the gas generation and recombination mechanisms, plus NMFA efforts in modeling to predict gas pressure and composition continue in order to reduce this risk.

- Unclear NM disposition pathway - A disposition pathway is identified for the portion of nuclear materials that are treated and sealed according to the current 3013 standard.  However, other nuclear materials such as some impure oxides and residues do not have a clear disposition pathway.  It appears that these orphan nuclear materials need priority attention to make sure shipping packages can be certified, shipments can be approved and expedited, and pathways for disposition can be quickly developed (or RFETS closure schedule needs to be revised).

- Unsure SNF cask funding - The baseline schedule for shipping of SNF to a repository is very much in jeopardy due to anticipated lack of funding for continued development of a transportation packaging (cask).

- Contingency planning needed - The roadmap shows pathways that have significant risk, which may indicate more emphasis should be placed on contingency planning.  For example, getter development and shipping of sealed containers of nuclear materials are activities that may need some contingency planning due their moderate to high probability of failure.

- TRU waste program performance improvements - The TRU program can currently perform all functions needed to disposition TRU waste.  The R&D activities being performed are to enhance performance of existing functions e.g., to allow greater amounts of waste in the shipping package thus decreasing transportation costs and schedule.

- Opportunities for sharing – The Task Group found many opportunities for sharing information about gas generation issues and potential solutions (see 6.2 Recommendations).  Areas of greatest potential cooperation appear to be in sharing methods, approaches, and strategies.

## Recommendations

In an effort to reconcile the findings, the Task Group offers the following recommendations for consideration. With each recommendation there are specific areas that need focus now and associated suggested actions that will identify and/or facilitate the implementation necessary to address the recommendation.

### Sharing of Information

The Task Group found that there are four areas that have the most potential for sharing of information.

#### Areas of Focus

  - Methods for measuring gas generation rates – Methods for measuring gas generation rates, sampling methods, analysis methods, procedures, and even equipment for making these measurements are part of what can be shared among the programs in this area.

  - Mechanisms for gas generation – Though gas generation mechanisms may differ due to the chemical and physical properties of the waste/materials in each program, the general mechanisms of radiolysis and some chemical interactions are the same or similar enough to warrant sharing of this information.

  - Modeling methodologies – The approach used to develop a model for gas generation (or the structure of the model) may very well be applied to several different materials. A model would most likely require some modification as it is applied across different materials because gas generation mechanisms differ.  Once developed, a model would require R&D data to demonstrate its applicability.

  - Approaches for elimination of gas generation or mitigation of impacts –

    - Use of getters – If regulatory approval can be obtained, getters will allow greater quantities of TRU waste to be transported in each shipment.  Although getters for materials other than TRU waste will likely be different because of the dissimilar environments in which they must operate, the processes for obtaining regulatory acceptance and the technical bases will likely be very much alike.

    - Permeable membranes – If proven successful for “venting” of metal containers while maintaining their robustness, this technology is one that could potentially be shared by various programs within the DOE Complex.

    - Drying/stabilization techniques – Drying/stabilization techniques are currently part of the planned or current baseline for preparing nuclear materials for long-term storage and transportation.  These techniques, developed by the NM programs, should have applicability to the SNF program.

    - Use of inert atmospheres – The NRC applies a simple 5% concentration limit to hydrogen in the container atmosphere. The DOE/EM regulator may be willing to consider instead a flammability limit for hydrogen content that considers limiting the oxygen concentration.  The conditions that the regulator might impose, such as requiring the container to be opened in an inert atmosphere or requiring the package to survive more severe accidents would likely apply to different materials.

#### Methods to Implement

The following are suggested ways of facilitating the sharing of gas generation information:

- Use of periodic symposium for sharing: Gathering the DOE Complex subject matter experts to openly discuss progress and issues are of immense value. Group dialogue most always leads to productive conclusions. This Task Group could be the nucleus of such a forum.

- Reports ‘clearinghouse’ establishment: Charter an existing organization to serve as a ‘clearinghouse’ to collect and disseminate information on R&D and other activities that relate to gas generation throughout the DOE Complex to all entities that could gain from the sharing of this information.

### Contingency Planning

There are pathways that are questionable single solution pathways.  Therefore, the group suggests that bottlenecks be defined and plans made as to how to mitigate them.  Should a single pathway prove impassible, alternatives should be considered or put into place or the consequences will most likely be “missed” or “slipped” milestones.

#### Areas of Focus

The following are items that should have contingency plans developed in case the existing baseline fails to achieve the expectations:

  - RFETS shipping schedule – The detailed schedules for shipment of nuclear materials from RFETS needs to be looked at in detail to determine if the baselines for shipping, development of the 9975 and SAFKEG shipping packagings, manufacture of the shipping packagings, and programmatic approvals, etc. are integrated and achievable.  Other alternatives should be explored in case one of the links is delayed or unattainable.

  - Treatment, shipping, and disposition of nuclear materials – Issue resolution activities are being worked, but their timely success to support baseline schedules (e.g., RFETS closure) is not very certain at this point for some impure Pu oxides and residues.

  - Uses of getters to enhance shipping capabilities – Regulators do not currently accept getters in transportation packages. As a consequence, use of getters involves not only the R&D to identify, develop, demonstrate, and deploy them, but also involves convincing the regulator that they will perform as designed.  Because of the real risk that the regulator may not approve the use of getters, the programs should plan for other contingencies.

  - Permeable membranes – As with getters, the regulator acceptance of permeable membranes to vent hydrogen gas buildup in shipping and/or disposal containers is questionable since they do not currently allow any “vented” Type B packagings and may even question the applicability of “venting” to disposal.  Contingency planning should be implemented to have alternatives in place if the regulators reject the concept or should the R&D prove to not work.

  - SNF Funding – The Task Group recommends that DOE management evaluate funding adequacy and timing of the SNF packagings to assure meeting shipping schedules and impacts of not meeting them.

#### Methods to Implement

The following are some suggested methods to help in identifying areas that are on critical pathways that need contingency planning.

- Continue to use this roadmap as a planning tool- the tool for decision-makers has been developed. Continued use of this roadmap would constitute good project management practices.

- Leverage the expertise and capability of the independent peer review group as mentioned in the following section.

- EM-20/EM-50 should assign responsibility to perform contingency planning to fold into the roadmap.

### Independent Peer Review Group

Establish an independent peer review group to address challenges of gas generation throughout the DOE Complex.  The following areas of focus are anticipated functions of this group.

#### Areas of Focus

  - Review proposed R&D and programmatic activities – This review would look at the details of the activities, including the schedule for development, to assure that the activity fully resolves the issue(s) or does so if combined with other activities.

  - Perform quality checks on applications to regulators – Using experts in writing applications for packaging certification would streamline the now lengthy process of submittal to a regulatory agency, waiting for comments (usually in regards to issues that could be caught before handing the application to the regulator), and then responding to the issues and resubmitting. The expert group would provide invaluable advice that would most likely shorten the certification process.

  - Act as facilitator – Being independent from the programs, this group could have greater influence with the regulator(s) by facilitating submittals from the applicants to the regulators.

  - Assure life cycle planning – In some instances, dispositioning a waste/material included only either long-term storage or transportation. When designing and developing packagings, decision-makers should thoroughly develop the disposition path that takes the material/waste from current to end state. Once the disposition pathway has defined functions, a decision-making process should be used to ensure DOE resources are prudently employed.

#### Methods to Implement

  - Establish the peer review group- DOE management enlists subject matter experts to participate in this group.

  - NTP independent review- Assign the NTP to independently review the baseline schedule for funding and development of the SNF packagings to determine immediacy of need for funding, etc.

  - Re-establish the ANSI 14.32 working group- The Standard for Gas Generation in Packages Used for the Storage or Transport of Radioactive Materials (ANSI 14.32) working group would assist others to plan for current to end state disposition of materials/wastes.  This group would define standards that the peer review group could use in their analyses of the programs’ activities.

## Path Forward / Assignment of Responsibilities

The following are activities / assignments that summarize the action items in the preceding Recommendations section.  The team members recommend that David Huizenga and Gerald Boyd of DOE-HQ take the lead role and initiate the activities located in the following table.

| Activities | Suggested Assignments |
| --- | --- |
| Assign responsibility for ‘clearinghouse’ function | NTP – begin immediately |
| Assign responsibility for report updates and timeframes for updates | NTP – every 6 months |
| Determine date of next status meeting on roadmap progress | EM-20 – Sept./Oct. 2001 |
| Set date of next symposium for sharing | Rotate NTP, NM, TRU, SNF – June 2001 |
| Assign responsibilities for contingency planning | Each Program – by July, 2001 |
| Assign responsibility for independent peer review group (e.g., NTP or an Integrated Product Team (IPT)) | IPT – lead by NTP – by June 2001 |

Attachment A- Roadmap Summary Graphic

This attachment contains the Roadmap Summary graphic.  This depiction is the heart of the report and it contains concise, useful information readable at a glance.  The roadmap summary is grouped and color-coded by waste/material type: (1) TRU, (2) NM, and (3) SNF.  Following the set of roadmap summaries is a description of how to interpret the layout and symbols on page A-6.  The roadmap summary shows the interrelation of R&D activities to the functions necessary to disposition the waste/materials over which DOE has stewardship.

Page A-2

Page A-3

Page A-4

Page A-5

ROADMAP SUMMARY EXPLANATION

The gas generation roadmap summary shows at a glance the functions involved to disposition a waste/material type, the R&D and regulatory activities associated with successfully completing a function, and the current condition of the functions and activities. This roadmap summary is designed to assist decision-makers by quickly showing how issue resolution activities are logically related to disposition functions and to direct decision-maker focus towards resolution of the issues.

Overview

Starting left to right on the roadmap summary (Attachment A) are four columns: (1) program name, (2) waste/material type, (3) issues and resolution activities, and (4) a timeline of functions and activities. To get a material/waste positioned for disposition/disposal, functions, like those defined on the roadmap summary, are needed (namely, treat, package, ship, and store). These functions are shown as bars and are labeled on the far right of the roadmap summary. The roadmap summary is designed to focus on how resolution activities enable a function to begin or improve. The activities do this is by producing deliverables (for example, regulator approval of a package type or gas generation rate data that helps prove the safety of a container) that provide a basis to begin performing or improving a function. The timeline column then identifies four dimensions for an activity: (1) risk, (2) time, (3) type of activity, and (4) possibility for sharing across programs. Risk is depicted by the colors (section 5.1.2) and time is shown by the location of an icon in relation to the timeline. The shape of the icon, as defined in the legend (section 5.1.3), shows the activity type and the possibility for a purple diamond surrounding an icon defines sharing.

Colors

It is essential the roadmap summary be colored. This added dimension provides significant information by identifying where emphasis and management involvement is needed. The colors indicate a level of risk as described by the following color definitions:

- Red indicates there is significant risk to achieving success. For example, the activity lacks funding, basic assumptions that provide the foundation for the activity or function are wrong, the regulator indicates that activity may be unacceptable, or the critical path appears to be unachievable unless heroic efforts are made.

- Yellow designates moderate risk. For example, the activity is behind schedule, the success of the activity is suspect (funding, schedule, regulatory approval, politics), an aggressive assumption has not been proven, or some combination of factors.

- Green indicates low risk. For example, an activity/function has funding, priority, and expects to meet its milestones and goals.

- Blue describes where a process improvement happens. Examples are: an increase in process efficiency, reduction in cost, schedule improvements, and increased safety.

- Striping shows that the function is ‘at risk’ unless, and until, the resolution activity is successfully completed. The color of the striping is indicative of the coloring of the resolution activity (indicating level of risk) feeding into the function.

Legend

The Legend is located at the bottom of the roadmap summary. It shows symbols for milestones, completion times for R&D activities, regulator approval times, and “at risk” activity flags. The flags are meant to be an added guide to direct decision-makers to focus on specific areas. The first row continues by showing if an activity extends beyond the timeline shown on the roadmap summary. An important symbol is the purple diamond surrounding an R&D icon. It designates a possible opportunity for programs to share information by virtue that they may be similar enough or have lessons-learned that another program can use for assistance. On the bottom row with the color definitions is a two-tier, two colored icon showing a performance improvement area. When a function has an increase in productivity or throughput because of an R&D activity, this icon shows it.

ATTACHMENT B- DETAILED MATRIX

The roadmap summary provides a broad overview of the issues within the DOE Complex. Because of the brevity, this attachment of the report contains more detail of each of the resolution activities shown on the roadmap summary. Only R&D resolution activities are enumerated plus detail concerning project objectives, responsible group and individual, and the expected deliverable format and content. The activities are cross-referenced to the roadmap summary by the material/waste letter coupled with the number of the activity. For example, on the first page of the roadmap summary, the first waste/material is called Non-Type IV and it is labeled with the letter ‘A’. If the activity ‘2’ ‘Reduce layers of confinement R&D’ is chosen then further information about the activity can be found in the matrix labeled TRU A-2.

There are three parts to the matrices color-coded with the roadmap summary: TRU waste program, NM programs, and the SNF program.

| ID | Activity Title | Task Description | Contact | Date Complete | Deliverable |
| --- | --- | --- | --- | --- | --- |
| TRU A-1 | Single Headspace Measurement for CH TRU | Option for use of a single headspace measurement for CH TRU waste in place of gas generation testing (test duration reduced from weeks to hours). | Phil Gregory (NTWP) | Done | This activity resulted in a submittal to the NRC to approve a proposed revision (#19) to the SAR for the TRUPACT-II. It was submitted in April 2000. The NRC is reviewing the application. |
| TRU A-2 | Reduce Confinement Layers within Drums | Hydrogen gas buildup can occur from restricted hydrogen gas release through the multiple layers of packaging within CH TRU waste drums. Removing the confinement layer may allow the waste to meet shipping requirements. | Whitney St. Michel / Sheila Lott (TMFA) | Sep-01 | Demonstrate commercial technology viability |
| TRU A-4 | Non-hydrogenous materials | This project is identified for FY-02 to develop non-hydrogenous waste packaging materials. Non-hydrogenous waste packaging materials can be used with those wastes that will be generated/packaged for disposal in the future, which include: TRU waste treatment operations, D&D activities, and ER projects. | Whitney St. Michel / Sheila Lott (TMFA) | Sep-02 | Report presenting information learned. |
| TRU A-5 | Hydrogen Gas Getters | Hydrogen Gas Getters For TRU Waste - Upon completion of the TMFA Hydrogen Gas Getters studies, NTWP will be ready to submit option to NRC for use of gas getters (potentially reduces hydrogen concentration in the TRUPACT-II ICV to below 5%) (wattage increase up to 50+ times). | Whitney St. Michel / Sheila Lott (TMFA) | Sep-01 | Reports evaluating getter performance and ability to meet anticipated regulatory concerns. |
| TRU B-1 | Gas Generation Tests for Organic Sludges | Perform gas generation tests on organic sludges. | Whitney St. Michel / Sheila Lott (TMFA) | Oct-01 | Report with data. |
| TRU C-1 | Headspace Gas Sampling of RH-TRU Waste Containers – LANL | By the end of FY-00, design, fabricate, and utilize a gas sampling system for RH TRU canisters to measure gas evolution rates and determine "effective G-values". This information will be used to determine whether the waste meets transportation requirements and WIPP acceptance criteria | Whitney St. Michel / Sheila Lott (TMFA) | Nov-00 | Report generated at LANL entitled- “Headspace Gas Sampling of RH-TRU Containers at LANL, FY-00 Status Report,” LA-VR-00-5213. |

| ID | Activity Title | Task Description | Contact | Date Complete | Deliverable |
| --- | --- | --- | --- | --- | --- |
| NM C-2 | Gas Generation Measurements of Residue Materials | Perform gas generation measurements for residues at conditions representative of the transportation environment. | Richard Mason (LANL)/ Sharon Arp (DOE-AL) | On-going Complete ?? | These measurements provide a technical basis for pressure and gas composition of nuclear materials in cans for shipment and storage. |
| NM A-2 | Gas Generation and Regeneration measurements materials with actinide content greater than 20 wt.% | Perform gas generation measurements for residues at conditions representative of the transportation environment. Headspace gases, radiolysis rates, chemical rates, etc. of oxygen, hydrogen, water, and other gases are being evaluated. | Richard Mason (LANL) | On-going Complete ?? | These measurements provide a technical basis for pressure and gas composition of nuclear materials in cans for shipment and storage. |
| NM A-3, C-3 | Modeling of Gas Generation During Storage & Shipping (Pure & Impure Pu & U Materials) | Develop advanced computer models to defensibly predict gas pressure and composition in nuclear material storage and transportation containers. Validate the predictive techniques to the satisfaction of regulators for nuclear materials shipments such that gas generation measurements of individual material containers prior to shipment are no longer required. Many of the key variables necessary for the modeling effort are being derived from gas generation studies in the 94-1 lab program and related studies at SRS. | Mark Paffet (LANL), Neal Askew (SRS) | Sep-03 | Advanced modeling predictions can provide a real decision-making tool for transport and storage of nuclear materials, eliminating the need for future gas generation measurements of individual material containers prior to shipment. |
| NM A-4 | Moisture Analytical Methods (Impure Pu Oxides & Residues) | Develop techniques to measure the moisture content of stabilized Pu materials. Both sample based and bulk measurement techniques are of interest. The techniques must be applicable to the entire range of stabilized materials. | Richard Mason (LANL) / Sharon Arp (DOE-AL) | Oct-00 | These measurements will provide a basis for determining that the materials have been adequately stabilized according to the 3013 criteria (namely, <0.5 weight percent moisture). |
| NM A-6, C-6 | Pu Container Monitoring System | Develop and deploy an advanced, remote sensor technology for the monitoring of pressures and other information within sealed 3013 nuclear materials containers, at Hanford in FY 2001. | Kurt Silvers, (PNNL) / Gary Roberson (NMFA) | Sep-01 | Direct measurement of internal pressure and temperature within 3013 NM containers would provide the data needed to identify potential problem containers well before reaching unsafe conditions. Monitoring of these critical parameters can be realized by integrating smart sensors with a mechanical pressure sensor and RF tagging technology. These systems will be demonstrated and deployed in FY 2001. |
| NM A-7, C-7 | Long-term Gas Generation Surveillance for Stabilized NM & Residues | Develop/implement program for long term surveillance of materials packaged according to STD-3013-99. Identify any sub-populations that have the potential to cause problems during long-term storage. All materials packaged into 3013 cans for long-term storage must be represented in this program. The majority of the experimental work is presently being conducted within the Materials Identification and Stabilization (MIS) program in response to 94-1 concerns. | Richard Mason (LANL) / Sharon Arp (DOE-AL) | Ongoing Complete ?? | The R&D will provide a technical basis for continued assurance of containment integrity and establishes the parameters for safe long-term storage of Pu-bearing materials in 3013 containers. |
| NM B-1 | Gas Generation in U-233 Materials | During FY-01, -02, perform alpha radiolysis studies to determine and model gas generation characteristics of U-233 materials. These studies will be performed on uranium oxide compounds that contain known amounts of fluoride impurities or sorbed water. The results for this work, combined with the results already obtained from the gamma radiolysis experiments on uranium oxides, will provide a clearer picture of the radiolytic behavior of these systems, demonstrating that they do not exceed container design pressures or compromise container integrity. | Alan Icenhour (ORNL) | Dec-02 | These measurements will provide a statistical basis for bounding limits on U-233 nuclear materials in cans for shipment and help establish a technical basis for the safe storage of these oxides. |

| ID | Activity Title | Task Description | Contact | Date Complete | Deliverable |
| --- | --- | --- | --- | --- | --- |
| SNF A-1 | Dry Physically Entrained Water in SNF | Establish a technical basis for the drying techniques and final dryness levels for dry storage of formerly wet spent fuels as a means of limiting the gas generation potential of these materials in storage. | Greg Wachs (NMFA) | Sep-01 | Report identifying a technical basis for drying techniques. |
| SNF A-4 | Permeable Membrane | SNF-05 – Development effort includes Pd-Cu membrane qualification tests and ceramic membrane development. Testing indicates that Pd-Cu membrane will remove hydrogen ~5 times the rate of generation at 100 C & 50 psig. Testing is needed at lower temperatures and pressures. (Work is complete, but tests are planned for lower temperatures and pressures) | Paul Lessing / Gregg Wachs (NSNFP) | Sep-01 | Report identifying rates versus temperatures and pressures |
| SNF A-5 | Hydrogen Generation Mechanism(s) | Task Description: Refine gas generation rates (corrosion, radiolysis, radiogenic). Sources of hydrogen in SNF packages: (1) corrosion reactions (inadequate drying; sludge, crud, & corrosion products and pockets within damaged cladding); (2) radiolysis of bound water (aluminum hydroxides & uranium hydrates); (3) radiolysis of hydrocarbons (if present); and (4) ternary fission product tritium. | Gregg Wachs (NSNFP) | Sep-01 | Report detailing the sources of hydrogen in SNF packages. |
| SNF A-6 | Detect Moisture Remaining in a Dry Fuel Storage System | Develop a technique to remotely measure moisture content of spent fuel at high accuracy to bind the gas generation potential of these materials in dry storage canisters. | Phil Winston Ron Denney (NSNFP) | Sep-01 | Report detailing the statistical approach to be used. |
| SNF A-7 | Testing of hydrogen effects on stainless steel | Hydrogen has a deleterious effect on stainless steel. The hydrogen diffuses into the molecular level of the steel matrix. This causes embrittlement of the steel and would eventually lead to canister failure over time. | Gregg Wachs (NSNFP) | Done | Report identifying the rates of deterioration and suggestions of how to mitigate any issues regard these findings. |

The latest version is DOE-STD-3013-2000, Stabilization, Packaging, and Storage of Plutonium-Bearing Materials, September 2000

Summary of Plutonium Storage Package Failures” by P. Gary Eller, Richard W. Szempruch, and James W. McClard, LA-UR-99-2896, June 1999.

DOE-STD-3013-2000, Stabilization, Packaging, and Storage of Plutonium-Bearing Materials