# Cross-Cutting activities

Purpose of this Document

The primary purpose of this chapter is to introduce and describe the activities of an ITS program that are important to successful migration.  These activities should occur throughout the life-cycle of all systems and software projects, including migration projects, and are thus referred to as “cross-cutting” activities. The three cross-cutting activities for the purposes of this document are:

- Change/configuration management and documentation - Identifies the policies, procedures, and tools to effectively manage system change.  Addresses documentation of the system configuration and the changes made to it.  Documentation allows an on-going understanding of the system and the changes made so that the system can evolve in a cost effective manner.  Documentation usually serves as a means to baseline a system and all of its components each and every time a change is made.

- Risk Management – An activity that helps to identify and resolve risks that may affect project success.

- Outreach – Provides the means through which the reasons for and benefits of system migration can be expressed.  Outreach also provides the ability to solicit and incorporate stakeholder feedback into the migration process.

The discussion of each of these activities that follows is intended to raise awareness of these activities and demonstrate the need to include them in a migration project.  Each section will refer to other documents that cover the subject activity in more depth.  Readers are encouraged to go to these references for information on how to conduct each of these activities.

Change/Configuration Management and Documentation

Transportation systems are in a constant state of change.  Regardless of whether systems are repaired, updated or replaced practitioners responsible for making these changes should follow a formal change control, or configuration management process.  Without a configuration management process, transportation systems may be changed without prior written approval or consideration of the impacts associated with the change.  Changes that are less important may be implemented, absorbing resources that could be applied to the most important and valuable changes.  Without configuration management, changes may not be documented at all.  Without documentation of changes, an effort to make a needed change may start from an old version of the system or may not take into account undocumented changes.  Reworking the needed changes is likely to result, causing more time and resources to be invested.

As transportation management systems become more complex and the cost of these systems grow, more and more agencies have established formal change control procedures to better manage changes to their systems.  Configuration management controls change by defining a new baseline every time system change occurs.  In doing so, adverse effects of system change are minimized and system performance, reliability and interoperability are improved.  A configuration management program will help establish an effective and consistent approach to manage system/software change and will mitigate the potential negative impacts associated with these changes.  The purpose of configuration management is to keep the physical implementation of a product consistent with the documentation that describes how to build it and what it is supposed to do.  This is achieved by keeping the product and all its associated documentation synchronized throughout the system life cycle.  (The FHWA has two excellent documents that discuss configuration management for ITS.  They are Configuration Management for Transportation Management Systems Handbook, report number FHWA-OP-04-013, and A Guide to Configuration Management for Intelligent Transportation Systems, report number FHWA-OP-02-048.)

Configuration management helps agencies to:

- Maintain the system.

- Maintain system reliability.

- Upgrade existing systems.

- Expand existing systems.

- Share information with other systems.

Change/Configuration management provides:

- A mechanism for individuals to request a change.

- An analysis of the impact of a change.

- A formal decision regarding the change.

Change/Configuration management processes are also needed to document the following;

- The individual or parties making the change,

- A description of the change that is made and its effects,

- Reasoning as to why the change was made, and

- The date and time when the change was made.

Documentation is critical for successfully completing TMS migration projects.  Generally speaking, documentation is needed to preserve knowledge of both legacy and target systems.  For instance, documentation is needed to preserve legacy system attributes and to communicate how these attributes will evolve over time to meet future agency needs and goals.  Documentation is also needed as aspects of the target system change over time.  In these roles, documentation helps maintain an up-to-date understanding of the system or project.  Failure to document changes may result in practitioners having to back track to baseline the system so future changes or improvements can be made.  In those cases where no documentation has been preserved, baseline systems cannot be reproduced at all.

At various points throughout an ITS migration project, aspects pertaining to the project should be documented and preserved in a formal change/ configuration management process.

Risk Management

All ITS projects, whether they are new implementations or migrations, should include a risk management process.  The process is easily scalable to the needs of each project, so it need not be onerous.  The essence of risk management can be boiled down to answering the following four questions:

- What can go wrong on this project?

- What is the likelihood of each of these risks?

- If realized, how severe would the effect of these risks be?

- What can I do to avoid, or reduce the impact of, key risks?

Risks are typically characterized as negative impacts to cost, schedule, and scope.

Cost

For a given project, the cost-based risks include those that cause the project to exceed the programmed budget and those that may result in losing project funding.  In addition, on a program-wide basis, the risk of unmanageable ongoing operations and maintenance costs needs to be assessed.  The business planning element of a migration plan should include mechanisms to minimize operations and maintenance costs.  Consideration should be given to costs of technology obsolescence, technology age, market conditions, staff skills, and other factors.

Schedule

Risks to an individual project that affect the ability to meet important schedule needs should also be identified.  Additionally, the impact of not meeting schedule, and appropriate contingency plans, should be included in project risk assessments.

Scope

The scope for an ITS project not only includes ensuring that a particular set of items is installed at locations noted in contract documents, but has a particular focus on functionality.  What are the risks that may cause a device or system to fall short of functionality goals? With respect to migration, an additional question to ask is question “What are the risks to maintaining system operation?”.

Risk Management Process

Time and effort are needed to identify and manage risks.  However, by proactively managing risks, potential problems and the costs associated with fixing them can be mitigated or avoided all together.  The act of managing risks is more easily accomplished if practitioners follow a commonly accepted process.  In March 2000, the American Association of State Highway and Transportation Officials (AASHTO) released a report, titled “ITS Software: Effective Acquisition Practices”.3  In this report a basic process for managing risks is defined.  This process is illustrated in Figure 8-1 and described in greater detail in the following sections.

Figure 8-1: Risk Management Process3

Risk Identification

The risk identification process typically is accomplished in a working meeting with the contractor and agency staff.  Useful tools to help facilitate risk identification include lists of key risks identified in previous projects, or in the literature. If no prior experience exists, the risks noted in Table 8-1 and Table 8-2, can be used as a starting point.  Table 8-1 is from Steve McConnell’s Rapid Development, which includes good discussion of risk management for software development projects.  Most of what McConnell includes for risk management can be applied to any technology project, including ITS projects.  Table 8-2 is from AASHTO’s ITS Software: Effective Acquisition Practices.”

Table 8-1: Example Project Risks

| Risk Category | Example Risks |
| --- | --- |
| Schedule Creation | Schedule is optimistic “best case”, rather then realistic “expected case”. Schedule omits necessary tasks. |
| Organization and Management | Project Languishes too long on the fuzzy front-end. Non-technical third party tasks are longer than expected. |
| End Users | End users insist on new requirements. End user finds product to be unacceptable, requiring redesign and rework. End user input is not solicited, so product ultimately fails to meet user expectations. |
| Customer | Customer insists on new requirements. Customer will not participate in reviews for plans, prototypes, and specifications, or is incapable of doing so – resulting is unstable requirements and time consuming changes. Customer-furnished components are a poor match for the product under development, resulting in extra design and integration work. |
| Contractors | Contractor does not deliver component when promised. Contractor delivers components of unacceptably low quality. |
| Requirements | Requirements have been baselined, but continue to change. Requirements are poorly defined, and further definition expands the scope of the project. |
| Product | Development of the wrong user interface requires additional redesign and rework. Operation in an unfamiliar or unproven software environment causes unforeseen problems. |
| External Environment | Product depends on governmental regulations, which change unexpectedly. Product depends on draft technical standards, which change unexpectedly. |
| Personnel | Personnel need extra time to learn unfamiliar software tools or environment. The personnel most qualified to work on the project are not available. Key personnel are available only part of the time. |
| Design and Implementation | Overly simple design fails to address major issues and leads to redesign and re-implementation. Schedule savings from productivity enhancing tools are overestimated. |
| Process | Amount of paperwork results in slower progress than expected. Inaccurate quality tracking results in not knowing about quality problems that affect the schedule until late in the process. Half-hearted risk management fails to detect major project risks. |

Table 8-2: Example Project Risk3

| Risk Category | Example Risks |
| --- | --- |
| Institutional | Departments within the agency do not work well together. The agency staff are inexperienced in ITS projects. The contractor staff are inexperienced in ITS projects. The decision making process at the public agency is slow. Contractor project management is poor. Loss/change over of key staff (agency or contractor) during the project development life cycle. |
| Technical | Attempting to implement a system that has never been developed before, or modifying a system to add never-before-developed functionality. Legacy systems are involved. “Closed” systems (proprietary) must be integrated. Inability to beta-test the system using “live” or real data. Poor functional requirements. |
| External Risks | Foreign market conditions change component costs or delivery schedules. Technology changes during development, affecting the system design. |

Risk identification is not a one-time activity.  As part of overall risk management, once a list is developed, it must be revisited to determine if new risks have been identified, and if any risks already identified have disappeared. Some projects merit reviewing the risk list as part of regular progress meetings. Others require review at key milestones.

Risk Analysis

Risk analysis involves identifying the risks that are most critical. This helps focus risk management efforts, and ensures that resources are used to manage only the worst risks.

Once risks are identified, they need to be analyzed for potential impact – the extent of damage that would occur if the risk were realized. The impact should relate to cost, schedule, and scope (functionality).  Risk analysis should also include assessments of risk to the agencies standing in the view of key decision-makers, agency leadership, and the general public, if appropriate. Risks can then be ranked with the most severe risks at the top of the list.

The analysis should also address the likelihood that a risk may occur.  A matrix can be developed with impact and likelihood on the axes, as shown in Table 8-3.

Table 8-3: Example Project Risk6

|  |  | Likelihood of Occurrence |
| --- | --- | --- |
|  |  | High | Medium | Low |
| Impact | High | A | B | C |
|  | Medium | D | E | F |
|  | Low | G | H | I |

The focus of risk planning and mitigation can then be placed on the risks in cells A, B, and D if the list does not become too long.  Many risk management experts also suggest that risks in cell C should not be ignored.  This is because participants in risk planning often are not able to accurately assess the likelihood of risk occurrence as well as risk impact.  Murphy’s Law applies, in that the risks that are not expected are often the ones that do occur.  In addition, individuals often mentally prepare for risks with high likelihood, while ignoring the risks with the lowest likelihood.

Risk Planning

Risk Planning involves identifying early indicators that the risk may occur, and identifying potential avoidance and/or mitigation strategies.  For example, an early indicator that key staff may be contemplating leaving could be high overall staff turnover.  Another indicator could be that competing industries (e.g., the dot.com industry) are growing and recruiting staff.  A mitigation strategy could include contract terms that ask the prime to contract with key staff who have departed to bring the project to conclusion or to a key progress milestone.  This action could only be implemented if the key staff agree to such a contract and there was a mechanism to compensate the contractor for any added costs that might occur because of this additional subcontracting effort.

Risk Resolution

Identifying, analyzing and planning for risks alone does not constitute an effective risk management process.  Identified risks may be avoided on a project-by-project basis; however, if risks are left unresolved, they may resurface, and may affect not only a current project but potentially a future project.  Therefore, the factors that cause a risk must be resolved so that risks do not reappear and inflict additional damage.  For example, a key risk that was identified by ITS practitioners is that staff lack key ITS skills.  A particular project may be successful despite the lack of skills, but the ITS Program should still address the staff skills issue to avoid future problems.

Risk Monitoring

Risks identified through the risk identification process should be continually monitored to determine the impact(s), if any, risks have had on the project, and how well the agency has mitigated the effects of these risks.  Practitioners should develop a means to track and prioritize risks as they are identified.  Depending on the needs of the practitioner, this may be as simple as listing risks on a sheet of paper and crossing them out when either they are addressed or as other “higher” risks are identified.

Outreach

ITS Program outreach activities include both delivering and gathering information from three key stakeholder groups:

- Intra-agency stakeholders.

- Inter-agency stakeholders.

- General public and key decision makers.

The key goals of ITS outreach programs are to:

- Gather support for ITS program activities and funding.

- Develop projects that meet stakeholder needs.

- Ensure that implemented ITS meets goals and objectives.

- Develop consensus for multi-agency ITS efforts.

Outreach efforts for an ITS program should be on-going, whether or not anything “new” is happening within the program.  Simply connecting with key stakeholders to let them know how the ITS systems are performing and delivering benefits is important.  Agency staff and key decision-makers are always changing and having a consistent means to deliver a consistent message is important to ensure continuity despite changes in personnel.  ITS program outreach can be integrated with project-specific outreach efforts such as those involved in developing regional ITS architectures, business plans, and project development activities.  Regular reports can be provided on a monthly or annual basis and disseminated to all of the stakeholder groups.  (More information on outreach efforts can be found in Building Quality Intelligent Transportation Systems Through Systems Engineering report number FHWA-OP-02-046 and Migration of Systems to Open Architectures from the Software Productivity Consortium.)

Intra- and inter-agency support and understanding of ITS activities, is critical to define migration efforts, and to ensure that key stakeholders understand the need for investment in migration.  Additional outreach is required when developing a specific migration project design, to develop the functional and technical requirements.

Intra- and inter-agency outreach provides a medium through which the reasons for, and benefits of, system migration can be expressed.  This helps to smooth the implementation of strategies by promoting inter-agency cooperation while at the same time mitigating any adverse reaction.  Outreach should target upper management, system users, and those individuals from other agencies that may be affected by migration activities.  Outreach should focus on obtaining support and input from these groups well in advance of when transportation systems are proposed to be migrated.  At a minimum, support and input from these three groups are needed to successfully determine what systems will be migrated, how migration will occur and what impacts, if any, may result.  Outreach directed toward the aforementioned groups should be tailored to the specific needs and concerns of each group.  Likewise, the reasons for and benefits of migration need to be expressed in terms each group can easily understand.

Intra-Agency Outreach

Practitioners should actively engage personnel at various levels within their organization during the ITS Business Planning stage, and at the project implementation stage.  Once internal consensus on a migration program is achieved, practitioners should extend outreach efforts to other individuals inside their respective organization to convey the reasons for, and the benefits of, migration.  In-reach efforts will not only ensure common understanding between personnel, but also provides a medium through which knowledge can be promoted and disseminated to individuals of outside agencies.

Upper Management and Support

System migration programs require approval and support from upper management and other department managers before they can be seriously considered.  Written approval should be obtained from upper management to demonstrate that upper management is committed to the migration effort and that the necessary resources will be available to ensure that the newly implemented target system can be integrated into the everyday operations of the agency.  Support from upper management is needed to secure the funding needed to complete migration activities and to support staff when the target system is rolled-out.  Input from managers of other departments is needed to verify the impact of migration on their current operations and to ensure that the target system can be effectively integrated with other systems used in the day-to-day operation of the agency.  Managers of other departments may also identify implementation challenges associated with the migration effort, which can be resolved before target systems are rolled-out.

User Involvement and Assistance

Intra-agency outreach should target legacy and target users to incorporate the needs of these individuals and to acquire input that will benefit the migration effort.  System users may provide valuable information that may be used to plan the ITS migration effort.  For instance, user input may help those responsible for migrating systems to more easily identify risks.  Such risks may only be identified with the knowledge of those who use the system.

Migration Management Team Formation

Practitioners charged with the responsibility of transportation system migration may wish to use outreach as a spring board for forming teams to conduct migration activities.

Inter-Agency Outreach

Practitioners responsible for migrating systems should seek to inform other agencies that may be potentially affected by migration activities at various points during the migration effort to keep these groups abreast of project progress and to solicit information when needed to support subsequent project activities.  At the onset of a migration project practitioners should engage in activities that expand the visibility of migration activities.  Practitioners should clearly explain the benefit of, and reasons for systems migration.  As the scope of the migration becomes clearer, practitioners should provide opportunities for stakeholders to review and comment on various activities that dictate how the legacy system will be migrated.

Public and Elected Officials

Intra- and inter-agency outreach is vital for planning and implementing ITS migration projects as previously stated.  However, outreach should extend beyond these groups to elected officials and, if the effects will be visible, to the general public.  Outreach efforts directed at these groups should convey the benefits of migration activities in terms the public can understand, which in turn helps to build consensus and support for not only migration related projects and activities but also every project implemented by the agency.  Outreach efforts directed at the general public and elected officials should seek to inform these groups of the following issues.

- The need for migrating the system,

- How migration projects will be funded,

- When migration activities will take place and timeframes for when benefits will be realized, and

- How projects will be developed, including any impacts that may be negatively perceived by the public.

# Endnotes

Configuration Management for Transportation Management Systems Handbook.  Report No. FHWA-OP-04-013.  Federal Highway Administration Operations Office of Transportation Management.  September 2003.  Available at: http://ops.fhwa.dot.gov/freewaymgmt/cm/docs/handbook/index.htm

A Guide to Configuration Management for Intelligent Transportation Systems.  Report No. FHWA-OP-02-048.  U.S. Department of Transportation Joint Program Office.  April 2002.  Available at: http://www.itsdocs.fhwa.dot.gov/JPODOCS/REPTS_TE/13622.html

ITS Software: Effective Acquisition Practices.  American Association of State Highway and Transportation Officials.  March 2000.

David Robinson.  Embracing Change in Real World ITS Deployments.  Open Roads Consulting, Inc.  Available at: http://tmcpfs.ops.fhwa.dot.gov/cfprojects/uploaded_files/EmbracingChange.pdf

Steve McConnell.  Rapid Development, Microsoft Press, 1996.

Building Quality Intelligent Transportation Systems Through Systems Engineering.  Report No. FHWA-OP-02-046.  U.S. Department of Transportation.  April 2002.

Migration of Systems to Open Architectures.  Software Productivity Consortium.  Available at: www.software.org/sysmigweb  Accessed January 15, 2004.