Section J, Attachment A

RAPID SPACECRAFT PROCUREMENT

STATEMENT OF WORK

June 6, 1997

1. Introduction............................................

2. Scope...................................................

3. Applicable and Reference Documentation..................

4. Work to be Performed by the Contractor..................

4.1 System Implementation

4.1.1 Core System(s)

4.1.2 Core System Option(s)

4.1.3 Mission-Specific Modifications

4.2 Non-Standard Services

4.2.1 Non-Mission-Specific Non-Standard Services

4.2.2 Mission Specific Non-Standard Services

4.3 Standard Services

4.3.1 Program Management

4.3.1.1 Quality Management System

4.3.1.1.1 Quality Assurance Management Requirements

4.3.1.1.2 Pre-Launch Reports

4.3.1.1.3 Post Launch Reports

4.3.1.2 Documentation

4.3.1.3 Reviews

4.3.1.3.1 Mission Design Review Requirements

4.3.1.3.2 Instrument Integration Readiness Review

4.3.1.3.3 Pre-Environmental Review

4.3.1.3.4 Pre-Ship Review

4.3.1.3.5 Program Status Reviews

4.3.1.4 Audits

4.3.1.5 Government Insight

4.3.2 Systems Engineering

4.3.2.1 Requirements Analyses and Allocations

4.3.2.2 Interface Definition, Verification and Control

4.3.2.3 Observatory/Launch Vehicle Interface

4.3.2.4 Design and Performance Verification Analyses

4.3.3 Spacecraft Bus

4.3.4 Implementation

4.3.4.1 Spacecraft Bus Integration and Test (I&T)

4.3.4.2 Observatory Integration and Test (I&T)

4.3.4.3 Spacecraft Bus/Observatory Storage

4.3.4.4 Spacecraft Bus, Observatory and Ground Support Equipment Shipment

4.3.5 Launch & Operations

4.3.5.1 Launch Support

4.3.5.2 Flight Operations Interfaces and Support

4.3.5.2.1 Ground System Interface Definition

4.3.5.2.2 Ground System Training and Flight Operations Support

4.3.5.3 On-Orbit Performance Verification

4.3.5.4 Support to On-Orbit Operations

4.3.6 Flight Software

4.3.6.1 Software Maintenance

4.3.6.2 Software Documentation	15

# 1.	Introduction

This statement of work (SOW) defines the contractor’s efforts required to provide a spacecraft bus and associated services that meet the needs of the National Aeronautics and Space Administration’s (NASA) flight science and technology missions.  Other United States Government Departments and Agencies may also utilize this contract.  Particular mission requirements and tailoring of this SOW shall be as defined in the delivery order issued for each specific mission.

# 2.	Scope

The scope of the work encompasses all necessary effort from receipt of an Indefinite Delivery Indefinite Quantity (IDIQ) contract through the delivery and on-orbit check out of specific missions.  A mission-specific delivery order will be issued by the Government in accordance with the ordering procedures contained in the contract schedule.  Delivery orders for non-standard services may be issued by the Government.

# 3.	Applicable and Reference Documentation

Reserved for mission specific use.

# 4.	Work to be Performed by the Contractor

## 4.1	System Implementation

For this contract, the effort to produce a specified core system, the selected options, and the mission-unique modifications required in the delivery order in accordance with the mission implementation specification, results in a product called the “Spacecraft Bus” or  “Spacecraft”.  The effort to integrate a payload (or instrument), and qualify the combined payload and spacecraft bus in accordance with the mission implementation specification, results in a system called an “Observatory”.

An order for a specific core system placed via delivery order may be a combination of a core system and options as contained in the contract schedule, as well as mission-specific modifications to the applicable core system and options.  The complete set of technical requirements as contained in the delivery order shall be applicable to the core system, the options and the mission-specific modifications.

### 4.1.1	Core System(s)

The contractor shall develop, implement, test, and qualify a spacecraft bus ready for payload integration, called the “core system.” , integrate the payload with the core system, qualify the resulting observatory, and provide launch and operations support, as well as satisfy all requirements of section 4.3 of the sow.  The core system shall conform with the applicable performance specification and mission implementation specification provided by the contractor with the proposal.

### 4.1.2	Core System Option(s)

The contractor shall develop, implement, test, and qualify performance option(s) to the core system such that the combined options and core system are ready for payload integration, and satisfy all of the requirements of section 4.3 of this SOW.  The option(s) to the core system shall conform with the applicable performance specification and mission implementation specification.

### 4.1.3	Mission-Specific Modifications

In order to meet the unique requirements of a specific mission a contractor may modify their core systems and options.  These modifications are to be implemented as necessary for the adaptation of the core system, options and implementation effort under the contract to meet the delivery order requirements.  The extent of the modifications may include, but are not limited to, the addition of performance parameters; changes to any performance parameter; changes to mission implementation specifications; the addition of new specifications, requirements, analyses, reports, hardware, software or support; adaptation of baseline hardware or software configurations; changes to baseline schedules, reviews, funding profiles, and milestones; and the modification of contract deliverable item lists, contents or formats.  It is expected that in some cases the extent of modifications required to meet the specific mission requirements may be extensive.

## 4.2	Non-Standard Services

The contractor shall provide all personnel, facilities, materials, and other necessary resources for the performance of non-standard services as ordered under this contract.

### 4.2.1	Non-Mission-Specific Non-Standard Services

The Government may, from time to time within the period of performance of this contract, issue non-standard service delivery orders.  Delivery orders issued under this section shall not be specific to any delivery order previously issued, but may address issues associated with possible future missions.

These delivery orders may be issued for the following types of efforts:

a.  Analyses related to a particular core system, which includes, but is not limited to, performance capability analyses, modeling parameters, potential core system modification analyses, launch vehicle compatibility analyses, instrument interface analyses, integration analyses, launch support and on-orbit check out analyses.

b.  Tasks, including but not limited to, core system design envelope enhancement, core system modifications, verification testing, core system technology update feasibility,  process definitions, reviews, and updates.

### 4.2.2	Mission Specific Non-Standard Services

The purpose of non-standard services ordered under this section of the statement of work shall be directly related to a specific mission under delivery order.

Non-standard services ordered may be for the following types of efforts:  Special studies, analysis, mission specific hardware fabrication and/or core system modification in support of a specific mission delivery order.

## 4.3	Standard Services

This section describes the effort required of the contractor upon receipt of a delivery order.  At a minimum the contractor shall provide all facilities, services, and personnel necessary for the successful and on-time implementation of all of the efforts necessary to meet the mission-specific delivery order requirements.

### 4.3.1	Program Management

The contractor shall provide a Program Management function that is responsible for the control of the specific mission effort.  The contractor’s Program Management function shall provide to the Government reporting and real-time insight into program status, as well as, technical and programmatic performance of all of the contractor’s responsibilities and activities performed under the delivery order.

The contractor shall perform various design, study, trade-off and analysis tasks relating to the development, implementation, characterization and operation of the specific mission as necessary.

The contractor shall be responsible for the submission of all change order proposals as required by this contract.

The items and services acquired under this contract are required to include accurate processing of the date and date-related data (including but not limited to calculating, comparing, and sequencing) by all hardware and software products delivered under this contract, individually and in combination, upon installation.  This also includes the manipulation of data with dates prior to, through, and beyond January 1, 2000, and shall be transparent to the user.  Hardware and software products provided under this contract shall, individually, and in combination, successfully transition into the Year 2000 with the correct system data, without human intervention, including leap year calculations.  Such products shall also provide correct results when moving forward or backward in time across the Year 2000 or subsequent years.

All systems delivered under this contract shall be Year 2000 compliant.

The contractor shall implement appropriate management systems which prevent the improper dissemination of Principal Investigator competition sensitive information.

#### 4.3.1.1	Quality Management System

The contractor will maintain and adhere to a Quality Management System in accordance with ANSI/ASQC Q9001-1994.

The Government reserves the right to impose other quality standards as mission-specific requirements to meet the needs of a specific mission.  These unique requirements shall be documented in the mission-specific delivery order.

ANSI/ASQC Q9001-1994, Paragraph 4.13.2 shall be augmented to include the following subparagraphs.

##### 4.3.1.1.1	Quality Assurance Management Requirements

Once the mission specific core system begins comprehensive performance test in demonstration of readiness for mission payload integration, a system of written problem/failure reports (PFR’s) will be used through launch.  The PFR’s will be written for any departure from design, performance, testing, or handling requirements which affect the function of the flight system, or ground support system which interfaces with the flight system, or that could compromise mission objectives.

##### 4.3.1.1.2	Pre-Launch Reports

Failure reports are to be reported in accordance with the CDRL.  Contractor format, generation, review, disposition and/or approval of failure reports will be described in applicable procedure(s) included or referenced in the contractor’s Quality Manual.

##### 4.3.1.1.3	Post Launch Reports

Following launch, flight hardware and software anomalies, problems and/or failures will be reported using the Spacecraft Orbital Anomaly Report (SOAR) in accordance with GMI 5310.1B, GSFC Problem/Failure Anomaly Reporting.

#### 4.3.1.2	Documentation

The contractor shall develop, produce, deliver, and maintain all documentation required by the Contract Data Requirements List (CDRL) and necessary to implement the mission-specific delivery order.  All efforts including the performance of tests and analyses not otherwise explicitly stated in other parts of this SOW, but needed to produce the required documentation, shall be performed and documented by the contractor.  All documentation, data and analyses generated for, or applicable to, the effort, whether formal or informal, shall be made available to the Government upon request at the contractor’s facility.

#### 4.3.1.3	Reviews

The contractor shall conduct usual and customary internal  reviews and provide for timely reporting of program status to the Government with discussions on problem areas, and a timely transfer of technical information to the Government, of major program milestones.  The contractor shall provide technical and management support to certify spacecraft bus or observatory readiness at the following program reviews:

| Review | # of Days | Personnel Required |
| --- | --- | --- |
| Mission Design Review (MDR) | 3 | Operation, Systems & Subsystems Design |
| Integration Readiness Review (IRR) | 2 | Systems, Quality & Test |
| Mission Operations Review (MOR) | 2 | Systems & Operations |
| Pre-Environmental Review (PER) | 2 | Systems, Quality & Test |
| Pre-Ship Review (PSR) | 3 | Systems, Quality & Test |
| Flight Operations Review (FOR) | 2 | Systems & Operations |
| Launch Readiness Review (LRR) | 1 | Systems, Quality & Test |

The MOR and FOR shall be held at NASA’s Goddard Space Flight Center and the LRR shall be held at the launch site, all other reviews shall be held at the contractor’s location.  The contractor shall ensure that appropriate personnel attend each review.

The baseline dates for each review shall be defined in Section J, attachment B of the contract and may be modified by the delivery order to meet unique mission requirements.

##### 4.3.1.3.1	Mission Design Review Requirements

The contractor shall host and provide data for the Mission Design Review where mission requirements and subsystem requirements flow-down will be confirmed, based on the mini-proposal design offered.  Interface documents will have been prepared and reviewed for understanding and ready for signature.  Mission-specific core system modifications will be confirmed and understood sufficiently to proceed with manufacture.

The contractor shall provide, at a minimum, the following data and information.

System Level:

- Mission Design overview showing a mature understanding of the mission objectives and the approaches that will be used to carry out the mission together with definition of roles and responsibilities.

- Mission performance requirements allocation and subsystem flow-down

- Resource allocations and margins (telemetry, commands, power, weight, data storage, processor capability, etc.)

- ICDs (instrument, ground system) ready for signature

- Performance verification approach and rationale

- Spacecraft bus integration and test sequence rationale

- Observatory integration and test sequence and rationale

- QA program applications, status, issues

- Orbit, orbit maintenance, and flight dynamics analysis

- Flight operations overview and status

- Mission ground support equipment (GSE)

- Approach for the next milestone review

- I&T software requirements, description, status, verification

- Flight software requirements, description, development and verification plan, status

Subsystem level (including flight software)

- Requirements flow-down specifications to each subsystem

- Performance verification and validation

- Design details of mission-specific elements

- GSE

Specific Analysis and Margins

- Stress and dynamics

- Loads determination

- Communication links

- Thermal flight predictions

- Power balance (end-of-life and battery DOD)

- Worse case

- Data flow, Storage and loading

- Pointing budgets including attitude control simulation results

- Flight dynamics, orbit insertion, maintenance, disposal

- Radiation, EMC, ESD, magnetics

- Failure mode and effects update

##### 4.3.1.3.2	Instrument Integration Readiness Review

The contractor shall present at the IIRR:

- The results of the latest spacecraft bus Comprehensive Performance Test

- A resolution plan for all failures, anomalies, and malfunctions encountered during system testing

- Any remaining open integration issues and their proposed resolution

- The readiness to perform Instrument integration (e.g. staffing, facilities, GSE, procedures, resources, etc.)

- Plans to proceed to Pre-Environmental Review (tests, activities, facilities, resources, schedule, flow)

- I&T software readiness and verification status

- Flight software development and verification status

##### 4.3.1.3.3	Pre-Environmental Review

The contractor shall present at the PER:

- The results of Instrument Integration and the status of the Observatory

- A resolution plan for all failures, anomalies, and malfunctions encountered during Instrument integration

- Review of all environmental test plans and procedures

- Present detailed thermal vacuum and thermal balance test plans showing the observatory in the chamber, the hot and cold plates and shrouds, optical or thermal targets, RF coupling, star camera and sun sensor stimulators, QCMs, cold finger, planned test profile, cleaning and outgassing plan.

- The structural qualification/acceptance plan, showing the final modal analyses and coupled loads analyses results

- Define the predicted test limits for the components of the core system and instrument payload for:

-Vibration

-Thermal-Vacuum, Balance

- Justify that the planned test environments adequately demonstrate the Observatory Performance requirements without presenting a hazard, and without degrading Observatory performance and lifetime

- Present the plans to proceed to PSR (e.g. tests, activities, facilities, staffing, resources, schedule, flow)

##### 4.3.1.3.4	Pre-Ship Review

The contractor shall present at the PSR:

- Results of all the environmental tests and the latest Observatory Comprehensive Performance Test

- A resolution plan for all failures, anomalies, and malfunctions remaining open from the implementation

- Flight software verification status

- Any remaining open issues under the contract and their proposed resolution

- Shipping documentation status (e.g. shipping lists, manifests, containers, handling, transport, etc.)

- Observatory documentation status (e.g. final configuration lists, trend data, test reports, mass properties, system safety plan, life-limited items, equipment logs, cleanliness certification, and any other necessary documents)

- Receiving point plans - arrival time and place, storage, handling, points-of-contact, mechanical and electrical test plans and procedures

- An overview of the launch support plans (e.g. activities, facilities, staffing, resources, schedule, flow)

##### 4.3.1.3.5	Program Status Reviews

Program Status Reviews shall be conducted bi-monthly at the contractor’s facility.  The contractor shall present the following information at the Program Status Reviews:

- Status of work being performed including appropriate metrics.

- Milestone Monitoring - The contractor shall report on the status of progress made toward accomplishing each of his major milestones.  Each report shall include a listing of major accomplishments and a discussion of any problems associated with each milestone as well as their resolution.

- Status of technical issues

- Changes to design parameters such as weight, power profile, communications, system performance, etc.

- Descriptions and status of technical problems and the resolutions.

- Subcontract technical performance

- Performance assurance status including non-conformance and failure report dispositions.

#### 4.3.1.4	Audits

The contractor shall support both formal and informal Government audits, as ordererd through non-standard services, of the contractor’s activities, processes, products, documentation and data in order to provide assurance to the Government that the program is being implemented according to all requirements and specifications.

#### 4.3.1.5	Government Insight

All contractor and subcontractor internal data, reviews, audits, meetings and other activities pertinent to the execution of a delivery order shall be open to Government attendance.  The contractor shall provide the Government with reasonable and timely notification, to facilitate Government attendance.  Government support contractors may also attend these reviews, audits, and meetings at the Government’s discretion.

### 4.3.2	Systems Engineering

The contractor shall perform the necessary systems engineering required to ensure that the core system, options, and modifications meet all of the performance, interface, and implementation requirements of the mission-specific delivery order.  The systems engineering effort shall comprise the analyses of technical requirements, allocation of derived system, core system, ground terminal and lower level requirements, definition and maintenance of interfaces, and verification of all defined and derived requirements.

#### 4.3.2.1	Requirements Analyses and Allocations

The contractor shall conduct complete analyses of the mission requirements which fully establish, define, maintain and control allocations.  An appropriately updated index of analyses and allocations shall be maintained by the contractor.  The results of all analyses shall be made available by the contractor for Government review at each subsequent major program review.

#### 4.3.2.2	Interface Definition, Verification and Control

Using the results of the analyses and allocations of technical parameters performed under the efforts described in Section 4.3.2.1, the contractor shall specify all interfaces not explicitly defined by Government specifications.  These interfaces shall then be defined, documented, verified and controlled for the duration of the delivery order, by the contractor.

#### 4.3.2.3	Observatory/Launch Vehicle Interface

The contractor shall define and maintain all design interface information between the observatory and the Government provided launch vehicle.  The contractor shall participate in the preparation and maintenance of the Observatory-to-launch vehicle Interface Control Documents (ICD).   The responsibility for writing, maintaining, and gaining approval of the ICD shall reside with the Government.

A flight ready mechanical fit check and an electrical interface verification test of the spacecraft bus (or observatory) to the launch vehicle interface shall be performed by the contractor prior to the final flight mate to the launch vehicle interfaces.  The mechanical fit check and electrical interface verification test shall be performed at the contractor’s location prior to shipment to the launch site.  The Government shall supply a test payload attach fitting which simulates the launch vehicle side of the interface.

The contractor shall provide the analytical models and shall perform all analyses and tests required to ensure proper electrical, mechanical, thermal, and operational compatibility between the observatory and the Government provided launch vehicle and launch vehicle environments.  The contractor shall develop, maintain and provide all technical and programmatic documentation required to ensure a successful launch activity.  This includes all observatory level safety-related documentation as required by the launch site and launch range organizations.

#### 4.3.2.4	Design and Performance Verification Analyses

The contractor shall perform and document all analyses of the data and information from the design, qualification testing, acceptance testing, compatibility testing and on-orbit testing of the contractor’s hardware and software which are required to ensure that the program will meet its specifications and objectives.

### 4.3.3	Spacecraft Bus

The contractor shall produce and verify a spacecraft bus which meets all of the requirements, specifications, and interfaces in accordance with the mission-specific delivery order.  The design shall be verified by a combination of analyses and test on engineering models, prototype or proto-flight hardware and software.

Prior to instrument integration the spacecraft bus shall under go a comprehensive performance test to demonstrate readiness for observatory level integration.

The contractor shall provide a spacecraft bus interface simulator for use by the mission for interface verification.  This item need not be mission-specific but may be adaptable by the contractor to meet the requirements of the mission-specific delivery order.

### 4.3.4	Implementation

#### 4.3.4.1	Spacecraft Bus Integration and Test (I&T)

The contractor shall integrate and test all spacecraft bus and payload interface hardware and software.  The spacecraft bus shall be tested with calibrated and maintained Ground Support Equipment and shall be compatibility tested with the ground control system as defined in the delivery order.

#### 4.3.4.2	Observatory Integration and Test (I&T)

To the extent defined in the mission specific delivery order, the contractor shall plan and conduct integration of the spacecraft bus and payload to form an observatory.  The contractor shall then plan, manage and execute observatory level interface verification, system test, environmental test program, and support mission payload specific tests as defined in the delivery order.

#### 4.3.4.3	Spacecraft Bus/Observatory Storage

When required by the delivery order, the contractor shall provide appropriate ground storage for the spacecraft bus or observatory prior to launch.  This activity shall encompass storage, storage maintenance, and post-storage activities necessary to bring the spacecraft bus to integration readiness or observatory to launch status.  This shall include, but not be limited to, the storage and maintenance of spare parts as well as ground support equipment.

#### 4.3.4.3	Spacecraft Bus, Observatory and Ground Support Equipment Shipment

The contractor shall be responsible for the shipment of the spacecraft bus and observatory between the places of manufacture, and integration and test, and storage and launch in appropriate shipment containers.  The contractor shall provide for the shipment of necessary ground support equipment required to support the spacecraft bus/observatory during each phase of test, integration and launch preparation.

### 4.3.5	Launch & Operations

#### 4.3.5.1	Launch Support

The contractor shall provide launch support of the completed observatory.  This shall include launch vehicle interface definition, design verification and management, observatory launch preparation and launch support.  The Government will make the final go/no-go decision for launch.  The launch support activity shall include, but not necessarily be limited to, the following efforts:

- Launch Operations Planning - This effort requires the development and maintenance of interfaces with all entities that play a role in observatory launch.  This involves coordinating, planning and performing all tasks which are necessary to implement a successful launch.  The contractor shall provide technical and management support of meetings required to define launch related interfaces.

- Launch Simulations - This effort encompasses the conduct, analyses and evaluation of pre-launch training and simulations of the launch (through orbit insertion).  Two training simulations plus one launch rehearsal are to be conducted.

- Pre-launch Integration and Test - The contractor shall perform all tasks necessary to integrate, test and prepare the observatory for launch at the launch site.

- Launch Operations - The contractor shall provide all required integration, safety, and engineering support to process the observatory through the ground processing facilities, launch facility and the launch vehicle.  In addition, this effort shall encompass the contractor’s efforts necessary to support the actual launch, post-launch orbit insertion, perform observatory initialization, deployments and preparation for on-orbit performance verification testing.  This activity will be under Government direction from launch through separation of the observatory from the launch vehicle.

#### 4.3.5.2	Flight Operations Interfaces and Support

##### 4.3.5.2.1	Ground System Interface Definition

The contractor shall provide observatory  compatibility with at least one of NASA’s available command and control systems (e.g. Space Network/TDRSS, Deep Space Network, Ground Stations, or EOS Ground Network), unless otherwise specified in the mission specific delivery order.

The contractor shall work closely with NASA mission engineers to perform communications, command, control and operational requirements trade analyses.

The contractor shall provide all necessary interfaces to the ground command, control and data system defined in the documents describing the observatory requirements contained in the delivery order.  This is to include all necessary system documentation, interface control documents, databases and test efforts.

##### 4.3.5.2.2	Ground System Training and Flight Operations Support

The contractor shall provide support to the mission operations team for training and on-orbit initialization, checkout, performance verification and anomaly resolution.

The contractor shall provide descriptions of flight software functionality and spacecraft bus operation adequate to be used by the flight operations team for flight operations.

The contractor shall provide a means to integrate Integration & Test activities with the mission operations teams.

#### 4.3.5.3	On-Orbit Performance Verification

The contractor shall perform an on-orbit performance verification program which will confirm that the spacecraft bus performance is in accordance with the mission requirements, specifications, and interfaces.  As a minimum this shall include:

- Spacecraft Bus On-Orbit Check-Out - This effort shall be performed by the contractor to verify the post-launch performance and state-of-health of the spacecraft bus.  All systems must be verified for proper function and performance.

- Spacecraft Bus/Ground Control and Data Systems Interface Verification - This effort shall be performed by the contractor after the spacecraft bus on-orbit performance and state-of-health have been confirmed.  The purpose of this test is to verify proper operations of the spacecraft bus to ground system interfaces and to provide the necessary calibrations.

- 30-Day On-Orbit Performance Report - The contractor shall prepare a brief report which summarizes the on-orbit performance  of the spacecraft bus compared to its predicted performance for the mission after launch.  Each subsystem is to be addressed and the performance of launch and flight operations crews are to be included.  All pertinent issues affecting mission success shall be addressed.  The extent of performance explanation required depends on the seriousness of the impacts that any problems identified may have on mission success.   This report summarizes the spacecraft bus performance on-orbit after launch and check-out to determine initial mission success and completion payment milestone status.

#### 4.3.5.4	Support to On-Orbit Operations

The contractor shall provide support to resolve all on-orbit observatory anomalies.  This responsibility shall remain in place until the end of the baseline mission life as defined in the delivery order.

### 4.3.6	Flight Software

#### 4.3.6.1	Software Maintenance

The contractor shall maintain the flight software along with the environments and emulators necessary to develop and verify these systems until the end of the program’s baseline mission life as defined in the delivery order.  The delivery order may modify this requirement for transfer of this responsibility to an alternate organization, in which case the contractor shall support the transition with the necessary ground based hardware, software, documentation and labor as required in the delivery order.  The contractor shall provide a description of how ground and flight operational software will be maintained, supported, verified, and managed to the end of the mission, and also describe the use of  personnel, what role others play, how others are to be trained and by whom.  In addition, the contractor shall describe configuration control methods and safeguards, how emulators are accessed or dedicated, how software corrections or changes are verified before uploading to the spacecraft bus on-orbit.  The contractor shall also describe the  documentation system, source code generation and use, and the methods of maintaining equipment.

#### 4.3.6.2	Software Documentation

The contractor shall provide Flight Software Documentation for the complete software lifecycle development to ensure reliability, maintainability, and operability.  This documentation will also be used for maintenance of the system.  Therefore, it shall also describe the hardware aspects of the system which are necessary for operations and maintenance of the emulator and its interface to external systems.