# ICECUBE "Phase 1" DAQ Work Plan

# “Plan B” , “Workplan H”

# LBNL Engineering

### Author: David Nygren

25 April 2002

Version 1.0,  25 April 2002,  RHMinor, added comments from Bob Stokstad, clarified  relation to current cost estimate, restored string 18.  This description is the basis for the cost estimate of 25 April 2002.

Version 1.1, 11 May 2002, DRNygren, added explicit descriptions of actions for each subtask, at request of Bob Paulos.

Version 1.2, May 13, 2002 RHMinor, DRNygren, CMcParland, R. Stokstad, updated document list. Corresponds to Plan_B_Deliver_vsn1.2.doc and daq_cost_vsn1.0.xls

## Overview

In its current state, this document consists of narrative descriptions of tasks associated with three general areas:

- IceCube DAQ Architecture

- The "preproduction" DOM Main Boardwith software and firmware;

- DOM HUB Design and Software + Documentation;

Numerous documents that are part of all this work are also listed. While the work plan will evolve, as needed, to reflect current status, Version 1.0 dated 25 April 2002 is used for the basis of the cost estimate spreadsheets of the same date.

Although this work plan includes IceCube DAQ Architecture, it does not cover software development for higher level functions such as string processor, global trigger, event builder, etc; these are not Phase 1 deliverables.

The costs included in this document are only for estimates for engineering and software professionals, plus resources needed by them for each sub-task.   Any effort by technicians, machinists, etc, is implicitly included in the estimates, not separately broken out in the subtasks. Travel costs are not included. The effort of physicists is not included; their effort, spread throughout many of these tasks, is largely directed toward scientific activities such as analysis, article and report preparation, organizational matters, etc. Travel costs, management costs and Physics support are included in the cost spreadsheet 3.3.1.xls.

The units for effort to produce Phase 1 deliverables are person-days; resources are in units of k$.  Initials of the estimators accompany the estimates for each subtask.   Priorities are not yet imposed on the subtasks in this narrative.  As soon as is practical, the plan's tasks will be transformed to a schedule format to permit definition and assessment of milestones.

Estimators: Jerry Przybylski  (GTP),  John Jacobsen (JJ),  Chuck McParland (CMcP), Thorsten Stezelberger (TS), David Nygren (DRN)  , Robert Minor (RHM), Bob Stokstad (RGS), Peter Denes (PD).

Of particular urgency is the DOM HUB Design Document, as this document will serve as the basis of an informal MOU between LBNL, DESY and the ICECUBE Project Office. The contents of this document must be agreed to by the participants before design effort should start.

#### Roles and Responsibilities

LBNL:  DOM Main Board circuitry, architecture, software, and firmware, except for feature extraction. DAQ architecture, and experiment control software.  Fast communication, DOM + DOM HUB architecture and requirements, in concert with DESY.

DESY: Fast communication, DOM  HUB architecture, requirements and firmware, in concert with LBNL.  Detailed circuit design of the DOM HUB in accordance with the DOM HUB Design Document.   K-H. Sulanke will travel to LBNL for part of one year to participate in this area.  This work plan does not include this work, but the effort is included in the cost estimates for the DAQ for Phase One.  Please see file 3.3.1.xls for information.

Stockholm: FPGA code for feature extraction within the DOM.  The effort for this work is not included in this work plan.

Penn: String processor software, including string trigger is not included in this work plan, but will be included in later phases of the project.

## Estimated Effort Summary:

Please see the cost estimate spreadsheets for details.

## Elements of the Workplan:

## Documentation:

This element includes effort for documentation preparation.  The engineering effort to produce the documents is listed elsewhere in this document.

- DAQ System Requirements				4	(DRN)

- DAQ Software Requirements

- DAQ System Architecture				4	(DRN)

- DOM MB						4	(DRN)

- DOM HUB						4	(DRN)

- Master Clock Distribution				2	(DRN)

- Test Software Suite					6	(DRN)

- DAQ Hardware Requirements

- DOM Main Board 					6	(DRN)

- DOM HUB 						4	(DRN)

- Master Clock Distribution				2	(DRN)

- DAQ System Design

- DOM MB Prototype Design Document		5	(DRN)

- DOM MB Software Design Document		5	(DRN)

- DOM HUB Prototype Design Document		5	(DRN)

- DOM HUB Software Design Document		5	(DRN)

- Master Clock Design Document			3	(DRN)

- Test Results

- DOM Main Board Performance 			6	(DRN)

- Two DOMs/twisted pair				4	(DRN)

- Other (Tech notes, presentations)				5          (RHM)

Sub-total:	74

## DAQ System  Architecture:

Although Phase 1 R&D work will primarily focus on development and implementation of the  DOM  Main Board (MB) design, software requirements and design documents for the DAQ system including the DOM HUB must be produced during the same time period.  These documents will formalize the performance requirements for all elements of the DAQ system, namely the String Processor, Global Trigger, Event Builder and DAQ Monitor.  While actual implementation of these components will take place in a phased manner during the IceCube construction effort, it is necessary to have their design finalized, documented and reviewed during this first phase of effort.  Validation of design will include some minimum level of simulation to verify expected network data transfer and message rates.   These simulations will be based on performance measurements taken from simple “mock-ups” of critical code sections in each of the above software components.  These programs will ultimately become part of the IceCube Test System described below.  It should also be pointed out that a fairly complete version of the String Processor code will be required for both the initial single string test and the following six string test.  While these tests are not scheduled until after phase 1, development of the String Processor code will need to preceed these scheduled tests.

ACTIONS:

- In consultation with the members of the Software Working Group and other stakeholders, define the framework for the ICECUBE DAQ software architecture;

- Prepare Documents as noted and initiate acceptance process through Project Office, following  procedures.

- Simulate network behavior.

Estimated EE effort:

Estimated CS	effort:	   	20  	(JJ)

Estimated sr. CS effort:	  30 	(CMcP)

Estimated TBD CS effort:	15	(CMcP)

Estimated resources:	Access to an array of networked Linux PCs will be required.  It is expected that resources will be available either at LBNL or within the collaboration.  Network switches may be required to simulate environment found at IceCube.  If necessary, ~$3K.

## DOM Main Board, LED Beacon Board Engineering & Software:

- Fast Communication: There is little if any doubt that fast communications at the level needed for IceCube can be achieved.  Fast communication is, however, tied up with other issues, such as timing "synchronization, and boot-strap mode.  It seems desirable to avoid, if possible, a design choice that limits flexibility.

An activity by the DESY group has demonstrated that more than 500 - 1000 kbits/s may be reliably transmitted/received over 2+ km of twisted quad using the commercially available HDLC protocol as offered by Altera.  HDLC offers the benefit of immediate availability and a mature implementation.  It recognizes bits through the use of analog filtering and discriminators.  It may ( or may not) have some undesirable features such as the need to tailor the equalization filters as a function of depth, or perhaps leaving the line in an unbalanced DC state (ignorance on our part at the moment).

At the media access layer, Jerry Przybylski of LBL has proposed to exploit a fast bipolar pulse ((' shape) of reversible polarity for modulation.  The encoder/decoder for the ('  modulation exists.  A 1440 ns pulse period is possible, corresponding to 700 kbaud. The modulation scheme is essentially independent of the data encapsulation scheme of HDLC, or any other likely protocol. In other words, the normally encoded serial data generated by the protocol can be passed directly to the ((',  -(') modulator.

The (' shape is very similar to the bipolar waveform used for time synchronization functions, differing only in duration.  Since the leading edge appears to be the best choice for timing measure, the length of the pulse should not affect resolution or accuracy, provided the cable is "quiet".   In the ((', -(') scenario, the fast communications "receiver" would consist of the FADC already in place for the timing measurements; it would look directly at the arriving waveform without need of filtering components.  Code in the FPGA would apply digital filtering, baseline tracking, etc.,  as needed.  This offers the flexibility inherent in any programmable digital processor, and would avoid a possible need to tailor filtering constants as a function of depth. On the other hand, the resources within the FPGA needed for this modulation/ demodulation scenario would be larger than with an analog decoder.

In any case, fast communication must be seamlessly integrated with the time "synchronization" functions.   This requires that the twisted-pair lines be quiet prior to transmitting a timing pulse, and that the timing pulse be "launched" at a known offset relative to the capture of the clock value in either the DOM MB or the DOM HUB. It appears that the actual instant (defined as = clock value when leading edge appears) of waveform generation can be captured and loaded into the data packet "on the fly". In this perspective, every transmitted packet can be time-stamped and digitized, without significant penalty in resources or effort to do this. Conversely, every received packet can be time-stamped "on the fly" as well. Both DOM MB and DOM HUB will be capable of this, since their circuitry is mandated to be equivalent, in order that the RAP method may avoid systematic error.  However, the higher level software need not attend to the information content provided by the clock value and/or leading edge digitizations; these will be utilized only as needed to maintain the level of accuracy.  For this to work robustly, the API must be established that places the correctly associated relevant time-stamps of packet transmission and packet waveform reception.

It is important to note, that in the functionality as defined above, the machinery of time-stamping automatically senses the appearance of the data packet leading edge, and loads the corresponding value of the clock at the predetermined slot into the packet.  Because of this, there is no constraint on software, protocol, or modulation schemes as to when a packet transmission must occur. This important feature makes all the timing functions, including RAP, completely transparent.  Higher level software algorithms must be written to cope with variable time intervals between points in the fits - a trivial requirement.

A further requirement for the fast communication capability is that a boot-strap mode be available that will provide the highest level of safety in communications to the DOM MB, presumably similar or equivalent to the 38kbaud technique in use now for string 18. In other words, fast communication functions shall not be necessary to start the DOM MB from a power-down state, and initiate higher levels of functionality from the surface.

The fast communication process must not introduce noise into the PMT signal capture process.  While this is definitely a concern during circuit design and PCB layout, it would seem unlikely to depend upon protocol choice.

ACTIONS:

- Determine if the DOM MB hardware can be designed to permit the use of either a digital or analog demodulator, preserving boot mode, etc.; while the digital waveform capture is necessary for timing functions, the analog demodulator may be necessary for boot mode.

- Design and make a test setup to demonstrate that the timing, noise, speed and bootstrap requirements are preserved.

- Complete circuit design applicable to both DOM MB and DOM HUB, in concert with DESY colleagues;

- Produce technical note describing anticipated performance for DOM MB.

- Determine impact of protocol selection on software applications executing on both the DOM MB and DOM HUB.  Analyze interaction between firmware implementation and low level software drivers to insure proper and efficient messaging behavior between DOM MB and DOM HUB.  Document key features and behavior requirements needed in final implementation.

Estimated EE effort:	 20  	(GTP)

Estimated CS	effort:	  6   	(JJ)

Estimated Sr CS effort: 20  	(CMcP)

Estimated TBD CS effort: 20  (CMcP)

Estimated resources:	$2K

- Bootstrap Scenario:  Guaranteed  communications must be available to each DOM MB after power-up. The existence of two DOMs/twisted pair will force some changes to the approach now in use for string 18.  In short, the DOM MB must be receptive and responsive immediately after power-up, so that very short commands from the surface can sequentially initiate higher levels of functional response.

ACTIONS:

- Modify existing bootstrap scenario to match new DOM MB design, which may likely involve an embedded CPU within the FPGA.  Substantial circuit design changes are appropriate, involving new block diagram, even though basic scenario will be similar.

- Demonstrate that the bootstrap methodology is robust against all foreseeable operational circumstances, and that risk of  loss of DOM due to bootstrap failure is below established performance requirement;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	12  	(GTP)

Estimated CS effort:   1	(JJ)

Estimated Sr CS effort: 10	(CMcP)

Estimated resources:	$2K

- Feature Extraction:  Most of the ATWD waveforms will be single photoelectron (SPE) pulses, for which timing information is crucial.  Amplitude information is of only secondary interest, once a decision has been made that the pulse is an example of an SPE.  The algorithm that makes the determination whether a waveform should be classified as SPE or not, is of crucial importance, since the SPE waveform will be discarded after feature extraction, and useful information about pulse timing and amplitude compressed to a simple datum of just a few bytes. The feature extraction algorithm must be simple enough to reside in the FPGA and involve only integer arithmetic. It must produce a measure of timing that introduces negligible systematic error in timing accuracy or degradation of resolution, it must be robust in the process of decision whether a waveform is complex or SPE so that event characterization will not be distorted, and it must operate quickly enough that no significant dead-time is introduced.  Feature extraction is essential if the IceCube array is to operate without local coincidence, since the amount of data generated by the DOM MBs without feature extraction plus local coincidence would exceed the bandwidth of the twisted pair.

ACTIONS:

- Demonstrate that a simple feature extraction firmware exists that can be integrated into the general FPGA design;

- Demonstrate that the flow of data from ATWDs can be handled without dead-time or system crashes;

- Evaluate test results to show that this functionality meets the performance criteria set for feature extraction

- Interact with Collaboration members extensively to establish that possible future developments displaying grater sophistication can be integrated.

Estimated EE effort:	5	(GTP)

Estimated CS effort:	3	(JJ)

Estimated Sr CS effort: 4	(CMcP)

Estimated resources:	- 0 –

Does not include effort by Stockholm effort. (RGS)

- Simultaneous Read-Write: This is an essential but as yet unimplemented feature of the current DOM MB design.  It requires FPGA design only to realize at this point. There should be sufficient resources in the FPGA to accomplish this goal. At present, the DOM MB loopS through a cycle of capture, digitize and transmit for each wave-form. The issue here is to determine if noise is introduced at the instant of waveform capture by the digital activity  associated with transmitting previously acquired data. This task is intrinsically connected to the need to buffer data, so that large blocks of data can be framed together.  It is a requirement that simultaneous read-write be shown to work.

ACTIONS:

- Design and integrate firmware into the DOM MB FPGA design and DOM MB application software.  This will require Event Buffering functionality to be operational (see next subtask section).

- Test behavior to establish that buffering/read/write functionality is robust. This means that data corruption is insignificant, according to the level established in performance requirements Documents.

- Measure messaging efficiency, i.e., determine if FPGA + RTOS are handling transactions efficiently.

- Establish that no dead-time is introduced during data acquisition via ATWD or FADC.

- Transfer tested code to String 18 DOMs to permit data acquisition of muon events.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	2	(JJ)

Estimated Sr CS effort: 8	(CMcP)

Estimated resources:	- 0 -

- Implement Event Buffering:  Fast communication is effective only when a large block of data is ready for transfer.  This obviously requires that the DOM MB be able to format and buffer events in large blocks which can be retrieved from memory, even while new events are being stored.  This is a fairly complex software/firmware task involving shared memory, and access control arbitration between FPGA and CPU.  A considerable effort was made previously by Forrest Anderson, but most of this code has been tested, and our ideas about implementation have evolved from that era.

ACTIONS:

- Modify existing DOM MB software application to accrue many events using an established format.  Initially, this will not involve feature extraction; final software must be able to accommodate both compressed and uncompressed event formats.

- Test functionality using dummy data to show that data corruption is insignificant.

- Test functionality using real data from Lab DOMs.

- Transfer tested code to String 18 DOMs to permit data acquisition of muon events.

Estimated EE effort:	20	(GTP)

Estimated CS effort:	3	(JJ)

Estimatedsr  CS effort: 10	(CMcP)

Estimated TBD CS effort:  10 (CMcP)

Estimated resources:	- 0 -

- Quad Cable Impedance Modifications: In the current design, power for the DOM MB flows through termination resistors at both source and sink.  This wastes substantial power.  Signal termination may be realized without forcing the DC to pass through the resistors.  It is undesirable to increase the DC source voltage beyond about 100 V for a variety of reasons such as personnel safety, and reliability (MTBF) of the DC/DC converter in the DOM MB.  This circuit engineering task may affect the choice for fast communication protocol, since the likely design path will include inductors to pass the DC, capacitors to block DC and pass the AC signals, all of which will introduce time constants and ballistic effects.

ACTIONS:

- Establish the maximum permissible distortion of the timing synchronization pulses, so that the electrical engineering goals are understood.

- Explore simple designs using passive components, especially inductors with desirable resonance characteristics.

- Simultaneously explore technical benefits of DC-DC converters to establish the supply voltage range; this affects the DC current and hence the ferrite saturation characteristics of particular inductors.

- Perform timing tests using the LBNL DOM pair to measure the performance of the impedance modifications for both power dissipation and timing.

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CSeffort: 0	(CMcP)

Estimated resources:	$1.5K

- Common-Mode Noise Rejection: The twisted-pairs that carry the DC and AC will be vulnerable to some extent to external noise sources, especially noise sources such as motor controllers for drilling and winch operations.  Some evidence now exists based on work by DESY that a better differential receiver design may be employed at both DOM MB and DOM HUB.

ACTIONS:

- Work together with DESY collaborators to understand and measure the performance of their design, including robustness against discharges, overloads.

- Measure performance of mutually agreed circuit design, as shown by timing resolutions and other criteria.

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	5	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:	     0	(CMcP)

Estimated resources:	$1K

- Communications Overload Recovery: This is an example of straightforward circuit design. The original DOM MB design was hurried and inappropriate component values were used.  The new design may also exploit new products with more desirable recovery characteristics.

ACTIONS:

- This requires measurements using overload pulses to ensure that no pathology or risk is present in that circumstance.

Estimated EE effort:	1	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CSeffort: 0	(CMcP)

Estimated resources:	- 0 -

- Delete optical fiber interface: String 18 is a hybrid design, and optical communications are not needed for IceCube. This is a short easy task.

ACTIONS:

- Eliminate components in circuit design that are no longer relevant.

Estimated effort:	0

Estimated resources:	0

Estimate to be added at later date as required – not included in cost estimate 25 April 2002 (RHM)

- Neighbor logic: The modifications desired for this functionality are to obtain flexibility in operation.  By using two transformers instead of one, the neighbor logic can, by FPGA design modification, be operated as a "coherence length", rather than be limited to nearest or next-to-nearest neighbor operation. The FPGA design would be changed to accept signals from either direction, and propagate them uni-directionally, but with ever-diminishing duration. Eventually, the signal length would become zero,  thereby ending the coincidence correlation. Thus,  by varying the initial signal duration, the coherence length can be chosen at will.  Or, the original nearest-neighbor or next-to-nearest neighbor logic can be retained by programmatic choice.  The circuit design changes would be minimal; however, test effort (accounted for elsewhere) to understand optimal behavior is substantial.

ACTIONS:

- Perform DOM MB circuit design changes;

- Perform simulations to demonstrate that  a coherence length is possible;

- Modify  FPGA design to permit individually generated pulses of controlled length;

- Test circuit design on bench to measure pulse characteristics, using a length of cable appropriate to “octopus” concept;

- Show that two DOMs can properly detect the new pulses;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	3	(GTP)

Estimated CS effort:	1	(JJ)

Estimated Sr CS effort:	     0	(CMcP)

Estimated resources:	$0.5K

- Implement ATWD ping-pong for dead-time reduction:  This general feature has been implemented successfully by T. Stezelberger in KamLAND, using however, VHDL code for Xilinx FPGA.  Nevertheless, the experience and code should be almost directly useful for IceCube. The additional resources within the Altera FPGA need to be considered as part of the choice of size. The effort has not yet been estimated.

ACTIONS:

- Transfer Xilinx-oriented code to Altera, modifying as needed to integrate into DOM MB FPGA code;

- Modify DOM MB application software to track existence of dual-provenance data;

- Test codes to establish that ping-pong functionality is seamless, and that data integrity is maintained;

- Measure analog performance to demonstrate that each channel is performing symmetrically.

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	5	(GTP)

Estimated CS effort:	2	(DRN)

Estimated CS	effort:	20	(TS)

Estimated resources:	$0.5K

Note:  this effort is not included in the cost estimate of 25 April 2002 , will be added in later iteration (rhm)

- Integrate three PMT gain channels to ATWD:  Due to time constraints, only two PMT signal channels were implemented, although a third ATWD channel is available. In string 18, this channel was implemented to provide calibration features, not yet exploited; these test features need to be re-examined as to need. Since the potential dynamic range from physical processes is so large, it is desirable to implement a third gain path, similar to that achieved for KAMLAND.  Connected to this task is the need to demonstrate low noise behavior of the DOM MB circuitry, so that the high gain channel, which has the ATWD launch discriminator, will operate in a stable fashion with thresholds in the 1 mV range.

ACTIONS:

- Review KamLAND design, eliminating high-power parts;

- Simulate performance to establish that low-power version will meet specs;

- Make prototype board of 3-range analog signal-processing chain, except for ATWD.

- Measure performance of  3-range analog signal-processing prototype board;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	1	(JJ)

Estimated Sr CS effort:  1	(CMcP)

Estimated resources:	$9K

- Demonstrate Low Analog Signal Path Noise: Unwanted noise can arise from a variety of sources, compromising performance.  One source observed in string 18 is the PMT HV base, almost surely the DC/DC converter coupling back through the interface.   More generally, this task may be characterized as the application of known design and layout practices, in concert with a "systems" design approach, that will reduce noise to the irreducible source levels inherent in the PMT itself and amplifiers prior to the ATWD and launch discriminator.

ACTIONS:

- In consultation with other electrical engineers, as appropriate, reach a consensus as to general design and layout principles;

- Emphasize choices affecting analog performance technical design approaches at each Design Review.

- Measure performance of each prototype board, including simultaneous read/write and any other potentially noisy operation.

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	6	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr  CS effort:  0	(CMcP)

Estimated resources:	$8K

- Delay Line Choice: The ATWD requires a PMT signal delay of about 70 ns prior to presentation to the ATWD inputs. Most of this arises from clock resynchronization, propagation delays in the high-gain signal path to the launch discriminator, etc.  The actual delay depends on DOM MB clock frequency,  number of desired baseline samples, etc.  In string 18, this delay was implemented as ordinary coax.  It resulted in an awkward looped bundle nested under the DOM MB.  Relatively heavy, it presented mounting and strain relief challenges, as well as concerns about reliability of the soldered connections to the DOM MB.  The main virtue of this solution was that the signals were relatively undistorted after passage through.  Thus there is motivation to consider a lumped delay line, á la KAMLAND, as a attractively compact alternative to the normal coax.  The concern about this form of delay line is that it involves a fairly large number of internal solder joints, which may compromise reliability. Another possibility then, is to use a stiff self-supporting rigid coax that could even serve to add mechanical strength; concerns about reliability would seem to be the smallest for this possible solution.  The task is to make an early but robust decision for this component.

ACTIONS:

- Consult with UW Physics/SSEC Engineering personnel who may have relevant expertise;

- Review technical performance criteria for trade-offs;

- Evaluate different technical pathways against performance requirements;

- Reach a decision including risk, cost, assembly/integration, factors;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	6	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:  0	(CMcP)

Estimated resources:	$4K

- FADC PMT Data Stream: The PMT anode signal path is split not only to channels of the ATWD, but also to a dedicated 10-bit FADC running at the DOM MB clock frequency. The motivation for this data stream is to capture very long signals that would be observed for extremely energetic events at a distance from the DOM, for which the ATWD record is too short for complete capture.  At these longer times, a highly structured signal is not expected.  For the ADC to capture the signal without aliasing or loss of information, pseudo-gaussian shaping with a ( roughly equal to the clock period is needed. In other words, the PMT signal must be “stretched” by about a factor of six.  The inescapable penalty is some loss of pulse-pair resolution; still much can be recovered, in principle.  This data stream in string 18 had been unexamined until now (8 May, 2002) due to lack of available FPGA design effort. Data is now being collected and examined; record boundaries need attention, but noise looks good. Both software and firmware effort is needed to integrate this data stream together with the ATWD record in a useful format.

ACTIONS:

- Design and write FPGA code to capture and integrate FADC data stream;

- Test code in LBNL DOM pair, demonstrating robust behavior;

- Transfer robust code to string 18;

- Establish integrity of string 18 data stream;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	2	(JJ)

Estimated CS	effort:	     2	(CMcP)

Estimated resources:	- 0 -

- PMT FADC Dynamic Range: At the DOM/DOM HUB meeting held at Penn, the idea to utilize a piece-wise linear transfer function gained the most support, relative to other possibilities such as square-root or log(amplitude).  The design issues here need to be examined to see what is reasonably possible.  The alternative approach to use two FADCs to achieve a higher dynamic range was felt to be inappropriate.

ACTIONS:

- Consult with stakeholders to establish technical goals.  This may require a mini-meeting by video- or teleconference.  Context of this meeting should include technical preparation so that trade-offs are understood.

- Reach a decision as to acceptable limitations in performance and choose pathway;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	8	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:  0	(CMcP)

Estimated resources:	$1K

- Two DOMs/Twisted Pair: This requirement imposes fundamental changes in the basic communications, and affects several aspects of software and firmware design. In addition, a network to split power and signals between the breakouts and the DOM pair must be included. The network has been at least partially designed, but reliability and packaging issues remain. A second option is to simply "add" an unterminated DOM to the twisted pair using only a short-stub cable.  This second option eliminates all parts, packaging, and connectors of the impedance matching network, with a presumed reduction in risk and cost; Instead, this second option introduces a small  impedance blip whose magnitude is directly proportional to the stub length. The second option needs considerable effort to characterize all expected systematic and resolution effects on timing. Initial tests show an impact that is in the ballpark expected. Software changes may be sufficient to compensate for pulse shape degradation. The software issues, such as conversion to a strict master/slave relationship, affect nearly all aspects of messaging, including the bootstrap process. Part of this task is to show that the excellent timing resolutions demonstrated with string 18 also can be achieved with two DOMs per twisted pair.

ACTIONS:

- Evaluate different technical approaches, which span the range of possible degrees of termination. This involves both circuit design and algorithmic design;

- Organize a mini-meeting among the stakeholders to evaluate test results;

- Reach a consensus decision that the degradation in performance using two DOMs/pair is understood and that the performance meets requirements;

- Produce technical note describing anticipated performance for DOM MB.

- Evaluate impact of signaling mechanism on low level communications with bootstrap.  Evaluate design to verify ability to selectively communicate with either DOM on the twisted pair during under both high speed and bootstrap communications models.

Estimated EE effort:	11	(GTP)

Estimated CS effort:	8	(JJ)

Estimated Sr CS effort: 10	(CMcP)

Estimated TBD CS effort: 10	(CMcP)

Estimated resources:	- 0 -

- Evaluate TOYOCOM Oscillators: This revisits the outstanding work done earlier to assess the frequency stability and phase noise of the TOYOCOM products now in string 18.  The test set-up will need to be re-established, and modified somewhat to match the new devices characteristics, and also to permit more devices to be tested, perhaps as many as three strings worth, i.e., about 200 parts.  Initial tests of one of  the new batch indicate promising results, i.e., stability of frequency is comparable to string 18.

ACTIONS:

- Re-establish the high precision test-bed used on an earlier batch of oscillators;

- Measure a statistically significant sample evaluation of the recent batch Toyocom devices;

- Promulgate results expeditiously, as results affect system behavior;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	15	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort: 0 	(CMcP)

Estimated resources:	$7K

- PMT HV Base Interface: The PMT HV base needs an interface that provides complete decoupling of any noise related to the DC/DC conversion. To realize this decoupling will require the replacement of the analog HV control with a digital interface, ground plane design to eliminate ground loops.  This task requires continuing liason with those responsible for the base design, and testing to prove that the goals of noise suppression and HV stability are met.

ACTIONS:

- Establish and maintain close communication with UW and Mainz regarding performance specifications and interface;

- Test PMT HV base with DOM MB as available to establish compatibility;

- Test PMT HV base with DOM MB as available to establish absence of degrading noise in DOM MB analog performance;

- Produce technical note describing anticipated performance for PMT HV base with DOM MB.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	1	(JJ)

Estimatedsr  CS effort: 0 	(CMcP)

Estimated resources:	- 0 -

- PMT Base Production Testing: We feel that we should be involved to make sure all needed performance requirements are met, and appropriate tests are done, and check results, even though the primary responsibility lies elsewhere. As is well-known, HV subsystems are notorious for problems and MTBF.  For example, in the requirements, GTP asked for a higher temperature PCB material to reduce the damaging effects of the soldering process.  Until proven otherwise, we should look carefully for PCB degradation associated with soldering to the PMT pins.  Several other tests are foreseen, but do not need to be listed here.

ACTIONS:

- Involvement in design, test, and production phases;

- Close communication with UW physics/SSEC engineering to ensure integrity.

- Produce technical note describing anticipated performance for PMT HV base with DOM MB.

Estimated EE effort:	2	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:    0 	(CMcP)

Estimated resources:	- 0 -

- LED Beacons: The GaN LED beacons work well, but little attention could be given to their optimization, especially to a calibration of the absolute light output, as viewed from some distance from the sphere. Both amplitude and frequency can be controlled.  The requirements for the beacons have not been set. This task requires effort on the part of the physics collaborators to determine the precise goals and requirements. There may be more engineering effort needed to realize these requirements, once they are well-defined. There has been discussion of adding "light output waveform" capability. While certainly possible, this would represent a complete redesign of this capability, and no effort has been allocated toward this possibility.

ACTIONS:

- A mini-meeting will be organized to establish the needs and corresponding requirements for calibration and event simulations;

- Performance requirements should be set and ratified.

- Design effort should be estimated for the ratified requirements, and engineering costs adjusted;

- Design modifications to LED Beacon Board;

- Produce technical note describing anticipated performance for DOM LED Bacon Board.

Estimated EE effort:	5	(GTP)

Estimated CS effort:	7	(JJ)

Estimatedsr  CS effort:  0	(CMcP)

Estimated resources:	$4K

- DC-DC Converters: The string 18 DOMs used a commercial part from Ericsson to convert the ~80 VDC to ±5VDC.  A few of these parts displayed early failures, despite an advertised MTBF of more than a million hours. In addition, the devices needed considerable filtering and decoupling to avoid noise injection. The family of DC-DC converters Ericsson offers accepts input from 36 VDC to 72 VDC, lower than the ~100 V we would choose.   Furthermore, the efficiency of these parts is less than can be obtained by custom design. Some effort is needed to determine whether newer commercial parts can offer the desired performance, or whether a custom discrete design provides a preferred solution.

ACTIONS:

- Consult with experts as appropriate;

- Review performance requirements for trade-offs;

- Evaluate attractive commercial candidate parts for efficiency, noise, filtering, robustness;

- Reach a decision that incorporates all factors.

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	15	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:  0	(CMcP)

Estimated resources:	$1K

- FPGA with Embedded ARM CPU, or not?  New product offerings from Altera provide an opportunity to combine the FPGA and an ARM CPU in one package. The product of particular interest would be a hard-core CPU with ~100K gate FPGA. The costs would be attractively reduced relative to separate packages, and reliability would presumably be enhanced.  One large BGA with 484 I/O traces would be used, rather than two 256 pin devices.  With fewer interconnects on the PCB, rerouting layout time will be reduced.  Noise may be reduced since most digital activity is confined within one chip. The smaller feature size, in concert with reduced trace numbers and lengths, will substantially reduce power dissipation. The software and firmware implications of this choice are not yet fully explored, but may be manageable, and may offer advantages in system operation.  For example, the buffering of events to accommodate simultaneous read/write may be facilitated by an embedded CPU. On the other hand, the bootstrap procedure must be reconsidered and perhaps restructured. This decision needs to be managed so that the risk of surprises along the way is minimized.

ACTIONS:

- Consult with Altera personnel;

- Identify and evaluate risk factors and commercial trends;

- Estimate effort levels for either technical path;

- Reach a technical decision, documenting the basis for choice.

- Produce technical note describing anticipated performance for DOM MB.

- Evaluate available RTOS for Altera ARM architecture and select OS for production DOM MB and application.  Evaluate and select suitable software development tool chain for application porting from existing string 18 processor.

- Evaluate proposed features of Altera ARM part for their impact on operation of both existing and to be developed DOM software components.

Estimated EE effort:	20	(GTP)

Estimated CS effort:	1	(JJ)

Estimated CS	effort:	     20	(CMcP)

Estimated TBD CS effort: 35	(CMcP))

Estimated resources:	$4K

- IceTop Design Variant: IceTop presents several important differences in operation relative to IceCube.  Will heating be required at all times to protect components from damage, or will heating be needed for stable operation, but not for damage? The bandwidth needed to transport IceTop data may be substantially higher than the ~10kbyte/s per DOM anticipated for IceCube.   The LED Beacon board may not be needed, or perhaps modified.

ACTIONS:

- Consult with ICETOP personnel to ensure that requirements are mutually understood and consistent with ICECUBE system design goals;

- Establish that differences exist only in software and firmware;

- Establish impacts for DOM HUB, if any;

- Establish impacts for Master Clock, if any;

- Include variant impacts, if any, as part of PDR;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	8	(JJ)

Estimated Sr CS effort:  ?	(CMcP)

Estimated resources:	$8K

- New DOM Main Board Layout: Clearly, with all the circuit design changes, the DOM MB layout will be essentially new.  Changes may occur in the LED beacon board as well.

ACTIONS:

- Choose software tools that optimize results;

- Perform new bottoms-up layout according to circuit design schematic and general layout principles;

- Hold review to provide opportunity for stakeholders and outside experts to evaluate the layout organization;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort:	35 	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:  0	(CMcP)

Estimated resources:	$3K

- "Production Engineering": All components will have to be carefully selected, and in some cases tested, for compatibility with -40o  C; for ICETOP, the working temperature is likely to be about -48o C.  String 18 DOMs were not engineered for reliability due to the extreme schedule pressures imposed by the deployment window, and there have been several failures.  For the production DOM MB version, component selection and fabrication procedures will require substantial investigation to maximize reliability within cost constraints.

ACTIONS:

- Consult with UW SSEC experts, and with experts that they recommend;

- Establish temperature cycling facility that meets both temperature range and cycling needs;

- Explore and understand available literature concerning impact of low temperature on MTBF of parts, procedures, and PCBs;

- Identify highest potential parts and fabrication risks;

- Perform some destructive testing to determine reliability of specs and parts;

- Hold review to provide opportunity for stakeholders and outside experts to evaluate the proposed plan for production engineering;

- Establish crude but useful estimates for MTBF;

- Produce technical note describing anticipated performance for DOM MB.

Estimated EE effort: 	40	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort: 0	(CMcP)

Estimated resources:	$7K

- DOM Main Board Fabrication: After design, at least two, and probably three versions will be fabricated and loaded.  Parts need to be purchased, organized, and delivered to chosen vendor. Vendors may need to be pre-qualified by some criteria to maximize reliability.  The unpleasant recent history experienced by the KamLAND group suggests the need for diligence. Assumptions are that the first run is four machine-loaded boards, the second run is six machine-loaded boards, and the third run (the DOM MB "production" model) will be 18 boards, then as many as 28 DOM MBs will be built. Cost assumptions are $2K set-up charge for machine-loading (incurred three times ( $6K), $10K for all three loading cycles, $18K for parts (for 28 boards), and $8K for three different PCB production cycles.

ACTIONS:

- Following ratified plan for production engineering, embark on plan for fabrication of DOM MBs as scheduled;

- Pre-qualified vendors will be visited prior to contract award, and monitored during fab;

- Produce technical note describing fabrication process and procedures.

Estimated EE effort:	15	(GTP)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:     0	(CMcP)

Estimated resources:	$42K

- DOM Main Board Test:  This requires the existence of an operational test setup, including firmware/software.  The availability of a temperature-cycling facility which can reach as low as -55 o C is essential.  Documentation of results will absorb significant effort.

ACTIONS:

- Establish a DOM MB test-bed which can support the Test Software suite;

- Perform tests that establish performance of DM MB against performance requirements. This is an extensive list of tests that will need to be defined as a separate document;

- Hold a mini-meeting to present and evaluate intermediate results;

- Revisit technical measurements as found necessary;

- Produce technical note describing measured performance of DOM MB.

Estimated EE effort:	30	(GTP)

Estimated CS effort:	4	(JJ)

Estimated Sr CS effort: 20	(CMcP)

Estimated TBD CS effort: 30	(CMcP)

Estimated resources:	$7K

- ATWD Evaluation: The development of the ATWD ASIC was underfunded, leading to insufficient testing and documentation of performance and behavior. Questions have been raised as to whether design flaws might exist, not yet fully appreciated, but potentially troublesome for Icecube.  No flaws sufficient to warrant a new design version are known at present,

ACTIONS:

- An evaluation of the ATWD  will be performed to verify its’ suitability for use in Icecube.  Simulations will be used to investigate behavior reported by  Kamland.

Estimated EE effort:	40	(PD,RHM)

Estimated Sr. EE effort: 80	(PD,RHM)

- DOM Main Board Software: As enumerated above, there are a number of  key features that remain to be implemented and demonstrated.  Several key features, fast communications, buffering of large blocks of PMT trigger and waveform data, simultaneous access and synchronization of shared data between FPGA and DOM application, are yet to be implemented in software.  Work on these features has been enumerated above.  However, DOM HUB design and testing as well as DAQ string processor design will require the development of a simulated DAQ test system.  This system will begin with the porting of existing and new DOM software to run as a collection of programs on a standard PC-based Linux system.  This effort will involve primarily the overall design and implementation of the DOM portion of that test system.

ACTIONS:

- Produce Design Document describing software design and anticipated performance;

- Produce technical note describing measured performance.

Estimated EE effort:	3	(DRN)

Estimated CS effort:	20	(JJ)

Estimated Sr CS effort: 25	(CMcP)

Estimated resources:	$12K

- DOM Main Board Firmware Integration:  Many changes will be necessary, as described in many of the sub-task descriptions above.  Effort will be needed to integrate and debug the fully fledged code with all capabilities included. Debugging effort may be extensive, and difficult to plan for precisely.

ACTIONS:

- Produce technical note describing firmware design and anticipated performance;

- Produce technical note describing measured performance.

Estimated EE effort:	30	(GTP)

Estimated CS effort:	5	(JJ)

Estimated Sr CS effort:  10	(CMcP)

Estimated resources:	$6K

## DOM HUB

- DOM HUB Design Document: The goal of this document is to provide a stable base for DOM HUB design effort by describing all aspects of DOM behavior and control, timing scenarios, fast communications, network loads, messaging, and string processor behavior.  The descriptive nature of this document is required for several reasons.  First, as a detailed inventory of DOM HUB capabilities, it will provide the basis upon which staff at LBNL and DESY will logically divide the tasks associated with the design and implementation of the DOM HUB.  Second, in combination with the software requirements document mentioned earlier, it will provide a common view of expected behaviors in a known set of usage scenarios.  Such a thorough, commonly held understanding is necessary for successful implementation of this key element of the ICECUBE DAQ at separate institutions.  Preparation of this document has begun. : We will produce a DOM HUB Software Requirements Document concurrently with the DOM HUB Design Document.

ACTIONS:

- Prepare DOM HUB Design Document in concert with DESY collaborators;

- Review DOM HUB Requirements at Engineering Requirements review;

- Consult with UW Project Office  as appropriate to maintain consistency with all software and configuration management issues.

Estimated EE effort:	15	(GTP)

Estimated CS effort:	10	(JJ)

Estimated Sr CS effort:  15	(CMcP)

Estimated resources:	- 0 -

- DOM HUB Software Requirements Document: We will produce a software requirements document covering the required capabilities and behaviors expected from the DOM HUB.  This document will be based on the ICECUBE high level software requirements document now being produced by the Software Advisory Group.  The DOM HUB software requirements document will extend the overall system design principles found in the ICECUBE document down to the DOM HUB and DOM subsystem level.  It will contain a mixture of both DOM HUB use case scenarios as explicit requirements governing the functionality and behavior of the DOM HUB software.   Use case scenarios will illuminate known circumstances and operations within which the DOM HUB will be accessed and used.  These should provide a complete set of operations within which the DOM HUB plays an explicit role.  Explicit requirements will place performance and behavior constraints on the DOM HUB software when used in these various scenarios.  This document will be fully consistent with its parent document, the ICECUBE software requirements document, and will act as the project’s first top-to-bottom design and implementation cycle.

ACTIONS:

- Prepare DOM HUB Software Requirements Document in concert with DESY collaborators;

- Ratification through established project procedures.

Estimated EE effort:	2	 (DRN)

Estimated CS effort:	4	(JJ)

Estimated CS	effort:	     15	(CMcP)

Estimated resources:	- 0 -

- DOM HUB Hardware:  The detailed circuit design, layout, prototyping, and testing of the DOM HUB will to be the responsibility of the DESY group.  As noted, the main effort for LBNL will be in the generation of the DOM HUB Design Document and DOM HUB Software Requirements Document.. Nevertheless, some effort on our part will be needed for coordination and integration. Video conferencing about detailed design aspects is expected to take time and preparation.

ACTIONS:

- Collaborative development of DOM HUB Design Document, followed by coordination during detailed design of DOM HUB hardware by DESY group.

Estimated EE effort:	4	 (DRN)

Estimated CS effort:	5	(JJ)

Estimated Sr CS effort: 5	(CMcP)

Estimated resources:	- 0 –

- DOM HUB Software: Initial implementation of DOM HUB software framework.

Functionality includes communication and testing of DOM HUB interface and design.

ACTIONS:

- Design interface mechanisms  and data structures for interface firmware and Linux driver software.

- Design and implement Linux driver to above specifications.

- Provide rudimentary application-level test software to verify operation of driver/hardware interface.

- Design of low-level data buffering structures and mechanisms.

- Design and implementation of DOM HUB external interface software.  This primarily consists of TCP/IP port and messaging mechanisms for programmatic interactions between DOM HUB and other systems.

- Implementation of DOM MB data buffering mechanism and DOM HUB test program to verify correct operation.

- Coordination as appropriate with other software designers.

Estimated CS effort:	80	(JJ)

Estimated CS	effort:	    30	(CMcP)

Estimated resources:	- 0 -

- Test System Software Requirements:  Phase 1 activities are not aimed at full production  of DOM MBs and DOM HUBS in volume.  When such production does begin however, a robust, production quality testing environment will be needed.  As part of Phase 1, we anticipate specifying the software requirements for a production test environment that will assist the production, deployment and maintenance of ICECUBE DAQ and computing hardware and software for the life of the experiment.  While some discussion has already taken place, we feel that Phase 1 activities will provide a fertile environment for fully developing and finalizing the requirements for such a system.  It is unlikely that Phase 1 funding will allow development of any production level testing software.  That effort will follow in subsequent production phases.

ACTIONS:

- Write test software suite requirements document, describing scope that will permit an evaluation of the DOM MB and DOM HUB performance and behavior. The software should be able to span all of the relevant capabilities, so that all performance requirements established for ICECUBE may be tested.

Estimated EE effort:	2	(DRN)

Estimated CS effort:	2	(JJ)

Estimated Sr CS effort:  10	(CMcP)

Estimated resources:	- 0 -

## String 18

- Simplified PMT Data Buffering scheme.  This is a simplified data buffering mechanism that will allow the capture of multiple events in look back memory.  Data thus captured will be read out using existing slow communications link and existing readout routines. This capability is now essentially realized.

ACTIONS:

- Modify current DOM CPU application to create a large buffer size;

- Modify current DOM CPU application to maintain pointers and byte counts, etc, to permit downstream analysis to unpack events.

Estimated CS effort:	5	(JJ)

Estimated Sr CS effort:  5	(CMcP)

Estimated resources:	- 0 -

- "DOMSERVER" Software:  Several distinct elements remain to be completed, some of which are now nearly complete, others in progress.

ACTIONS:

- DOMCOM control/autonomous sending of messaging to DOMs;

- Communications state machine which prevents conflicts or collisions between messages coming from DOMSERVER threads, or externally, from the executive;

- Migrations of SYNCSERVER software functions, e.g., time calibrations, into DOMSERVER;

- Automatic retrieval of data and sending to the software package EBTRIG,  (formerly known as PennDAQ);

- Many more subtasks, as defined in "String 18 Operations in Detail", by JJ

Estimated EE effort:	1	(DRN)

Estimated CS effort:	12	(JJ)

Estimated Sr CS effort:   1	(CMcP)

Estimated resources: 	- 0 -

- "DOMEXEC" Software: This is the String 18 "executive".  It controls both DOMSERVER and EBTRIG.

ACTIONS:

- Design script to integrate operations of the two software modules, presenting a reasonably straightforward interface to user.

Estimated EE effort:	0	(DRN)

Estimated CS effort:	9	(JJ)

Estimated Sr CS effort:   0	(CMcP)

Estimated resources:	- 0 -

- Buffering of DOM Data: This task will hopefully have substantial overlap with the IceCube DOM firmware/software.  Experience gained here should be very valuable. This task is closely related to the Simplified PMT Data Buffering  task.  This capability is now close to full realization.

ACTIONS:

- Modify current FPGA design to interleave memory access between CPU and FPGA;

- Modify current DOM CPU application to manage multiple events.

Estimated EE effort:	3	(DRN)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort:  0	(CMcP)

Estimated resources:	- 0 -

- Commissioning Plan:  This process is proceeding very well so far, but in an ad hoc manner. Benefits should occur if an orderly plan is evolved.

ACTIONS:

- Define priority sequence for string 18 tasks, balancing Icecube development goals with physics content analysis.

Estimated EE effort:	10	(GTP)

Estimated CS effort:	1	(JJ)

Estimated Sr CS effort:     2	(CMcP)

Estimated resources:	- 0 -

- Event Capture and System Efficiency: Not every event needs to be acquired and analyzed. However,  a captured event need to be acquired with all DOMs live and ready to acquire data; in other words, events partially registered are of little to negative value for analysis.  Goals need to be set for what fraction of all possible events need to be acquired to achieve analysis goals.  This is also tied up with fast communications if a fraction larger than what "slow" communications can provide. This is also connected intimately with the next subtask.

ACTIONS:

- Analyze relationship of physics content with effort levels to obtain data sets of optimum size for Icecube event characterization.

Estimated EE effort:	2	(DRN)

Estimated CS effort:	1	(JJ)

Estimated Sr CS effort:  1	(CMcP)

Estimated resources:	- 0 -

- Data Analysis Goals: These have not yet been written down with clarity, and are needed to integrate other collaboration members into a wider effort.

ACTIONS:

- Work together with Icecube collaborators to define goals for string 18 software developments, balancing effort level estimates against return for Icecube.

Estimated EE effort:	0	(DRN)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort: 1	(CMcP)

Estimated resources:	- 0 –

- Timing Tests with Atomic Clock: The new rubidium clock will be more stable than the GPS units that have been previously used.   These tests are underway, made possible by heroic efforts on the part of String 18 team. Initial analysis indicates that the resolutions now observe fall in the range of 1 - 2 ns rms, a truly excellent result.

ACTIONS:

- Using current software and firmware, make new measurements of DOM Toyocom oscillator clock stability in the lab, and at the pole, with the goal of identifying sources of noise in either the DOMCOM cards and the string 18 DOMs.

Estimated EE effort:	2	(DRN)

Estimated CS effort:	0	(JJ)

Estimated Sr CS effort: 0     	(CMcP)

Estimated resources:	$1K

Not included in estimate of 25 April 2002. (RHM)