The Populus Genome Science Plan :

# From Draft Sequence to a Catalogue of All Genes through the Advancement of Genomics Tools – 2004-2009

## Panel: Informatics, Annotation & Database Development

Francis Martin			fmartin@nancy.inra.fr			INRA – Nancy

Jan Karlsson			jan.karlsson@plantphys.umu.se	Umeå Plant Science Centre

Dan Weems			dcw@ncgr.org				National Center Genome Research

Loren Hauser			hoi@ornl.gov				Oak Ridge National Laboratory

Natalie Pavy			nathalie.pavy@rsvs.ulaval.ca		Université Laval

Pierre Rouzé			Pierre.Rouze@gengenp.rug.ac.be	Ghent University

1. Delineation of the scope

Aims of this panel include the formation of publicly accessible, readily updateable, globally linked intraspecific and interspecific genomics databases. Three main tasks:

## – Development of bioinformatic resources

## – Annotation of the Populus genome

## – Development and curation of databases

2. Description of the current state of the science, including a catalog of the up-to-date status of physical, financial, and human resources

2.1. Physical resources

Canada:

–Laval University (CRBF) Gene prediction & genome annotation, gene profiling databasing (Mac Kay et al.).

– UBC: ?

Belgium

- Gene prediction & genome annotation, with special emphasis on plants (Ghent, Rouzé et al.)

- Databasing & search for transcriptional regulatory elements (Leuven, Y.Moreau's Team; Brussels, J.Van Helden; Ghent, Rouzé et al.)

- Modeling Pathways & Gene Interactions (Brussels, S.Wodak/J.VH; Ghent, M.Kuiper; Leuven, Y. Moreau)

– Comparative genomics, genome duplication, gene families (Ghent, Rouzé et al./ Y. Van de Peer)

France:

- EST annotation, SAGE, search for transcriptional regulatory elements, microarray databasing: INRA-Orléans (Leplé & Pilate et al.).

- The INRA PoplarDB database containing annotations, functional classifications for unigenes of root ESTs, and blast services: INRA-Nancy (Martin et al.).

- The LIGNOME EST database & EST clustering: INRA-Bordeaux (Plomion et al.)

Germany & Finlande ??

#### Sweden: The UPSC PopulusDB database containing annotations, functional classifications for unigenes of >100.000 ESTs, and blast services. Curation of the database is funded for 2004 (Karlsson et al.).

#### USA: ORNL facilities + Michigan Tech (?)

2.2.Financial resources: No specific funding, except at UPSC (Sweden). The EU "Network of Excellence", so-called EVOLTREE,  if agreed will allocate funding to Populus genome annotation.

2.3. Human resources

Human resources are requested at three steps of the process:

- Development/tuning of software & tools for annotation

- Structural (syntactic) annotation : modeling of genes  for the whole genome

- Functional annotation: give functional attributes to every gene and/or gene product.

Step.1 will be done in a very few teams which are already involved in such developments, like ORNL, The Ghent Team (Rouzé et al.) and possibly Umea IPGC & UBC.

Step.2 is straightforward as soon as the tools are developed and validated in Step.1. It is mostly automated and will need a few dedicated curation people, well organized, database-minded, but not necessarily highly qualified, their number and duration of the task depending on the flow and quality of sequence data produced. Their job will be finished (as a first  version) quite early on after a decently full sequence will be obtained. This job should better be done inside, or in close contact with (and feedback from), the teams having performed step.1 (ORNL & Ghent). The output could be one initial gene model for the genome, or (more likely) several concurrent gene models, as produced using the different tools available. Pierre Rouzé suggests to keep these alternative models separate, documented as completely as possible, and to leave the choice for one or the other models to the annotators in step.3 here below.

Step.3 is the most human-demanding step. It can be  done in a processive way, with a first covering  done merely through BLAST homology. This simple pass is time-demanding, since the curator has to check if this annotation fits with the gene model, and correct it otherwise. A more elaborate functional annotation will come through analysis of gene families (potentially through external experts), and more elaborate analysis of the gene products according to the accepted Gene Ontology procedure, and using additional criteria. The Ghent team would only take part in this step if additional financial support  would be allocated specifically for it (see below).

Identified human resources (May 2003)

Canada:

- Laval University: 1 post-doctoral fellow dedicated to Populus genome

- UBC: ??

Belgium

The Ghent bioinformatics team (Rouzé et al.) is a partner in PLANeT, an EU-founded initiative coordinated by Klaus Mayer (MIPS) which aims at providing plant scientists access to plant genomics data, knowledge and resources collected  in the different partners countries, and to share curation tasks and know-how. One post-doc will be funded for Populus genome annotation in addition to the current staff and PhDs currently involved in such task.

France:

– Antoine Kramer (INRA-Bordeaux) is coordinating the EU network EVOLTREE (involving up to 200 scientists from a dozen of european countries), aiming at investigating tree biodiversity and involving genomics as the first component. Poplar is one of the three species chosen in this programme, and helping its annotation one of the milestone of the proposal. If funded, this proposal will provide support to hire people to perform this task, up to the functional step if funding allows.

INRA: Full time equivalent for 2004 : 5 mans/year, mainly on functional genomics and QTLs. One man/year could be involved in gene annotation.

Germany ??

#### USA: Currently, no human resources for doing gene modeling and annotation???

#### Sweden: One man/year that could be more or less directly involved in the annotation of the Populus genome and post-genomic activities.

### 3. List of short-term [1-2 years], mid-term [2-5 years] and long-term [5+ years] goals

3.1. [1-2 years]

- Generate a data-set of non-redundant full length cDNAs and ESTs to build a relevant database and train GRAILEXP or/and EuGene components. This will involve ORNL, UPSC, UBC, Laval, and INRA. Up to 1000 full-length cDNAs and 150K ESTs are currently available.

- Check (mostly through automatic routines) all poplar BACs for these documented genes, as well as evolutionary conserved genes. Annotate automatically & check manually all these annotations. Build the relevant training sets from these annotation

- Validate the existing comparative annotation program for adequation to comparison of poplar and Arabidopsis genomes

- Depending on the results, tune one or several of them, and possibly develop additional in-house capabilities

- Through collaboration between ORNL and Ghent Team search for and enter in database specific genome features to be filtered out (or annotated separately) in the annotation process  (repeats, rRNAs, transposons, ..)

- Build the BLAST databases for the protein and cDNA comparisons components of EUGENE_POP and/or GRAILEXP

- Validate, tune and train the ab-initio components of EUGENE_POP and/or GRAILEXP (Markov models for Exon, Introns, UTRs and Intergenic, Splice site predictors, Translation Start, ..)

- Integrate Genome Comparison Algorithm(s) as EUGENE_POP component(s)

- Train EUGENE_POP and/or GRAILEXP and validate

- Beta-trial of EUGENE_POP/GRAILEXP on routine with feedbacks

- Syntactic (structural) annotation of the poplar genome, BAC-wise using EUGENE_POP/GRAILEXP

- Comparative evaluation of syntactic annotation (collaboration ORNL-Ghent). Depending on sequencing status, provide a provisional complete genome annotation (with or without functional annotation, see below)

- Agree on stategy and share of tasks with ORNL-Ghent and other teams on functional annotation. Build routines to collect comparative functional annotation.

- Routine first functional annotation through database matches (SwissProt, Gene Ontology and Interpro, …)

- Enter Ontology consortium and validate for poplar

3.2. [2-5 years]

- Compare GRAILEXP and EuGene gene models (and any other modeler that IPGC scientists want to use).  This comparison will be on going for a number of years.  To be discussed at the yearly meetings.

- After an agreed upon time and as more full length cDNAs and assembled ESTs become available, the entire genome will be remodeled with retrained GRAILEXP and EuGene gene models.

- Final annotation and distribution of the workload.  To be discussed at the yearly meetings

- Train a number of poplar biologists on how to do annotation since they will be the ones who will  primarily use and edit the final poplar database.

- Developpement of the Poplar Genome Anatomy Project (PGAP) aiming to determine the gene  expression profiles of poplar tissues/cells, leading eventually to improved detection and diagnosis for the economically-relevant traits. The PGAP will provide comprehensive genomic data, including expressed sequence tags (ESTs), gene expression patterns, single nucleotide polymorphisms (SNPs), cluster assemblies, and cytogenetic information, together with informatics tools to query and analyze the data & Information on methods and resources for reagents developed by the project.

### 3.3. [long-term >5years]

- Build a visualization tool to understand architectural structuration of gene expression in trees (linking gene annotation, Gene Ontology, microarray gene expression profilings).

4. Discussion on a) strategies for reaching each goal and b) potential future applications.

Gene prediction & annotation in poplar will be largely using tools (GRAILEXP/EuGene) that have been developed for other genomes (e.g., Arabidopsis). Nevertheless several  points have to be noticed:

- the coverage of Populus sequencing will be quite low (x6) which will have a negative influence on the performance of ab initio gene finding.

- there are many ESTs (150 K) but not plenty, and quite few entire cDNAs: gene finding will gain only marginally from data from the  expressed genome (contrary to human or even Arabidopsis & Rice).

- In contrast, there is/will be soon several plant genome entirely sequenced, or with large sequence data (Arabidopsis, rice, medicago, maize, ..): gene prediction in poplar should use comparative genomics to a large extent. This approach has been promoted recently for the human genome, but  mainly dealing with more closely related organisms (human/mouse). There will be a need to tune or re-develop the existing tools to cope with our needs. We suggest to balance the low coverage concern which will leave many  gene models with uncertainties by a back-and-forth mechanism between sequencing and annotating teams, in order for the second to pinpoint potential anomalies (e.g. frameshifts) to be checked on sequence readings  and spectra by the firsts (Rouzé’s team did it on a small scale when sequencing Arabidopsis, and corrected  several sequencing errors this way). Ghent team is planning to build an integrated gene prediction platform based on EUGENE, the one they developed for Arabidopsis in collaboration with Thomas Schiex (INRA Toulouse) plugging in an additional comparative genome component.