|  | Title | Comment | Comment made by | Assigned To | Response |
| --- | --- | --- | --- | --- | --- |
| 1. | Magnet Braking Systems | With all the weight on the cart and magnet mover going down this slope, what are the chances of magnet falling off or a load breaking away. How are the braking systems for these two machines, what are the possibilities of this systems failing. | G. Gentry | Mayling Wong |  |
| 2. | Zero Layer Schedule Acceleration | Need to decide "early" (How Soon?) if zero layer installation is to be changed from 1 shift/day to 2 shifts/day. If decide to accelerate schedule too late, following tasks may not be able to get ready in time. (Man power resources especially). | D. Ayres | I.T. |  |
| 3. | Magnet Steel Installation | Ultimately, the magnet is aligned relative to the beamline. What I think I heard was that the stands are installed, and then the magnets on the stands. Consider the tolerances needed on the stand placement, and your ability to move the stands when doing the final placement at the magnet off the transporter. (Goes for other components too) | J. Kerby | Sam Childress |  |
| 4. | Magnet Status | Confirm the individual magnet (& other tech components) are Ok'd to go into the tunnel. Finish the thermal analysis of the 3C120's. | J. Kerby | Sam Childress |  |
| 5. | Block Transporting | Having two forklift drivers and one truck driver appears to be very inefficient. The forklift drivers are going to be sitting & waiting most of the time. A second truck driver would be much more efficient - one could be being loaded at the railhead while the other is being unloaded at MI-65. (Analyze this cost benefit of leasing a 2nd truck & driver) | P. Martin | I.T. |  |
| 6. | Scheduling Question | Nice scheduling layout. How much flexibility is there for tasks that sit later in the schedule can be moved up when there is available time/resources? | M. Wong | Tom Prosapio |  |
| 7. | Access | Is there keyed access to the stairs at MI-65? | J. Cassidy | Mike Andrews |  |
| 8. | Ventilation | How will the configuration of the ventilation system at MI-65 & target hall affect the ventilation system currently in place a the absorber room and MINOS hall? | J. Cassidy | Elaine McCluskey |  |
| 9. | Radio Communications | Tom Prosapio said that the 2-way radio system works well for the 2 following conditions: 1) in the access shaft from top to bottom 2) in the tunnel from one end to theother, but not from inside the tunnel to the surface. Is it possible to use a repeater (signal booster) in the access shaft so that someone in the tunnel can talk to the surface and vice-versa. This communication ability would be great to have in an emergency. | W. Boettinger | Bob Ducar |  |
| 10. | Air Seal Installation - Galvaneal welding | The air seal in the target hall pit is made of a material by the name of galveneal which galvanized sheet metal. It was mentioned that the air seal is to be welded along the bottom seams. My question is actually two. 1. Is it a good idea to weld on a galvanized material seeing as wehn welding may poisionous gases are produced? (maybe the bottom seam could have a mechnical lock, like is done in ductwork in HVAC work) 2. What would be the expected life of the air seal given that 1) the welded areas are no longer galvanized, 2) corrosion ususally starts in the heat affected zone, 3) the humidity of the area that the welds will be in, 4) the area will probably never be able to be repaired to to the high radiation? | W. Boettinger | Andy Stefanik |  |
| 11. | Magnet List? | Need a list of magnets, with serial numbers & status, that will be installed in NuMI (carrier & pretarget). | W. Smart | Sam Childress |  |
| 12. | Installation of Transporter Rails | How are transporter rails attached to 1/2 inch steel plate on the target access area floor? How many times will the transporter rails be installed & removed? | W. Smart | Jim Hylen & Tom Prosapio |  |
| 13. | MI65 Hardstand blue/green blocks staging | With 304 blocks on hardstand (week 4) are they going to be arranged so first blocks needed (for installation) are available? | W. Smart | Tom Prosapio |  |
| 14. | Pre-Installation Checkout | Develop a plan for certifying magnets before they are delivered into tunnel. Possible checks included: 1. Hi-pot, 2. Flow test, 3. Leack check, 4. Basic electrical (l, r,) | P. Martin | Sam Childress |  |
| 15. | Entry Procedure | Realize that discussion of entry procedure may not be in full agreement with the final "approved" procedure. | B. Ducar |  |  |
| 16. | Daily Work Planning Meetings | The daily work planning meetings should include a short term forecast of "new" work to be started. Knowing of new work a few days in advance can really help to smooth out the installation. | B. Ducar |  |  |
| 17. | Target Chase Liner | The apparent new choice of a galvanite liner for the target chase brings significant safety concerns given its being welded. In the whole, this could really be a big time penalty to near critical path work. Material choice being driven by corrosion for a chase. This is now fundamentally dry & will get quite warm during operation! | B. Ducar |  |  |
| 18. | Roof Panning | Concern that copper pipe from new roof panning to be installed by ragnar benson will clog with calcites & rusticles. This is also a concern for existing panning. | B. Ducar |  |  |
| 19. | Maintainng Cleanliness | Debris must be kept clear of the ? System. What measures will be taken to assure this condition of cleanliness (nuts, bolts, wire, debris)? | E. McCluskey | Greg Lawrence |  |
| 20. | Accomodating RBI to get in for punchlist items | How will this be handled? |  | Tom Prosapio |  |
| 21. | Ventilation System | Should be operatble 2 weeks prior to beneficial occupancy (so we can ? The tunnel) |  | Tom Prosapio |  |
| 22. | Magnet Stands | How heavy are they, and what is the provision for moving them up the slope of the tunnel? |  | Mayling Wong |  |
| 23. | Evacuation of Power Supply Room in Case of Fire and or Smoke | The power supply and RAW water utility room has only one exit to the bottom of the shaft. Egress must be made past the elevator cage to get to the emergency exit stair well. It was noted during the review that there is water sprinkler system in the area that would help suppress fire. There is still a problem with smoke. In case of smoke I would suggest that PPE hoods with air supply be kept in the power supply and RAW water utility rooms. This would enable the personnel to evacutate to the stairwell. | D. Tinsley |  |  |
| 24. | Welded Gaveneal Air Block Seal Between Block Layers | The following two paragraphs are taken from International Zinc Association web page: http://www.iza.com/zwo_org/Applications/Continuous_Galv/030609.htm The AWS specification calls for welds to be made on steel that is free of zinc in the area to be welded. Thus, for galvanized steels, the zinc coating should be removed at least 2.5 to 10 cm (1 - 4 inches) from either side of the intended weld zone and on both sides of the work piece. Grinding back the zinc coating is the preferred and most common method. Burning the zinc away or pushing back the molten zinc from the weld area also are effective. However, while a zinc free weld area is preferred, it is not an absolute requirement. All welding processes produce fumes and gases to a greater or lesser extent. However, galvanized steels will produce added fumes from the vaporized zinc coating. Welders must identify the hazards associated with welding coated and uncoated steel and must be trained to maintain work practices within Occupational Safety and Health Administration (OSHA) regulations. If it is not possible to weld on steel with the zinc coating ground back away from the weld area, OSHA permissible exposure limits (PELs) for zinc oxide and lead may be exceeded. Every precaution, including high-velocity circulating fans with filters, air respirators and fume-extraction systems suggested by AWS, should be employed. Concerns: 1. Welding zinc coated steel will produce undesirable fumes. 2. Welding zinc coated steel will burn away the zinc and the steel will corrode in the weld area. 3. Welding steel sheet will warp the sheet. Recommendations: 1. Hot dip galvanized steel has better corrosion protection than electrolytic galvanized or galvanneal steel sheets. 2. Cost comparison should be made with stainless steel sheet. 3. Slip together connection between the sheets should be made like in the HVAC industry. These connections have a moderately low leak rate. 4. Soft solder can be used to make the connection leak tight in high radiation areas. 5. Construction techniques of the copper roof industry should also be looked at. |  |  |  |
| 25. |  | If the installation of the zero layer will really take a month, we should look at whether ramping up a second shift after the first week would make sense. | Jim Hylen |  |  |
| 26. |  | A rigorous procedure is needed to keep the tunnel floor drains from getting clogged. This should include identification of responsibility and method to accomplish and maintain these. | Sam Childress |  |  |
| 27. |  | At the target region presentation, the plate welding to provide an air seal could potentially have a significant a schedule impact which may not yet be incorporated. Careful understanding of this effort is needed | Sam Childress |  |  |
| 28. |  | Identification of all early stage alignment resource efforts are needed. For an initial period of >/=1 month after target region BO, all alignment people will be committed to accelerator shutdown activities. We should attempt to accomplish all initial alignment requirements prior to BO, | Sam Childress |  |  |
| 29. | Overall presentation | I was somewhat disappointed in the lack of detail presented. This makes it hard to make comments on the nitty-gritty aspects of the installation. In particular, the biggest task of the target pile installation was not described in sufficient detail to allow me to judge as to whether the time estimates are at all realistic. My gut instinct tells me this job will take longer than planned. If there are sufficient crews, and if there is adequate fixtures, etc. then it could go as planned. I understand (from some discussion afterwards) that the plan is to lower two blocks at a time. To go smoothly, this requires at least two people upstairs and at least two downstairs during this process. If there is another separate crew to transport these blocks, and if there are several of the baskets or whatever are being used to transport the blocks, then it might work. But none of this sort of detail was presented. | Phil Martin |  |  |
| 30. | Organization | This is one area where I am please to see a lot of progress, and of course it HAD to be there by now since this effort is really getting underway in less than two months. However, the supervisor/task manager structure still seems a bit thin, especially if, as you told me on Thursday, the expectation is that Tom Prosapio will only be involved till the end of the year or so. I don’t think a floor manager needs to be present on the evening shift, but if not, then the lead task manager needs to be a very capable one and everyone needs to understand his added role of responsibility. Since I believe there is only one task going on second shift, this should be OK. I would worry about not having enough task managers to cover two shifts, with sick leave, vacations, etc. | Phil Martin |  |  |
| 31. | Access Control | The plan of allowing only medically qualified individuals, and of using special access passes, with employee or contractor ID cards left in MI-65 appears to me to be a good solution. Since there will only be a limited number of access passes, this controls the total number of people in the tunnel. The only issue I see is enforcement. People need to understand that they have to treat this as seriously as controlled accesses into accelerator enclosures. | Phil Martin |  |  |
| 32. | 13-Month Installation period | If we are starting installation in Oct ’03 and ending in Aug ’04, what happened to allow the schedule to be shortened by 3 months? Do we have all the tasks? (checkout, hot horn handling, etc.)? | Bruce Baller |  |  |