## Sheet1
DENVER SERVICE CENTER
SUBMITTAL TRACKING FORM
[12 empty] | Revision Date: | 2004-07-07 | Total | % of Total | % of Submitted to Date
PARK NAME |  |  | Death Valley National Park | [10 empty] | 78 | 100% | NA | Number of Material Submittals Required
PACKAGE NO. |  |  | DEVA-500, Cow Creek Maintenance Facilities, Phase 2 | [10 empty] | 76 | 97.44% | 100% | Submitted to Date
CONTRACT NO. |  |  | 1443C8000030904 | [10 empty] | 0 | 0% | 0% | Pending
PROJECT MGR. |  |  | David Ballard | [10 empty] | 32 | 41.03% | 42.11% | Approved
CM Representative |  |  | Alyssa M. Demos | [10 empty] | 43 | 55.13% | 56.58% | Approved with Notations
COR |  |  | Cathleen Malmstrom | [10 empty] | Re-Submittals:
[14 empty] | 1 | 1.282% | 1.316% | Dis-Approved/Re-Submittal Required
[14 empty] | 1 | 100% | NA | Pending Re-Submittals
Supplemental Submittals:
[14 empty] | 0 | NA | NA | Pending Suplemental Submittals
Trans. No. | Item No. | Spec. Section | Para. No. | Description | S | SD | MD | C | CS | W | Date Rec'd by Proj. Sup. | Date Sent to Review Team | No. of Copies to ARG | No. of Copies to DSC | Signed by Reviewer | Signed by COR | Date Rec'd from DSC | Date Sent to Cont. | Apprv'd | Apprv'd with Notations | Dis-Apprv'd/ Resubmit
|  | 02110 | 1.3 | Excavation, Removal, and Handling of Hazardous Materials
NA |  |  |  | Excavation Safety Plan (Submitted under Section 1360) | [5 empty] | x | NA | NA | NA | NA | NA | NA | NA | NA | X
|  | 02120 | 1.4 | Off-Site Transportation and Disposal
|  |  |  | Copies of Manifests Signed by Transporter and Disposal Facility |  |  |  | x
72 |  |  |  | Original Weigh Tickets from Disposal Facility |  |  |  | x |  |  | 2004-06-09 | NA | NA | NA | 2004-06-09 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  |  |  | Evidence that Transport Vehicles and Drivers are Appropriately Licensed and Permitted to Haul Hydrocarbon-Contaminated Waste |  |  |  | x
|  | 02220 | 1.3 | Removal of Building, Pavement, and Structures
|  |  |  | Proposed Methods of Building Demolition | [5 empty] | x
|  |  |  | Schedule for Shutting Off Utility Services | [5 empty] | x
|  | 02220 | 1.6 | Removal of Buildings, Pavements, and Structures
|  |  |  | Project Record Drawings Showing All Abandoned Utilities |  |  |  |  | x
|  | 02320 | 1.2 | Utility Trenching and Backfilling
23 |  |  |  | Procedure for trench dewatering and disposal of fluidized materials removed. | [5 empty] | x | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
23A |  |  |  | Barricading, Shoring, Cribbing, Bracing, and Sloping Precautions | [5 empty] | x | 2003-12-11 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  | 02501 | 1.3 | Testing of Water and Sewer Lines
|  |  |  | Accuracy Certification |  |  |  | x
71 |  |  |  | Testing Information | [5 empty] | x | 2004-06-02 | NA | NA | NA | 2004-06-02 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  | 02502 | 1.2 | Utility Line Marking
21 |  |  |  | Samples: Strips of Tape and Markers | x | [5 empty] | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
21 |  |  |  | Materials Certification |  |  |  | x |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
|  | 02511 | 1.4 | Water Piping and Appurtenances
14 |  |  |  | Manufacturer's Literature and Certificates of Compliance |  |  | x | x |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
14.1 |  |  |  | Manufacturer's Installation Instructions or Guide | [6 empty] | 2003-11-17 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
14.2 |  |  |  | Procedure for cleaning water lines and disposing of fluidized materials removed. | [6 empty] | 2004-06-08 | NA | NA | NA | 2004-06-08 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  | 02517 | 1.2 | Fire Hydrants
Catalog cuts.
|  |  |  | Gradation Analysis for Drainage Aggregate | [5 empty] | x
|  |  |  | Manufacturer's Data |  |  | x
|  |  |  | Certification that Hydrant Complies with AWWA C502-94 |  |  |  | x
|  |  | 1.3 | Fire Hydrants - Closeout Submittals
|  |  |  | Tools |  |  |  |  | x
|  |  |  | Spare Parts |  |  |  |  | x
|  |  |  | Outlet Nozzles |  |  |  |  | x
|  |  |  | Auxiliary Valve Extension Handles |  |  |  |  | x
|  |  |  | Operation and Maintenance Data |  |  |  |  | x
|  | 02620 | 1.2 | Subdrainage
65 |  |  |  | Product Data | [6 empty] | 2004-01-12 | NA | NA | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 | X
65.1 |  |  |  | Product Data - Terra-Tex SD Non-Woven High Strength Geo-Textile | [6 empty] | 2004-02-19 | NA | NA | NA | 2004-02-24 | 2004-02-24 | 2004-02-26 | 2004-03-04 | X
|  | 02725 | 1.2 | Aggregate Base Course
70 |  |  |  | Certified Weight Tickets, One Copy Per Load (Truck No. - Daily Report) |  |  |  | x |  |  | 2004-05-25 | NA | NA | NA | 2004-05-26 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  |  |  | Material Certification, if from Commercial Source |  |  |  | x
|  | 02740 | 1.5 | Asphalt Pavement
68 |  |  |  | Product Information and Mix Design |  |  | x |  |  |  | 2004-01-27 | NA | NA | NA | 2004-02-10 | 2004-02-12 | 2004-02-12 | 2004-02-17 | X
68 |  |  |  | Product Certification |  |  |  | x |  |  | 2004-01-27 | NA | NA | NA | 2004-02-10 | 2004-02-12 | 2004-02-12 | 2004-02-17 | X
68.1 |  |  |  | Weight Slips | [6 empty] | 2004-06-02 | NA | NA | NA | 2004-06-02 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  | 02765 | 1.2 | Traffic Markings
22 |  |  |  | Materials Certificate |  |  |  | x |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  |  | X
22A |  |  |  | Materials Certificate |  |  |  | x |  |  | 2003-11-17 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
|  | 02778 | 1.2 | Concrete Walks, Curbs, and Gutters
26 |  |  |  | Concrete Mix Design |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-17 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  |  |  | Description of Machines Proposed for Concrete Extruding or Slip-Forming | [5 empty] | x
|  | 02785 | 1.4 | Site Stonework
49 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-17 | NA | NA | NA | 2003-11-25 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
49 |  |  |  | Sample: Stone Pavers | x | [5 empty] | 2003-11-17 | NA | NA | NA | 2003-11-25 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
|  |  |  | Sample: Colored pointing mortar and grout. | x
|  |  |  | Sample: Sealant | x
|  | 02821 | 1.3 | Ornamental Gates
61 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-12-11 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  |  | X
61 |  |  |  | Product Data |  |  | x |  |  |  | 2003-12-11 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
|  |  |  | Sample: Color Selection for Polyester Finishes | x
|  | 02846 | 1.2 | Concrete Wheel Stops
10 |  |  |  | Manufacturer's Data, if from a Commercial Source |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
|  | 03300 | 1.3 | Cast-in-Place Concrete
26 |  |  |  | Placing Drawings |  | x |  |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-17 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
26 |  |  |  | Batching and Hauling Plan | [5 empty] | x | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-17 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
26 |  |  |  | Masonry Dowel Location Plan |  | x |  |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-17 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
26A |  |  |  | Rebar Certifications | [6 empty] | 2004-01-12 | NA | NA | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 | X
|  | 04100 | 1.2 | Mortar
|  |  |  | Samples: Dry Mortar Materials; Cured Mortar | x
13 |  |  |  | Materials Certificate |  |  |  | x |  |  | 2003-10-27 | NA | NA | NA | 2003-10-27 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
13 |  |  |  | Test Reports | [5 empty] | x | 2003-10-27 | NA | NA | NA | 2003-10-27 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
|  | 04201 | 1.3 | Masonry Work
|  |  |  | Shop Drawings |  | x
|  |  |  | Samples: Masonry Units | x
|  |  |  | Manufacturer's Literature: Admixtures |  |  | x
28 |  |  |  | Materials Certification |  |  |  | x |  |  | 2003-10-27 | NA | NA | NA | 2003-10-27 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
|  |  |  | Test Reports | [5 empty] | x
28.1 |  |  |  | Proposed Hot and Cold Weather Construction Procedures | [5 empty] | x | 2003-11-17 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
|  |  |  | Description of Grouting Method | [5 empty] | x
|  |  |  | Grout Mix Design |  |  | x
|  | 04720 | 1.3 | Cast Stone
56 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 |  | X
56B |  |  |  | Shop Drawings - Window Type T | [6 empty] | 2004-01-12 | NA | NA | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 | X
56 |  |  |  | Samples: Cast Stone | x | [5 empty] | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 | X
56 |  |  |  | Samples: Colored Mortar | x | [5 empty] | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 | X
|  | 05120 | 1.4 | Structural Steel
62 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-12-11 | 2003-12-12 | 5 | NA | 2004-12-30 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
62 |  |  |  | Manufacturer's Literature: Shop Primer Paint |  |  | x |  |  |  | 2003-12-11 | 2003-12-12 | 5 | NA | 2004-12-30 | 2004-01-13 | 2004-01-13 | 2004-01-15 | X
|  | 05311 | 1.3 | Steel Roof Deck
|  |  |  | Shop Drawings |  | x
|  |  |  | Manufacturer's Literature: Specifications and Load Tables |  |  | x
|  | 05400 | 1.3 | Cold-Formed Metal Framing
|  |  |  | Shop Drawings and Erection Diagrams |  | x
|  |  |  | Mill Certificates |  |  |  | x
|  |  |  | Welder Certificates |  |  |  | x
|  | 05500 | 1.3 | Metal Fabrications
60 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-12-11 | 2003-12-12 | 5 | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  |  | X
|  |  |  | Samples for Each Type and Finish | x
|  | 06100 | 1.2 | Rough Carpentry
|  |  |  | Material Certificates |  |  |  | x
2 |  |  |  | Truss Shop Drawings (CC-118) |  | x |  |  |  |  | 2003-10-07 | 2003-10-31 | 5 | 2 (12-3-03) | 2004-01-06 | 2004-01-22 | 2004-01-26 | 2004-01-26 |  | X
2.1 |  |  |  | Truss Shop Drawings (CC-316) | [6 empty] | 2003-10-07 | 2003-10-31 | 5 | 3 (12-3-03) | 2004-02-04 | 2004-02-12 | 2004-02-12 | 2004-02-17 |  | X
2.2 |  |  |  | Truss Shop Drawings (CC-118 and CC-316) | [6 empty] | 2004-02-02 | 2004-02-06 | 5 | NA | 2004-02-09 | 2004-02-12 | 2004-02-12 | 2004-02-17 | X
2.3 |  |  |  | Simpson Hardware and Hilti Anchoring Systems | [6 empty] | 2004-02-02 | 2004-02-06 | 5 | NA | 2004-02-09 | 2004-02-12 | 2004-02-12 | 2004-02-17 |  | X
|  | 06102 | 1.2 | Wood Treatment
25 |  |  |  | Manufacturer's Written Recommendations for Application of Wood Treatments | [6 empty] | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
25A |  |  |  | Manufacturer's Written Recommendations for Application of Wood Treatments | [6 empty] | 2004-06-10 | NA | NA | NA | 2004-06-10 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  | 06402 | 1.3 | Interior Architectural Woodwork
63 |  |  |  | Product Data |  |  | x |  |  |  | 2004-01-07 | 2004-01-09 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 |  | X
63 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2004-01-07 | 2004-01-09 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 |  | X
63 |  |  |  | Hardware | [6 empty] | 2004-01-07 | 2004-01-09 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 | X
63 |  |  |  | Sample: Shop-Applied Opaque Finishes | x | [5 empty] | 2004-01-07 | NA | NA | NA | 2004-01-09 | 2004-01-22 | 2004-01-26 | 2004-01-26 | X
|  |  |  | Sample: Plastic Laminates | x
|  |  |  | Sample: Lumber and Panel Products with Shop-Applied Opaque Finish | x
|  |  |  | Sample: Plastic-Laminate-Clad Panel Products | x
|  |  |  | Sample: Corner Pieces | x
|  |  |  | Sample: Exposed Cabinet Hardware and Accessories | x
63A |  |  |  | Product Certificates |  |  |  | x |  |  | 2004-06-09 | NA | NA | NA | 2004-06-09 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
63 |  |  |  | Qualification Data | [5 empty] | x | 2004-01-07 | 2004-01-09 | 5 | NA | 2004-01-14 | 2004-01-22 | 2004-01-26 | 2004-01-26 | X
|  | 07100 | 1.4 | Cold Fluid-Applied Waterproofing
11 |  |  |  | Product Data |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
|  |  |  | Shop Drawings |  | x
11B |  |  |  | Installer Certificates |  |  |  | x |  |  | 2004-04-26 | NA | NA | NA | 2004-04-27 | 2004-05-06 | 2004-05-06 | 2004-05-06 | X
|  |  |  | Product Test Reports |  |  |  |  | x
11B |  |  |  | Sample Warrenty |  |  | x |  |  |  | 2004-04-26 | NA | NA | NA | 2004-04-27 | 2004-05-06 | 2004-05-06 | 2004-05-06 | X
|  | 07190 | 1.2 | Water Repellents
46 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-17 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 |  | X
46A |  |  |  | Certification of VOC | [6 empty] | 2003-11-25 | NA | NA | NA | 2003-11-25 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
|  |  |  | Quality Assurance Submittals - Close-Out |  |  |  | x
|  |  |  | Operation and Maintenance Data - Close-Out |  |  |  |  | x
|  |  |  | Warranty - Close-Out |  |  |  |  | x
|  | 07210 | 1.3 | Building Insulation
9B |  |  |  | Insulation Certification |  |  |  | x |  |  | 2004-05-25 | NA | NA | NA | 2004-05-26 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
9 |  |  |  | Product Data |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  |  | X
9A |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 | X
|  | 07260 | 1.2 | Vapor Retarder
24 |  |  |  | Manufacturer's Installation Instructions and Recommendations |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
|  | 07600 | 1.2 | Flashing and Sheet Metal
69 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2004-04-21 | 2004-04-22 | 5 | NA | 2004-04-27 | 2004-05-05 | 2004-05-06 | 2004-05-06 | X
69 |  |  |  | Samples: Sheet Metal Material | x | [5 empty] | 2004-04-21 | 2004-04-22 | 6 | NA | 2004-04-28 | 2004-05-05 | 2004-05-06 | 2004-05-06 | X
69 |  |  |  | Manufacturer's Literature |  |  | x |  |  |  | 2004-04-21 | 2004-04-22 | 5 | NA | 2004-04-27 | 2004-05-05 | 2004-05-06 | 2004-05-06 | X
|  | 07610 | 1.3 | Sheet Metal Roofing
67 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2004-01-12 | 2004-01-16 | 5 | NA | 2004-02-05 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
67 |  |  |  | Samples: Sheet Metal Panel and Accessories | x | [5 empty] | 2004-01-12 | NA | NA | NA | 2004-01-13 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
67 |  |  |  | Manufacturer's Literature |  |  | x |  |  |  | 2004-01-12 | 2004-01-16 | 5 | NA | 2004-02-05 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
|  | 07900 | 1.3 | Sealants
15 |  |  |  | Manufacturer's Technical Data and Application Instructions |  |  | x |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
15 |  |  |  | Samples: Sealant Colors | x | [5 empty] | 2003-10-20 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
|  | 08100 | 1.3 | Aluminum Doors
1 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
1.1 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-11-25 | 2004-12-01 | 5 | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  | X
1 |  |  |  | Product Data |  |  | x |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
1.1 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-25 | 2004-12-01 | 5 | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  | X
43A |  |  |  | Samples: Finishes | x | [5 empty] | 2004-02-26 | NA | NA | NA | 2004-02-02 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 08110 | 1.3 | Steel Doors and Frames
3 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
3 |  |  |  | Manufacturer's Catalog Cuts and Installation Recommendations |  |  | x |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
3 |  |  |  | Door Schedule | [5 empty] | x | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
|  | 08210 | 1.3 | Architectural Wood Flush Doors
4.1 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2004-03-30 | 2004-04-01 | 5 | NA | 2004-04-12 | 2004-04-21 | 2004-04-27 | 2004-04-27 |  | X
4 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  | 08361 | 1.5 | Sectional Overhead Doors
|  |  |  | Product Data |  |  | x
12 |  |  |  | Shop Drawings: Wiring Diagrams | [6 empty] | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
12A |  |  |  | Framing and Pad Details and lift Clearance Track | [6 empty] | 2004-03-17 | NA | NA | NA | 2004-03-30 | 2004-03-31 | 2004-03-31 | 2004-04-08 | X
|  |  |  | Sample: Frame | x
|  |  |  | Sample: Panel | x
12B |  |  |  | Installer Certificates |  |  |  | x |  |  | 2004-06-02 | NA | NA | NA | 2004-06-02 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
12B |  |  |  | Manufacturer's Certificates |  |  |  | x |  |  | 2004-06-02 | NA | NA | NA | 2004-06-02 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  | 08520 | 1.3 | Aluminum Windows
1 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
1.1 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-11-25 | 2004-12-01 | 5 | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  | X
1 |  |  |  | Product Data |  |  | x |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
1.1 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-25 | 2004-12-01 | 5 | NA | 2004-01-13 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  | X
43A |  |  |  | Samples: Finishes | x | [5 empty] | 2004-02-26 | NA | NA | NA | 2004-02-02 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 08553 | 1.5 | Wood Windows
42 |  |  |  | Shop Drawings |  |  | x |  |  |  | 2003-11-09 | 2003-11-13 | 4 | NA | 12/12/2003 (Sent back to ARG - 12/31/03) | 2004-01-12 | 2004-01-12 | 2004-01-14 |  | X
43 |  |  |  | Manufacturer's Literature |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 12/12/2003 (Sent back to ARG - 12/31/03) | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
43 |  |  |  | Test Reports | [5 empty] | x | 2003-11-10 | 2003-11-14 | 5 | NA | 12/12/2003 (Sent back to ARG - 12/31/03) | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
43 |  |  |  | Sample: Colors of Exterior Aluminum Finish | x | [5 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 12/12/2003 (Sent back to ARG - 12/31/03) | 2004-01-13 | 2004-01-13 | 2004-01-15 |  |  | X
43A |  |  |  | Sample: Colors of Exterior Aluminum Finish | [6 empty] | 2004-02-26 | NA | NA | NA | 2004-02-02 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 08710 | 1.2 | Finish Hardware
18 |  |  |  | Hardware Schedule | [5 empty] | x | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-17 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
|  |  |  | Templates |  | x
|  | 08710 | 1.4 | Finish Hardware - Closeout Submittals
|  |  |  | Operating Tools |  |  |  |  | x
|  |  |  | Keys |  |  |  |  | x
|  |  |  | Operation and Maintenance Data |  |  |  |  | x
|  | 09251 | 1.3 | Gypsum Wallboard
17 |  |  |  | Manufacturer's Technical Literature and Installation Instructions |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  |  | X
17A |  |  |  | Manufacturer's Technical Literature and Installation Instructions |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 |  | X
|  | 09310 | 1.6 | Ceramic Tile
50 |  |  |  | Samples | x | [5 empty] | 2003-12-11 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
50 |  |  |  | Manufacturer's Literature | x | [5 empty] | 2003-12-11 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
50 |  |  |  | Certification | [6 empty] | 2003-12-11 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  | 09310 | 1.6 | Ceramic Tile - Closeout Submittals
|  |  |  | Extra Stock | x
|  |  |  | Maintenance Data | x
|  | 09650 | 1.2 | Resilient Flooring
58 |  |  |  | Samples: Floor Covering Material and Base Material | x | [5 empty] | 2003-12-11 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  | 09650 | 1.5 | Resilient Flooring - Closeout Submittals
|  |  |  | Maintenance Manuals |  |  |  |  | x
|  |  |  | Extra Stock |  |  |  |  | x
|  | 09680 | 1.2 | Carpeting
59 |  |  |  | Samples: Carpeting | x | [5 empty] | 2003-12-11 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
|  | 09680 | 1.3 | Carpeting - Closeout Submittals
|  |  |  | Extra Stock |  |  |  |  | x
|  |  |  | Maintenance Data |  |  |  |  | x
|  | 09901 | 1.4 | Painting
66 |  |  |  | Material List | [5 empty] | x | 2004-02-05 | NA | NA | NA | 2004-02-17 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
66 |  |  |  | Manufacturer's Information |  |  | x |  |  |  | 2004-02-05 | NA | NA | NA | 2004-02-17 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
66 |  |  |  | Sample: Manufacturer's Color Charts | x | [5 empty] | 2004-02-05 | NA | NA | NA | 2004-02-17 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
66 |  |  |  | Sample: Paint Applied on Same Surface Material as will be Used in the Work | x | [5 empty] | 2004-02-06 | NA | NA | NA | 2004-02-17 | 2004-02-18 | 2004-02-18 | 2004-02-19 |  | X
66A |  |  |  | Manufacturer's Information |  |  | x |  |  |  | 2004-03-17 | NA | NA | NA | 2004-03-30 | 2004-03-31 | 2004-03-31 | 2004-04-08 | X
66A |  |  |  | Sample: Paint Applied on Same Surface Material as will be Used in the Work | x | [5 empty] | 2004-03-17 | NA | NA | NA | 2004-03-30 | 2004-03-31 | 2004-03-31 | 2004-04-08 | X
|  | 09901 | 1.11 | Painting - Closeout Submittals
|  |  |  | One Quart of Each Type and Color of Paint Used |  |  |  |  | x
|  |  |  | Maintenance Data |  |  |  |  | x
|  | 10200 | 1.4 | Metal Louvers
44 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-17 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 |  | X
|  |  |  | Sample: Each Required Finish | x
44 |  |  |  | Shop Drawings |  |  | x |  |  |  | 2003-11-17 | NA | NA | NA | 2003-11-20 | 2003-12-01 | 2003-12-01 | 2003-12-02 |  | X
|  | 10440 | 1.2 | Interior Signs
45 |  |  |  | Product Data | [6 empty] | 2003-11-17 | NA | NA | NA | 2003-12-29 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  |  | X
45A |  |  |  | Product Data | [6 empty] | 2004-01-19 | NA | NA | NA | 2004-01-21 | 2004-01-22 | 2004-01-26 | 2004-01-26 |  | X
|  |  |  | Samples | x
|  | 10800 | 1.2 | Toilet and Bath Accessories
5 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
|  | 10800 | 1.7 | Toilet and Bath Accessories - Closeout Submittals
|  |  |  | Keys |  |  |  |  | x
|  |  |  | Operation and Maintenance Data |  |  |  |  | x
|  |  |  | Toilet and Bath Accessory Schedule Listing | [5 empty] | x
|  | 11452 | 1.2 | Kitchen Appliances
6 |  |  |  | Product Data |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
|  | 11458 | 1.2 | Telescoping Access Ladder - Deleted
8 |  |  |  | Product Data |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
|  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
|  | 12500 | 1.3 | Window Treatments
7 |  |  |  | Product Data: Horizontal Louver Blinds |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
7 |  |  |  | Shop Drawings |  |  | x |  |  |  | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 |  | X
7 |  |  |  | Samples: Horizontal Louver Blinds | x | [5 empty] | 2003-10-07 | NA | NA | NA | 2003-10-22 | 2003-10-27 | 2003-10-27 | 2003-10-31 | X
7.1 |  |  |  | Schedule: Horizontal Louver Blinds | [5 empty] | x | 2004-06-09 | NA | NA | NA | 2004-06-09 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  |  |  | Maintenance Data - Close-Out |  |  |  |  | x
|  | 13800 | 3.1 | Fuel Island Upgrade - Closeout Documentation
27 |  |  |  | Manufacturer's Installation Checklists - UST System Equipment | [6 empty] | 2003-10-27 | 2003-10-31 | 5 | NA | 2004-01-23 | 2004-02-03 | 2004-02-04 | 2004-02-05 |  | X
Manufacturer's Data
Piping Closure Report
Certification
Manufacturer's Installation and Setup Checklists - Electronic Overfill Prevention Device
Permits and Certifications
As-Built Construction Drawings
Piping Test Results
Amended Tank Registration Form
Release of Liens
|  | 13800 | 3.1 | Fuel Island Upgrade
27.1 |  |  |  | 20,000 Gallon, Double Wall, Multi-Compartment, Fiberglass Fuel Tank - XERXES | [6 empty] | 2004-04-13 | 2004-04-13 | NA | Electronic | 2004-04-14 | 2004-04-19 | 2004-04-19 | 2004-04-21 |  | X
|  |  |  | Double Wall Tank Brochure, XERXES | [6 empty] | 2004-04-13 | 2004-04-13 | NA | Electronic | 2004-04-14 | 2004-04-19 | 2004-04-19 | 2004-04-21 | X
|  |  |  | Double Wall Warranty, XERXES | [6 empty] | 2004-04-13 | 2004-04-13 | NA | Electronic | 2004-04-14 | 2004-04-19 | 2004-04-19 | 2004-04-21 | X
27.2 |  |  |  | Shop Drawings | [6 empty] | 2004-06-14 | 2004-06-18 | NA | 5 | 2004-06-23 | 2004-06-24 | 2004-06-28 | 2004-07-08 | X
|  | 15010 | 3.2 | Mechanical General Provisions
NA |  |  |  | List of Mechanical Equipment Manufacturer's, Material Suppliers, and Subcontractors - Within 2 Months of NTP | [5 empty] | x | NA | NA | NA | NA | NA | NA | NA | NA | X
|  | 15060 | 1.4 | Piping and Accessories
|  |  |  | Shop Drawings (As-Builts) |  | x
29 | Plumbing |  |  | Manufacturer's Data - Cast Iron Pipe, Copper Tubing, Pipe Insulation, Roll Jacketing, Insulation Covers, Insulated Fitting Covers and Jacketing, |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-02 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
29.1 | HVAC |  |  | Manufacturer's Data - Copper Tubing |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  |  |  | Test Reports | [5 empty] | x
29A |  |  |  | Brazing and Welding Certifications |  |  |  | x |  |  | 2004-06-09 | NA | NA | NA | 2004-06-09 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
|  | 15100 | 1.3 | Valves (Included in Plumbing Submittal)
29 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-02 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  | 15140 | 1.3 | Supports, Hangers, Anchors, and Sleeves
32 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
32 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
32 |  |  |  | Details of Hangers, Anchors, and Supports | [6 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 15150 | 1.3 | Access Doors in General Construction
|  |  |  | Shop Drawings (As-Builts) |  | x
33 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-11-18 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 15170 | 1.3 | Electric Motors (Included in Sectional Overhead Door Submittal)
12 |  |  |  | Motor Efficiencies |  |  | x |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
12 |  |  |  | Certified Dimensions, Insulation Class, NEMA Frame Size, Materials of Construction, Base Details, and Mounting Details |  | x |  |  |  |  | 2003-10-07 | 2003-10-31 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
|  | 15190 | 1.3 | Systems Identification
|  |  |  | Shop Drawings - Close-Out (Verify with BCS) |  | x
34 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-18 | 2004-03-03 | 2004-03-03 | 2004-03-04 |  | X
|  |  |  | Maintenance Manuals - Close-Out |  |  |  |  | x
|  | 15240 | 1.3 | Vibration Isolation and Seismic Restraints - Deleted
35 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-24 | 2004-03-03 | 2004-03-03 | 2004-03-04 |  |  | X
|  |  |  | Shop Drawings |  | x
|  | 15250 | 1.3 | Insulation
36 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-18 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  |  |  | Details of Sheet Metal Boxes |  | x
|  | 15400 | 2.3 | Domestic Water Systems
30 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2003-12-02 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
30A |  |  |  | Instantaneous Water Heater Information | [6 empty] | 2004-01-19 | NA | NA | NA | 2004-01-21 | 2004-01-22 | 2004-01-26 | 2004-01-26 | X
|  | 15440 | 2.1 | Plumbing Fixtures
31 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 | X
|  | 15470 | 2.1 | Fire Protection Systems
64 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2004-01-07 | 2004-01-09 | 5 | NA | 2004-01-20 | 2004-02-03 | 2004-02-04 | 2004-02-05 |  |  | X
64A |  |  |  | Product Data CC-118 and CC-316 | [6 empty] | 2004-02-26 | 2004-02-27 | 5 | NA | 2004-03-29 | 2004-03-31 | 2004-03-31 | 2004-04-06 |  | X
64A |  |  |  | Plans CC-118 and CC-316 | [6 empty] | 2004-02-26 | 2004-02-27 | 5 | NA | 2004-03-29 | 2004-03-31 | 2004-03-31 | 2004-04-06 |  | X
64A |  |  |  | Calculations CC-118 and CC-316 | [6 empty] | 2004-02-26 | 2004-02-27 | 5 | NA | 2004-03-29 | 2004-03-31 | 2004-03-31 | 2004-04-06 |  | X
|  | 15733 | 1.3 | Direct/Indirect Evaporative Coolers
37 CC118 |  |  |  | Manufacturer's Data (MasterCool CC-118) | [6 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 |  | X
37 CC316 |  |  |  | Manufacturer's Data (Split Cooling System CC-316) | [6 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 |  |  | X
37.1 |  |  |  | Manufacturer's Data (10-Ton Trane Heat Pump Unit CC-316) | [6 empty] | 2004-04-02 | 2004-04-02 | Electronic | NA | 2004-04-25 | 2004-05-05 | 2004-05-06 | 2004-05-06 | X
37.2 |  |  |  | Honeywell Thermostat Alternate | [6 empty] | 2004-04-21 | 2004-04-22 | 3 | NA | 2004-05-05 | 2004-06-24 | 2004-06-24 | 2004-06-28 |  | X
37 |  |  |  | Thermostat | [6 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
37 |  |  |  | Unit Heater | [6 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 15800 | 1.3 | Ductwork
38 |  |  |  | Product Data - Duct Seal, Elbows, Spiral Pipe, Flexible Connectors, 40 Degree Fittings |  |  | x |  |  |  | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-24 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
38A |  |  |  | Shop Drawings (CC-118) |  | x |  |  |  |  | 2004-02-26 | 2004-02-27 | 5 | NA | 2004-03-17 | 2004-03-31 | 2004-03-31 | 2004-04-08 |  | X
38.1 |  |  |  | Shop Drawings (CC-118) | 38.2 |  |  |  | Shop Drawings (CC-118) | 38.3 |  | 2004-04-01 | 5 | NA | 2004-04-25 | 2004-05-05 | 2004-05-06 | 2004-05-06 |  | X
38.2 |  |  |  | Shop Drawings (CC-316) | [6 empty] | 2004-04-05 | 2004-04-06 | Electronic | NA | 2004-05-25 | 2004-06-24 | 2004-06-24 | 2004-06-28 | X
38.3 |  |  |  | Shop Drawings (CC-316) | [6 empty] | 2004-04-21 | 2004-04-22 | 3 | NA | 2004-05-06 | 2004-05-18 | 2004-05-19 | 2004-05-20 | X
|  |  |  | Proposed Method of Mounting | [5 empty] | x
|  | 15880 | 1.3 | Air Filters and Cleaners
39 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-20 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
39 |  |  |  | Materials of Construction, Joining and Fastening Details for Filters, Frames, and Holding Assemblies | [6 empty] | 2003-11-10 | NA | NA | NA | 2003-11-20 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
39 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-20 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  | 15910 | 1.3 | Dampers
40 |  |  |  | Regulator Information (Not required.) | [6 empty] | 2003-11-10 | 2003-11-14 | 5 | NA | 2004-02-23 | 2004-03-03 | 2004-03-03 | 2004-03-04 | X
|  |  |  | Performance Data |  |  | x
Smoke Damper and Combination Fire/Smoke Damper Schedule (As-Builts)
|  | 15940 | 1.3 | Air Outlets and Inlets
41 |  |  |  | Manufacturer's Data |  |  | x |  |  |  | 2003-11-10 | NA | NA | NA | 2003-11-18 | 2004-03-03 | 2004-03-03 | 2004-03-04 |  |  | X
41 |  |  |  | Manufacturer's Data (Approved by Park - Field Memo Dated 1-20-04) |  |  | x |  |  |  | 2004-01-20 | NA | NA | NA | NA | NA | NA | NA |  | X
|  |  |  | Sample: Product Accessories | x
|  |  |  | Sample: Color and Finish | x
|  |  |  | Schedule of Sizes and Model Numbers (As-Builts) | [5 empty] | x
|  | 15990 | 1.5 | Mechanical Systems Balancing
42 |  |  |  | Information for LA Air Balance Co., Inc. | [6 empty] | 2003-11-10 | NA | NA | NA | 2003-11-18 | 2004-03-03 | 2004-03-03 | 2004-03-04 |  | X
|  |  |  | Excerpts from Recent Previous Final Balancing Reports | [5 empty] | x
|  |  |  | Calibration Certifications |  |  |  | x
|  | 15990 | 3.4 | Mechanical Systems Balancing - Balancing Report
|  |  |  | Balancing Report - Close-Out | [5 empty] | x
|  | 16010 | 3.2 | Electrical General Provisions
NA |  |  |  | List of Electrical Equipment Manufacturer's, Material Suppliers, and Subcontractors - Within 2 Months of NTP | [5 empty] | x | NA | NA | NA | NA | NA | NA | NA | NA | X
|  | 16030 | 1.4 | Vibration Isolation and Seismic Restraints - Deleted
|  |  |  | Product Data |  |  | x
|  |  |  | Shop Drawings |  | x
|  |  |  | Seismic Restraint Calculations | [5 empty] | x
|  |  |  | Field Inspection Report | [5 empty] | x
|  | 16110 | 1.2 | Raceways and Boxes
51 |  |  |  | Product Data: Modular Wiring Systems |  |  | x |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 | X
|  |  |  | Shop Drawings: Modular Wiring Systems (As-Builts) |  | x
|  | 16120 | 1.4 | 600V Wire and Cable
52 |  |  |  | Product Data | [6 empty] | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 | X
|  |  |  | Field Test Reports - Close-Out | [5 empty] | x
|  | 16140 | 1.4 | Wiring Devices
53 |  |  |  | Product Data |  |  | x |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  |  | X
53A |  |  |  | Weatherproof Motion Sensor and Photocell | [6 empty] | 2004-03-10 | 2004-03-12 | 5 | NA | 2004-03-16 | 2004-03-31 | 2004-03-31 | 2004-04-08 | X
|  |  |  | Shop Drawings (As-Builts) |  | x
|  | 16462 | 1.4 | Power Line Conditioners (Deleted Per Park's Direction - 4/29/04)
57 |  |  |  | Product Data |  |  | x |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  |  | X
|  |  |  | Factory Test Reports | [5 empty] | x
|  |  |  | Shop Drawings |  | x
|  | 16470 | 1.4 | Panelboards
54 |  |  |  | Product Data |  |  | x |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
54 |  |  |  | Shop Drawings: Branch Panelboards |  | x |  |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
54 |  |  |  | Shop Drawings: Distribution Panels |  | x |  |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  | X
|  | 16500 | 1.4 | Luminaires and Accessories
55 |  |  |  | Product Data |  |  | x |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  |  | X
55 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-12-10 | 2003-12-12 | 5 | NA | 2004-01-06 | 2004-01-13 | 2004-01-13 | 2004-01-15 |  |  | X
55A |  |  |  | Fixture Type D for Wet Locations | [6 empty] | 2004-03-10 | 2004-03-12 | 5 | NA | 2004-03-16 | 2004-03-31 | 2004-03-31 | 2004-04-08 |  | X
55A |  |  |  | Fixture Type N | [6 empty] | 2004-03-10 | 2004-03-12 | 5 | NA | 2004-03-16 | 2004-03-31 | 2004-03-31 | 2004-04-08 |  | X
|  | 16680 | 1.4 | Grounding Systems
|  |  |  | Field Test Report - Close-Out | [5 empty] | x
|  | 16720 | 1.5 | Fire Alarm and Detection System
|  |  |  | Minutes of Supplier's Meeting with Fire Department | [5 empty] | x
16 |  |  |  | Product Data |  |  | x |  |  |  | 2003-11-05 | 2003-11-07 | 5 | NA | 2003-11-19 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  | X
16 |  |  |  | Shop Drawings |  | x |  |  |  |  | 2003-11-05 | 2003-11-07 | 5 | NA | 2003-11-19 | 2004-01-15 | 2004-01-15 | 2004-01-15 |  | X
|  | 17155 | 1.3 | General Outdoor Backbone Cabling Practices
|  |  |  | Manufacturer's Product Data Sheets |  |  | x
|  | 17156 | 1.3 | Outdoor Copper Twisted Pair Backbone Cabling
47 |  |  |  | Manufacturer's Product Data Sheets |  |  | x |  |  |  | 2003-11-17 | 2003-12-01 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
47.1 |  |  |  | Cat 5E Protection Products - Protector Pack 505E | [6 empty] | 2004-04-26 | 2004-04-30 | 5 | NA | 2004-05-07 | 2004-05-18 | 2004-05-19 | 2004-05-20 | X
|  | 17157 | 1.3 | Outdoor Optical Fiber Backbone Cabling
48 |  |  |  | Manufacturer's Product Data Sheets |  |  | x |  |  |  | 2003-11-17 | 2003-12-01 | 5 | NA | 2003-12-12 | 2004-01-05 | 2004-01-05 | 2004-01-08 |  | X
47.2 |  |  |  | Cat 5E Protection Products - Test Summary | [6 empty] | 2004-06-28 | NA | NA | NA | 2004-06-28
|  | 17160 | 1.3 | General Indoor Horizontal Cabling Practices
|  |  |  | Manufacturer's Product Data Sheets |  |  | x
|  | 17161 | 1.3 | Indoor Unshielded Twisted Pair Horizontal Cabling: 4 Pair
3 |  |  |  | Manufacturer's Product Data Sheets |  |  | x |  |  |  | 2004-04-26 | 2004-04-30 | 5 | NA | 2004-05-07 | 2004-05-18 | 2004-05-19 | 2004-05-20 | X

## Sheet2
2007-02-23
PLEASE SEND OVERNIGHT TO THE FOLLOWING:
THANK-YOU!
ELLEN LITTLE, x2221
DSC - PM
TRANSMITTAL: