| PRIORITY ONE: Developing a competent workforce for co-occurring disorders |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategy(-ies) | Action(s) |  | Manager¹ | Implementer² | Expected Outcomes |  | Benchmarks | Completion Date (Estimated) |
| Strategy 1.1 Assessment of current workforce, including clinical supervision | Action 1.1.1 Identify key competencies |  | Tom Rehak and Rosie Anderson-Harper | COSIG Steering Committee | List of clinical and cultural competencies |  | Develop list | October, 2005 |
|  | Action 1.1.2 Assess workforce competencies, gaps, capacity availability and diversity |  | Jan Soucie, Mark Stringer & Kathy Carter | Office of Human Resources, Division of CPS & ADA, and CCMHC’s | Detailed analysis of workforce demographics, skill sets, experience and geographic distribution |  | Gather information from various sources Analyze information to determine system strengths and weaknesses. | October, 2005 |
|  | Action 1.1.3 Assess workforce attitudes and readiness to change, including organizational attitudes |  | Ashley Haden | Missouri Institute of Mental Health | Survey results measuring willingness and readiness to change of current workforce |  | Conduct survey Survey analysis | Ongoing |
| Strategy 1.2 Develop supportive infrastructure (Policy) | Action 1.2.1 Identify components of current infrastructure (i.e. – policies, procedures, statutes, credentialing, certification etc. |  | Jan Soucie, Marsha Buckner , Tom Rehak and Laurent Javois | Office of Human Resources, Divisions of CPS & ADA, COSIG Steering Committee workgroup | Comprehensive list of things that are working, need modification and development |  | Develop list | October , 2005 |
|  | Action 1.2.2 Identify potential incentives for infrastructure support |  | Jan Soucie, Marsha Buckner & Tom Rehak | Office of Human Resources, Divisions of CPS & ADA | Knowledge of incentives for infrastructure support |  | Meet for purpose of identifying potential incentives | December, 2005 |
|  | Action 1.2.3 Develop change matrix |  | Jan Soucie, Diane McFarland & Michael Couty | Office of Human Resources, Divisions of CPS & ADA | Implement change matrix to effect infrastructure support |  | Based on information gleaned from actions 1.2.1 and 1.2.2, meet to develop change matrix | February, 2006 |
| Strategy 1.3 Develop training | Action 1.3.1 Identify and develop academic approaches to training |  | Quentin Wilson, Dorn Schuffman, Pat Stilen, Debbie McBaine and Andy Homer | Department of Higher Education, COSIG Steering Committee, Department of Mental Health, Mid-America ATTC | Each University in the state will have a curriculum which will have the capacity to provide trained/credentialed staff |  | COSIG identifies required skill sets. Meet with Department of Higher Education to identify need and request assistance. Joint development of curriculum. | January, 2006 |
|  | Action 1.3.2 Identify and develop non-academic approaches to training |  | Pat Stilen, Debbie McBaine and Mark Miller | Mid-America ATTC and Divisions of CPS & ADA | List of resources that could provide non-academic ongoing education and training |  | Meet to develop training approaches not involving academic institutions. | June, 2005 |
|  | Action 1.3.3 Institute process that will facilitate ongoing supervision |  | Pat Stilen, Debbie McBaine and Mark Miller | Mid-America ATTC, Divisions of CPS & ADA | Development of curriculum to support supervision utilizing co-occurring competencies |  | Meetings to develop ongoing training for clinical supervision. | August, 2005 |
| Progress to Date |  | Barriers and/or Situational Changes |  |  |  | Immediate Next Steps (including potential technical assistance needs) |  |  |
| Practice Guidelines for the Treatment of Adults with Co-Occurring Substance Use Disorders and Mental Illness completed by Missouri in September, 2002 including agency and provider workforce competencies. Have completed initial current practice survey. Have developed “barriers and incentives report”. Have completed initial ATTC workforce survey. |  | Fiscal resources may not be currently available to support widespread training. |  |  |  | Request training and TA on best practices for clinical supervision strategies for community-based services with this population. Request information and possible TA consult from the State of Arizona. Request information on physician training for working with this population (possible TA request for consult with Fred Osher or Sars Maxwell. |  |  |

¹  The Manager is the individual responsible for coordinating each action.

²   The Implementer is the individual (or entity) responsible for carrying-out each action.

| PRIORITY TWO: Create an integrated service system infrastructure |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Strategy(-ies) | Action(s) | Manager | Implementer | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 2.1 Broaden and strengthen advocacy base and public education/awareness | Action 2.1.1 Develop talking points and public information tools for key stakeholders (administrators, providers, consumers, families, media and policymakers) | Andy Homer, Laurent Javois, Joe Yancey and Office of Public Affairs | COSIG Steering Committee | Secure commitment from leadership (i.e.- division directors, legislators, governor’s office, MHA, NAMI, FOA and CCMHC’s | Meetings to develop talking points and public information/education strategies. | March, 2005 |
|  | Action 2.1.2 Develop a communication plan | Laurent Javois | COSIG Steering Committee | A clear, viable and effective plan for communicating the need for, required components, and public benefit of effective treatment for co-occurring disorders | Communication plan tool has been completed. Meet to develop and identify content and strategy for utilizing communication tool. | March, 2005 |
|  | Action 2.1.3 Target education and information sessions to key stakeholders first (legal system, medical colleagues, universities, criminal justice, legislators) | Laurent Javois, Joe Yancey and Jeanne Henry | COSIG Steering Committee and Office of Public Affairs | All stakeholders, interested parties, and the general public will be informed of the state’s initiative to address co-occurring disorders | Identify key stakeholder group Set up meeting with identified stakeholders to provide information and secure buy-in. | May, 2005 |
| Strategy 2.2 Improve collaboration and coordination of care | Action 2.2.1 Identify current barriers to collaboration and coordination and provide guidance and incentives for working together as a team | Laurent Javois, Mark Stringer, and Gary Lyndaker | COSIG Steering Committee, Divisions of CPS and ADA, Office of Information Systems | A comprehensive list of potential barriers – i.e.(policies, procedures, fiscal, information systems etc. of the current environment | COSIG committee meets with Division representatives to identify potential barriers to effective implementation. | July, 2005 |
|  | Action 2.2.2 Develop quality and outcome reports that allow measurement of effectiveness including a process evaluation | Pat Stilen and Heather Gotham | Mid-America ATTC and MIMH | Information that will provide the capacity to ascertain progress toward collaboration and coordination of care on an ongoing basis as well as inform implementers regarding overall implementation | Meet to identify required indicators. Select method(s) for gathering required data on indicators. Develop reports. Analyze reports. Provide feedback. | January, 2006 |
|  | Action 2.2.3 Develop standardized assessment and treatment planning documents, effective business agreements and capacity for supportive consult | Andy Homer, Laurent Javois, Rosie Anderson-Harper, Joe Parks, John Long | COSIG Steering Committee, Divisions of CPS and ADA and Office of Administration | Clinical documentation, memorandums of understanding, contracts and consultation which will facilitate effective care and treatment for the consumer with co-occurring disorders | Build on prior work to develop standardized clinical documents between two divisions. Convene work group to develop standardized clinical documents and identify necessary business agreements. | January, 2006 |
|  | Action 2.2.4 Increase collaboration and coordination of care with primary care physicians | Sharon Burnett and Joe Parks | COSIG Steering Committee, Missouri Hospital Association | Primary care physicians and community-based AOD and mental health providers will have a greater capacity to work in concert to meet the needs of the consumer with co-occurring disorders | Identify components for effective coordination. Identify best method for communication of identified components. Convene work group to develop plan for pursuing collaboration. | March, 2006 |
| Strategy 2.3 Create an engaging and welcoming environment | Action 2.3.1 Review intake process and contrast with principles of a welcoming environment for treatment | Laurent Javois, Mark Stringer, Kathy Carter, Rebecca Carson | COSIG Steering Committee, CCMHC’s, Office of Quality Management and ADA Provider Work Group | Intake staff are comfortable, empathetic and optimistic with consumers presenting with co-occurring disorders and those consumers feel welcomed through program literature, intake procedures and payment mechanisms | Review current intake process for community providers. Identify desired process for intake and encourage/incentivize Implementation with community providers. | June, 2005 |
|  | Action 2.3.2 Define the components of a culturally competent environment and implement throughout the system | Derek Willis, Laurent Javois, Joe Yancey | DMH Cultural Competence Work Group, COSIG Steering Committee | Consumers with co-occurring disorders will receive culturally relevant care that addresses and respects language, customs, values, mores and has the capacity to respond to the unique family, culture, traditions and gender concerns of the consumer | Incorporate the work that has been done through the Office of Multi-cultural Affairs into the training curriculum as a component of workforce development. | June, 2005 |
|  | Action 2.3.3 Establish focus groups of consumers, families and other stakeholders to gather input | Christine Squibb, Karen Maddox, Nancy Howard, Tyrone Moore, Edward Allen | COSIG Steering Committee, Office of Consumer Affairs, Coalition of Community Mental Health Centers, NAMI, Mental Health Association, Primary Consumers | Quality input will be received from consumers, families and other stakeholders and incorporated into the planning and implementation of a responsive system for addressing consumers with co-occurring disorders | Identify the information to be gleaned. Identify the questions that will provide the desired information. Coordinate with consumer groups, Federation of Advocates and others to establish focus groups. | June, 2005 |

| PRIORITY TWO: Create an integrated service system infrastructure |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Strategy(-ies) | Action(s) | Manager¹ | Implementer² | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 2.4 Identify and provide early Intervention to children, adolescents and young adults with mental illness and substance abuse. | Action 2.4.1 Request departmental office of prevention to develop actions | Charles Williams | Department of Mental Health Office of Prevention |  |  |  |
|  | Action 2.4.2 |  |  |  |  |  |
|  | Action 2.4.3 |  |  |  |  |  |
| Strategy 2.5 Improve data capacity | Action 2.5.1 Develop standardized screening and assessment, including universal language | Andy Homer | Heather Gotham, Divisions of CPS and ADA | Accurate identification of individuals with co-occurring disorders | Review prior work toward development of standardized documents. | January, 2006 |
|  | Action 2.5.2 DMH providers have the ability to access historical treatment data at time of intake | Andy Homer | Department Office of Information Systems | Accurate identification of individuals with co-occurring disorders | Initial meeting with OIS to identify strategies. Develop method for accessing information. | January, 2006 |
|  | Action 2.5.3 State level coordination and sharing of information | Andy Homer, Laurent Javois and Pam Leyhe | Department Office of Information Systems, COCMHC’s, Division of Medical Services | Accurate identification of individuals with co-occurring disorders | Initial meeting with OIS, DMS, and provider representatives to identify strategies. | January, 2006 |

| Progress to Date | Barriers and/or Situational Changes | Immediate Next Steps (including potential technical assistance needs) |
| --- | --- | --- |
| Currently piloting screening and assessment tool. Completed current practice survey. Completed barriers and incentives report. Practice Guidelines for the Treatment of Adults with Co-Occurring Substance Use Disorders and Mental Illness completed by Missouri in September, 2002. | Coordination and collaboration between pilot sites. Lack of standardized tools currently used across overall system. | Facilitation of planning process to develop system-wide plan for rollout of integrated infrastructure. Press release on policy academy and state action plan. Brief constituencies and other stakeholders. Request consult from Hawaii regarding their welcoming attitude strategies. |

¹  The Manager is the individual responsible for coordinating each action.

²   The Implementer is the individual (or entity) responsible for carrying-out each action.

| PRIORITY THREE: Enhance Service Capacity |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategy(-ies) | Action(s) |  | Manager | Implementer | Expected Outcomes |  | Benchmarks | Completion Date (Estimated) |
| Strategy 3.1 Increase current service capacity | Action 3.1.1 Determine model for service delivery for consumers in different quadrants of New York model |  | COSIG Steering Committee | Rosie Anderson-Harper, Tom Rehak and Joe Parks | Consumers will receive appropriate type, level and intensity of services |  | Review and research literature on various service models by quadrant type. | December, 2005 |
|  | Action 3.1.2 Determine needed capacity vs. existing capacity (indicators such as wait times, waiting lists, census at existing facilities) |  | COSIG Steering | Divisions of Comprehensive Psychiatric Services and Alcohol and Drug Abuse (CPS & ADA) | Identification of the required service capacity to support an integrated service system infrastructure |  | Convene a workgroup to project required service capacity. Use information to design future budget decision items. | December, 2005 |
|  | Action 3.1.3 Identify actions to address needed capacity |  | Michael Couty and Diane McFarland | Division staff of ADA and CPS, Departmental Office of Administration, | Plan to increase service capacity to level required to support identified service need |  | Feed information gleaned to division directors. | April, 2006 |
|  | Action 3.1.4 Identify barriers to accessing appropriate services |  | COSIG Steering Committee | Divisions of ADA and CPS, CCMHC’s and ADA Provider Workgroup | Detailed listing of policies, procedures, fiscal resources, capacity issues etc. that serve as impediments for consumer access |  | Workgroup to gather data on barriers through focus groups, surveys and other means. | February, 2006 |
| Strategy 3.2 Increase consumer involvement | Action 3.2.1 Gather information related to client satisfaction, services received, use the input/feedback received (e.g., focus groups in neutral locations) |  | Heather Gotham | Missouri Institute of Mental Health, CCMHC’s and ADA Provider Workgroup | Input from primary consumers that will inform the overall process |  | Develop survey. Conduct survey. Analyze survey results. | October, 2005 |
|  | Action 3.2.2 Continue having consumer representation on planning committees using evidence-based model |  | Andy Homer | COSIG Steering Committee | Meaningful quality participation from consumers and families that will inform overall process |  | Research and review literature on evidence-based best practices for quality consumer participation. | March, 2005 |
|  | Action 3.2.3 Assure that consumer leadership is involved in trainings both as trainers and as participants |  | Pat Stilen | Mid-America ATTC | Training will be directly informed by consumer’s personal experience |  |  | May, 2005 |
|  | Action 3.2.4 Assess number of dual recovery groups that exist in Missouri and explore ways to offer support, including technical assistance on best practices for dual recovery groups |  | Pat Stilen | Mid-America ATTC | Identification and development of dual recovery groups which will function as quality community self-help components of the overall service delivery system |  | Identify dual recovery groups in Missouri. Set up communication with these entities to discuss potential support. | April, 2005 |
|  | Action 3.2.5 Survey providers and other key stakeholders to determine service needs, priorities and suggestions for improving system |  | Heather Gotham | Missouri Institute of Mental Health | Comprehensive feedback from provider community to inform overall process |  | Develop survey. Conduct survey. Analyze results. | June, 2005 |
|  | Action 3.2.6 Provide information and support on other consumer involvement models (e.g., peer mentoring, self help, consumer advisors, warm line), possibly using other states as models |  | Andy Homer and Laurent Javois | COSIG Steering Committee | The process will be informed of the array of options available, including best practices, for consumer involvement |  |  | June, 2005 |
| Strategy 3.3 Implement Community Psychiatric Rehabilitation Program (CPRP) Enhancements | Action 3.3.1 Implement existing plan (including outreach, substance abuse counselors, education groups, group therapy) |  | Tom Rehak | Division of CPS and Division of Medical Services | Necessary components of an integrated service delivery system will be in place |  | Division of Medical Services signs off on plan. Training for community provider staff. Implement enhancements. | June, 2005 |
|  | Action 3.3.2 Expand CPRP philosophy to include focus on substance use treatment |  | Tom Rehak and Joe Parks | Division of CPS and CCMHC’s | Rehabilitation philosophy inherent in CPRP will include rehabilitation and recovery from substance use |  | Convene workgroup to develop strategies for infusing substance use treatment into the philosophy. | June, 2005 |
|  | Action 3.3.3 Evaluate impact of who is being served, look for ways to provide services for those who are not being served |  | Heather Gotham and Andy Homer | Missouri Institute of Mental Health, Department Office of Quality Management and Divisions of CPS and ADA | Analysis of plan implementation will provide information for improving services. Reduction in utilization of high end services (i.e.- ER, inpatient, etc.) |  | Use epidemiological data to estimate number of eligible consumers not being served. Provide training on outreach and engagement. Implement. | December, 2005 |
|  | Action 3.3.4 Continue to review and revise the CPRP program as new information is available |  | Tom Rehak | Division of CPS and Division of Medical Services | Continuous Quality Improvement of CPRP program to better serve the needs of the co-occurring consumer |  |  | Ongoing |
| Strategy 3.4 Implement trauma services | Action 3.4.1 Select service models for Missouri |  | Rosie Anderson- Harper | Department Trauma Workgroup | Missouri will utilize Missouri service providers will have trauma service models that are appropriate for the various subsets of the co-occurring consumer population |  |  | May, 2005 |
|  | Action 3.4.2 Initiate training based on the treatment model-include the treatment philosophy, beginning and advanced training modules |  | Rosie Anderson-Harper and Pat Stilen | Department Trauma Workgroup, Mid-America ATTC and Community Services (CPS) | Missouri service providers will be competent in providing trauma informed services for the co-occurring population |  | Trauma workgroup designs trauma training. Incorporate trauma training modules into general training for co-occurring. | August, 2005 |
|  | Action 3.4.3 Develop quality measures and implement a process for monitoring the provision of trauma informed services |  | Rosie Anderson-Harper and Rebecca Carson | Department Trauma Workgroup and Department Office of Quality Management | Capacity to monitor service providers for implementation and quality of trauma informed services |  | Convene workgroup to identify indicators for quality in trauma services. Meet with Office of Quality Management to insert indicators into certification process. | January, 2006 |
| Strategy 3.5 Alternative Services and Providers | Action 3.5.1 Identify non-traditional and faith-based providers that help consumers with co-occurring disorders |  | Andy Homer | COSIG Steering Committee and Division of ADA | A comprehensive listing of non-traditional and faith-based providers that utilize a treatment model for co-occurring disorders |  |  | June, 2005 |
|  | Action 3.5.2 Review models and services to determine which are appropriate for DMH consumers |  | Andy Homer | COSIG Steering Committee | A listing of non-traditional and faith-based providers who could provide services to DMH consumers |  | Convene workgroup to review alternative provider’s models/services. | August, 2005 |
|  | Action 3.5.3 Utilize and expand existing telemedicine capacity |  | Joe Parks | COSIG Steering Committee, Divisions of CPS and ADA | Telemedicine will be available in all parts of the state, especially those areas experiencing a shortage of physicians |  | Identify current areas where telemedicine is available. | March, 2006 |
| Progress to Date |  | Barriers and/or Situational Changes |  |  |  | Immediate Next Steps (including potential technical assistance needs) |  |  |
| Both the divisions of CPS and ADA have completed general service capacity assessments. Trauma is considered a departmental priority and a trauma workgroup has been established. |  | General Revenue funding has continued to decrease over the past several years. Community-based service providers are currently operating at capacity and still only meeting a relatively small percentage of the target population. |  |  |  | Obtain approval by Medicaid for CPRP enhancements. COSIG steering committee to develop working relationship with the Trauma workgroup. Initiate rollout of Procovery philosophy. Staff training for CPRP enhancements. Technical assistance consult with Connecticut regarding their recovery-based system. TA consult with other states that have done a good job with consumer involvement and participation in planning and implementation. |  |  |

| PRIORITY FOUR: Developing Financing Options |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategy(-ies) | Action(s) |  | Manager | Implementer | Expected Outcomes |  | Benchmarks | Completion Date (Estimated) |
| Strategy 4.1 Assess utilization of existing resources | Action 4.1.1 Identify current resources and how they are being used. |  | Steve Reeves, Marsha Buckner and Laurent Javois | Divisions of CPS and ADA. COSIG Steering Committee | Updated service matrix, tailored to co-occurring population. Modify system based on gaps. |  |  | April, 2005 |
|  | Action 4.1.2 Assist programs with adaptation of services and billing to better serve consumers with co-occurring disorders |  | Andy Homer and Laurent Javois | Divisions of CPS and ADA, CCMHC’s and COSIG Steering Committee | Streamlined services within an agency. Efficient use of service providers per consumer, i.e., one case manager. Overhead costs reduced for programs. |  |  | October, 2005 |
|  | Action 4.1.3 Maximize use of outpatient services to decrease utilization of inpatient services |  | Andy Homer and Laurent Javois | COSIG Steering Committee | Reduced inpatient days for consumers diagnosed with co-occurring mental illness and substance use |  |  | Ongoing |
| Strategy 4.2 Pursue other funding partners, grants, and sources | Action 4.2.1 Explore joint funding of services with DOC and other state agencies, other jurisdictions (e.g., counties, cities, Mil tax). |  | Andy Homer | Office of the Director, Divisions of CPS and ADA and COSIG Steering Committee | Costs for treatment will be shared by other state systems involved with the consumer. |  |  | Ongoing |
|  | Action 4.2.2 Explore public and private grant opportunities |  | Heather Gotham | Missouri Institute of Mental Health, Divisions of CPS and ADA, COSIG Steering Committee | Viable grants will be identified and applications submitted |  |  | Ongoing |
|  | Action 4.2.3 Explore community action organizations such as United Way, Salvation Army, and other funding streams such as Medicare |  | Andy Homer | COSIG Steering Committee | Exploratory meetings with community action organizations and other potential community partners for the purpose of procuring additional sources of funds for co-occurring services |  |  | June, 2005 |
|  | Action 4.2.4 Pursue legislation to include substance use treatment parity, increase appropriations, or develop appropriation specific to co-occurring services |  | Diane McFarland and Michael Couty | Divisions of CPS and ADA | Substance use treatment will have insurance parity. The department will include a budget decision item funding co-occurring treatment services |  |  | May, 2006 |
| Strategy 4.3 Efficient Utilization of Medicaid | Action 4.3.1 Implement CPRP enhancement service codes to reduce inpatient services |  | Tom Rehak | Division of CPS | Reduced use of POS service codes |  |  | September, 2005 |
|  | Action 4.3.2 Develop a service code for outreach/engagement in the CSTAR (Comprehensive Substance Treatment and Rehabilitation) and CPRP programs. |  | Tom Rehak and Mark Stringer | Divisions of CPS and ADA | Increasing services that can be matched with Medicaid funding will enable more individuals to be served |  |  | October, 2005 |
|  | Action 4.3.3 Insure that Medicaid eligible consumers are enrolled in the Medicaid program |  | Andy Homer and Laurent Javois | Coalition of Community Mental Health Centers, ADA Provider Workgroup and COSIG Steering Committee | More eligible consumers will be enrolled. |  |  | Ongoing |
| Strategy 4.4 Cost Benefit Analysis | Action 4.4.1 Conduct cost benefit analysis or utilize data from a similar analysis conducted in a comparable state |  | Andy Homer | COSIG Steering Committee | A competent analysis of the overall cost (including societal costs) of serving the target population with the current service system contrasted with the overall cost of serving the target population in a co-occurring enhanced service system |  |  | January, 2006 |
| Progress to Date |  | Barriers and/or Situational Changes |  |  |  | Immediate Next Steps (including potential technical assistance needs) |  |  |
| CPRP enhancements have been developed which should bring additional resources to bear on the target population. New data system being developed by the department (CIMOR) which should be complimentary to data gathering and analysis. |  | Medicaid agreement on CPRP enhancements has not yet occurred. Current state budget environment does not present an optimistic view of procuring additional appropriations. |  |  |  | Request TA for cost-benefit analysis Gain Medicaid agreement on CPRP enhancement Brief governor and governor’s staff on policy academy and resulting plan. Technical Assistance with developing a public education and awareness strategy. |  |  |

¹  The Manager is the individual responsible for coordinating each action.

²   The Implementer is the individual (or entity) responsible for carrying-out each action.