Vermont Department of Environmental Conservation

Retail Gasoline Sector Environmental Results Project

Quality Assurance Project Plan

June 28, 2004

Vermont Department of Environmental Conservation

103 S. Main Street

Waterbury, VT 05671-0404

Project Manager: Peter Marshall

103 S. Main St./West Office Bldg.

Waterbury, VT 05671-0404

(802) 241-3868 phone

(802) 241-3296 fax

peter.marshall@anr.state.vt.us

# A	PROJECT MANAGEMENT

## A1.	Approval Sheet

____________________________________________	_______________________

Peter Marshall, Project Manager				Date

Vermont Department of Environmental Conservation

Chief, Hazardous Waste Management & Prevention Section

____________________________________________	_______________________

Winslow Ladue, Quality Assurance Officer			Date

Vermont Department of Environmental Conservation

## A2.	Table of Contents

A	PROJECT MANAGEMENT	1

A1.	Approval Sheet	1

A2.	Table of Contents	2

A3.	Distribution List	3

A4.	Project/Task Organization	3

A5.	Problem Definition/Background	4

Rationale for initiating the project.	4

Objectives of the project.	5

Regulatory information, applicable criteria and action limits.	6

A6.	Project/Task Description	6

Project overview.	6

Project summary and work schedule.	7

Geographic focus.	9

Resource and time constraints.	9

A7.	Quality Objectives and Criteria	9

Detailed performance measures.	9

Quality objectives.	9

A8.	Special Training/Certification	10

A9.	Documents and Records	11

Report format/information.	11

Document/record control.	11

Other records/documents.	11

Storage of project information.	11

Backup of electronic files.	12

B	DATA GENERATION AND ACQUISITION	12

B1.	Sampling Process Design (Experimental Design)	12

B2.	Sampling Methods	13

B3.	Sample Handling and Custody	13

B4.	Analytical Methods	13

B5.	Quality Control	13

Preparation of data collection instruments.	13

Training.	13

Crosschecking data.	13

Data anomalies.	14

Data entry.	14

B6.	Instrument/Equipment Testing, Inspection and Maintenance	14

B7.	Instrument/Equipment Calibration and Frequency	14

B8.	Inspection/Acceptance for Supplies and Consumables	14

B9.	Non-Direct Measurements  (I.e., Secondary Data) 	14

Key resources/support facilities needed.	15

Determining limits to validity and operating conditions.	16

B10.	Data Management	16

C	ASSESSMENT/OVERSIGHT	16

C1.	Assessment and Response Actions	16

C2.	Reports to Management	16

D	DATA REVIEW AND EVALUATION	17

D1.	Data Review, Verification and Validation	17

D2.	Verification and Validation Methods	17

D3.	Evaluating Data in Terms of User Needs	18

## A3.	Distribution List

Each person listed on the approval sheet and each person listed under Project/Task Organization will receive a copy of this Quality Assurance Project Plan (QAPP).  Individuals taking part in the project may request additional copies of the QAPP from personnel listed under Section A4.

This document has been prepared according to the United States Environmental Protection Agency publication EPA Requirements for Quality Assurance Project Plans dated March 2001 (QA/R-5).

## A4.	Project/Task Organization

Personnel involved in project implementation are listed in Table 1, and shown as an organization chart in Figure 1.

| Table 1: Project Implementation Personnel |
| --- |
| Individual | Role in Project | Organizational Affiliation |
| Peter Marshall | Project Manager | VT DEC |
|  | QA Manager/Officer | VT DEC |
| Marc Roy | Supervisor | VT DEC |
| Ted Unkles | UST Program Coordinator | VT DEC |
| June Middleton | Outreach/Compliance | VT DEC |
| Andrew Shively | Inspections/Verification | VT DEC |
| Susan Thayer | Inspections/Verification | VT DEC |
| Position to be hired | Data Management and Project Support | VT DEC |
| ERP Contractor | Support on Project Design and Implementation (Detailed below) | TBD |
| VT DEC IT Group | IT Support/Database Mgt | VT DEC |

The VT DEC Project Manager will be responsible for the following activities:

- Conduct outreach with regulated industry and internal/external stakeholders

- Coordinate with Contractor

- Maintain official, approved QAPP

- Develop revised QAPP

- Issue quarterly and annual reports to U.S. EPA

Contractor (to be determined (TBD)) will be responsible for the following activities:

- Assist with project design

- Develop statistical methodology

- Assist VT DEC Information Technology (IT) staff in the development of necessary data systems and hardware infrastructure

- Assist VT DEC staff in review and presentation of outreach materials

- Assist VT DEC staff in stakeholder outreach, especially concerning the benefits of ERP from experiences of other states

- Assist VT DEC staff in analysis of project data and presentation of results

- Review data and provide QA/QC

The participating facilities will be responsible for submitting self-certification materials and, if applicable, returning to compliance.

Figure 1:  Project Organizational Chart

See attached project organizational chart.

## A5.	Problem Definition/Background

### Rationale for initiating the project.

There are approximately 2,600 Underground Storage Tanks (USTs) at approximately 1,100 facilities in Vermont, and the majority of these facilities are in the Retail Gasoline Sector (RGS). In the 1960s and 1970s, frequent releases from USTs resulted in extensive soil and groundwater contamination that required costly remedial actions. In response to this growing problem, the federal Underground Storage Tank program was developed (a part of the Resource Conservation and Recovery Act of 1976 (42 U.S.C. §§ 6991 et. seq.).

The early priorities of this program were to establish: (1) a national inventory of UST facilities through a registration requirement; and (2) minimum environmentally protective standards for UST systems and a milestone by which all subject facilities would need to meet these standards (December 22, 1998). While the rules and programmatic requirements did go beyond these two priorities to areas such as spill and overfill protection, requiring upgrades that would prevent catastrophic releases (such as through sudden failure of a tank or piping system due to corrosion) was the primary focus.

Now that the UST system upgrade milestone has passed (and VT facilities have achieved compliance with this requirement), the focus of the program has turned to the operation and maintenance (O&M) of UST systems. Unlike the hardware upgrades of the 1998 deadline, which were a “one-time” event to attain and sustain compliance, O&M compliance is a daily, ongoing task. This difference applies to ascertaining compliance as well – while a single inspection (or third party evaluation) will provide enduring documentation of compliance with the upgrade requirements, compliance with O&M requirements is continually changing at all 1,100 facilities.

While the goals of the UST Program have remained constant – to prevent releases by requiring effective design, operation, and maintenance of UST systems – the focus of the program has changed as the sources of the worst risks have changed. The change in focus of the program has led to a need for more frequent compliance evaluations for the O&M requirements, which, when neglected, are now the greatest source of risk of release.

The Vermont UST Program, with current resources, can inspect approximately 100 facilities per year.  At this rate, it takes over ten years to inspect each facility once. Significant new resources are not expected in the future from either EPA or the Vermont Legislature.  In addition, to justify additional resources, a program must be able to document that the work that it does is effective at solving the problem it is expected to address. With existing resources and programmatic operations, the program is: (1) unable to inspect facilities for compliance with O&M requirements at a level that would adequately protect the environment; and (2) unable to gather sufficient program performance data to show either where the problems lie in O&M compliance or that any of the existing or future approaches to solving these problems is effective.

### Objectives of the project.

This project is designed to improve environmental results by the intended outcomes of: reducing the threat of releases of petroleum hazardous wastes and materials to groundwater (a significant source of drinking water in Vermont) and soils through enhanced compliance with UST, RCRA, UIC, and sector-specific BMPs; reducing air emissions through enhanced Stage I & II vapor recovery compliance; and reducing hazardous waste generation through the use of the BMPs.

The ERP model will allow for the measurement of annual compliance progress for the entire sector, with several environmental laws. This proposed ERP model consists of an initial round of inspections of a statistically valid number of facilities, sector-based multimedia outreach and education, a mandatory multi-media self-certification on a sector-specific form, a processing fee, random inspections to confirm self certifications, and data analysis that will result in statistically valid compliance reports to document project performance. Targeted inspections will be used to promote submission of self-certifications as well as assure compliance.

Where facilities indicate they are not in compliance with all applicable regulations under this project, or where inspections find non-compliance, a return to compliance plan will be required.  All non-compliance will be documented.  When self-certifications indicate non-compliance, the facility will be required to submit a return-to-compliance schedule to the VT DEC. Random and targeted inspections will be used to confirm return to compliance at selected facilities.  These schedules will be tracked in the project database.  When inspections identify facility non-compliance, the VT DEC will respond by both informing facility personnel on-site and sending a letter documenting the non-compliance and requiring a return to compliance by a date certain.

This proposed Environmental Results Project will include the following components:

- A workbook that includes Best Management Practices (BMPs) and compliance requirements.  The workbook is a guide to compliance with the self-certification form mentioned below;

- A BMP checklist for use by the facility in assessing the status of compliance, pollution prevention, and other health and safety practices;

- A compliance self-certification form that the facility owners and operators are required to complete, sign and return. On the form, the facility owners and operators must certify the current compliance status of the facility and acknowledge that the facility must comply with all applicable environmental laws;

- A Return to Compliance form that is used to address compliance problems identified in the self-certification process that cannot be corrected at that time. The form establishes a return to compliance schedule and deadline for compliance. This form must be signed and returned when a facility cannot certify full compliance with all applicable regulatory requirements;

- Workshops to provide technical and compliance assistance to facility owners and operators, and to provide training on the requirements of the ERP process;

- Inspections by the VT DEC to confirm the accuracy of the certifications and compliance with the applicable environmental regulations; and

- Ongoing technical and compliance assistance by telephone, on-site assistance (as resources allow), and a project-specific web page with FAQs and additional resources.

### Regulatory information, applicable criteria and action limits.

This project focuses on priority environmental issues by targeting an industry sector that is present statewide with significant potential for environmental releases and emissions. The project is intended to improve compliance within the sector with requirements of four federally-delegated programs: UST, RCRA generator requirements, the Clean Air Act (CAA) Stage I & II requirements, and the Safe Drinking Water Act (SDWA) UIC requirements.

This project would establish a sector-specific, cross-media workbook covering regulatory as well as Best Management Practices (BMPs). The purpose of the BMPs would be to encourage facilities to go beyond compliance to reduce waste, pollution, and emissions. This project would encourage the regulated community to achieve reduced compliance costs by addressing all compliance and environmental issues at once through cross-media BMPs (that lead to compliance) rather than narrowly focusing on whatever problem was identified during the last regulatory inspection.

This project will build on “lessons learned” from the last decade of searching for ways to measure prevention efforts by using a mechanism (ERP) that specifically measures results. The project is likely to produce quantifiable reductions in hazardous waste generation as well as quantifiable improvements in compliance with all four prevention programs. The goal of reducing actual spills and leaks may not be quantifiable because of the time lag between a spill or leak and its detection.

## A6.	Project/Task Description

### Project overview.

This project will allow the VT DEC to explore whether an approach modeled upon the Environmental Results Program (ERP) can help achieve these goals, while improving regulatory cost-effectiveness.   The Environmental Results Program (ERP) is an innovative approach to solving high-priority environmental problems in industry sectors largely comprised of small businesses.   The ERP concept combines technical assistance, self-certification, inspections, and statistically based performance measurement in order to reduce environmental impacts of business.

The promise of ERP is that it will cost-effectively reduce environmental impacts of small businesses that may present a substantial cumulative environmental risk.  Businesses targeted so far by ERP include gas stations, auto salvage yards, auto body and mechanical repair shops, dry cleaners, and printers.  ERP can help environmental agencies identify previously unknown facilities, measure performance, increase regulatory efficiency, and help improve overall environmental performance.  ERP is in part designed to help facilities that want to comply but don’t understand their requirements, and evidence suggests that ERP can motivate firms to comprehensively review their environmental performance and take needed action to come into compliance and adopt best practices.

### Project summary and work schedule.

This project's major tasks and timeline are outlined in the table below.

Table 2:  Schedule of Major Project Tasks

| Task/Milestone | Task Description | Start Date | End Date |
| --- | --- | --- | --- |
| Stakeholder Outreach | Outreach to internal and external stakeholders (including targeted facilities) about the project. | 10/15/04 | 09/30/05 |
| Goals identification | Finalize the goals of this project, upon which metrics will be based | 10/15/04 | 12/30/04 |
| Develop Logic Model | Develop a logic model with stakeholder involvement. Logic model can assist in development of metrics and data needs. | 10/15/04 | 1/15/05 |
| Measures identification | Development of metrics to be tracked by this project. | 12/30/04 | 3/30/05 |
| Prepare legislation | Prepare draft legislation for (1) generic ERP enabling legislation for agency (not necessary for this ERP, but helpful), and (2) fee legislation to cover program costs after grant period | 10/15/04 | 12/1/04 |
| Revise UST Regulations | Draft language for mandatory self-certification for all UST facilities (or all UST facilities in the RGS) | 10/15/04 | 12/15/04 |
| Formal APA Rule Revision Process | Average timeframe for selective rule revisions is 6 months | 1/1/05 | 7/1/05 |
| Facility identification | Determine the exact characteristics of facilities to be targeted, and compile a list of facilities from reliable sources. | 10/30/04 | 12/30/04 |
| Statistical methodology | Development of a statistical methodology to drive performance measurement and analytical tasks. | 1/1/05 | 3/1/05 |
| Data input & management | Development and implementation of an approach to cost-effectively inputting and managing ERP data, including primary and secondary data. Primary data consists of data from inspection reports and facility forms (including self-certification forms). Secondary data sources include lists of facilities from regulatory and private-sector databases. | 11/1/04 | 6/30/06 |
| QAPP finalization & approval | Finalize QAPP based upon results of the measures identification, statistical methodology, and data management tasks. Primary data collection will not occur before relevant parts of the QAPP are finalized and approved by EPA. | 3/1/05 | 5/1/05 |
| Baseline inspections | Inspections at facilities to establish a performance baseline. Facilities selected at random from the entire targeted population, based upon sample design from statistical methodology. | 5/1/05 | 7/1/05 |
| Workbook and Certification Form Finalization | Finalization of workbook, outreach and assistance materials, web resources, and certification forms. | 3/1/05 | 7/1/05 |
| Facility assistance/Outreach | Delivery of compliance/technical assistance to facilities, which is expected to take the form of workbooks, fact sheets and/or workshops. | 7/1/05 | 10/31/05 |
| Self-certification | Implementation of a mandatory facility self-certification approach. Self-certification refers to the submission of a legally binding record of a facility’s compliance and beyond-compliance practices. | 9/1/05 | 10/31/05 |
| Self-Certification Deadline | Self-Certification and RTC forms due | 10/31/05 | 10/31/05 |
| Analysis of Self-Certification Data | Analysis of Self-Certification data with primary purpose of identifying opportunities for selective follow-up (next step). | 11/1/05 | 12/15/05 |
| Selective follow-up | Selective follow-up with self-certifying facilities, based upon analysis of self-certification data. Targeted follow-up may include phone calls, inspections and enforcement. | 12/15/05 | 3/15/06 |
| Post-certification inspections | Inspections at facilities to establish whether sector performance measures (and other measures) have changed since the baseline. Inspection data also used to cross-check self-certification data at inspected facilities. Facilities selected at random from the entire targeted population, based upon sample design from statistical methodology. | 4/15/06 | 5/15/06 |
| Data analysis | Analysis of baseline, self-certification, and post-certification data to understand change in facility performance and overall outcomes of interest. Assessment of project efficiency. | 5/15/06 | 7/15/06 |
| Preparation of Final Project Report | Draft and finalize final project report. | 8/15/06 | 10/15/06 |
| Reporting to EPA | Reporting shall include quarterly, annual and final reports. | 12/30/04 | 9/30/06 |

### Geographic focus.

This is a statewide project for the state of Vermont.

### Resource and time constraints.

## A7.	Quality Objectives and Criteria

### Detailed performance measures.

This project is primarily interested in the following draft performance measures.  Note that one of the tasks of this project involves revisiting and reaffirming/revising these performance measures.

Improved compliance with UST, RCRA, CAA Stage I & II, and SDWA UIC Rules

Improved facility understanding of UST O&M requirements as measured by facility self-certification accuracy

Delivery of at least five outreach workshops in different areas of state

Delivery of at least 1,200 multi-media compliance guides for sector

Development of a well-documented methodology for transfer to other sectors/states

Reduced hazardous waste generation as measured by a reduced need to empty sumps and spill buckets, and reduced air emissions by increased compliance with vapor recovery requirements.

Reduced incidence of petroleum product in sumps, spill buckets, interstitial space – such incidence is the equivalent of a system operating without spill and overfill protection (because they are already full or have inadequate sensor placement) or without secondary containment.

### Quality objectives.

Quality objectives for these performance measures will be developed as part of the Measures Identification and Statistical Methodology tasks.  Specific quality objectives for these measures as a group (and, if necessary, individually) will be provided in the anticipated revision to the QAPP.

This revision to the QAPP will ensure that the quality objectives for these performance measures are appropriate for the decisions to be made based upon those measures.  This determination will take into account best practices for similar projects and resources available for this project.  In part, the Project Manager will rely upon EPA's Generic Guide to Statistical Aspects of Developing and Environmental Results Program (2003) for advice in making decisions related to the optimizing the following aspects of data quality for this project:

Precision

Bias

Representativeness

Completeness

Comparability

Sensitivity (if applicable)

## A8.	Special Training/Certification

The VT DEC and the selected ERP Contractor (TBD) will develop and deliver mandatory and voluntary training sessions to key parties to ensure quality data collection, to the extent practicable.

Mandatory intensive in-person training sessions will be delivered to the following individuals to ensure quality data collection:

inspectors who will be collecting baseline and post-certification data

data-entry personnel who will be processing data from inspections and self-certification responses

QA/QC personnel (if any additional training is needed to familiarize them with the project)

Individuals who will be compiling the database containing the universe of facilities

Each session will cover proper data collection and QA procedures.  Training will be augmented by debriefing personnel shortly after their tasks have begun, to correct and clarify appropriate practices.

Voluntary, intensive, in-person training sessions will be offered to the self-certifying facilities.  Facilities will also be provided with clear written instructions on how to prepare and submit data.

The Project Manager is responsible for ensuring that all personnel involved with data generation (including state personnel, contractors, and partners) have the necessary QA training to successfully complete their tasks and functions.  The Project Manager will document attendance at all training sessions.  Attendance records for voluntary trainings may not include names, given privacy/confidentiality concerns.

The Project Manager is also responsible for ensuring the self-certification materials sent to facilities clearly document how facilities should properly prepare and submit their data.

## A9.	Documents and Records

### Report format/information.

The format for all data reporting packages will be consistent with the requirements and procedures used for data validation and data assessment described in this QAPP.

### Document/record control.

The recording media for the project will be paper, electronic, and photographic.  The project will implement proper document control procedures for all.  For instance, hand-recorded data records will be taken with indelible ink, and changes to such data records will be made by drawing a single line through the error with an initial by the responsible person.  The Project Manager will have ultimate responsibility for any and all changes to records and documents. Similar controls will be put in place for electronic records and both digital and film-based photographic records.

The VT DEC Quality Assurance Officer shall retain all updated versions of the QAPP and be responsible for distribution of the current version of the QAPP.  The VT DEC Quality Assurance Officer and the VT DEC Project Manager will approve annual updates.  The Project Manager shall retain copies of all management reports, memoranda, and all correspondence between the VT DEC and all project personnel identified in A4.

### Other records/documents.

Other records and documents that will produced in conjunction with this project include:

- Inspection checklists and reports

- Self-certification forms

- Return-to-compliance forms

- Non-applicability forms

- Enforcement documentation

- Facility outreach materials, including workbook, fact sheets, brochures, etc.

- Revised QAPP

- Readiness reviews (see below)

- Data handling reports

- Quarterly and annual progress reports to EPA

- Project final report (to include discussion of QA issues encountered, and how they were resolved)

### Storage of project information.

Project information will be stored: (1) in paper files located at the VT DEC offices in Waterbury, VT; (2) in electronic files in various locations according to VT DEC standard operating practices; (3) audio and video tapes located at the VT DEC offices in Waterbury, VT; and (4) photographs located at the VT DEC offices in Waterbury, VT.  All project records shall be retained for three years or longer as determined by agency records retention policies and procedures.

### Backup of electronic files.

This section describes the specific data management process, tracing the path of the data from their generation to their final use or storage.

Many of the VT DEC data files are located on a central file server located on the Agency network, which is behind the Agency firewall. The file server houses production data for many of the Agency’s programs, specifically those programs that send data to US EPA. The file server also houses program-related files.

All ANR servers are all located in a secure, environmentally controlled server room, and attached to separate UPS devices and tape backup systems. Tapes are made, stored, and rotated on a daily, monthly, and yearly cycle, with tape storage located in a separate State facility off-site. Each server platform is equipped with RAID controllers as an additional means of fault tolerance.

Only network and database administrators and their supervisor(s) have access to the server room through a lock and key mechanism. Administrator user IDs and passwords to the servers are only know to the administrators. User IDs and passwords are assigned to all staff who require access to all applications running on the servers. No separate userid/passwords are required for the various applications on the servers since the Agency employs a single network login approach.

# B	DATA GENERATION AND ACQUISITION

## B1.	Sampling Process Design (Experimental Design)

A key task in this project will be to develop a sound statistical methodology for collecting and analyzing facility data, in order to draw inferences related to the selected performance measures.  The major quality objective will be to collect representative data that truly reflect the conditions of the target population of facilities. Facility data is of three types:  (1) statistical inspection data, which will be collected by trained VT DEC inspectors from randomly sampled facilities; (2) judgmental inspection data, based on inspections targeted from inconsistent responses to self-certification questions; and (3) self-certification data, which will be collected from facilities through a mail survey process.  Facilities will be required to respond, so this step is similar to a census. While the precise methods are not known at this point, they are expected to be built upon the advice given in EPA’s Generic Guide to Statistical Aspects of Developing and Environmental Results Program (2003).

This section of the QAPP will be revised upon completion of the project-specific statistical methodology.

## B2.	Sampling Methods

This section of the QAPP will be revised upon completion of the project-specific statistical methodology.

## B3.	Sample Handling and Custody

Upon completion of paper checklists, inspectors will sign the checklists. Inspectors will either enter data directly to an electronic format (such as tablet PC’s and PDAs), or from paper checklists into the electronic database.  Facilities will either enter self-certification data into web-based forms, or mail signed forms to the VT DEC where data-entry staff will input data into the electronic database. Electronic signatures would need to be used in connection with facility self-certifications that are entered into web-based forms by the facility. This section of the QAPP will be revised upon completion of electronic data input/management strategies.

Chain of custody is not relevant to this project.

## B4.	Analytical Methods

This project will follow well-recognized statistical analytical methods.  This section will be revised upon completion of the detailed statistical methodology.   No physical tests or chemical analyses are anticipated for this project.

## B5.	Quality Control

This project will undertake both proactive and corrective quality control.

### Preparation of data collection instruments.

All data collection instruments will be subject to multiple rounds of review by relevant internal and external stakeholders to help assure the collection of high-quality and representative data.  Data collection instruments will be prepared in accordance with the guidance on data collection instruments provided in EPA's Generic Guide to Statistical Aspects of Developing and Environmental Results Program (2003). Specifically, preparation will follow the checklist for data collection instruments provided in an appendix of that guide.

### Training.

As noted elsewhere in this QAPP, steps will be taken to provide appropriate QA/QC training to all implementing personnel, particularly personnel that are collecting and processing data.  Facilities receiving self-certification packets will also receive instructional materials on how to complete their forms, an opportunity to attend workshops that will explain how to complete the forms, and a phone number to call to ask questions.

### Crosschecking data.

Primary data collection forms will be designed in such a way to allow internal crosschecking of data by comparing answers of different questions to each other, and such crosschecking will be automatic for electronically entered data. Further, post-certification inspections will offer the opportunity to compare inspection results with self-certification results, if the facilities sampled have submitted self-certification forms.

### Data anomalies.

Procedures for handling data anomalies (such as outliers and missing data) will be handled based on guidance prepared in the project-specific statistical methodology.

### Data entry.

Procedures for entering hand-written data into the database will follow standard quality control procedures (e.g., 100% verification using independent double key entry).  Detailed quality control procedures for data entry and acceptance will be prepared during the development and implementation of a data management strategy.  The final QAPP will reflect the strategy.

## B6.	Instrument/Equipment Testing, Inspection and Maintenance

This section is not relevant to this project.  The project will not involve such scientific instruments and equipment.

## B7.	Instrument/Equipment Calibration and Frequency

This section is not relevant to this project.  The project will not involve such scientific instruments and equipment.

## B8.	Inspection/Acceptance for Supplies and Consumables

This project will use photographic film as the only supply or consumable requiring inspection and acceptance procedures. All film will be required to have an expiration date, and film that is beyond that date will not be used. Any film in damaged or otherwise corrupted packaging will not be accepted for use.

## B9.	Non-Direct Measurements  (i.e., Secondary Data)

This project will rely upon secondary data to identify the facilities in the target population.

| Table 3: Non-Direct Measurements (I.e., Secondary Data) |
| --- |
| Data Sources | Intended Use | Rationale for Use | Acceptance Criteria |
| VT DEC UST program database of facilities | Identifying the target population, for the sample | Commonly accepted source of facility list | All records will be accepted unless sample response indicates facility should not be part of target population. VT DEC will crosscheck any facility that self-identifies as non-applicable to this project. |
| VT DEC facility file information - UST, APCD, UIC, RCRA | Identifying background conditions at facilities where such information could provide greater precision to the analysis of background or baseline conditions | Commonly accepted source of compliance information, photographs, statements by facility owners and operators | All records will be accepted unless placed in file in error. VT DEC will, on a random basis, crosscheck self-certification conditions and baseline conditions with multi-media file information. |
| Release Data from VT DEC Sites Management database | Identifying reduction in prevalence and severity of releases | One accepted source of release data | Since this is not representative data, this will be a project area to explore. This will be a challenge to address in the QAPP revision process |
| Inspection data that is not observed | A portion of the facility compliance data will be that which is supplied to inspectors by facility personnel, but not observed. An example would be a description of an activity that is or is not compliant, but the inspector does not observe the activity itself. Provides a more complete compliance picture. | More complete compliance information. | Data will be accepted unless conditions or information indicate inconsistencies. VT DEC inspection personnel will use available crosschecks from observed data. |
| Return to compliance data from facility | Measures of facility performance | Commonly accepted form of compliance certification | Data will be accepted unless conditions or information indicate inconsistencies. VT DEC personnel will use available crosschecks from data observed on follow-up inspections. |

### Key resources/support facilities needed.

VT DEC will require access to the data sources mentioned above, and this information will be managed within the database created/utilized for the overall project.  VT DEC does not anticipate any obstacles to this approach.

### Determining limits to validity and operating conditions.

Database containing the list of targeted facilities will be designed such that the original source for all facility data is marked, and procedures will be in place such that only the Project Manager can officially remove a facility entry from the target population.  In such cases, facility entry will not be deleted from the database but will be marked as non-applicable, and corrective data will be provided in fields parallel to the original data.

## B10.	Data Management

As part of this project, VT DEC and the ERP Contractor will develop a data management strategy, and revise the QAPP based upon the strategy.  The Project Manager is responsible for ensuring that that strategy is developed and that the QAPP is revised to reflect that strategy. Once revised, this QAPP section on data management will provide information on the following issues:

Data management scheme, from field to final use and storage

Standard recordkeeping and tracking practices, and document control system (citing relevant agency documentation)

Data handling equipment/procedures that will be used to process, compile, analyze, and transmit data reliably and accurately

Individuals responsible for elements of the data management scheme

Process for data archival and retrieval

# C	ASSESSMENT/OVERSIGHT

## C1.	Assessment and Response Actions

The Quality Assurance Officer will conduct a Readiness Review immediately prior to the five major data collection tasks:  identifying targeted facilities, baseline inspections, self-certification, targeted follow-up, and post-certification inspections..  The QA Officer will report findings to the Project Manager, who will take corrective action (if any is necessary) before the data collection task begins.  Further, the Project Manager and QA Officer will thoroughly debrief project implementation staff a short time after beginning their respective implementation tasks, to identify emerging/unanticipated problems and take corrective action, if necessary.

## C2.	Reports to Management

Three kinds of reports will be prepared: readiness reviews (described above), regular quarterly and annual progress reports, and project final report.  Progress reports will note the status of project activities and identify whether any QA problems were encountered (and, if so, how they were handled).  Project final report will analyze and interpret data, present observations, draw conclusions, identify data gaps, and describe any limitations in the way the data should be used.

Project QA Status Reports

| Type of Report | Frequency | Preparer | Recipients |
| --- | --- | --- | --- |
| Revised QAPP | Once, before primary data collection begins | VT DEC Project Manager | All recipients of original QAPP |
| Readiness Review | Before each major data collection task | VT DEC QA Officer | VT DEC Project Manager, Project Manager Supervisor |
| Progress Report | Quarterly | VT DEC | U.S. EPA |
| Progress Report | Annually | VT DEC | U.S. EPA, stakeholders |
| Final Project | Once | VT DEC | U.S. EPA, stakeholders |

# D	DATA REVIEW AND EVALUATION

## D1.	Data Review, Verification and Validation

The QAPP shall govern the operation of the project at all times.  Each responsible party listed in Section A4 shall adhere to the procedural requirements of the QAPP and ensure that subordinate personnel do likewise.

This QAPP shall be reviewed at least annually to ensure that the project will achieve all intended purposes.  All the responsible persons listed in Section A4 shall participate in the review of the QAPP.  The Project Manager and the Quality Assurance Officer are responsible for determining that data are of adequate quality to support this project.  The project will be modified as directed by the Project Manager.  The Project Manager shall be responsible for the implementation of changes to the project and shall document the effective date of all changes made.

It is expected that from time to time ongoing and perhaps unexpected changes will need to be made to the project.  The Project Manager shall authorize all changes or deviations in the operation of the project.  Any significant changes will be noted in the next report to EPA, and shall be considered an amendment to the QAPP.  All verification and validation methods will be noted in the analysis provided in the final project report.

## D2.	Verification and Validation Methods

To confirm that QA/QC steps have been handled in accordance with the QAPP, a readiness review will be conducted before key data collection/analysis steps, and data handling reports will be prepared after each step.  Standard statistical tests (described below) will be used to determine the extent to which inferences can be drawn from the sample data.

## D3.	Evaluating Data in Terms of User Needs

This section will be written and finalized after completion of the project-specific statistical methodology.  This section will present the following information:

Meeting and reporting needs of your project: a description of how the results of the study will be analyzed and evaluated to determine whether the needs of the project were met and then reported

Mathematical and statistical formulae: details of formulae that will be used to calculate precision, accuracy/bias, completeness, comparability and sensitivity (if applicable) of the project data.

Approach to managing unusable data:  Description of what will happen if data are unusable, with particular emphasis on the impact of such unusability on data representativeness.

# Footnotes

These records document protocols used in data reduction, verification, and validation. Data reduction addresses data transformation operations such as converting raw data into reportable quantities and units, use of significant figures, recording of extreme values, blank corrections, etc. Data verification ensures the accuracy of data transcription and calculations, if necessary, by checking a set of computer calculations manually. Data validation ensures that QC criteria have been met.

Includes data from self-certification forms, return-to-compliance forms, and non-applicability forms.