Transition Strategy and

Management Plan

(TSMP)

Prepared by

General Services Administration

(GSA)

April 15, 2008

This document is hereby authorized for limited release by the General Services Administration.

________________________________	_4/18/08___

Richard Williams	Date

Networx Transition Manager

Integrated Technology Services

General Services Administration

Table of Contents

1.0  Introduction	5

1.1  Background	5

1.2  Networx Program	6

1.3  Transition Strategy Management Plan (TSMP) Document Overview	9

2.0 TRANSITION OVERVIEW	9

2.1 Transition Goals	10

2.1.1 Minimize Service Impact	10

2.1.2 Transition Service Prior to FTS2001 Contract Expiration	10

2.1.3 Expedite Availability of New Services	10

2.1.4 Minimize Transition Expense	10

2.2 Overview of Transition Approach	11

2.3 Transition Sequence of Events	12

3.0 Transition Roles and Responsibilities	13

3.1 GSA Transition Team	14

3.2 Technology Service Managers (TSMs)	18

3.3 Contract Management and Support	18

3.4 Interagency Management Council (IMC)	18

3.5 IMC Transition Working Group (TWG)	19

3.6 Agencies	19

3.6.1 Agency Transition Manager	19

3.6.2 Agency-Level Transition Team	20

3.6.3 Local Government Contacts (LGCs)	21

3.7 FTS2001 Contractors	22

3.8 Networx Contractors	24

4.0 Transition Planning	25

4.1 Inventory Establishment	25

4.2 Estimate and Budget for Transition Costs and Reimbursement to Agencies	26

4.3 Modify Incumbent FTS2001 Contracts	27

4.4 GSA Regional Services	27

4.5 Certification & Accreditation (C&A) Concerns	28

4.6 Designated Agency Representative (DAR) Guidelines	29

4.7 Contractor Support for the Transition Coordination Center (TCC)	29

4.8 GSA’s Operational Support System (OSS) Enhancements	30

4.9 Agency Level Transition Planning	30

4.10 GSA Support for Fair Opportunity	31

4.11 Contractors’ Transition Plans	31

4.12 Schedule Development	31

5.0 Staffing and Training	31

5.1 Staffing	32

5.2 Training	32

6.0 Transition Execution And Management	33

6.1  Service Provisioning	33

6.2 Progress Tracking and Reporting	33

6.3  Communications and Issue Resolution	35

6.4 Custom Design Documents (CDDs), Managed Design Documents (MDDs), and Contract Modifications	35

7.0 Transition Support Tools	36

7.1 Transition Baseline Inventory (TBI)	37

7.2 Transition Information Portal (TIP)	38

7.3 Transition Coordination Center (TCC) Problem Resolution	41

7.4 Networx Pricer	41

7.5 Networx Inventory Management Application (NIM	41

8.0 Risk Management	42

8.1 Sources of Risk	42

8.2 Risk Mitigation	42

9.0 Transition Coordination Center (TCC)	43

9.1 TCC Objectives	43

9.2 TCC Structure And Functions	44

9.3 Operations	45

10.0 Regional Services Transition Plan	45

10.1 Customer Support For Regional Transition	45

10.2 Goals And Objectives	46

11.0  Change History	46

Appendix A:  Glossary	47

Appendix B:  Acronyms	54

Appendix C:  FTS2001 Transition Lessons Learned Document	56

Appendix D:  Transition Contract Support Vehicles	64

Appendix E:  Risk Mitigation Strategies	73

Appendix F:  Communications Plan	74

Appendix G:  Responsibility Matrix	75

# 1.0  Introduction

The Networx Transition Strategy and Management Plan (TSMP) was developed to provide guidance on managing the transition from current FTS2001 contracts to the Networx contracts.  This document addresses the program-level approach that GSA will follow to manage a successful transition to Networx.  In addition, this document advocates the importance of coordination and cooperation among transition stakeholders by clearly defining transition roles, addressing key issues impacting transition, explaining the underlying systems supporting transition, and establishing guidance on transition processes and procedures.  This comprehensive approach provides the framework for managing a successful transition to Networx.

The objective of the TSMP is to present GSA’s approach to successfully managing its role in the transition from current FTS2001 Bridge and Crossover contracts.  It is intended to provide guidance to the GSA transition team as well as inform Agencies and contractors.  The TSMP also serves as a planning reference to guide Agencies through all phases of the transition.  This document describes the approaches, processes, factors, and considerations required at the program level for the transition to Networx.

This document is aimed at a strategy and plan for GSA to provide support to Agencies during the transition timeframe.  In addition the Networx Program Office of GSA is also developing, implementing and executing processes for the long term support of the Networx program during the transition period. Those efforts are not described in this document.

## 1.1  Background

The General Services Administration (GSA), Federal Acquisition Service (FAS), Integrated Technology Services (ITS) group provides telecommunications and network services contracts for the use of all Federal Agencies.  As current contracts expire, Agencies rely on GSA to provide replacement contracts that will ensure the continuity of mission-critical services.

Accordingly, GSA initiated a follow-on acquisition called Networx to meet Agency needs for the next-generation of telecommunications and related information technology (IT) services.  Networx will provide continuity for the services provided by current contracts as well as a portfolio of new and emerging, next-generation services.

Development of the Networx program has been a collaborative effort between GSA and the Interagency Management Council (IMC), a body representing the Agency customers of FAS. The IMC worked in partnership with senior GSA leadership to identify Networx goals.  These goals have driven Networx program requirements, which GSA developed with Agency representatives of the IMC.  In addition, the Agencies, working closely with the GSA Networx program team, participated in the definition of the GSA Networx strategy and detailed requirements for the technical, pricing, management, operations, and transition elements of the program.

1.1.1  Expiring Contracts (FTS2001 Bridge and Crossover)

GSA has a long-standing history of providing leading-edge telecommunications services to the Federal Government at best value.  In 1998 and 1999, GSA awarded two eight-year follow-on contracts to replace Federal Technology Service (FTS2000) that provided long-distance telecommunications services to Federal Agencies.  Named FTS2001, these contracts enhanced and optimized the service offerings of FTS2000 at significantly lower prices.  Subsequently, Crossover contracts that included long-distance services became available under the FTS2001 Program, providing additional sources and increasing GSA’s leverage for lower prices.  FTS2001 contracts expired in 2006 and 2007, while the subsequent FTS2001 Crossover contracts are set to expire between 2008 and 2010.  In an effort to decrease the immediate transition burden on Agencies migrating from existing FTS2001 contracts, GSA awarded Bridge contracts that provide for continued service with Sprint and MCI beyond the December 2006 and January 2007 timeframes respectively.  The Sprint Bridge contract began in December 2006, and MCI’s Bridge contract was awarded in January 2007; both will continue for a minimum of 24 months, with three (3) six month options to extend beyond the base period.

Note that generally throughout this document the term “FTS2001 contracts” includes both the Bridge and Crossover contracts.

1.1.2  Lessons Learned

GSA and the IMC conducted a thorough analysis of the upcoming Networx transition in order to avoid similar issues encountered with the FTS2001 transition effort.  The results comprise a set of lessons learned that can be categorized into the following areas:

- Transition planning

- Transition execution

- Transition control, tracking, and monitoring

More detailed information is available in the “FTS2001 Transition Lessons Learned” document, which is included as Appendix C.  GSA and the IMC’s Transition Working Group (TWG) use these lessons learned as a foundation and guide for transition planning.  Further, the Government Accountability Office (GAO) emphasized the importance of lessons learned when it audited the transition planning efforts.

## 1.2  Networx Program

GSA Networx provides high-quality telecommunications and network services and solutions at attractive prices that meet or exceed Agency mission requirements and conform to Government policies and standards.  GSA anticipates that the unprecedented success of FTS2001, achieved by aggregating the buying power of Federal Agencies, will continue with Networx, resulting in continued savings to the Government.  GSA Networx provides continuous competition to satisfy specific networking projects, emerging requirements, technology refreshment, and access to innovation.

1.2.1  Networx Goals

GSA and IMC representatives established the following program goals for the Networx program:

- Service continuity:  All services to all locations that are currently provided on the FTS2001 and Crossover contracts must be included in the Networx program.

- Highly competitive prices:  Prices on the Networx program must continue to be better than prices available elsewhere in the telecommunications marketplace.

- High-quality service:  Service on the Networx contracts must be provided by reliable providers.  The contracts must include enforceable specifications that will ensure high-quality service is delivered throughout the term of the contracts.

- Full service providers:  Service providers who are awarded contracts on Networx must be capable of providing a broad array of services, allowing Agencies to select a single source for multiple needs.

- Alternative sources:  Networx must provide access to a broad spectrum of industry service providers that give Agencies access to innovative developments.

- Operations support:  Networx must improve service management, ordering, billing, and inventory management and the information systems that support service delivery.

- Transition assistance and support:  The contracts must include provisions that facilitate a successful transition.  These provisions include demonstration of contractors’ operational support systems (OSS) so transition can begin and proceed efficiently, detailed transition reporting, and provisioning Service Level Agreements (SLAs) to help ensure timely transition.

- Performance-based contracts:  The contracts must have enforceable standards with SLAs.

GSA also identified specific transition goals, and these are discussed in detail in Section 2.

1.2.2  Networx Contracts

The Networx contracts were awarded as follows:

ACQUISITION	AWARDED	CONTRACTORS

Universal	March 2007	AT&T, MCI (Verizon Business), and Qwest

Enterprise	May 2007	AT&T, MCI (Verizon Business), Level (3), Sprint, and Qwest

1.2.3 Program Schedule

In partnership with transition stakeholders such as the IMC, GSA is tracking key programmatic milestones as Agencies prepare for the transition to Networx.  While not transition activities themselves, they impact transition and are of interest to those concerned with the success of transition.  Awards of the Universal and Enterprise contracts and the Notice to Proceed to each vendor, signifying the beginning of performance on the contracts, were the first important milestones.  After award, the Agencies began determining the contractors from whom the Agencies will order services; this is done through the Fair Opportunity process.  With those decisions made, the Agencies will place their transition orders, and transition will begin.  The timeline for these activities is depicted in Exhibit 1.2.2 below.

Exhibit 1.2  Networx Program Schedule

## 1.3  Transition Strategy Management Plan (TSMP) Document Overview

1.3.1  TSMP Objective

The objective of the TSMP is to present GSA’s approach to successfully managing its role in the transition from the FTS2001 contracts.  It is intended to provide guidance to the GSA transition team as well as inform Agencies and contractors.  The TSMP also serves as a planning reference to guide Agencies through all phases of the transition.  This document describes the approaches, processes, factors, and considerations required at the program level for the transition to Networx.

1.3.2  TSMP Document Scope

- Provides an overview of each of the characteristics of the transition effort.

- Describes the roles and responsibilities of all involved stakeholders.

- Describes, in detail, each of the transition planning activities to ensure transition stakeholders are adequately prepared for transition.

- Discusses GSA’s approach to transition management.

- Discusses the transition support tools that GSA will use and make available to Agencies, in order to facilitate each Networx transition activity.

- Discusses the transition cost reimbursement process for Agencies.

- Describes risk management strategies to mitigate risk during transition.

- Discusses the GSA Transition Coordination Center (TCC), which is the liaison between all transition stakeholders to ensure transition to Networx runs according to schedule and expectations.

- Describes GSA’s approach to Regional Services transition, which consists of moving long-distance services that connect to customers through consolidated regional systems.

Appendices provide more detailed information pertaining to transition planning.

# 2.0 TRANSITION OVERVIEW

Transition is defined as the movement of services from the FTS2001 contracts to Networx and continues until the disconnection of all services from the FTS2001 contracts.  Transition planning, transition execution, and management activities are critical to the success of the transition to Networx and require participation by all stakeholders.  The Agencies using FTS2001 services have the primary responsibility for completing transition successfully.  GSA, as the owner of the contracts and program manager, supports the Agencies by managing the contractors and providing a Government-wide perspective to planning and execution.

## 2.1 Transition Goals

In line with the Networx program goal of Transition Assistance and Support, GSA identified four major transition goals, which are described in this section.  These were recognized from GSA and transition stakeholder planning sessions, and, more specifically, the lessons learned from the transition from FTS2000 to FTS2001.

### 2.1.1 Minimize Service Impact

It is important to minimize interruptions in Agencies’ operations as services are transitioned from FTS2001 to Networx.  One way to manage this is for Agencies to identify mission critical services to be transitioned during low risk periods.  Similarly, cutovers should be performed at times of lowest activity whenever possible.  Agencies should also define critical periods of operation during which transitions should be avoided or more carefully orchestrated, such as during tax season for the IRS or hurricane season for FEMA.  It is also important that the contractors test new services in advance of the scheduled cutover time and that GSA manage the contractors to established procedures for falling back to incumbent services if cutovers fail.

### 2.1.2 Transition Service Prior to FTS2001 Contract Expiration

While the base period of the Bridge contracts will provide FTS2001 services through December 2008, the volume of activity associated with a transition effort as large as the FTS2001 transition to Networx requires that GSA and the Agencies begin transition activities as soon as possible to ensure no break in service due to expiration of the contracts.

### 2.1.3 Expedite Availability of New Services

The Networx acquisitions includes services currently in use on the FTS2001 contracts as well as approximately 20 new services that reflect new technologies and new customer requirements.  This provides the Agencies the opportunity to transform from legacy services to converged services such as Voice Over Internet Protocol (IP) (VOIP) and to newer technologies, such as from Asynchronous Transfer Mode (ATM) or Frame Relay to IP.  The combination of more services, greater competition, and improved performance provide significant incentive to transition to Networx.

### 2.1.4 Minimize Transition Expense

The costs associated with the Networx transition are directly related to the overall length and scope of the effort.  For example, costs such as Government staff augmentation and contractor support can be significantly reduced with proper planning.  The need to run parallel operations during the transition also can significantly impact an Agency’s overall costs for transition.  In an attempt to minimize financial impacts, GSA began working with the Agencies in 2003 to plan for transition.   This planning has provided necessary time to identify risks and implement mitigation solutions as well as program for financial resources well in advance.

## 2.2 Overview of Transition Approach

The GAO report, “Full Adoption of Sound Transition Planning Practices by GSA and Selected Agencies Could Improve Planning Efforts,” June 2006 identified best practices for conducting effective transition planning.  In particular, GAO identified five sound transition planning practices:

- Establish an accurate telecommunications inventory and an inventory maintenance process

- Perform a strategic analysis of telecommunications requirements and use this to shape the Agency’s management approach and guide efforts when identifying resources and developing a transition plan

- Establish a structured management approach that includes a dedicated transition management team that will use clear lines of communications in addition to key management processes, such as project management, configuration management, and change management

- Identify the funding and human capital resources that the transition effort will require

- Develop a transition plan that includes transition objectives, measures of success, and risk assessment, and a detailed timeline.

GSA and the Agencies have been working together for several years to ensure not only sound transition planning but also execution and management of transition.  In fact, the TWG was formed in 2003 and currently meets regularly.  GSA has taken a strategic role in defining transition planning, transition execution, management activities and stakeholders.  GSA’s approach to planning for transition includes facilitating the establishment of the inventory to be transitioned and leading the definition and resolution of program-level factors and issues.  While the Agencies using FTS2001 services have the primary responsibility for executing transition successfully, GSA supports the Agencies by managing the contractors and providing a Government-wide perspective on execution, which includes tracking and facilitating issue resolution.

GSA’s strategic planning activities include:

- Establishing the inventory of services on existing contracts

- Estimating the program costs of transition

- Modifying incumbent FTS2001 contracts to provide greater transition support

- Planning for transition of services delivered through GSA’s regional offices

- Addressing the impacts of security compliance on the start of transition

- Standardizing the guidance on who can place orders on the Networx contracts

- Establishing a Transition Coordination Center (TCC)

- Assessing the readiness of GSA’s operational support systems (OSS) for transition

- Offering support to Agencies for transition planning

- Providing guidance to Agencies for making their fair opportunity decisions

- Guiding the contractors’ development of their transition plans

- Maintaining a master schedule of Government-wide activities.

GSA’s role in transition execution and management includes:

- Advising Agencies on the terms of the contracts regarding provisioning services and monitoring progress of service delivery

- Progress tracking and reporting

- Communications and issue resolution

- Transitioning customized solutions

## 2.3 Transition Sequence of Events

There are several key milestones in the Networx program that drive the schedule for transition events.  As discussed in Section 1.2.3, chief among these milestones is award of the contracts and subsequent Notice to Proceed.  Since Networx contractors may not process orders until they have successfully demonstrated their OSS meet the verification requirements for ordering and billing and for federal security policies, these achievements are also important to the schedule.  Driving the schedule for the completion of transition are the terms of the Bridge contracts.

The Networx transition schedule identified in Exhibit 2.3 below highlights several significant transition activities and their expected timeframes as part of the Networx program schedule.

- Validation of Transition Baseline Inventory: Inventory has been identified as a critical success factor for effective transitions.  GSA and transition stakeholders have collected FTS2001 contract data to develop a comprehensive inventory.  Agencies will then validate the inventory data.  In order to establish a baseline for tracking transition progress, GSA took a snapshot of the inventory just prior to the Agencies’ beginning to place orders.  This becomes the Transition Baseline Inventory (TBI).  As transition proceeds, new FTS2001 orders and disconnects from FTS2001 will continue to be maintained in the TBI database.

- Fair Opportunity for Reimbursement:  GSA will reimburse Agencies for certain transition costs, provided those Agencies meet specific criteria.  One of those criteria is to complete the Fair Opportunity decisions for services to be transitioned.

- GSA Recommendations:  To further expedite transition, GSA recommends Agencies make the majority of their Fair Opportunity decisions by March 2008, submit the majority of their transition orders by January 2009, and submit their disconnects by January 2010.

- Submit Disconnects for FTS2001: As mentioned previously, the end of the Bridge contracts signifies the latest time by which all services must be disconnected from those contracts, whether the services transition to Networx or not.

- E-MORRIS:  Enhanced Monthly Online Records and Reports of Information Technology Services (E-MORRIS) is an internal OSS GSA uses to process inventory and billing information.  E-MORRIS will process the first invoices and inventory data for Networx.

Exhibit 2.3  Networx Transition Schedule

# 3.0 Transition Roles and Responsibilities

The primary stakeholders in Networx transition include all who are responsible for planning, executing, and managing the transition.  Exhibit 3.0 presents the five major groups of Networx transition stakeholders: GSA Transition Team, IMC, TWG, Agencies, and contractors for FTS2001 and Networx contracts.  Although some of these groups include many of the same people, the role the group members fill differs across the groups.  GSA’s Technology Service Managers (TSMs formerly known as GAMs) also have a significant role in transition, as they are often the primary interface between GSA and the Agencies.  In addition, Contract Management comprises the program offices for FTS2001 and Networx, who work closely with the transition team on matters impacting the success of transition.

Exhibit 3.0 Transition Stakeholders

Each group of transition stakeholders is discussed in more detail in the subsequent sections of this chapter.

## 3.1 GSA Transition Team

The GSA Transition Team is comprised of three interdependent functions: GSA Transition Planning and Management, the Transition Coordination Center (TCC), and Regional Services.  The GSA Transition Team is responsible for providing oversight of the activities for the FTS2001 and Networx programs that are directly related to transition.

3.1.1 GSA Transition Planning and Management

The GSA Transition Planning and Management team includes the overall planning, execution and management of transition from GSA's perspective.  The GSA Transition Manager leads the Transition Planning and Management team and is responsible for managing all aspects of transitioning services from the FTS2001 contracts to Networx.  The Transition Manager is supported by a dedicated transition team to help coordinate the execution of transition tasks and activities, including transition planning, transition oversight, and project management.  Exhibit 3.1.1 documents the roles and responsibilities of this team.

Exhibit 3.1.1 GSA Transition Planning and Management Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| GSA Transition Planning and Management Team | Transition Activities | Coordinate activities of GSA Transition Planning and Management Team and TCC, GSA’s support contractors, Agency Transition Managers, and Networx contractors. |
|  | Networx Transition Strategy | In conjunction with TWG and Agencies’ Transition Managers (TMs), develop and disseminate strategic guidance and Government-wide plans. Develop overall strategy for transitioning to the Networx contracts that takes into account requirements of the Agencies as well as GSA. |
|  | Transition Strategy and Management Plan (TSMP) | Develop TSMP to describe how the transition will be conducted to include processes and timelines needed to meet the requirements of the overall transition effort. |
|  | Agencies’ Guidance | Participate as a member of the TWG in defining, developing, and disseminating guidance to customer Agencies regarding the Networx transition effort. |
|  | Networx Contract Compliance | Enforce compliance with Government responsibilities for transition in the Networx contracts. |
|  | TCC Management | Manage the overall operation of the TCC and transition efforts. |
|  | Planning and Execution with Regional Services | Coordinate transition planning and execution activities with Regional Services. |
|  | Agency Assistance | Provide guidance and assistance to Agencies for the transition to Networx. |
|  | Performance Monitoring | Monitor Networx contractors’ performance during the transition. |
|  | Program Management | Provide program management and control for transition, including maintaining master schedule for transition. |
|  |  | Define the roles and responsibilities of GSA organizations and teams supporting transition and establish interfaces to them. |
|  | Coordination with Oversight Stakeholders | Support GSA management in its coordination with external stakeholders such as Congress, the Office of Management and Budget (OMB), and the GAO concerning the Networx transition. |
|  | Program Analysis | Complete an estimate of program costs of transition and manage expenditure of budgeted monies |

3.1.2 GSA Transition Coordination Center (TCC)

The TCC is a GSA organization headed by the TCC Manager and reporting to the GSA Transition Manager.  The TCC Manager is the primary interface between the TCC, TWG, Agency Transition Managers, and transition teams of the FTS2001 and Networx contractors.  Exhibit 3.1.2 identifies the functions that comprise the TCC.  Section 9 describes the TCC concept of operations.

Exhibit 3.1.2 GSA TCC Roles and Responsibilities

| Stakeholder | TCC Team | Transition Role Details |
| --- | --- | --- |
| Transition Coordination | Cut Team | Provide cutover assistance to TCC customers as required. |
|  | Systems Support Team | Perform system development, administration, maintenance, and troubleshooting of the software applications that support the TCC. |
|  | Operations Team | Conduct the day-to-day TCC activities, which include: tracking action items, managing day-to-day assignments of work schedules, developing Standard Operating Procedures (SOPs), conducting TCC internal training, tracking and reporting on transition, and managing trouble tickets. |
|  | Project Management and Control Team | Develop and maintain a schedule of all TCC activities, manage and administer the TCC contractors’ performance under their Task Order, and provide oversight of the other TCC teams’ activities. |
| Regional Transition Support |  | Serve as liaison to the Regional Transition Managers that are located throughout the eleven GSA regions. |
|  |  | Facilitate resolution of issues that affect multiple customers and multiple regions. |

3.1.3 GSA Regional Support

GSA Regional Services is responsible for planning and coordinating the transition from FTS2001 to Networx for the Agencies who have service through the regions’ consolidated systems.  Exhibit 3.1.3 summarizes the roles and responsibilities of GSA Regional Services for Networx transition.  The Regional Support liaison function will coordinate between the TCC and Regional Services.  Additional information regarding Regional Services is available in Chapter 10.

Exhibit 3.1.3 Regional Services Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| GSA Regional Services | Regional Transition Managers (RTMs) | Provide transition support for the consolidated systems in their regions. Track and report the to the TCC completion of transition orders for their specific regions. |
|  | Transition Plans | Develop regional transition plans. |
|  | Assessments | Perform regional assessments. |
|  | Resources | Identify regional transition resource requirements. |
|  | Communication | Communicate with customers on a local, regional, and national level and with the TCC. |
|  | Participation | Participate in transition and acquisition working groups and work with the Networx PMO and Transition Team to resolve issues and assist customers with using Networx in conjunction with regional contracts. |

## 3.2 Technology Service Managers (TSMs)

TSMs are GSA FAS personnel assigned to specific Agencies and who serve as the customer's single point of contact for network services.  TSMs serve as an Agency’s first line of communication with GSA.  They coordinate with the TCC to provide customer outreach as required.  TSMs provide advisory and education services to major Agencies; however, they will not provide dedicated support for transition execution.  The Networx PMO (NxPMO) Help Desk (see Section 7.3) will be the primary interface to GSA (specifically the TCC) for transition support.  The Communications Plan in Appendix F contains additional information on the role of the TSMs in communications between Agencies and GSA.

## 3.3 Contract Management and Support

Contract Management is responsible for overall life-cycle management of the FTS2001 and Networx contracts and supports transition through Subject Matter Experts (SMEs) in the areas of inventory, billing, ordering process, contract deliverables, GSA OSS, FTS2001 and Networx OSS, contract modifications, the Statement of Work (SOW) process, and other topics that, while not specifically transition, certainly impact the success of transition.  SMEs have an in-depth understanding of telecommunications technology and the Networx contracts.  They will coordinate with Agency personnel and contractors (FTS2001 and Networx) as needed throughout the life of the contract.

## 3.4 Interagency Management Council (IMC)

The IMC serves as an advisory body for the development, coordination, and oversight of telecommunications programs pertaining to the Federal Government and related activities and organizations.  The IMC is comprised of senior Federal executives representing fourteen (14) Cabinet-level departments and several other Agencies.  The IMC also provides a forum for Agency participation in the planning and oversight of GSA’s telecommunications services.  Additionally, the IMC resolves issues escalated by the IMC TWG as needed.

## 3.5 IMC Transition Working Group (TWG)

The IMC TWG is responsible for channeling Agency issues to the appropriate groups including the IMC and other key stakeholders in order to provide meaningful guidance on transition issues.  As an active member of the TWG, GSA facilitates resolution of TWG issues in coordination with the TWG Chairperson.  GSA is responsible for capturing all Agency issues, providing guidance where necessary, and tracking the issues through resolution.

The TWG promotes collective Government planning related to the transition from expiring FTS2001 contracts to the Networx contracts.  The TWG has encouraged Agencies to send representatives to TWG meetings in order to voice transition concerns, seek guidance on transition issues, and learn about transition best-practices.  Specifically, the TWG addresses technical, contractual, operational, political, and financial aspects of the FTS2001 and Networx contracts.

## 3.6 Agencies

The primary responsibility of each Agency is to manage and monitor all activities and functions relative to the Agency-level transition to Networx.  All Agencies have appointed a Transition Manager and a Transition Team to coordinate the transition activities within the Agency.

### 3.6.1 Agency Transition Manager

Each Agency’s Chief Information Officer, or other authority as appropriate, appoints an Agency Transition Manager.  GSA hosts regular meetings of all TMs to pass along information, conduct workshops, deliver training, and other communication of decisions, plans, and helpful resources that come from the TWG.   Exhibit 3.6.1 identifies the roles and responsibilities of Agency Transition Managers.

Exhibit 3.6.1 Agency Transition Manager Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| Agency Transition Manager | Address Requirements | Engage Agency staff to address requirements for : - Personnel - Financial Resources - Critical functions - Inventory Validation. |
|  | Issue Escalation | Escalate issues to TWG or Agency Management as appropriate. |
|  | Program Management Support | Provide overall program management support of the Agency’s transition to Networx. |
|  | Transition Strategies | Plan and prepare Agency-specific transition strategies. |
|  | Execution Activities | Execute activities of the overall transition to ensure that FTS2001 services are transitioned to Networx |
|  |  | Ensure new orders are placed in a timely manner. |
|  | Agency-Level Support | Serve as the designated point of contact for the planning and management of all transition activities. |
|  | Transition Team Interface | Serve as the interface to the GSA Transition Team. |
|  | OSS Access | Submit or validate and forward requests for Agency personnel to access transition systems in order to centrally control who has what authorities within each system. |

### 3.6.2 Agency-Level Transition Team

Agency-Level Transition Teams, if needed, will provide sub-Agency and local level support, Agency transition support, and FTS2001 contract support.  Exhibit 3.6.2 identifies some possible roles and responsibilities of Agency-Level Transition Teams, which include the Designated Agency Representatives (DARs) who place and manage orders following the ordering process as defined in the FTS2001 and Networx contracts.

Exhibit 3.6.2 Agency-Level Transition Team Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| Agency Transition Team | Sub-Agency and Local Level Support | Serve as the interface to the Local Government Contacts (LGCs) or end-user customers. |
|  |  | Provide Fair Opportunity support using the Networx contracts. |
|  |  | Distribute transition information to the Agency. |
|  | Transition Support | Support the GSA Transition Manager in establishing an FTS2001 Transition Baseline Inventory (TBI) |
|  |  | Alert the Agency Transition Manager to any Agency-specific challenges. |
|  |  | Review site transition plans as needed. |
|  |  | Prepare, process, and validate all Networx service orders (performed by the DAR). |
|  |  | Validate and place FTS2001 disconnect requests (performed by the DAR). |
|  |  | Report transition status to the Agency Transition Manager. |
|  |  | Ensure orders are processed and accepted within the prescribed intervals or timelines. |
|  |  | Alert the Agency Transition Manager of obstacles and/or delays in executing transition. |

Additional information on Agency-level transition planning is available in Section 4.9.

### 3.6.3 Local Government Contacts (LGCs)

LGCs are technical contacts at service delivery points or Agencies’ sites who work in conjunction with FTS2001 contractors, Networx contractors, Agencies, and other transition stakeholders to successfully transition services to Networx.  Exhibit 3.6.3 presents the roles and responsibilities of LGCs.

Exhibit 3.6.3 Local Government Contacts Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| Local Government Contact (LGCs) | Provide Site Access | Coordinate site visits. |
|  |  | Review contractor credentials. |
|  |  | Coordinate site access. |
|  | Coordinate Government Furnished Property | Receive need for Government Furnished Property (GFP). |
|  |  | Coordinate delivery of GFP. |
|  | Installation Coordination | Review orders to prepare for installation. |
|  |  | Communicate with the Networx contractor(s) and site contacts. |
|  |  | Ensure site, equipment, and resources are prepared. |
|  | Changes or Notifications | Receive notifications from contractor(s) on changes or problem notifications of transition orders. |
|  |  | Verify impact of changes or problems. |
|  |  | Coordinate with local points of contact to resolve problems that may arise. |
|  |  | Manage change requests. |
|  | Test and Service Acceptance | Coordinate and oversee test and acceptance procedures. |
|  |  | Test services as provided. |
|  |  | Report and resolve issues with the Networx contractor(s) regarding faulty service. |
|  |  | Issue acceptance notices as required by Agencies. |

## 3.7 FTS2001 Contractors

FTS2001 contractors have a critical role in the cutover and ultimate disconnection of services from their contracts.  They participate in service-by-service transition planning activities and interact with the GSA Transition Team, Agencies, and Networx contractors.  The FTS2001 contractors are responsible for coordinating with Agencies and Networx contractors to disconnect all FTS2001 services as requested by the Agencies.  Additionally, the FTS2001 contractors will interact with the GSA TCC by providing transition status reports.  The GSA TCC Team will use these reports to track overall progress as Agencies transition to Networx.   Exhibit 3.7 below identifies the specific roles and responsibilities of FTS2001 contractors.

Exhibit 3.7 FTS2001 Contractors’ Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| FTS2001 Contractor | Provide Transition Planning Support | Assist Agency efforts to prepare for transition execution, such as to develop baseline inventory, determine system requirements, and gather site-specific information. |
|  | Identify a Transition Point of Contact (TPOC) | Select a TPOC to facilitate the transition of services to the Networx contract. |
|  | Participate in Detailed Service-by-Service Transition Planning | Participate in a detailed service-by-service transition planning with Networx contractors beginning with the award of the Networx contract and continuing until the last circuit is disconnected. |
|  | Provide Circuits as Gateways Required to Interface with Successor Provider Networks | Support the Network Interface Facilities (NIF) for gateways in accordance with service orders placed by GSA. GSA will coordinate the NIF requirements with the Networx contractor prior to placing service orders. |
|  | Provide Transition Support Data | Provide additional provisioning information to the Agency Transition Manager or Local Government Contact on the transitioning service within two weeks of receiving the request. FTS2001 contractors are not required to provide proprietary details of the network internals. |
|  | Prepare Routing Translations and Orders | Prepare, pre-test, and activate network routing and trunking translations, and other required software changes with the Networx contractor on a coordinated basis. Networx contractors must provide a minimum of two weeks for testing. |
|  | Support Pre-Cutover Testing | Support pre-cutover testing and access to the network of the Networx contractor during normal business days (NBD). The Networx contractor must provide a minimum of two weeks notice of testing dates to the FTS2001 contractor. |
|  | Support Fall Back Requests | Provide fallback capabilities if a transition cutover fails or there is a problem with the Networx contractor’s service after cutover. |
|  | Provide Transition Status Reports | Present weekly transition/phase-out status report to the GSA Transition Manager and the Agency Transition Manager. The report contents and data elements must conform to the FTS2001 contractual reporting requirements. |

## 3.8 Networx Contractors

The Networx contractors are responsible for delivering services ordered by Agencies in compliance with the Networx contracts.  Networx contractors will work directly with Agency representatives to provide transition planning, transition execution, and communication support, with GSA’s oversight.  Networx contractors will also coordinate essential transition activities with the GSA TCC to ensure that Agencies receive quality service with an emphasis on making transition successful.  Toward that end, service level agreements (SLAs) on the Networx contracts are in full effect during transition.  Exhibit 3.8 identifies the roles and responsibilities of Networx contractors.

Exhibit 3.8 Networx Contractors’ Roles and Responsibilities

| Stakeholder | Transition Roles | Transition Role Details |
| --- | --- | --- |
| Networx Contractors | Transition Planning Support | Provide transition planning documents as specified in the contract, including Transition Management Plan (TMP), Agency-Level Transition Plans (ALTP), and Transition Project Specific Plans (TPSP). |
|  |  | Provide guidance to GSA and the IMC relative to industry issues, interests, and best practices. |
|  | Transition Execution Support | Accept and acknowledge orders. |
|  |  | Provide services ordered within contractual intervals. |
|  |  | Conduct cutover of service. |
|  |  | Provide the status of transition activities. |
|  |  | Support efforts of Agency and contractors to mitigate schedule issues while meeting provisioning SLAs. |
|  | Communications Support | Provide Transition Action Notices that describe transition activities scheduled for execution in sixty (60) days. |
|  |  | Provide GO/NO-GO Transition Notices that alert recipients to the status of transition cutovers or other significant activities scheduled within the next 24 to 48 hours. |
|  |  | Provide Weekly Transition Planning Reports that describe progress in scheduling transitions. |
|  |  | Provide Weekly Transition Execution Reports that describe progress in completing transitions. |

# 4.0 Transition Planning

Transition planning encompasses anticipating and addressing all the possible factors affecting the start and successful completion of transition.  These activities include: establishing inventory, estimating and budgeting for transition costs, modifying incumbent FTS2001 contracts, developing Regional Services coordination, addressing Certification & Accreditation (C&A) concerns, documenting Designated Agency Representative (DAR) Guidelines, establishing the Transition Coordination Center (TCC) and contractor support, developing enhanced operational support systems (OSS), advocating Agency-level transition planning, supporting Fair Opportunity, analyzing contractors’ transition plans, developing Networx transition schedules, and defining an approach for prioritizing transition orders during crises on a large scale or across multiple Agencies.

## 4.1 Inventory Establishment

Establishment of an FTS2001 baseline inventory ensures all stakeholders have a comprehensive understanding of the services that must be disconnected and provides information for planning for the initial growth of services on Networx.  Inventory establishment, that is, the development of Transition Baseline Inventory (TBI), is a necessary requirement for a successful transition as identified in the FTS2001 Lessons Learned document (Appendix C).  GSA’s role relative to inventory establishment is to assist Agencies in developing an accurate baseline inventory.   An accurate and complete inventory will:

- Establish a validated baseline inventory that accurately identifies the services to be transitioned and subsequently disconnected

- Provide a baseline of record for measuring transition progress in a consistent manner across all Agencies, vendors, and services

- Provide input to the Networx Pricer in order to facilitate Agency Fair Opportunity planning

- Serve as an input to the Transition Information Portal (TIP) (see Section 7.2) for transition tracking

- Support the transition credit process.

The TBI has evolved through a period of development and continuous building of the data therein.  GSA populated TBI with data from the FTS2001 contractors and merged it with billing data GSA routinely receives.  In January of 2007 GSA released the TBI into production and gave Agencies access to validate their records it contained or to upload their own data from Agency-specific databases.  At the end of this validation period,  GSA took a snapshot of the data to form the baseline from which to measure transition progress.  Also during the validation period, GSA provided the list of street addresses from TBI to Telcordia to validate as many addresses as possible and their formats prior to Agencies placing orders.  This should minimize provisioning errors or delays resulting from unknown addresses.

Although Agencies are not required to use the TBI application, there are several significant reasons for Agencies to validate the data.  First and foremost, it will become the database of record for GSA’s reporting of transition progress, Government-wide and Agency- or vendor-specific, and Agencies should use this as a basis for their internal reporting needs.  One of the lessons learned from the previous transition prescribed single-source reporting to avoid conflicting data.  Also, GSA has recommended that Agencies who do not have an existing FTS2001 inventory use the TBI application for transition planning.  The application will provide a starting point for Agencies to establish their validated baseline inventory.

The TBI application and how it is used for tracking transition are discussed in greater detail in Sections 7.1 and 7.2.

## 4.2 Estimate and Budget for Transition Costs and Reimbursement to Agencies

Transition costs can be separated into component elements that are either the responsibility of the Networx program or of the Agencies.  The Networx program will reimburse certain transition costs the Agencies incur in order to reduce the financial burden of transitioning from the expiring contracts.  The Taxonomy developed by the TWG and signed by the IMC identifies the transition cost elements to be borne by the Networx program and by the Agencies.

GSA completed a detailed, comprehensive estimate and budget for Networx transition costs for program-level support and certain costs GSA will reimburse to the Agencies, as defined in the Taxonomy. It is based on similar costs to transition to FTS2001, a projection of traffic and service mix from what is on FTS2001 to what can be expected on Networx, and an assumption of how much FTS2001 service will actually undergo physical transition to a new service provider on Networx.  The transition estimate applies to Networx program costs only and does not include Agency-specific costs.  A detailed white paper describing the methodology is available to Government personnel.  GSA has budgeted for the FTS2001 transition to Networx through the Acquisition Services Fund (formerly known as the IT Fund-299X).

GSA subsequently developed a detailed process for reimbursing Agencies those costs identified as Networx program costs.  It became incorporated into the Taxonomy on May 31, 2007, and the IMC approved it June 11, 2007.  This process will form the basis for development of an application to administer the process in E-MORRIS.

## 4.3 Modify Incumbent FTS2001 Contracts

The incumbent FTS2001 contracts were modified to ensure that appropriate contractor assistance will be provided throughout the FTS2001 to Networx transition.  Coordination with FTS2001 contractors was identified as a significant lesson learned for the FTS2001 transition.  Therefore, GSA negotiated modifications with each of the FTS2001 contractors to ensure their involvement in the transition to Networx.

The FTS2001 contract modification includes those responsibilities defined in Section 3.7, above, which include, but are not limited to the following activities:

- Assisting GSA and Agencies in planning for transition to Networx by gathering FTS2001 inventory data, system requirements, and site specific information

- Participating in service-by-service transition planning and execution activities with the ordering Agency and Networx contractor(s)

- Providing weekly transition status reports based on disconnected FTS2001 services during the previous reporting period

Note that the Networx contracts have been structured so that these transition support requirements are included, eliminating the need to add them for future transitions.

## 4.4 GSA Regional Services

GSA Regional Services’ role in transition planning is to coordinate with Agencies to establish processes for the transition of local services delivered through the Regional consolidated systems.  Currently, Regional Services is conducting the following transition planning activities:

- Reviewing lessons learned from previous transitions

- Developing regional transition plans to accommodate various scenarios

- Documenting transition-related processes

- Performing regional assessments

- Identifying resource requirements

- Identifying GSA regional transition managers and other points of contacts (POCs) at both the national and field levels

- Preparing guidelines for using the Networx contracts in conjunction with regional contracts

Regional Services can help to reduce or eliminate potential risks to Agencies by sharing lessons learned from prior transitions, implementing best practices, and providing expertise in resolving challenging transition issues.  Additional details on Regional Services can be found in Section 10 and in the Regional Transition Plan that GSA published separately.

## 4.5 Certification & Accreditation (C&A) Concerns

The Federal Information Security Management Act (FISMA) sets requirements for protecting Government data and mandates a certification and accreditation (C&A) process within each Agency for the systems it uses to store, process, and transmit the data.  The TWG developed a series of concerns it raised to GSA with regard to the impact of C&A on the transition to Networx.  Specifically, the TWG’s concerns and issues and current status are described below in Exhibit 4.5.

Exhibit 4.5 C&A Concerns/Issue Resolution

| Issue Number | Description | OMB Guidance | Current Status |
| --- | --- | --- | --- |
| 1 | The impact of transition on existing C&As | Only the Agencies can determine the impact of transition on their existing C&As | Closed |
| 2 | The ability for Agencies to use an Interim Authority to Operate (IATO) when transitioning services that use the public telecommunications network | OMB does not recognize IATOs | Closed |
| 3 | The ability of the Government to C&A the public network | OMB does not expect the Government to C&A the public network | Closed |
| 4 | The responsibilities of Agencies, such as GSA, that provide contracting vehicles for telecommunications services | GSA published guidelines identifying the appropriate reviews, reports, and other information documenting contract compliance that Agencies need to assist them in certifying their networks | Closed |

As a result of the meeting with OMB to obtain further guidance on each concern, GSA was tasked with developing a series of documents, which would in turn, resolve Issue 4.  These documents consisted of the following:

- A “crosswalk” of the security requirements on FTS2001 to Networx.

- A list of security requirements for Networx service providers on Government contracts.

- A list of actions of administrators of Networx services contracts to monitor contractor’s adherence to security requirements.

These documents have been completed and distributed to Agencies through the TWG to aid in transition planning efforts.

## 4.6 Designated Agency Representative (DAR) Guidelines

As part of the transition planning process, GSA has advised Agencies to designate DARs and DAR Administrators.  DARs are individuals appointed by each Agency and are responsible for placing and managing orders for their respective Agency.  The DAR Administrator, who is also appointed by an Agency, is an individual responsible for maintaining the list of DARs, providing instruction and training for DARs, and providing Agency Hierarchy Codes (AHCs) for ordering.  GSA will track Agencies’ designation of DAR Administrators as an indication of Agency preparedness for the transition.

GSA developed a set of DAR Guidelines to provide Agencies with additional guidance on the DAR roles and responsibilities for the Networx contract.  The DAR Guidelines provide a general set of guidelines for individuals appointed as DARs and DAR Administrators and clarifies that DARs are authorized to place orders on the Networx contracts.  The DAR Guidelines have been completed and distributed to Agencies through the TWG.

## 4.7 Contractor Support for the Transition Coordination Center (TCC)

GSA’s TCC assists transition stakeholders, is staffed by GSA and contractor support, and became operational at Networx Universal contract award.  GSA awarded a task order in February 2007 to acquire contractor support for the TCC from three telecommunications consulting firms:  Apptis, CACI, and GTI.  The TCC contractors support the TCC in the roles and responsibilities identified in Section 3.1.2, above, by providing the following functions:

Strategic guidance

Customer outreach

Cutover assistance

Agency-specific transition support

TCC operations

Transition tracking and reporting

Tier 2 and Tier 3 Help Desk referrals.

Section 9.0 describes the TCC.

## 4.8 GSA’s Operational Support System (OSS) Enhancements

GSA has developed and enhanced several OSS tools to assist Agencies as they prepare to transition to the Networx contracts.  GSA OSSs such as the TBI, TIP and Networx Pricer will ensure that Agencies are provided with sufficient resources to effectively transition to the Networx contracts.  Section 7.0 describes each of the transition support tools in greater detail.

## 4.9 Agency Level Transition Planning

In coordination with the TWG, GSA provides guidance through a variety of documents to support Agency level transition planning activities.  Documents such as the TWG Pre-Award Transition Guide, DAR Guidelines, and various templates for Agencies to use at their discretion have been and are being developed to provide Agencies with specific transition planning guidance.  With regard to transition planning, GSA expects Agencies to:

- Establish a transition baseline inventory of their FTS2001 services

- Prioritize their services to be transitioned

- Develop transition schedules and share them with GSA

- Conduct risk management activities in order to minimize transition risks

- Copy GSA on the appointment letters for DAR Administrators and DARs

- Notify GSA of Fair Opportunity decisions the Agency has made

- Support GSA in reporting valid transition progress status.

Effective planning will best prepare an Agency to transition to Networx by defining what services will be transitioned, how the transition will be executed, and by whom.  While GSA is not expecting Agencies to develop formal transition plans, some Agencies may choose to do so.  GSA would like to receive a courtesy copy of any Agency plans so that GSA is aware of Agency requirements, critical needs, mission impacts, schedules, priorities, and approaches to factor them into GSA’s management approach.  At a minimum, GSA needs to know each Agency’s high-level approach to transition, including how it expects to group services and sequence them for transition, the target timeline, and any mission-critical factors.

Additionally, most Agencies have appointed Transition Managers who are responsible for key aspects of the transition including planning, execution, tracking, and reporting of their Agency’s process.  GSA has asked the TMs to identify what level will maintain transition responsibility, whether it be at the headquarters level or distributed among Agency Bureaus or other subcomponents and to provide points of contact for those levels.  The establishment of Agency points of contact is a significant step in transition planning and ensuring proper communication to all transition stakeholders.  Transition Managers will act as the lead contact for the Agencies with FTS2001 and Crossover contractors, Networx contractors, and GSA.  They will also carry out the roles and responsibilities as previously defined in Section 3.6.1, above.

## 4.10 GSA Support for Fair Opportunity

GSA will support the Fair Opportunity process by providing resources to aid in Agencies’ Fair Opportunity planning activities and by monitoring their Fair Opportunity selections.  Because the details of the Fair Opportunity process will likely vary based on each Agency’s mission and transition requirements, GSA has advised each Agency to develop its processes based on its own unique Agency requirements. The TWG has developed additional Fair Opportunity guidance to ensure Agencies are adequately prepared to plan for Fair Opportunity; this Fair Opportunity guidance is available on the Networx Transition website, which is a link off the Networx website at www.gsa.gov/networx.  Further, GSA provided a Fair Opportunity and SOW Guide for the SOW process as defined in the Networx contracts; Agencies may go to the Networx website or contact their TSMs for a copy of this Guide.  Lastly, GSA and the TWG have established an estimated timeline for completing Fair Opportunity to ensure Agencies transition in a timely manner.  GSA will then track each Agency’s first Fair Opportunity decision as an indicator of Agency preparedness for transition and the receipt of notification of the final Fair Opportunity decision as a criterion for transition reimbursement.

## 4.11 Contractors’ Transition Plans

GSA is responsible for ensuring the Transition Management Plans (TMPs) from the Networx contractors meet the terms of the contracts.  In preparation for Networx award, GSA validated that the TMPs addressed all requirements in Section C.4.4.2.1 of the Networx RFP.  While reviewing each Contractor’s TMP post award, GSA identified issues, risks, and potential conflicts with the Government’s plans.  GSA will publish summaries of the plans for the TCC’s and Agencies’ reference and has made the plans themselves available to the Agencies to review.

## 4.12 Schedule Development

GSA established, and the TWG approved, a transition schedule with appropriate milestones to address the various activities that occur during transition planning and transition execution. This schedule appears in Section 2.3, above.  Agencies should use the transition schedule to coordinate Agency transition activities around major transition milestones.

# 5.0 Staffing and Training

The transition to Networx will require significant resource demands on each transition stakeholder.  Therefore, it is imperative that staffing and training requirements are defined early in order to effectively plan for transition.  The sections below identify GSA’s role relative to the planning for staffing and training to support the Networx transition.

## 5.1 Staffing

GSA has assembled a transition team consisting of GSA and contractor resources, totaling approximately 38 people.  The GSA staff includes personnel with experience in other large transitions, including FTS2000 to FTS2001, as well as other critical program management (PM) skills.  The contractor staff complements the GSA team with experts from five consulting firms specializing in program management, systems development, customer support, telecommunications design and operations, program analysis, and first-hand experience with the previous transition from both a Government and service provider’s perspective.  Noblis provides a key PM role for the transition team in that it has done a comprehensive resource assessment that validates and complements GSA’s assessment and forms the basis for the functional roles of members of the transition team.  See Appendix G for the Responsibility Matrix of the GSA Transition Team.

Agencies should likewise determine transition staffing requirements prior to Networx contract award.  They should determine if existing Government personnel are available to staff transition roles or if contractor support is required.  The TWG Pre-Award Transition Guide encourages Agencies to forecast staffing, financial, and other resources that may be needed throughout the transition to Networx.  This includes examining staffing levels, determining if adequate personnel exists, addressing staffing shortfalls that may require contractor support, and identifying personnel to receive training.  In addition, Agencies are advised to apply sound internal project management best practices in order to plan for the expected transition workload and establish a hierarchy of transition teams at the sub-Agency level if appropriate.  If Agencies determine additional Agency-specific support is required to manage Networx transition activities, GSA can advise Agencies, through their TSMs, on Government-Wide Acquisition Contracts (GWACs) that can provide staffing support for the transition effort; a listing of vehicles is included in Appendix D.

## 5.2 Training

GSA is making available several training opportunities for its own transition team as well as for Agencies.  First, the TCC has developed and maintains a library of SOPs and ensures TCC staff are kept current on these SOPs.  Second, GSA will deliver training sessions to the Agencies for the following:  TBI, TIP, and the Networx Agency Pricer.  In fact, GSA has already trained nearly 200 Agency personnel in TBI classes and all the Agencies in use of the Pricer.  Third, GSA will publish a Transition Training Handbook (TTH) that covers a variety of topics critical to the success of transition as well as helpful in ensuring Agencies get through transition with minimal frustration and confusion.  Of course, GSA will benefit from the same training.  The TCC will deliver training topics from the Handbook in a variety of media appropriate to the topic and audience.  Lastly, Networx contractor training programs will be available to the Agencies in accordance with Section C.3.7 of the Networx contracts.  These programs include:

- Training for Executives who are senior level Government managers

- Training for Designated Agency Representatives (DARs) who are Agency representatives with the authorization to order products and services

- Training for Network Operations personnel who are Agency representatives with network monitoring responsibilities

The training programs offered to Agencies will ensure staff are sufficiently knowledgeable of transition resources and activities.

# 6.0 Transition Execution And Management

Once Agencies begin placing transition orders, execution and management of transition begins.  This consists of the provisioning process and tracking and reporting transition status.

## 6.1  Service Provisioning

When the Agency places transition orders, it is responsible for monitoring the provisioning of the services through completion of implementation and transition.  An Agency may place orders individually or group them into Transition Project Specific Plans; in either case, the Agency must indicate they are transition orders by indicating Transition =Y and identify the service it is transitioning from.  The Agencies will receive a series of acknowledgments from the contractor, culminating in a Service Order Completion Notice (SOCN).  From that time, the Agency has three working days to test the service and notify the contractor if it is not working acceptably.  If during the cutover from FTS2001 service to the Networx service, the Agency or the Networx contractor determines the new service is not working properly, there are terms in both the Networx and FTS2001 contracts for falling back to the FTS2001 service.  Agencies can become familiar with these terms through the TTH, from their TSMs, or by researching the contracts themselves.

Although GSA does not track individual orders through the provisioning cycle, it receives and analyzes transition progress reports from the Networx contractors and disconnect reports from the FTS2001 contractors.  Through these reports GSA keeps abreast of transition orders that are to be implemented inside windows of 60 days, one week, and 24 hours.  GSA uses disconnect reports to track the progress of moving off FTS2001 contracts.

## 6.2 Progress Tracking and Reporting

GSA provides oversight to ensure transition execution occurs on schedule.  The primary purposes of this oversight are as follows:

- GSA’s transition team and the TWG will use tracking data to analyze trends in order to identify problems with a specific vendor, a certain service, or an Agency that needs assistance and to formulate resolutions proactively.

- GSA senior management will have information to gauge the need for exercising options on the FTS2001 contracts.

- The Networx PMO, GSA senior management, and Agency TMs will forecast the duration of transition and factor that into resource planning, both financial and personnel.

- The TWG has committed to using GSA’s tracking reports as the definitive measure of transition progress across the Federal Government.  Additionally, Agencies may augment with their own additional details.

GSA’s tracking system employs three methods of data collection and analysis.  It records Agency decisions and information that indicate an Agency’s readiness for transition.  It measures the extent to which services are being disconnected from expiring contracts and implemented on Networx contracts.  And it involves inspection of reports to identify major or chronic issues or negative trends

The transition tracking system records

- Agencies’ appointments of DAR Administrators and DARs.  Agencies send a letter to GSA with this information.

- Agencies’ Fair Opportunity decision(s).  Agencies send a letter(s) to GSA with this information.

The tracking system provides the following two measures, by type of service and at the Government-wide as well as Agency level:

- Percentage of disconnects measured against the TBI snapshot.  This information comes from reports the FTS2001 vendors provide to GSA.

- Number of transition orders completed on the Networx contracts.  This is based on the SOCNs GSA will receive when services are implemented.  The SOCNs will include a flag identifying transition orders.

Note that because of the differences between services on the FTS2001 and Networx contracts, and because not all services are expected to be moved to the Networx contracts, the percentage of disconnects and number of transition orders completed cannot be correlated to one another.

The transition tracking approach includes inspection of various reports, which can be summarized at the Government-wide level as well as sorted by service, vendor, or Agency.  GSA tracks troubles reported by those involved in transition.  This allows the transition team and the TWG to identify major or chronic problems and trends that need attention.  It could include, for example, transitions that fail to complete on their first attempt or failures to meet SLAs.  Additionally, GSA monitors transition progress reports the Networx vendors deliver to GSA.  These include several deliverables that report the vendors’ own measures of transition activities.

The transition tracking system will store data and prepare reports using the TIP.  This is a web-based system that authorized stakeholders may access to see the status of transition in a dashboard format.  Reports will be completed monthly and include

- DAR Administrators appointed, reported as total number and as a percentage of the Agencies with TMs

- Agencies that have made Fair Opportunity decisions, reported as total number and as a percentage of the Agencies with TMs

- Disconnects, measured as a percentage of the TBI snapshot, reported Government-wide and by Agency, vendor, and service.  Further, GSA will track disconnects against a quarterly estimate of what is expected during transition, based on the actual business volume trends in the previous transition to FTS2001, giving a general idea of how transition is progressing.  As Agencies provide more information specific to their transition strategies, GSA may update this expected profile.

- Transition orders completed on Networx contracts, measured as number of SOCNs received for transition orders, reported Government-wide and by Agency, vendor, and service

- Major or chronic issues, reported by source, either vendor reports or trouble tickets, short description, and status of resolution.

Specific details of regarding the TIP are in Section 7.2.

## 6.3  Communications and Issue Resolution

Extensive communication and coordination across GSA and transition stakeholders will play a critical role in the success of transition execution.  The GSA Transition Team and the TSMs will play a central role as the liaisons between transition stakeholders and will support issue resolution for Agencies and contractors.  GSA’s detailed Communications Plan is located in Appendix F.

## 6.4 Custom Design Documents (CDDs), Managed Design Documents (MDDs), and Contract Modifications

CDDs, MDDs, and contract modifications provided the capability to make changes to the FTS2001 contract.  CDDs and MDDs are custom services that are not standard CLINs on the FTS2001 contracts.  These custom services have resulted in the need for Agencies to decompose all FTS2001 custom services into Networx Contract Line Item Numbers (CLINs) to determine what services can and cannot be defined as CLINs on Networx.  Many of these custom services were provided to Agencies by FTS2001 contractors in order to meet unique Agency requirements.  However, the development and procurement of these CDDs and MDDs services pose a unique set of challenges to Agencies as they are transitioning their services from the FTS2001 contracts to Networx because many of these custom services were not fully documented, making it difficult to identify the components that make up each unique service.

In order to minimize this challenge, Agencies should conduct a gap analysis of the custom CDDs and MDDs services against the Networx contract services.  If gaps exist, Agencies may elect to discontinue the service or elect to develop a SOW to define the service requirements for ordering the service on Networx.  Moreover, Agencies must consider a wide range of Fair Opportunity decision criteria for each SOW.  In order to assist Agencies with these challenges in developing SOWs, GSA developed a Networx Fair Opportunity and SOW Guide that provides Agencies specific guidance on how to develop a SOW.  Following the notification from the Agency of the selection of a Networx contractor to provide the services in the SOW, GSA will then modify the Networx contract to make the custom service available to all Agencies.  For assistance with any customized solution or the SOW process, Agencies should contact their TSMs.

# 7.0 Transition Support Tools

Transition support tools have been established to facilitate transition activities as Agencies move from the FTS2001 contracts to Networx.  The transition support tools discussed below include GSA OSSs such as the TBI application, TIP, NxPMO Help Desk, the Networx Pricer, and the Networx Inventory Management Application (NIM).  These tools address many of the lessons learned from previous transitions.

GSA has a centralized location and process for accessing transition information and tools.  The transition website, www.gsa.gov/networxtransition, is the home page for linking to these tools and requesting access to them as well as finding additional information and resources helpful to Agencies and contractors involved in transition. Examples of information that could be included on or linked to from the Web site are:

Transition updates

Schedules and milestones

Advantages of transition to Networx

Transition policies, procedures, and supporting documentation

Transition Training Handbook

TSMP

Transition templates

Guidelines for managing Agency baseline inventories

Transition Action Notices

Points of contact at GSA and incumbent and Networx contractors

Agency points of contact (DARs, Transition Managers, etc.)

Hyperlinks to related web sites

Transition tutorial and other resources

FAQs

## 7.1 Transition Baseline Inventory (TBI)

The TBI application, which is located at https://morris.ftsbilling.gsa.gov/ (login required), provides Agencies a means for establishing a baseline inventory of FTS2001 services to be transitioned to Networx.  Exhibit 7.1a below displays a screenshot from the TBI application.

Exhibit 7.1a TBI Application Screenshot

The TBI application is intended to support key transition activities such as:

- Establishing a validated inventory

- Providing input to the Networx Pricer

- Serving as a baseline for transition tracking

- Supporting the transition reimbursement process

The design of the TBI application was based on input provided by and in collaboration with the TWG.  First, the TWG developed a recommended inventory template for each type of service, which GSA used to design the database structure.  GSA then populated the database with FTS2001 inventory and billing data collected from the contractors and from GSA’s billing system.  GSA then conducted a Beta Test of the TBI application with nine Agencies of varying size to ensure system requirements met user expectations.  Through the Beta Test period, several of the testers identified additional requirements that should be incorporated into the application.  GSA then released the TBI application for production in January 2007 so that Agencies could begin validating their inventory.  The TBI application will have future releases to deliver enhancements and improve the system functionality.

Access to the TBI application is controlled by each Agency’s Transition Manager(s).  Transition Managers designate who has access to the TBI application and to what Agency Hierarchy Codes (AHCs).  By controlling access at the AHC level, Transition Managers ensure users are restricted only to inventory data they are responsible for validating.

Agencies are encouraged to establish their TBI and validate their inventory through one of the following methodologies as defined in Exhibit 7.1c below.

Exhibit 7.1b Inventory Validation Methodologies

| Methodology | Description |
| --- | --- |
| 1 | Using the online TBI application, an Agency user validates its complete inventory. |
| 2 | Using the online TBI application, an Agency user downloads inventory data for off-line comparison with any existing Agency inventory data. Once the Agency has conducted an off-line cross reference analysis between the TBI application data and Agency inventory data, the Agency user may upload the validated inventory data set into the TBI application. |
| 3 | An Agency user may upload the current Agency-owned inventory into the TBI application. |
| 4 | An Agency user submits the current Agency-owned inventory data in the TBI template format to GSA. GSA then loads the Agency inventory into the TBI application. |

The inventory validation period will last until a “snapshot” is taken of the TBI at a date determined by the TWG.  During the inventory validation period, the TBI application will receive monthly updates from the FTS2001 contractors to keep the data current.  On January 11, 2008, GSA took a snapshot of the validated records to establish a baseline from which to measure transition progress.  GSA expects Agencies to continue to monitor their TBI each month in order to keep their inventory data accurate and complete; for those Agencies who choose to upload their inventory into TBI and not keep it current, the TWG has determined those Agencies must provide GSA with transition status reports, meeting a format specified in the TIP user requirements document, so GSA can update TBI.  In addition, the TBI will be used to support the transition reimbursement process as defined in the Taxonomy document.

## 7.2 Transition Information Portal (TIP)

The TIP is being developed to allow GSA and Agencies to track the transition progress from the FTS2001 contracts to Networx.  The TIP tool became operational following Networx contract award and is ready to serve its role as Agencies begin placing disconnect and install orders on the FTS2001 and Networx contracts respectively.  GSA anticipates that Agency personnel will use the TIP tool to monitor their overall transition progress by AHC in order to execute their transition activities according to their Agency transition schedule.  GSA’s ultimate goal is to disconnect 100 percent of the FTS2001 services and transition them to Networx prior to the expiration of the FTS2001 contracts.

The TIP inputs include reports and notices from FTS2001 and Networx contractors that identify the status of disconnect and install orders.  Additionally, those Agencies who choose to upload their inventory into TBI and do not keep it current, the TWG has determined those Agencies will provide GSA with transition status reports, meeting a specified format, so GSA can update TBI, which will then update TIP reports.  Exhibit  7.2a below depicts the reports and notices from FTS2001 and Networx contractors that will be used as inputs for the TIP tool.

Exhibit 7.2a TIP Inputs

| Contract | Report Source | Description |
| --- | --- | --- |
| FTS2001 | FTS2001 Disconnect Report | Count of disconnects |
|  |  | Percentage of disconnects |
|  |  | Status of disconnects |
| Networx | Transition Action Notice (C.4.3.4.1 of Networx RFP) | Identify activities required for a specific transition order. It will be sent sixty (60) calendar days prior to the transition event, such as a service cutover. |
|  | Go/No Go Notice (C.4.3.4.2 of Networx RFP) | Confirms or denies a scheduled cutover. It will be sent not less than 24 hours before each scheduled cutover or other significant transition activity. |
|  | Weekly Transition Planning Reports (C.4.3.4.3 of Networx RFP) | Provides a forecast of scheduled cutovers ranging from 6 months out to within the current week. |
|  | Weekly Transition Execution Reports (C.4.3.4.4 of Networx RFP) | Provides a weekly confirmation of the cutovers from the previous week. |

The TIP also uses the TBI inventory data to serve as a baseline for tracking of FTS2001 disconnects.  As Agencies place installation orders under the Networx contracts, they will subsequently (or concurrently) place disconnect orders for related FTS2001 services.  These disconnect orders and installation orders will be reflected as transition progress in the TIP tool.  The TIP receives a monthly update from the TBI application to provide an accurate transition measurement.

The outputs of the TIP consist of reports that GSA and Agencies can use to track FTS2001 disconnects and Networx installs.  TIP users will be able to view a variety of reports displaying that status of both disconnects and installations at a Government-wide and Agency-specific view.  Exhibit 7.2b below provides a sample report from the TIP tool.

Exhibit 7.2b Sample TIP Report

As defined by the Agency’s Transition Manager, Agency users will have access to Agency-specific reports based on AHC.  In addition, some Government-wide reports on transition progress will be made available to Transition Managers.  However, other transition reports, such as contractor performance reports, will only be made available to GSA staff in order to monitor performance trends.  These reports consist of the listing below in Exhibit 7.2c of TIP output reports.

Exhibit 7.2c TIP Output Reports

| Report Type | Report Description |
| --- | --- |
| FTS2001 Disconnect Status Reports | TBI by Service for all FTS2001 contractors combined |
|  | TBI by Service by FTS2001 contractor |
|  | Disconnects by Order Status for all FTS2001 contractors combined |
|  | Disconnects by Order Status by FTS2001 contractor |
|  | Disconnects by Order Status for all Services combined |
|  | Disconnects by Order Status by Individual Services |
|  | TBI versus Completed Disconnects by Service |
|  | TBI versus Completed Disconnects by FTS2001 contractor |
| Networx Installation Status Reports | Installations by Order Status for all Networx contractors |
|  | Installations by Order Status by Networx contractor |
|  | Installations by Order Status for all Services combined |
|  | Installations by Order Status for Individual Services |

Ultimately the TIP will be used to identify transition completion.  Transition completion will occur when all services from the FTS2001 TBI have been disconnected.

## 7.3 Transition Coordination Center (TCC) Problem Resolution

GSA has implemented a Help Desk to manage transition-related issues Agency customers and contractors experience.  However, it is not intended to replace the primary means of resolving issues with a service provider.  The FTS2001 and Networx contracts include trouble management functions and procedures that Agencies should follow when there are problems with the performance of their services or the contractor.  Agencies can contact the GSA Help Desk for assistance when this primary method is not satisfactory.  The Help Desk is staffed by GSA and contractor personnel who are knowledgeable with regard to FTS2001 and Networx related issues.  Tier 1 includes a call center as well as the TSMs, both of whom take calls or emails reporting problems or inquiries, open tickets, and, when necessary, hand them off to the appropriate Tier 2 subject matter expert, who may be an organization or individual to resolve the issue.  The Help Desk handles questions or issues related to service clarification, contract, billing, ordering, inventory, Regional Services, and other transition, management, and operational areas.  An escalation process has been implemented with the issue resolution process to ensure that Agencies, FTS2001 contractors, and Networx contractors receive responses to their questions in a timely manner.  This structure allows GSA to capture a record of all contacts, perform trend analysis, and manage performance of the Help Desk.  Agencies and contractors can reach the Help Desk at 866-472-0274 or networx.support@gsa.gov .

## 7.4 Networx Pricer

The Networx Pricer tool facilitates Agency transition activities for selecting Networx services.  The public Networx Pricer tool, which contains current and prior year prices, was released in mid-May 2007.  The first release of the Networx Agency Pricer tool, which contains prices for the full ten years of the Networx contracts, was implemented in early June 2007.  GSA solicited Agency involvement in the development of the Networx Pricer requirements to ensure it incorporates Agency user requirements.  The Networx Pricer allows users to compare pricing information among Networx vendors for market research and Fair Opportunity evaluations.   Users will be able to produce individual price quotes and multi-point price quotes, search for CLIN pricing across all Networx contractors, model “what-if” scenarios, and research FTS2001 prices.  Agencies can access the Networx Pricer from a link on www.gsa.gov/networx.  Access to the 10-year Pricer is restricted.

## 7.5 Networx Inventory Management Application (NIM

The Networx Inventory Management (NIM) application will populate and maintain a database that provides an accurate record of all services installed on the Networx Universal and Enterprise contracts.  NIM is a GSA application intended for use by the Government.  The application will use the SOCN received from Networx contractors to populate and maintain an inventory of all Networx services installed. It provides a method for GSA and Agencies to audit the inventory records of the Networx contractors.

# 8.0 Risk Management

Risk management includes identifying sources of risk and establishing mitigation strategies that address potential risks which may affect transition. GSA and the TWG are identifying and managing risks associated with the transition to Networx proactively.   Risk management will minimize the likelihood of expected and unexpected transition delays.

## 8.1 Sources of Risk

The FTS2001 Lessons Learned document, located in Appendix C, provides a thorough analysis of the known sources of risk based on previous transition experiences.  Risks may occur during one or more of the transition project phases defined below:

- Transition Planning Phase:  Includes establishing schedules, determining necessary resources, and identifying potential risks.

- Transition Execution Phase: Involves the implementation of the transition plan and execution of transition activities.  Transition activities include Fair Opportunity, vendor selection, and service acceptance.

- Transition Monitoring, Controlling and Tracking:  Involves the tracking of transition performance in accordance with the transition schedule and ensuring FTS2001 and Networx contractor performance.

These risks were documented by transition stakeholders.

## 8.2 Risk Mitigation

By analyzing and determining the sources of risk proactively, GSA has developed effective risk mitigation strategies that use industry best practices.  Risk mitigation strategies alleviate potential risks to transition stakeholders that can adversely affect transition activities.  To aid in this effort, GSA has identified and categorized a series of mitigation strategies that are applied to lessons learned from previous transitions to address each of the identified areas of risk.  A sample of the risk mitigation strategy document is listed in Exhibit 8.2 below and the full set appears in Appendix E.

| Risk Identification | Risk Impact | Risk Mitigation Strategy |
| --- | --- | --- |
| Project Phase | Risk Description |  |  |
| Transition Planning | Magnitude was not fully appreciated | Cost and schedule overruns, inadequate training for staff | GSA has outlined in Section C.1.2 of the Networx RFP the scope of the activities required to transition to the Networx contracts. |
|  |  |  | GSA has created planning documents such as the TSMP, Transition Timeline, and Site Transition Template, that outline the specific roles and responsibilities relative to transition. These documents did not exist in previous transition efforts |
| Transition Execution | Poor contractor support during transition | Schedule delays and service interruptions | GSA has referenced SLAs in Section C.3.2.2 of the Networx RFP to which the Networx contractors must adhere. |
| Transition Monitoring, Controlling, & Tracking | Different Government-wide reporting structures | Not a clear understanding of transition objectives and progress measurements | Protocol regarding transition reporting has been outlined in Section 4.4 of the Networx RFP. Reporting formats have been defined to ensure that desired data elements are presented in a consistent manner. |
|  |  |  | Progress monitoring and tracking procedures have been clearly articulated in a users’ requirements document the TWG developed, representing the agreement for all Agencies to use a single source of transition status across the Government. |

Exhibit 8.2 Sample Risk Mitigation Strategies

# 9.0 Transition Coordination Center (TCC)

To assist and support Agencies with the movement of services from the expiring FTS2001 telecommunications contracts to Networx, GSA established a Transition Coordination Center (TCC).  The TCC is headed by a TCC Manager and will report to GSA’s Transition Management Team.  It is staffed by both GSA and contractor personnel.  The TCC’s customers are both internal and external to GSA and include the 11 GSA Regions, Agencies, FTS2001 vendors, and Networx Vendors.  The TCC may also respond to requests for information and assistance from GSA management, TSMs the IMC, the IMC TWG, and other entities.

This section contains a brief description of the TCC and its operation.

## 9.1 TCC Objectives

An objective of the Networx transition process is for all Agencies’ FTS2001 services to be disconnected before the incumbents’ contracts expire.  The TCC assists in achievement of the overall Networx transition objective as follows:

It facilitates the transfer of Federal Agencies’ telecommunications products and services from the FTS2001 and Crossover contracts to Networx contracts.  The TCC provides guidance through this process to help Agencies develop their transition plans and other documentation to facilitate the transition process.  In addition, the TCC responds to transition-related questions and issues from customers and acts as a liaison between the Agencies, telecommunications contractors (both incumbent and new), and various GSA organizations, including the Regions.

The TCC monitors all Agencies’ transitions to provide a Government-wide view of the status and progress of transition.  By analyzing transitions across Agencies, the TCC is able to identify common issues and problems and take a proactive role in resolving them and preventing recurrence.

The TCC provides reports and briefings on the status and progress of the Networx transition to GSA leadership, the Transition Working Group (TWG), and the IMC.  The information gathered by the TCC is used to respond to requests for Congressional testimony and from other stakeholders.

## 9.2 TCC Structure And Functions

The TCC contains the following teams:

The Cut Team provides cutover assistance to TCC customers, as needed.

The TCC Operations (TCC Ops) Team is responsible for the day-to-day TCC activities.  TCC Ops tracks action items, develops and implements procedures, and manages TCC day-to-day resource assignments.

The TCC Project Management and Control Team develops and maintains a master schedule of all TCC activities and performs management and administration of TCC support contractors’ Task Orders.

The TCC Systems Support Team performs system development, maintenance, and trouble-shooting of the software applications that support the TCC.  These applications include the portal for tracking transition progress, i.e., the Transition Information Portal (TIP) web site.

Regional Transition Support is the liaison function to the GSA Regions and facilitates transition of the customers they serve.

The Transition Management Team and the TCC offer efficient and timely customer service and support through conduct of the following functional areas:

Strategic guidance

Customer outreach

Cutover monitoring and assistance

Agency-specific transition support

TCC operations

Transition tracking and reporting

Tier 2 Support and Tier 3 Help Desk Referrals.

## 9.3 Operations

The TCC operates in GSA office space in the Willow Wood complex in Fairfax, Virginia.  The TCC became fully operational at the time of the first award of the Networx contract in March 2007 and will function through the end of the transition, that is, when all services have moved from expiring FTS2001 contracts.  TCC personnel maintain a physical presence at the GSA facility from 6 AM to 10 PM (EST or EDT, as applicable), Monday through Friday as needed.  If transition activities, such as cutovers, are planned from 10 PM to 6 AM weekdays or anytime during a weekend, staff will be present at the TCC and at the Agency site, if requested.  If no activities are planned between 10PM to 6AM weekdays or on a weekend, physical presence at the TCC is not required but at least one person will be on-call.

# 10.0 Regional Services Transition Plan

GSA is developing a detailed plan for transition of customers on regional consolidated switches, and it will be published separately.  This section introduces the plan.

The Office of Regional Services delivers local voice, data, and video telecommunications services to customers through 11 regional offices and more than 600 existing systems nationwide.  GSA Regional Services uses a strategy of aggregated procurement within the 11 GSA Regions for the benefit of Federal Agencies seeking local telecommunications services.  GSA Regional Services provides the majority of local telecommunications services through regionally-contracted Metropolitan Area Agreements (MAA) to ensure best service and price to the Government and to maximize competition, similar to the successful FTS2001 program.  MAAs were positioned to establish a framework that could meet the evolving telecommunications needs of Agencies into the future. GSA Regional Services remains committed to providing local telecommunications services through MAAs (existing and new) and to supporting Agency transitions to Networx as part of a flexible complement of local and long-distance telecommunications services.  It will be necessary for each Agency to evaluate all possible contract vehicles—Networx, local MAA, local indefinite delivery/indefinite quantity (IDIQ), and Washington InterAgency Telecommunications System (WITS) (National Capitol Region [NCR] only)—as part of the Networx transition cycle to identify the best overall value and fit for its future local and long-distance telecommunications needs.

## 10.1 Customer Support For Regional Transition

Regional Transition is the process of planning for and transitioning Agency local and long-distance telecommunications services currently provided on a GSA consolidated switch to the new Networx contract.  GSA Regional Service Transition Managers (RTMs) and GSA Regional Services staff will function as the highest tier technical and customer service representatives to Agencies where GSA provides services through its consolidated switches.  A listing of these RTMs can be found under GSA Regional Services on the Networx transition website.

Because GSA Regional Services is generally the customer of record and owner of telecommunications services provided to any consolidated switch customer, GSA Regional Services staff will be directly responsible for the local services transition activities of consolidated switch services in each GSA region.  Any Agencies that buy GSA consolidated switch services through GSA Regional Services should use GSA Regional Services transition teams for all aspects of transition support.  If a Networx transition activity or task is owned by a stakeholder other than GSA, GSA RTMs (or staff) will coordinate and validate the transition activity with the responsible parties and against the accepted transition plan.

## 10.2 Goals And Objectives

The goal for GSA Regional Services transition staff is to complete the transition of 100 percent of the Agencies’ current FTS2001 and Crossover consolidated switch services to the chosen Networx services in a timely, efficient, and seamless manner.  GSA Regional Services transition staff will achieve this transition goal by managing local services transitions for their customers and keeping the transition objectives in mind.

# 11.0  Change History

| VERSION | DATE OF CHANGE | AUTHOR | EXPLANATION |
| --- | --- | --- | --- |
| 1.0 | 6/12/2007 | Multiple | Initial |
| 1.1 | Draft, 1/7/08 | Debbie Hren | Update with current information, reduce attachments published elsewhere |
| 1.2 | Draft, 4/15/08 | Debbie Hren | Updated with comments from Richard Williams, changing future tense to present and correcting CDD language |

## Appendix A:  Glossary

The glossary in this Appendix serves to define terminology used in the TSMP and to provide additional information, as related to the Networx transition.

Agency Bureau (AB) Code: A four-digit numerical code for the Bureau within the Cabinet Department or independent Agency.  Agency Bureau codes are unique to an Agency.

Agency Hierarchy Code (AHC): The Agency Hierarchy Code designates the Agency to which services are to be invoiced and the level within the Agency where these costs are grouped. Except for the first 4 characters, the AHC is a 28

character string that belongs solely to the Agency; it is not to be tampered

with by any other outside organization. The AHC is determined by the

Agency and should follow that Agency's rules concerning the setup of their

[A] - Own budgetary accounting codes (I.E., should ultimately identify the

office that will actually pay for the service being provided), and/or [B] -

Reporting Requirements. The AHC may also be identified with whoever is

actually receiving the service being provided.

Agency-Level Transition Plan (ALTP):  The Networx contractor will provide each Agency with an Agency-Level Transition Plan that describes transition activities specific to each Agency.

Agency Service Request Number (ASRN): Agency-provided service order

number.

Asynchronous Transfer Mode Service (ATMS) Performance Report: A report which provides network statistics, exception analysis, network availability, latency, error rates, and utilization of ATMS over the given period

Certification and Accreditation (C&A): A comprehensive assessment of the management, operational, and technical security controls in an Agency’s information system based on an existing System Security Plan for the Agency, which is followed by the official management decision given by a senior Agency official to authorize operation and to explicitly accept the risks to Agency operations identified in the certification phase.

Comma Separated Values (CSV): A file type that stores tabular data as found in an spreadsheet.

Contract Line Item Numbers (CLINs):  Describes the numbering procedures that are given to offerings and that are mandatory for all contracts.

Custom Designed Documents (CDDs): Documents which contain custom services that are not standard CLINs on the FTS2001/Crossover contracts.

Designated Agency Representative (DAR): A DAR is an employee of a Government Agency who has been authorized by his/her respective Agency to initiate and track Agency specific Networx orders. An Agency designates and authorizes one or more individuals to perform DAR functions for its Networx services. Through the Agency DAR Administrator, each Agency identifies to the contractor its authorized DARs, providing the following information: name, Agency represented, current address, telephone number, E-mail address, the services the DAR is authorized to order and an indication as to whether the DAR has expedited ordering authority.

Designated Agency Representative (DAR) Administrator: Each Agency will appoint a DAR Administrator who will be responsible for maintaining and updating a list of DARs to provide to the contractor(s), providing necessary instructions or training to DARs to ensure that they are fully aware of the requirements and limitations of their ordering authority, and provide Agency Hierarchy codes for their Agency to their Agency’s Networx contractors.

Designated Agency Representative (DAR) Guidelines:  A set of DAR Guidelines that will provide Agencies with additional guidance on the DAR roles and responsibilities for the Networx contract. DAR guidelines will ensure that Agency DARs are properly prepared to place orders on the Networx contracts.  The GSA DAR Guidelines will specifically discuss and provide a general set of guidelines for individuals appointed as DARs and DAR Administrators to follow.

Federal Acquisition Regulation (FAR): The primary regulation for use by all

Federal Executive Agencies in their acquisition of supplies and services with  appropriated funds. It became effective April 1, 1984 and is issued within  applicable laws under the joint authorities of the Administrator of General Services, the Secretary of Defense, and the Administrator for the National aeronautics and Space Administration, under the broad policy guidelines of the Administrator, Office of Federal Procurement Policy, Office of Management and Budget.

Federal Acquisition Service (FAS):  The consolidation of GSA’s Federal Technology Service (FTS) and Federal Supply Service (FSS).

Frame Relay Service (FRS): A data communications service that provides for data connectivity between and among widely distributed end-user locations.

General Services Administration (GSA):  GSA  is the Agency responsible for serving as a the Federal Government’s acquisition Agency.  GSA consists of the Federal Acquisition Service (FAS), the Public Buildings Service (PBS), and various Staff Offices, including the Office of Governmentwide Policy (OGP).

GSA Planning and Management Team: The GSA Team that will carry out the planning and management of the Networx transition.

Global Account Managers (TSMs): Persons who are GSA Federal Acquisition Service (FAS) associates who are responsible for supporting Agencies by providing customer support for selection, ordering, implementation, and maintenance of FTS2001/Crossover and Networx services.

Government Accountability Office (GAO): An Agency that works for Congress that studies the programs and expenditures of the Federal Government.  GAO studies how the Federal Government spends taxpayer dollars and advises Congress and heads of Executive Agencies about ways to make Government more effective and responsive.

Government Furnished Property (GFP): Property in the possession of, or directly acquired by the Government and subsequently made available to the contractor.

Government-wide Acquisition Contracts (GWACs): Contracts which provide professional and technical services to Government Agencies under various contracts with the General Services Administration (GSA) Federal Supply Service.

GO/ NO GO Transition Notice:  Alerts recipients to the status of transition cutovers or other significant activities scheduled within the next 24 to 48 hours.

Interim Authority to Operate (IATO):  A temporary authorization to process information under a set of defined conditions.

Interagency Management Council (IMC):  The Interagency Management Council  (IMC) for Federal Telecommunications is a group of senior Federal executives, representing 14 Cabinet-level departments and several other Agencies. The IMC serves as an advisory body for the development, coordination, and customer-driven oversight of the telecommunications programs of the Federal Government and related activities and organizations. The IMC advises the Administrator of the General Services Administration on telecommunications matters.

Local Government Contact (LGC): An individual designated by a DAR on a

service request to interface with the contractor at a specific Agency

location on his behalf. LGC participates in service transition planning and

implementation activities for a location, however, the decision to change or

modify an order placed by the DAR, remains with the DAR unless

otherwise specified in writing by the DAR on the service request of record.

Managed Designed Documents (MDDs): Documents which contain custom services that are not standard CLINs on the FTS2001/Crossover contracts.

Managed Tiered Security Services (MTSS) Performance Report : Reports which provides statistics on availability, configuration/rule change, event notification, help desk statistics, and security incident reporting over the given period.

Network Interface Facilities (NIF): The point in an Agency’s network where the Agency’s network meets the service provider’s network

Networx: Networx is part of the follow-on to the FTS2000 program and is the third generation of this Government-wide telecommunications program. It is  intended to provide all of the services currently available on GSA’s multibillion- dollar long-distance FTS2001 contracts and many of the services now provided  on its local MAA contracts. In contrast to the earlier contracts, Networx will be a two-part program:

(1) Networx Universal – is the full service portion and will continue to provide for the full range of domestic and international network services.  The program requires “continuity” with current FTS2001 coverage, a  reduction of 70% in wire center requirements, and billing requirements are  to be greatly reduced.

(2) Networx Enterprise – is the smaller, more focused service part designed to allow participation by providers who offer specialized services  with less extensive geographic coverage than required by Networx  Universal. Networx Enterprise will include a smaller geographic coverage  requirement and fewer mandatory services.

Networx Pricer:  A GSA support system that will facilitate the Agency Fair Opportunity evaluation process..

Normal Business Day (NBD): Term that describes the working hours from eight o’clock in the morning until close of business at five o’clock in the evening, Monday through Friday.

Notice to Proceed (NTP): A Government notice that directs the contractor to proceed with the performance of work called for by a contract.

Office of Management and Budget (OMB): Executive Office of the President that oversees the preparation of the federal budget and to supervise its administration in Executive Branch Agencies.  OMB evaluates the effectiveness of Agency programs, policies, and procedures, assesses competing funding demands among Agencies, and sets funding priorities.  OMB ensures that Agency reports, rules, testimony, and proposed legislation are consistent with the President's Budget and with Administration policies.

Operational Support System (OSS): A system that is used to allow a network operator to perform the administrative portions of the business. These functions include billing, service ordering, customer support, service management,  inventory management, and program management. For purposes of this RFP,  the definition includes all systems required to support the communications  company including billing, service ordering, customer support, service  management, inventory management, and program management.

Preliminary Transition Management Plan (PTMP): Describes the contractor’s proposed strategy and approach to the project management of the transition from FTS2001 to the Networx contract.

Primary Interexchange Carrier (PIC) Charge:  Charges that are billed by local telecom companies to access long distance carriers

Program Management Office (PMO):  An office within the GSA/FTS organization responsible for management and contract administration of a telecommunications program. Within the context of this document, it refers to the  Specific PMO responsible for the Networx program.

Regional Services: An office within GSA that is comprised of Regional Transition Managers that are located throughout the eleven GSA regions.  GSA Regional Services is responsible for planning and coordinating the transition from FTS2001/Crossover to Networx on a regional level.

Regional Transition Managers (TMs): Individuals who are responsible for tracking and reporting the completion of transition orders for a specific region.

Risk Management: The identification of sources of risk and the establishment of mitigation strategies that address potential risks which may affect transition.

Service/Agency (S/A) Representatives:  Provides the primary interface between the Transition team and the Service or Agency.  Roles include:  customer service support, implementation support, coordination and tracking support, and FTS2001 contract close-out.

Service Level Agreement (SLA): An agreement between the Government and the contractor that the contractor delivers a specified service at a performance  Level that meets or exceeds the agreed performance objectives for the service.  The SLA also specifies the measurement approach and the type and amount of  credits that the Government is entitled to receive.

Service Order Completion Notice (SOCN): The notice that contains data

elements notifying the Agency that the service for a given order has been

fully installed and is ready for acceptance.

Standard Operating Procedures (SOP): A set of written instructions that document a routine or repetitive activity followed by an organization.

Taxonomy Document:  The Taxonomy document has been constructed to provide guidance to Agencies in need of budgetary assistance throughout the transition to Networx.  Agencies will use this document to determine which transition costs (if any) may qualify for reimbursement.

Transition Account:  Funds set aside in the Acquisition Services Fund (formerly known as the IT Fund) from retained earnings to be used for certain costs associated with the transition from FS2001 to Networx.

Transition Action Notice:  Describes transition activities scheduled for the next 60 days.

Transition Baseline Inventory (TBI) Application: The TBI application will provide Agencies a means for establishing a baseline inventory of FTS2001/Crossover services to be transitioned to Networx.  The TBI application is intended to support key transition activities such as, establishing a validated inventory, providing input to the Networx Pricer, serving as a baseline for transition tracking, and supporting the transition credit process

Transition Coordination Center (TCC): Defined as the team which will be a virtual GSA organization headed by the TCC Manager and will report to the GSA Transition Team.  The role of the TCC will be to assist Agencies with transition needs.

Transition Coordination Center (TCC) Manager:   The person responsible for the overall operation of the TCC, establishing and enforcing TCC processes and procedures, managing personnel, and ensuring that the TCC staff is properly trained.

Transition Execution Phase:  Defined as the phase that begins with the Networx contract award and completed when all Government Agencies accept all new Networx services. This phase may include service provider  selection, placement of new install orders, placement of FTS2001 disconnect orders, and the delivery of systems and services by the contractor(s).

Transition Information Portal (TIP):  A tool that is being developed to allow GSA and Agencies to track the transition progress from the FTS2001/Crossover contracts to Networx

Transition Management Plan (TMP):  Describes the contractor’s proposed general approach to the project management of transition, to include Agency transition goals and expectations.  The contractor should include proposed project management processes, procedures, and tools for all Networx transition activities.

Transition Manager:  The person responsible for managing all aspects associated with moving services from the incumbent service provider to the Networx contractor(s).  This individual’s responsibilities include initiation, planning, execution, monitoring and controlling, and close-out.  Oversees the Transition Team.

Transition Planning Phase:  Defined as the phase which includes establishing schedules, determining necessary resources, and identifying potential risks.

Transition Project Specific Plan (TPSP):  Identifies the project management processes, procedures, and tools for a Transition Project.

Transition Stakeholder: All parties involved in the transition process including; the GSA Team, contractors, IMC, TWG, and Agencies.

Transition Team:  Support staff consisting of Government personnel and extended staff that assist in the planning and management of the transition effort.  The transition team performs the following roles: operations support, design and engineering support, configuration management support, program and budget support, administrative support, communications support, and contract close-out.

Transition Strategy and Management Plan (TSMP):  Document developed by GSA to define and discuss the overall transition approach to be used by GSA throughout all phases of the Networx transition.

Transition Working Group (TWG): A group of Agency representatives who are responsible for advising of transition activities.  Also known as ITWG.

Weekly Transition Execution Reports: Provides a weekly confirmation of the cutovers from the previous week.

Weekly Transition Planning Reports:  Reports that provide a forecast of scheduled cutovers ranging from 6 months out to within the current week.

## Appendix B:  Acronyms

The acronyms listed in this Appendix serve to define terminology used in the TSMP and provide additional information, as related to the Networx transition.

| ACRONYMS |
| --- |
| AB | Agency Bureau |
| AHC | Agency Hierarchy Code |
| ALTP | Agency-Level Transition Plan |
| ASRN | Agency Service Request Number |
| ATMS | Asynchronous Transfer Mode Service |
| C&A | Certification and Accreditation |
| CDD | Custom Design Documents |
| CLINs | Contract Line Item Numbers |
| CSV | Comma Separated Values |
| DAR | Designated Agency Representative |
| FAR | Federal Acquisition Regulation |
| FAS | Federal Acquisition Service |
| FRS | Frame Relay Service |
| FTS | Federal Technology Service |
| TSMs | Global Account Managers |
| GAO | Government Accountability Office |
| GFP | Government Furnished Property |
| GSA | General Services Administration |
| GWACs | Government-Wide Acquisition Contracts |
| IATO | Interim Authority to Operate |
| IMC | Interagency Management Council |
| IP | Internet Protocol |
| IT | Information Technology |
| ITWG | Interagency Transition Working Group |
| LGC | Local Government Contact |
| MDD | Managed Design Documents |
| MTSS | Managed Tiered Security Services |
| NBD | Normal Business Days |
| NIF | Network Interface Facilities |
| NTP | Notice to Proceed |
| OMB | Office of Management and Budget |
| OSS | Operational Support System |
| PIC | Primary Interexchange Carrier |
| PMO | Program Management Office |
| POC | Point of Contact |
| PTMP | Preliminary Transition Management Plan |
| RFP | Request for Proposal |
| RTM | Regional Transition Manager |
| SLA | Service Level Agreement |
| SME | Subject Matter Expert |
| SOCN | Service Order Completion Notice |
| SOP | Standard Operating Procedure |
| SOW | Statement of Work |
| TBI | Transition Baseline Inventory |
| TCC | Transition Coordination Center |
| TM | Transition Manager |
| TMP | Transition Management Plan |
| TPOC | Transition Point of Contact |
| TPSP | Transition Project Specific Plan |
| TSMP | Transition Strategy and Management Plan |
| TWG | Transition Working Group |

## Appendix C:  FTS2001 Transition Lessons Learned Document

In response to previous transition efforts, this Appendix examines the FTS2001 Lessons Learned.  This Appendix is a synopsis of teaching points from the previous transition effort that was documented by the IMC TWG to ensure the same issues are not repeated in the Networx transition.

FTS2001 Transition

Lessons Learned

Prepared by

GSA Federal Technology Service

March 25, 2005

FTS2001 Transition

Lessons Learned

Table of Contents

I.	TRANSITION PLANNING

LL1 - Magnitude of Effort Not Fully Appreciated

LL2 – The Use of the Transition Fund Was Critical to Transition Execution

LL3 – GSA and Agency Plans for Funding Transition Should Be Determined Early

LL4 – Budgetary Impact of Transition on Agencies

LL5 - Accurate FTS2000 Telecommunications Service Inventory Needed

LL6 - Roles and Responsibilities of GSA, Agencies, and Service Providers Not Clearly Defined

LL7 - Agencies Needed Customized Services

LL8 – Activities Needed for Transition Should Be Started As Soon As Possible

LL9 - Program Management Approach Relied Extensively on Agency Action

LL10 - Program Management Approach Relied Too Heavily on FTS2001 Contractor Action

LL11 - Impact of External Events on Planning

LL12 - Need For Adequate Arrangements Between Gaining And Losing Vendors

LL13 - Concurrent Network Optimization Largely Unfeasible

LL14 - Lack of Coordinated Stakeholder Transition Planning

II.	TRANSITION EXECUTION

LL1 - Customer Agencies Needed To Upgrade Services

LL2 - Minimum Revenue Guarantees (MRGs) Impacted Incentives for Timely Transition

LL3 - Slow Agency Service Provider Selection

LL4 - Slow Agency Placement of FTS2001 Orders

LL5 - Slow Action By Some Agencies Raised Costs For All

LL6 - Poor Contractor Support During Transition

LL7 - Problems Obtaining Access Facilities

LL8 - Lack of Contractor Transition Resources

LL9 - Lack of Timely Delivery of Acceptable Support Systems By Contractors

LL10 - Some Agency Sites Were Responsible For Transition Delays

LL11 - Billing Problems Contributed to Transition Delays

III.	TRANSITION MONITORING, CONTROLLING, & TRACKING

LL1 - Focus on Phase-Out Rather Than Phase-In

LL2 - Problems with Service Provider Reporting

LL3 - Different Government-Wide Reporting Structures

FTS2001 Transition

Lessons Learned

The General Services Administration (GSA) awarded two FTS201 contracts to Sprint and MCI (later WorldCom) in December 1998 and January 1999 respectively to replace the AT&T and Sprint FTS2000/Extended Service Agreement contracts.  The Notice to Proceed went to both contractors on January 11, 1999.  Services were to transition from the FTS2000 vendor networks to the FTS2001 networks over a period of 18 to 24 months.  The transition goal was not met.  This paper provides a catalog of “lessons learned” from the FTS2001 transition to facilitate the eventual replacement of FTS2001.

The issues discussed and the lessons learned from them were drawn from many sources.  They are divided into the following functional categories:

- TRANSITION PLANNING

- TRANSITION EXECUTION

- TRANSITION MONITORING, CONTROLLING, & TRACKING

TRANSITION PLANNING

LL1 - Magnitude of Effort Not Fully Appreciated

Lesson Learned: The replacement of the telecommunications infrastructure for a large part of the federal community is a huge task.  The transition stakeholders (that is GSA, the user Agencies and the gaining service providers) need to be fully prepared for the undertaking.

LL2 – The Use of the Transition Fund Was Critical to Transition Execution

Lesson Learned: A funding mechanism like the Transition Fund is strongly recommended for any future transition efforts similar to FTS2001.

LL3 – GSA and Agency Plans for Funding Transition Should Be Determined Early

Lesson Learned: To make Agency resource planning easier, it is recommended that guidelines based on the “Taxonomy” document be established early enough in the budget cycle for Agencies to do the financial planning required to ensure that needed resources are available.

LL4 – Budgetary Impact of Transition on Agencies

Lesson Learned: The reimbursement plan between GSA and the Agencies should be based on clear financial criteria that result in predictable Agency impact.

LL5 - Accurate FTS2000 Telecommunications Service Inventory Needed

Lesson Learned: A complete and accurate “baseline” inventory prior to contract award is critical.  In order to facilitate this requirement it is suggested that inventory validation should be an on-going effort during the life of the contract to provide a complete and accurate baseline for not only transition, but also other operations such as billing validation and service optimization.

LL6 - Roles and Responsibilities of GSA, Agencies, and Service Providers Not Clearly Defined

Lesson Learned:  The roles and responsibilities of all transition stakeholders (that is GSA, Agencies, and service providers) should be clearly defined and communicated to ensure critical activities are appropriately performed.

LL7 - Agencies Needed Customized Services

Lesson Learned: Many Government requirements cannot be met by standard Commercial services.  Although commercial solutions are encouraged, solicitation documents and all planning must include Government unique requirements.

LL8 – Activities Needed for Transition Should Be Started As Soon As Possible

Lesson Learned: Agencies should be prepared for the ‘worse-case’ scenario of their FTS2001 service provider either not being awarded a successor contract or not being selected through the fair opportunity process and plan accordingly in order to ensure a rapid transition effort with minimal impact on the continuity of service.

LL9 - Program Management Approach Relied Extensively on Agency Action

Lesson Learned: A “one size fits all” approach to program management must be avoided since Agency capabilities differ widely.  For each Agency will likely not have the same transition experience.  At the same time, the approach must ensure that the needs of all Agencies, large and small, are being addressed.  The approach either needs to ensure that resources are available when the plan requires or that the plan can be tailored to fit the available resources.

LL10 - Program Management Approach Relied Too Heavily on FTS2001 Contractor Action

Lesson Learned:  Agencies should anticipate and account for the new service provider’s possible inability or unwillingness to execute all transition requirements as promised, thus ensuring that they:

Establish and maintain effective oversight throughout transition

Escalate problems with the service providers to GSA FTS with documentation

GSA FTS should anticipate and be prepared to deal with service provider’s possible inability or unwillingness to meet contractual obligations.

LL11 - Impact of External Events on Planning

Lesson Learned: Overall transition planning should have sufficient flexibility so that Agencies can coordinate transition with other ongoing activities regardless of the impact of external events.  Likewise, contracts should be flexible to accommodate unforeseen marketplace issues.

LL12 - Need For Adequate Arrangements Between Gaining And Losing Vendors

Lesson Learned: Coordinated and synchronized disconnects and activation by different service providers are essential to ensure transition success.

LL13 - Concurrent Network Optimization Largely Unfeasible

Lesson Learned:  Network optimization should be addressed as part of normal network management and not as a mandatory task during transition.

LL14 - Lack of Coordinated Stakeholder Transition Planning

Lesson Learned:  The planning activities of the transition stakeholders (that is GSA, Agencies, and service providers) should be coordinated to ensure all activities are appropriately accounted for and that dependencies are adequately addressed.

TRANSITION EXECUTION

LL1 - Customer Agencies Needed To Upgrade Services

Lesson Learned: The task of transition is not limited to transitioning a static list of services on a like-for-like basis.  Therefore, Agencies should anticipate the need for changing connectivity during the transition effort and mitigate those factors in their transition plan(s).

LL2 - Minimum Revenue Guarantees (MRGs) Impacted Incentives for Timely Transition

Lesson Learned: Care should be exercised when determining the MRGs to be offered to ensure that:

They do not become an impediment to Agency choice and competition in the future

They do not become a disincentive to winning contractors to aggressively move forward

In short, MRGs should be managed so as not to impede the transition effort.

LL3 - Slow Agency Service Provider Selection

Lesson Learned: The delay in Agencies selecting their vendors significantly impacted the timeline for transition.  Therefore, a “deadline” for vendor selection should be incorporated into the overall transition schedule.

LL4 - Slow Agency Placement of FTS2001 Orders

Lesson Learned:  Agency procedures and resources were inadequate to manage the extraordinary volume of service orders associated with the transition effort.

LL5 - Slow Action By Some Agencies Raised Costs For All

Lesson Learned: Agencies responsible for slow contractor selection, transition planning and/or order entry that directly results in extension of incumbent contract(s) and services should bear the costs associated with those extensions.

LL6 - Poor Contractor Support During Transition

Lesson Learned: In any future efforts, service providers should be held to the required levels of service from contract award (including the transition period).

LL7 - Problems Obtaining Access Facilities

Lesson Learned:  Agencies should ensure their plans accommodate for potential issues associated with access facilities, as often service providers do not control the entire provisioning process.

LL8 - Lack of Contractor Transition Resources

Lesson Learned:  Service providers did not provide sufficient resources to meet contract terms (including properly trained staff).  Therefore, service providers need to apply sufficient resources in order to meet the identified transition goals.

LL9 - Lack of Timely Delivery of Acceptable Support Systems By Contractors

Lesson Learned:  Future transition planning should not permit transition to begin until service provider support systems are in-place, tested, and accepted.  Further, service providers should be required to deliver support systems for both Commercial and Government unique services that meet Government expectation prior to contract award.

LL10 - Some Agency Sites Were Responsible For Transition Delays

Lesson Learned:  Some delays could be avoided if Agencies:

Take care not to approve a TPSP or site survey if services are not in fact what they need to operate (e.g. all 800 numbers were not included in site survey)

Advise service provider of any special access requirements for the site

Make arrangements for the entry of service provider technicians into site in order to avoid unnecessary ‘turn a-ways’

Ensure that they know and understand the plan for their site including the type of cutover (parallel, managed, or coordinated) planned

Have material/equipment installed and ready on scheduled cutover date (e.g. cabling, inside wiring, PBX cards, or other GFE equipment)

Have needed technicians on hand for both pre-test and cutover (e.g. PBX technician was not present on scheduled test dates resulting in dialing plan problems)

LL11 - Billing Problems Contributed to Transition Delays

Lesson Learned:  GSA FTS and Agencies should proactively examine invoices during transition to verify that services are being invoiced against the right contract and the right rate and that the details of billing meet contract requirements.  Also, billing discrepancies should be brought to the attention of service providers promptly and GSA FTS must hold them responsible for resolving billing problems expeditiously.

TRANSITION MONITORING, CONTROLLING, & TRACKING

LL1 - Focus on Phase-Out Rather Than Phase-In

Lesson Learned: The progress of transition should be measured by both the “old” services replaced and disconnected as well as by the “new” services installed.

LL2 - Problems with Service Provider Reporting

Lesson Learned:  Government should specify the information required from the service providers relative to transition progress as opposed to the method by which it is delivered.  Further, how information is captured and presented by the service provider and GSA needs to be carefully documented for the Agencies and the Agencies need to be flexible as to how they can manipulate and use this data.

LL3 - Different Government-Wide Reporting Structures

Lesson learned:  The process used for monitoring the installation of new services was not done in a consistent manner; therefore, effective transition metrics should be established and agreed upon by all transition stakeholders prior to contract award.

## Appendix D:  Transition Contract Support Vehicles

In preparing for transition to Networx, as well as executing transition activities, Agencies will likely need to acquire additional resources to handle the workload associated with transition.  The contract support vehicles identified in this Appendix have been developed as a high-level guide to Agencies to provide information on existing GWAC and FSS contracts.

As the Government prepares for transition to the Networx Contract there will likely be requirements for program and technical support needed by the Agencies throughout the transition effort.  As such, GSA has sought to identify alternatives for sources similar transition support provided during previous transition efforts of this magnitude (i.e., Transition Management Support and Telecommunications Support Contract 2 contracts).

The information contained within this document is shared within the public domain and is not intended to advocate specific contractual vehicles.  All information discussed is presented to provide GSA and its Agencies assistance in identifying available Government-Wide Acquisition Contracts (GWACs) applicable for providing the type of support needed in the transition effort.  Specifically, the respective areas of support required by the Government will likely include any of the following areas:

- Telecommunications Planning and/or Transition Support

- Program Management Support

- Engineering and Analytical Support

- Design and Engineering Support

- Acquisition Support

- Installation, Integration and Implementation

- Customer Support

- Operations and Maintenance Support

Agencies should decide whether these support services applicable for transition to Networx can best be sourced using either in-house Government resources or outsourced to applicable vendors via respective GWAC vehicles.

Although GSA has not created specific contract vehicles to offer support to Agencies throughout the transition from FTS2001 to Networx, there are a number of GWACs available to Agencies in need of support as noted in the table below.

GWACs Available to Support Networx Transition

| Name | Description | Services | Applicable Labor Category(s) | Contractor(s) |
| --- | --- | --- | --- | --- |
| Connections | 8-year (i.e., 3 base years +5 one-year options) Government-wide, Multiple Award, Indefinite-Delivery Indefinite-Quantity contract. More than half of the Awardees are small businesses. There are countless product manufacturers and subcontractors available. | 1. Equipment & Services – includes equipment or services that could be used to evolve the Agency's telecommunications infrastructure 2. Support Services – includes many different services in support of the telecommunications infrastructure, offered within three basic areas: Professional, Technical, and E-Business 3. Solutions – includes turn-key solutions that are characterized by integrators and managed services | Site Manager Quality Assurance Engineer Network Systems Manager Communication Analyst Configuration Management Specialist | ATS Booz Allen Hamilton Centech EDS EPS GTI ISS MC Dean MAI ManTech NextiraOne Omega SAIC SBC SETA Signal Solutions Verizon |
| Millenia | Consists of nine Indefinite Delivery/Indefinite Quantity (IDIQ) Contracts which are accessible to all Federal Government Agencies. Millenia provides IT services, including ancillary hardware, software and firmware. | 1. Communications – Definition, design, implementation, and management of digital and integrated or linked communications systems 2. Software Engineering – Managing software from initial conception and planning, through design and development, to conversion, maintenance and improvement 3. Systems Integration – All activities needed to develop and initiate automated information systems | Sr. Subject Matter Expert Emerging Technology Expert Senior IT Analyst Junior IT Analyst Senior Technician Technician | Booz Allen Hamilton CSC CSC Systems and Solutions, LLC Lockheed Martin Services, Inc. Northrop Grumman Information Technology, Inc. Raytheon Technical Services Company SAIC SRA Unisys Corporation |
| ANSWER* | $25 Billion Multiple Award/ Indefinite Delivery Indefinite Quantity (MA/IDIQ) contract that provides IT solutions that deliver the best value and innovation to support client missions worldwide | 1. Infrastructure & Operations - Facilities planning, design, relocations & management. LAN/MAN/WAN systems, voice communication/telephony systems, network management, and others. 2. Information Systems - Database management systems, web site development & maintenance, information assurance, and others. 3. Telecommunications - Call center engineering, network switching & signaling systems, intelligent network systems, billing & customer support systems, network security/information protection, emergency response planning & operations, market strategy, research & analysis, competitive reengineering, and others. | Site Manager Info Sys Admin and Planning Manager Strategic Planner Technician Technical Subject Matter Expert Network Engineer Network Systems Manager Network Systems Administrator Telecommunication Integration Engineer Communication Facility Engineer Quality Assurance Specialist Test Engineer Senior Project Manager Data Communication Manager Voice Communication Manager \ Business Continuity Planning Manager | Anteon Corporation Booz Allen Hamilton CSC CSC Systems and Solutions, LLC Information Systems Support, Inc. (ISS) ITS Corp. L-3 Government Services Inc. (L-3 GSI) Northrop Grumman IT TASC, Inc. SAIC |
| IT Professional Services Schedule (FSS) | Under GSA FSS IT Schedule 70 contractors are able to supply the full range of IT professional services to all Federal Government Agencies on a fee-for-service basis. Contract periods are five years, plus three separate five year option periods. | 1. IT Strategic Planning and Management – includes all expertise to ensure that the Agency's foundation and direction in the application of IT are well-defined, efficient, and consistent with commercial and Government best practices and legislation. 2. IT Systems Analysis –includes analysis services are designed to ensure they meet IT investments are focused information systems and telecommunications networks that solve the Agency's problems. 3. IT Systems Engineering – includes system engineering services ensure that information systems and telecommunications networks are designed to capitalize on Agency architectures and IT standards, to provide interoperability with other systems and networks, to be reliable and maintainable. | Program Manager Project Manager Subject Matter Expert 1-3 Business Process Engineer Financial Analyst Senior Systems Engineer Telecom Systems Analyst Telecom Operations Specialist Communications Network Manager Communications Specialist Help Desk Manager Project Control Specialist Technical Writer/Editor Systems Design Engineer Systems Security Expert IT Consultant Functional Expert Consultant | Approx. 5,000 vendors – list available via WWW.GSA.GOV |
| CIOSP2 (HHS) | The National Institutes of Health (NIH) maintains an IDIQ contract for acquiring a wide range of IT products and services for NIH and all other Federal Agencies. The geographic scope of this requirement includes the United States and abroad. | 1. Equipment & Services – includes equipment or services that could be used to evolve the Agency's telecommunications infrastructure 2. Support Services – includes many different services in support of the telecommunications infrastructure, offered within three basic areas: Professional, Technical, and E-Business 3. Solutions – includes turn-key solutions that are characterized by integrators and managed services | Program Manager Project Manager Telecom Engineer Disaster Recovery Specialist Communications Software Specialist Communications Hardware Specialist Quality Assurance Specialist Technical Writer/Editor Cost Analyst | AST, Inc. ALTS Systems Aquilent Booz Allen Hamilton CRC Calibre Systems Cap Gemini E&Y Cerokee Information Services CSI, Inc. COMSYS DST, Inc. GMR, Inc. IBM Intekras Insight Technology Solutions James Communications, Inc. JIL Information Systems KRA Corp. LMR, Inc. Management Systems Designers, Inc. MicroTech LLC MCCS, Inc. Millenium Solutions, Inc. NCI Information Systems, Inc. Siemens SBSI TAJ Technologies, Inc. Vistronix, Inc. Xtria LLC |
| MOBIS | Management, Organizational and Business Improvement Services (MOBIS) is a Federal Supply Schedule offered to Federal Agencies by GSA to provide them with a streamlined procurement device to access management services for the implementation of quality management and other related system change processes. | 1. Consulting Services – includes expert advice, assistance, guidance or counseling in support of management, organizational and business improvement efforts 2. Facilitation Services – includes decision support services to Agencies engaging in collaboration efforts, working groups or integrated product, process or self-directed teams 3. Survey Services – includes expert consultation, assistance and deliverables associated with all aspects of surveying within the context of MOBIS 4. Training Services – includes off-the-shelf or customized training packages to meet specific Agency needs related to management, organizational and business improvement services 5. Support Products – includes items used in support of services described, to include workbooks, training manuals, etc. 6. Privatization Support Services and Documentation (A76) – includes expert advice, consultation, assistance and documentation in support of studies conducted under OMB Circular A-76 or other privatization/commercial activities studies, projects, or efforts 7. Program Integration and Project Management Services – includes services to manage and integrate various management and business improvement programs and projects | Officer Principal Senior Associate Associate Senior Consultant Consultant Researcher Analyst Support Staff Others… | Too many to list (over 1600 contractors total) |
| PES | Professional Engineering Services (PES) is designed to simplify the acquisition of professional engineering services in thousands of technical areas. | 1. Strategic Planning for Technology Programs/Activities – includes the expertise necessary to define and interpret high-level organizational engineering performance requirements 2. Concept Development and Requirements Analysis – includes the ability to conduct abstract or conceptual studies and analyses, define requirements, develop preliminary plans and evaluate alternative technical approaches 3. System Design, Engineering and Integration – includes translating the project concept into a preliminary and detailed design, performing risk identification, analysis, and mitigation, as well as integrating the various components into a working prototype 4. Test and Evaluation – includes the application of various techniques for demonstrating that a prototype performs in accordance with the objectives outlined in the original design 5. Integrated Logistics Support – includes the analysis, planning, and design of all engineering specific logistics support 6. Acquisition and Life Cycle Management – includes the performance of planning, budgetary, contract and program management execution functions required to produce, render operational, and provide life cycle support to technology-based systems | Program Manager Project Manager Requirements Engineer Design Engineer Test Engineer Logistics Engineer Operations/Research Analyst Management Analyst Financial Analyst Trainer Support Specialist Project Control Specialist Information Specialist Functional Expert Consultant | Too many to list (over 700 contractors total) |
| ITSP II | The Information Technology Services Program (ITSP) II is designed to provide the United States Air Force, Electronic Systems Center (ESC) with a wide range of commercially available information technology support services for new and existing systems. The ITSP BPA is not a contract; it is a written agreement based on existing GSA schedules that set forth the clauses that apply to future delivery/task orders. | 1. General Purpose Commercial Information Technology Equipment, Software, and Services – includes the full range of Information Technology professional services to work cost-effectively, improve Agency mission performance, and enhance the quality of service to Agency customers 2. Financial and Business Solutions – includes a full range of auditing and financial management professional services to all Federal Government Agencies on a fee-for-service basis 3. Logistics Worldwide – includes all aspects of logistics, including supply and value chain management, acquisition, distribution and transportation, deployment and training | Network Installation Technician Telecommunications Network Engineer Telecommunications Analyst Telecommunications Operations Specialist Communications Network Manager Communications Specialist Quality Assurance Specialist Information Technology Subject Matter Expert | Over 5000 contractors |
| ITS | Information Technology Services (ITS) is a blanket purchase agreement (BPA) designed to provide the Department of Defense with a wide range of commercially available information technology support services for new and existing systems. | 1. Enterprise IT Policy and Planning – includes the review of current policy and evaluation of future IT needs 2. Integrated Solutions Management – includes the thorough analysis of disparate systems, and provides solutions to facilitate seamless integration 3. Performance Benchmarking – includes the review of current operating procedures and performance 4. Requirements Analysis – includes a detailed evaluation of current environment versus desired state 5. Test and Evaluation – includes the application of various techniques for demonstrating that a prototype performs in accordance with the objectives outlined in the original design | Network Manager Network Administrator Communications Technician Network Equipment Tech Network Integration Specialist Electronics Tech Communications Engineer Quality Assurance Specialist | Multiple |
| ITSS | The Department of the Navy may use this Blanket Purchase Agreement (BPA) to acquire a wide range of commercially available information technology support services for new and existing systems. | 1. Enterprise IT Policy and Planning – includes the review of current policy and evaluation of future IT needs 2. Integrated Solutions Management – includes the thorough analysis of disparate systems, and provides solutions to facilitate seamless integration 3. Performance Benchmarking – includes the review of current operating procedures and performance 4. Requirements Analysis – includes a detailed evaluation of current environment versus desired state 5. Test and Evaluation – includes the application of various techniques for demonstrating that a prototype performs in accordance with the objectives outlined in the original design |  |  |

*Note:  Asterisk indicates contract expiration late 2008

## Appendix E:  Risk Mitigation Strategies

## Appendix F:  Communications Plan

Under development

## Appendix G:  Responsibility Matrix

| ROLE | GSA LEAD | OTHER GSA | CONSULTANTS | MAJOR TASKS |
| --- | --- | --- | --- | --- |
| Transition Manager | Richard Williams |  |  |  |
| Transition Planning and Management | Debbie Hren | Fred Adams Hillary Parlow Gary Koch | Sharon Dantzig, Noblis Rod Hahn, Noblis Jim Hott, Noblis Caroline Inglefield, Noblis | TSMP Development and Maintenance; Contractors’ TMPs; TWG and TM Interface; TM Management ; Transition Cost Estimate, Reporting, Reimbursement and Inventory |
|  |  |  | James Hunter, Apptis Alvin Sanders, Apptis Beth Burch, Apptis LaToya Jenkins, Apptis | Task 0002 – Strategic Guidance (TMP Review, Transition Training Plan, Transition Training Handbook, Vendor Performance Reports) |
|  |  |  | Phil Beasley, CACI Mike Edwards, CACI Valerie Callaway, CACI | Task 0003 – Customer Outreach (Agency Transition Planning, selection of services) |
| Regional Services Transition Coordinator | Paulette Gemmer |  | James Hunter, Apptis Alvin Sanders, Apptis | Task 0002 – Strategic Guidance (TMP Reviews) Task 0006 – TCC Operations (Communication Package for the Regions) |
|  |  |  | Phil Beasley, CACI Mike Edwards, CACI | Task 0003 – Customer Outreach (Site Transition Plan and Survey Templates) |
|  |  |  | Jo Brown, GTI JR Simpson, GTI | Task 0004 – Cutover Monitoring and Support (Cutover Procedures, Templates and Checklists) |
|  |  |  | Harry Atkinson, Apptis Joy Shelton, Apptis | Regional Services Transition Support Contract |
| GSA/TCC DAR | Hillary Parlow, DAR Administrator | Hillary Parlow, DAR Troy Wolfington, DAR |  | Ordering FTS2001 and Networx services, particularly Disconnect Reports and Gateways |
| TCC Manager | Debbie Hren |  | Rod Hahn, Noblis Sharon Dantzig, Noblis | TCC guidance, staffing, schedule, problem resolution |
|  |  |  | Herman Graham, Apptis Jeff Randall, CACI Chuck Brock, GTI | Task 0001 – Task Order Management, Contract Administration and Financials |
| TCC COTR | Dan Scott Primary | Troy Wolfington, Alternate | Herman Graham, Apptis Jeff Randall, CACI Chuck Brock, GTI | Task 0001 – Task Order Management Contract Administration and Financials |
| TCC Systems Support | Fred Adams | Jason Ji | Mike Edwards, CACI Valerie Callaway, CACI Phil Beasley, CACI Pixstar | Task 0003 – Customer Outreach (Web site design and content, TIP design, implementation, operations and data administration) |
| TCC Operations | Debbie Hren | Jason Ji | Clyde Bowie, Apptis Kate Halstead, Apptis Alvin Sanders, Apptis James Hunter, Apptis Hayden Sears, Apptis Larry Gsellman, Apptis; Juan Linares, Apptis Katryn Richardson, Apptis | Task 0006 – TCC Operations (SOPs, Plans, e.g., PM, QA, CM, Communications, TCC Regional Liaison, Web Site Requirements, Web Site Content Updates) Task 0007 – Transition Tracking and Reporting |
|  |  |  | Tom Hartsock, CACI Mike Edwards, CACI Phil Beasley, CACI Valerie Callaway, CACI Dick Higdon, CACI | Task 0003 – Customer Outreach |
|  |  |  | Ken Palmer, GTI Bob Collet, GTI | Task 0008 – Tier 2 and 3 Help Desk Support |
| TCC PM&C | Dan Scott Troy Wolfington |  | Clyde Bowie, Apptis Beth Burch, Apptis Rod Hahn, Noblis | Task 0006 – TCC Operations Transition Master Schedule; Configuration Management, Deliverables Tracking; COOP Plan |
| TCC Cut Team | Debbie Hren | Fred Adams Jason Ji | Karl Straley, GTI Bob Collet, GTI | Task 0004A – Cutover Monitoring and Support (including periodic quality checks) Task 0004B – Review and comment on Agency-prepared cutover procedures, issues and conflicts upon direction from the COTR. Task 0004D – Prepare schedules, taking into account all activities within a location or region, to identify potential conflicts, and review Agency cutover schedules and identify and mediate any schedule conflicts. |
| Help Desk | Jason Ji |  | Van Andros, Noblis John Veiga, Noblis Mike Nelson, Noblis | Requirements and Change Control, Contractor Interface |
|  |  |  | LaTonya Morgan, Access Systems Ronni Collier, Access Systems Denise Hayes, Access Systems Donald Kennard, Access Systems Jennifer Schultz, Access Systems Denise Spencer, Access Systems Andrew Walker, Access Systems | Tier 1 Support |
|  |  |  | Ken Palmer, GTI Bob Collet, GTI Tony Christiansen, GTI | Task 0008 - Tier 2 and 3 Help Desk Support |
|  |  |  | Joann Brown, GTI JR Simpson, GTI Frank Titus-Rogan, GTI Tom Hartsock, CACI |  |
| TCC CO | George Davis |  |  | Contracting Officer for Connections, TCC Task Order, and Regional Task Order |