PROGRAM DESIGN:

CO-MANAGEMENT OF TROPICAL FOREST RESOURCES IN BANGLADESH

Strategic Objective 6 (Environment) Team

USAID/Bangladesh

### TABLE OF CONTENTS

| SECTION | TITLE | PAGE |
| --- | --- | --- |
| 1 | INTRODUCTION | 4 |
| 1.1 | USAID Activities and Interests in the Environment Sector | 4 |
| 1.2 | Adding a Tropical Forest Resources Program--Potential for Synergy | 6 |
| 1.3 | Purpose of the Present Document | 8 |
| 2 | BACKGROUND | 8 |
| 2.1 | Overall Status of Tropical Forest Resources and Biodiversity in Bangladesh | 8 |
| 2.2 | Relationship to Government of Bangladesh Priorities | 9 |
| 2.3 | Other Donor Programs and Plans | 10 |
| 2.4 | Relevance/Complementarity with the Mission Strategic Plan and Programs | 10 |
| 3 | RATIONALE/JUSTIFICATION FOR A FORESTRY PROGRAM | 12 |
| 3.1 | Goals and Objectives | 12 |
| 3.2 | Program Concept and Strategy | 14 |
| 3.3 | Understanding the Meaning of Co-Management | 14 |
| 3.4 | Overview of the Program | 16 |
| 4 | PROGRAM IMPLEMENTATION STRATEGY | 17 |
| 4.1 | Building a Coherent Model and the Capabilities to Implement It | 17 |
| 4.2 | Institutional Framework for Program Implementation | 18 |
| 4.3 | Program Implementation Staff | 21 |
| 4.4 | Candidate Sites for Program Activities | 22 |
| 4.5 | Illustrative Description of Activities | 24 |
| 4.6 | Indicative Implementation Schedule | 30 |
| 4.7 | Reporting Requirements | 36 |
| 4.8 | Performance Monitoring and Evaluation | 37 |
|  | ANNEXES | 41 |
|  | Annex A- Participatory Forestry Modalities in Bangladesh | 42 |
|  | Annex B- Issues and Opportunities for Biodiversity Conservation in the Hills | 44 |
|  | Annex C- Reference List | 48 |

PROGRAM DESIGN FOR

CO-MANAGEMENT OF TROPICAL FOREST RESOURCES IN BANGLADESH

1.	INTRODUCTION

1.1	USAID Activities and Interests in the Environment Sector

USAID/Bangladesh's current plans and investments in the environment sector are a direct result of decades of assistance to rural development, family planning, poverty alleviation and food security.  These programs were themselves keys to addressing the crux of Bangladesh's primary environmental dilemma of catering for the needs of its large population with the limited resources of this small country. Achievements in these areas, in particular increased agricultural productivity and a reduction in the population growth rate, have given rise to an opportunity to refocus the overall program characterized by the Mission's stated goal:

Poverty Reduced through Sustainable Economic Growth

As part of its programmatic response for realizing this goal, and in light of the three "areas of greatest importance to the sustainability of economic growth in the country--population, food and water", USAID/Bangladesh has created an explicit environmental strategic objective-

Improved Management of Open Water and Tropical Forest Resources

The predominant paradigm of this Strategic Objective (SO 6) program is to develop community-based approaches and institutional capabilities for the wise management, sustainable productivity and conservation of these critical elements of the natural resource base of Bangladesh.  The present arrangements and institutional framework for the use of these open water and tropical forests have led to their de facto treatment as "open access" resources-- the property of all but the responsibility of none-- with a consequent degradation of the resource base and declining productivity.  The Intermediate Results of this Strategic Objective are:

- Effective Community-based Resource Management Mechanisms Implemented;

- Select Habitats and Ecosystems Restored;

- Selected Policies Implemented that Support the above;

- Public Awareness of Key Issues Increased; and

- Improved Institutional Capacity

Figure 1: SO 6 Results Framework

1.2 Adding a Tropical Forestry Resources Program--Potential for Synergy

USAID/Bangladesh in planning its strategic approach to the environment and natural resources sector in the country has long recognized the basic similarities in the problematic way both open water and tropical forest resources are being used.  These include: over-exploitation beyond carrying capacity (of the fishery, wetlands and tropical forests); inappropriate use and conversion reducing the extent of these critical ecosystems; and the lack of a structured administrative and management system to counter the problems.  The commonality of these issues is leading to a general degradation and fragmentation of the resource base, declining productivity eroding their potential contribution to development of the country and the communities dependent on them, and significant threats to their long-term sustainability.

By its very nature, occupying the sprawling inter-linked delta of three great river systems– the Ganges, Meghna and Brahmaputra, Bangladesh is highly susceptible to the conditions of its upstream watersheds.  Flood periodicity and volume originating upstream affects a great deal of the floodplain and its open water fisheries ecosystems.  At the moment, there is little the country can do to mitigate the impacts felt from inappropriate land-use and declining forest cover in these transnational upstream watersheds. There are some areas, however, within the country where the watershed conditions in adjacent hilly areas are directly linked to the productivity and sustainability of open water bodies and ecosystems. For example, in the northeastern sections of the country around the Haor Basin where the on-going activities of the Management of Aquatic Resources through Community Husbandry Project (MACH) Project are concentrated, the forest cover of the surrounding hilly regions have been severely degraded and often completely deforested.  Inappropriate land-use choices and forest degradation on the hills has both localized and downstream consequences, as follows:

Linkages--Upstream Forest Degradation and Downstream Open Water Ecosystems

| Tropical Forest Ecosystems | Open Water Ecosystems |
| --- | --- |
| - Deforestation, over-cutting and over-grazing on sloping forest lands causes: degradation of the watershed function leading to erosion; greater rainfall run-off and less infiltration; torrential streamflow, drying of perennial streams; and loss of habitat and biodiversity assets. - Poor agricultural land-use choices on hilly areas also leads to similar problems and low crop productivity due to loss of topsoil and organic matter content, stressing crop plants during the dry season. - Impoverishment of the local population and hardship due to low site productivity, typically resulting in increasing pressure on the remaining forest cover. - Loss of perennial forest cover as carbon sinks thus contributing to greenhouse gas production and its companion global warming phenomena. | - Off-site consequences in lower-lying downstream areas, water bodies and water courses because of: higher flash floods, particularly during early monsoon that affects the boro rice crop; siltation and sedimentation of beels, canals and rivers eliminating fish habitat or ecosystem connectivity; lower water levels in remnant wetlands during the dry season inhibiting reproduction of the open water fishery; deposition of unwanted sand and sediment on crop fields; stream bank and riparian zone erosion affecting crop lands (e.g., tea estates at midstream), local infrastructure (roads and bridges) and adjacent villages. - Impoverishment of the local population, particularly fisher folk dependent on the products of the wetlands (fish and aquatic plants). - Loss of floodplain biodiversity assets. |

These unavoidable linkages between the uplands and the lower-lying wetland areas clearly demonstrate the need and opportunity for an approach to tropical forest resource management focused on their role in integrated water resources management.  The MACH Project has made significant progress in developing a community-based response to the issues affecting the sustainability of open water resources.  Their natural resources management accomplishments include: reductions in fishing pressure through community-imposed regulations; the establishment of fish sanctuaries in dry season water bodies; excavation of silted-up canals and portions of rivers to restore ecosystem connectivity; re-introduction of important missing fish species through stocking; and revegetation in both the riparian areas (stream courses) and swamp forest areas.

While these activities have certainly restored a measure of productivity and sustainability in the wetlands, their efficacy will continue to be undermined if proactive measures are not also taken to address the problems of the local watersheds in the surrounding hilly areas.  Herein lies a significant opportunity for achieving synergy across the elements of the USAID's SO 6 environment program.

This potential for synergy becomes even more compelling in light of the fact that some of the remaining refuges of tropical forest biodiversity are “protected areas” and also serve as portions of the watersheds for MACH wetland sites in the northeast.  They represent a special opportunity as potential pilot areas for the development of the co-management approach that could also be replicated elsewhere in the country, for example in the Chittagong Hill Tracts.  These areas constitute the last refuges of terrestrial biodiversity in Bangladesh.  Despite their protected status, all of these areas are under relentless human pressures from surrounding communities and from occasional illegal logging activities.  It should be noted that not all the protected areas need be approached from an exclusively watershed management perspective.  In the southeast, the integrated water resources management paradigm would also play out in that forests such as the Teknaf Game Reserve protect neighboring communities from the ravages of cyclones in the nearby Bay of Bengal.  What is clear, however, is that all of them are sites where there is a significant opportunity for applying the co-management model with local communities.

1.3	Purpose of the Present Document

This document constitutes a detailed program design for the proposed bilaterally funded program component promoting conservation and improved management of tropical forest resources that USAID/Bangladesh would like to launch.  The design directly reflects USAID's overall approach to achieving the strategic objective and embodies the intermediate results (see SO 6 Results Framework graphic above) that will provide the basis for a Strategic Objective Grant Agreement between USAID and the Government of Bangladesh. It has been prepared on the basis of extensive consultations in Bangladesh with representatives of government, the NGO sector and other specialists familiar with the sector.

The sections which follow include: background information on the status of tropical forest resources in Bangladesh and the potential fit of a USAID-funded forestry component with current GOB and USAID plans and programs (Section 2); a summary explanation of the rationale and justification and the conceptual basis for such program component (Section 3); a more detailed explanation of the design and its implementation strategy (Section 4); and concludes with a series of supporting annexes.

2.	BACKGROUND

2.1	Overall Status of Tropical Forest Resources and Biodiversity in Bangladesh

Reliable, up-to-date statistics on the quantity and quality of tropical forest cover in Bangladesh are hard to come by and contradictory figures are the norm rather than the exception.  Recent order of magnitude data suggests that there are about 2.6 million hectares (covering 18 % of the total land surface) in the country.  They include: state forest land of 2.2 million hectares composed of 1.3 million hectares of natural forests and plantations (there are extensive plantation areas on reserved forest land, particularly in the hilly regions of the country) under the jurisdiction of the Forest Department and about 0.9 million hectares of unclassified state forest administered by the Ministry of Lands.  The remainder of the forest cover is in private hands, notably including the very successful homestead plantations common across the flood plain areas of the country and small tracts of natural forest and plantations on estate lands.  With the exception of some of the most inaccessible areas whose actual status is not well known (e.g. in the Hill Tracts), all of the remaining natural forests are reportedly under constant pressure, have been significantly degraded and fragmented, thereby threatening their value as habitat for biodiversity conservation and in the provision of vital environmental services.

Recognizing the perilous situation of natural forests in the country, the Forest Department has established a series of protected forest areas (distinct from gazetted forest reserves).  The protected areas of Bangladesh, established under the aegis of the Forest Department, include 7 national parks, 8 wildlife sanctuaries and 1 game reserve.  Approximately 84,000 hectares (out of a total protected area of approximately 250,000 hectares, the rest being in lowland coastal areas primarily within the Sundarbans) of these relatively intact upland forests are found in the northeast and along the spine of the eastern hills.  Doubtless, there are other areas of natural forests left in Bangladesh, both within the Reserved Forest system or as ungazetted state forest lands where the community-based co-management model being proposed here might also eventually be promoted.

2.2		Relationship to Government of Bangladesh Priorities

Concern for biodiversity assets in the country date back to colonial times– the 1879 Elephant Preservation Act and the 1912 Wild Bird and Animals Protection Act.  These regulations were repealed in 1973 when the Government passed the Wildlife (Preservation) Act.  Bangladesh is a signatory to the 1992 Biodiversity Convention elaborated at the Earth Summit in Rio de Janeiro, Brazil and biodiversity issues have received some attention in a variety of sector policy and strategy documents since that time.  Bangladesh has also been a participant in earlier global conservation initiatives before "biodiversity" became the watchword of the day.  The country has ratified the 1971 RAMSAR Convention on wetlands of international importance and waterfowl habitat, the 1972 Convention concerning the protection of World Cultural and Natural Heritage and the 1973 Convention of International Trade in Endangered Species (CITES).

Of more recent vintage, the theme of biodiversity conservation is discussed in the 1995 National Environmental Management Action Plan (NEMAP), the 1997 draft of the National Conservation Strategy, the 2000 ADB Environmental Operational Strategy, and the 1993 Forestry Master Plan.  Just recently, the Ministry of Environment and Forest (MOEF) with the collaboration of IUCN/Bangladesh and funding support from UNDP, has begun the preparation of the Bangladesh Biodiversity Conservation Strategy and Action Plan.  This 18-month initiative is expected to comply with the requirement for such a plan for each country signatory to the Convention on Biodiversity.  Interestingly, the U.S. Fish and Wildlife Service is currently working with IUCN/Bangladesh and NACOM, a local conservation NGO on action research as part of the Asian Elephant Conservation Fund in Bangladesh; a survey of existing elephant populations is being carried out.

There has also been another recent development related to Governmental concern for biodiversity and the sustainability of the natural resources base with the declaration of ecologically critical areas (ECA).  The Bangladesh Environmental Conservation Act of 1995 includes a provision whereby if the Government is concerned that the degradation of an ecosystem has reached "a critical state" or is so threatened, it may declare the area to be an ECA by notification in the official gazette.  In April 1999, this authority was exercised for the first time by the Secretary, MOEF with the advice of the Director General of the Department of the Environment in officially notifying the establishment of seven separate wetland areas covering approximately 40,000 has as ECA's. While the details of the Act suggest that the DOE could identify forest areas for designation as ECA’s, this has not been done to avoid institutional conflict with the Forest Department.

2.3		Other Donor Programs and Plans

Specific biodiversity conservation components have been included in some of the major multilateral bank funded loan projects, including the World Bank-funded Forest Resources Management Project (FRMP), the Asian Development Bank-funded Forestry Sector Project (FSP), and most recently, in the Asian Development Bank-funded Sundarbans Biodiversity Conservation Project.  A recent project approved by UNDP and GEF-- the Coastal and Wetland Biodiversity Management Project (BGD/99/G31)-- will be the first effort to make the ECA concept operational at four sites: Cox's Bazaar Beach and adjacent islands and Hakaluki Haor (UNDP 2001).

Under the Ministry of Environment and Forest-implemented and UNDP-supported Sustainable Environmental Management Program (SEMP), a number of sub-components actively pursue participatory wetland ecosystems management and biodiversity conservation in Haor, Floodplain and Charlands.  All these sub-components have significant activities in participatory forestry.  SEMP is in the fourth year of implementation of a five-year program.

Under the FSP, a series of management plans were prepared for various protected areas and the importance of biodiversity conservation in each of the country’s Forest Divisions was also synthesized to guide the efforts of the Forest Department to engage in this new mandate for biodiversity conservation.  These plans, however, have as yet to be acted upon and they have been used in part, with the blessing of the Forest Department, in the elaboration of the present programming document for USAID.

  - Relevance/Complementarity with the Mission Strategic Plan and Programs

The current Strategic Plan of USAID/Bangladesh is focused on a “more proactive approach toward broad-based economic development” to help reduce poverty in the country.  The floodplains of Bangladesh are already noted for the intensification of the management of the agricultural land-use base that helps to accommodate the very high population densities and has lead to notable positive impacts on both food security and poverty alleviation.  To maintain this momentum, the country will also be challenged to extend the sustainable use and management to all corners of the Nation so as to ensure that the rural landscape fully contributes to the goal of poverty alleviation.  Because of mounting demographic pressure, many of the marginal areas, especially in the hilly zones of the country are unfortunately now being treated as “open access resources” despite some official efforts to designate them as “protection areas”.

Without early and affirmative action, the natural resource base of the hill lands, now being inexorably degraded, will result in a declining spiral of production and productivity  irreversibly linked to the destiny of both the people who now make increased use of them and downstream communities on the floodplains.  As has been demonstrated elsewhere in a number of Asian countries, appropriate land-use on the steeper hilly areas can be rationally improved and intensified through a co-management approach.  By brokering the stewardship of these lands and their resources among the communities who are increasingly dependent on them, sustainable and diversified production alternatives will ensure a greater chance for a more optimum contribution to poverty mitigation and local development.  Finally, although these activities will be designed to have a tangible result for both the people and the lands involved, their real contribution will be in fostering the model of community-based, co-management that can be replicated elsewhere in Bangladesh.

USAID’s investment in co-management of tropical forest resources and biodiversity conservation will also provide important cross-sector relationships and opportunities for synergy with other programs of the portfolio.  On the one hand, local level, forest related land-use planning and management skills, as foreseen with both community-based resources management committees and at the Upazila level Development Committees, will by definition, constitute a prima facie case of decentralization- a goal of USAID’s Democracy and Governance Program.  By vesting greater understanding and authority for land-use planning at the more local level, communities and the authorities which represent them will enhance their capacities for “drawing down” the development resources they justly need, thereby overcoming the perennial issue of the “top-down” approach to development that now troubles local development in the country.

Furthermore, the fragile nature of the resource base in the hills demands alternatives that compensate local communities for accepting the production trade-offs implicit in a sustainable land-use pattern.  Helping local communities to analyze their impacts on and understand the inherent limitations of these sites will inevitably lead to an improved capacity for “self-help” that breaks the mold of uncontrolled subsistence use.  This program of activities in the forestry sector will include building entrepreneurial capabilities under an alternative income generation component promoting micro-enterprise at the village level highly compatible with the Mission’s Enterprise Development Program.

3.		RATIONALE AND JUSTIFICATION FOR A FORESTRY PROGRAM

3.1		Goals and Objectives

In Bangladesh, as in few other countries of the world, the mix of program interests of the current USAID environment SO-- Improved Management of Open Water and Tropical Forest Resources--is more than a fortuitous combination of interests; it is an obligation.  USAID is convinced that its support for the management of both aquatic and terrestrial ecosystems will show the real benefit of the "integrated approach", in that the results of the whole will be significantly more important than the simple sum of its component parts.  Accordingly, the goal of a full-fledged, bilaterally-funded program on conservation and co-management of tropical forest resources and biodiversity is to complement the on-going wetland/open water conservation and management activity of MACH and to be responsive to the intermediate results and indicators seen as essential to reaching the Strategic Objective.

The first SO level indicator-- "Extent to which best practices from USAID-funded projects are used elsewhere"-- underscores the importance of innovation in developing a model that can be understood and replicated elsewhere.  With the modest resources available for this component, the goal goes beyond simple physical impact on the targeted sites.  The clear focus on the development of a model suggests that technological, institutional and policy realizations will also result, leading to an improved enabling environment for co-management approaches to natural resources management in Bangladesh.  Having said that, however, it is also logical that the proof of the effectiveness and efficiency of the model can only be corroborated by measuring its outcome in realistic terms.  For this reason, the application of this model is expected to lead to two important results: (as defined by the indicators):  "Increased production of natural resources (forests and wetland products) in targeted areas" and "Increased biodiversity in targeted areas".

In order to contribute to the realization of the SO and meet its indicators, the activities of the forestry program will be organized along lines that reflect the Intermediate Results identified in the SO 6 Results Framework.  In effect, these intermediate results constitute the more specific objectives of the forestry program.  As a gauge to guide the measurement of performance of the activities in reaching the IR's, a series of proposed indicators have been further identified.  Figure No. 2 below presents these indicators aligned with their respective IR's and will serve as a basis for the overall detailed design of the forestry program and its activities.

Figure 2: Proposed Forestry Program Indicators

| Strategic Objective 6- Improved Management of Open Water and Tropical Forest Resources SO Indicators: Indicator 6.a- Extent to which best practices from USAID-funded projects are used elsewhere Indicator 6.b- Increased production of natural resources in targeted areas (forest & wetland products) Indicator 6.c- Increased biodiversity in targeted areas |
| --- |
| Intermediate Results for SO 6- Improved Management of Open Water and Tropical Forest Resources (as per the existing PMP) |
| IR 6.1- Effective Community Based Resource Management Mechanisms Implemented | IR 6.2- Select Habitats and Ecosystems Improved – IR 6.2.1- Innovations and Best Practices Adopted – IR 6.2.2- Alternative Incomes Realized for Target Groups | IR 6.3- Select Policies Implemented that Support IR’s 1 & 2 | IR 6.4- Public Awareness of Key Issues Increased | IR 6.5- Improved Institutional Capacity |
| Proposed Forestry Program Indicators |
| Indicator 6.1b - Number of protected areas and overall total area in which sustainable co-management plans are being implemented Indicator 6.1c- GOB agreements to expand protected areas as appropriate Indicator 6.1d- Declining incidences of unsustainable and illegal use of protected areas | Indicator 6.2b- Upland forest habitat improved in targeted areas (ha) Indicator 6.2.1c- Area of degraded forest habitat restored (percent of total targeted area) Indicator 6.2.1d- Watershed management and/or buffer zone plans and practices operationalized Indicator 6.2.2b- Increased income of targeted beneficiaries | Indicator 6.3c- Number of formalized co-management agreements in place with communities surrounding targeted protected areas Indicator 6.3d- Inter-Agency agreements in place allocating usage rights to local communities Indicator 6.3e- Co-management policy agenda established and being acted upon by GOB | Indicator 6.4b- Number of communities and beneficiaries that participate in training cum planning sessions resulting in co-management agreements for protected areas Indicator 6.4c- Growing public awareness and understanding of the importance of biodiversity conservation and environmental services | Indicator 6.5b- Forest Department skills and experience to promote co-management of protected area improved Indicator 6.5c- Enhanced GOB Agency capabilities for working together on integrated NRM programs Indicator 6.5d- Local Govt. w/ improved land-use and NRM planning & governance capabilities Indicator 6.5e- Improved local NGO capabilities to support ICDP |

3.2		Program Concept and Strategy

The efforts to develop the co-management of protected forest areas approach under this program are expected to be an innovative approach to the relationship between local communities and adjacent forest lands and the governmental authorities responsible for them.  It is important to note, however, that although the typical modus operandi of the Forest Department in Bangladesh is that of principal steward of the officially reserved forests identified and used to meet national production goals for forest products, there are a number of existing precedents wherein the Department (and indeed the local NGO community) provides participatory and social forestry program services for the direct benefit of the rural public.  These may generally be categorized as follows: forest village agreements, social forestry programs, participatory forest management, and homestead forestry (see Annex A).

Before moving forward with a discussion of co-management, it is also necessary to set the record straight about national efforts to deal with deforestation in Bangladesh.  Despite serious concerns about the deforestation rate in this densely populated country (something very difficult to quantify with accuracy), the success of massive efforts at reforestation should also be noted.  On the floodplains of the country, virtually every tree (bush, shrub, and bamboo clump) that can be seen, has been planted by the hands of men and women.  Homestead plantations, tree-planting campaigns and days, linear plantations, mangrove reforestation along the coastal zone and extensive replanting in many reserve forests readily attests to the local capacity for reforestation.  It would probably not be an exaggeration to say that Bangladesh is among the leading countries of the world where the government, civil society and the people all embrace tree planting.  Therefore, this program is not about tree planting.  It is about saving the remaining scattered patches of natural forest as a living legacy for future generations, as habitat for the increasingly threatened biodiversity assets of the nation and ensuring their role as watershed areas critical to the viability of adjacent wetland ecosystems.

3.3		Understanding the Meaning of Co-Management

Experience world-wide has now corroborated the fact that the "Co-Management Approach" must be based on the simple reality that conservation, no matter how compelling from a societal or even global perspective, can rarely be achieved on the backs of those local people least able to afford it.  Attempting to rigorously enforce unilateral protection of valuable conservation areas is almost impossible to achieve.  Such an approach flies in the face of the simple economic realities of supply and demand.  Rigorous protection of forest resources has the effect of curtailing supply or at a minimum creating the perception of curtailed supply.  As demand is likely to remain constant, given the subsistence nature of much of the usage patterns in de facto "open access" forest areas, prices will rise.  This stimulates more pressure on the forest resource base, something that becomes especially acute in a densely populated country like Bangladesh.

The composite elements of the co-management approach, all of which will be necessary for its successful implementation, may be characterized as follows:

The Value of Conservation for Local Communities: A central theme therefore of the co-management approach is to demonstrate the value of natural resources management (matching land-use to land capability) to local people, i.e., that they themselves will be better off over the long-run by participating in the sustainable use and management of the resource base (whether aquatic or terrestrial).

Brokering Genuine Community Participation: Achieving the community consensus for sustainable natural resources management requires concerted dialogue and a real partnership between the communities and those governmental agencies charged with the goal of protecting these resources for society at large.  Turning the present usage patterns around necessitates understanding and commitment from both sides.  In the case of protected forest areas, communities will agree to relinquish unsustainable usage patterns in return for compensatory measures (and including alternative income generation activities) which help them meet the demands for wood and forest products and income on which they may have become dependent.

Sharing the Full Benefits Stream--Products and Services: It is also worth noting that securing community compliance with the conservation imperatives within the protected areas will be more challenging than the situation experienced under the MACH Project.  Although MACH uses sanctuaries and fishing regulations to achieve conservation, community participants benefit in the near-term as the annual brood results from the beel sanctuaries spread out during the flood, grow and are harvested.  The core areas within the protected terrestrial forest areas will not be harvested and therefore they require an off-site source of benefits to compensate local people with either recognized user rights or traditional user rights for the production trade-offs they willingly accept to meet the conservation goals of the program.  There are several ways in which the resources formerly harvested by local users will be compensated under the forestry program.  Social forestry, homestead forestry, participatory forestry plantation programs on adjacent reserved forest land, sustainable use zoning and khas land-based community forestry schemes (a potential innovation) opportunities will be explored and where appropriate promoted in the buffer zones around the protected area.

The forest areas benefitting from this enhanced community stewardship will in turn yield other values in the form of environmental services (watershed and biodiversity conservation, disaster prevention from storm protection).  These services will have positive impacts as well on the productivity of downstream wetland ecosystems, on floodplain agriculture, on safe-guarding home and community infrastructure from flash floods, and on recharging vital groundwater aquifers.  They may also provide interesting opportunities to diversify the local economy through the provision of outdoor recreation and ecotourism based enterprises.

Local Organizational Development--An End unto Itself:  The other fundamental part of the co-management approach is localized organizational development.  These efforts bring together the user community and different interest groups within them (women, woodcutters, collectors of non-wood forest products, livestock owners, etc) and makes it possible for them to express a degree of community consensus about their needs and expectations related to the adjacent forest areas, thereby empowering them as co-managers of the resource.  Furthermore, such an approach is the epitome of enhanced local governance systems whereby local people learn to analyze their local problems and participate in deciding how they may be resolved.  Such an approach, anchored in the actions to meet natural resources management and conservation goals will also spin-off a build-up of self-esteem and self-reliance within the communities.  Creating this capacity to "draw-down" the well-justified governmental assistance they need to meet locally identified development goals will go a long way to overcoming the present "top-down" approach to development.

3.4		Overview of the Program

The proposed forestry program will in many ways mirror the effective approach being utilized under the MACH Project–working with local communities and local authorities to develop co-management models around a series of targeted protected areas.  The overall objective is to take the pressure off of these areas so as to safeguard and restore their role as important habitat for tropical forest biodiversity and ensure that they continue to provide critical environmental services, in particular watershed protection.  This will be achieved through a program of coordinated activity streams:

- creating local organizational mechanisms for community awareness and as a means to broker co-management of the natural resources in and around these protected areas;

- development and demonstration of locally adapted natural resources management investments and interventions leading to sustainable use of these protected areas and their buffer zones;

- building and strengthening institutional skills and capabilities to facilitate community-oriented conservation and management on a local government and inter-ministerial basis;

- intra and inter-ministerial policy dialogue and reform aimed at ensuring an enabling environment of policies, plans, rules and regulations conducive to the widespread replication of the co-management approach;

- developing, field testing and promoting alternative income generation and employment activities for local communities to counter the production trade-offs necessary for wise use and conservation of the protected areas; and

- providing program implementation and support capacities providing technical guidance and assistance to other program partners (GOB agencies, local government, NGO’s and CBO’s).

This program component will be authorized for a period of five years, starting in FY 2003 with a total budget of approximately U.S. $ 7.4 million.  On-the-ground implementation will be phased in over the first three years, working initially in one or two protected areas and extending to another two or more areas by year three.  Illustrative targeted protected areas include: start-up year activities in the northeast selected from among Lawachara National Park, Rema-Kalenga Game Sanctuary and Satchuri Reserved Forest with out-year activities in the southeast of the country, for example, in Teknaf Game Reserve, or Sangu or Matamuhuri Headwaters Reserve or other areas in the Chittagong Hill Tracts.  There are also likely to be additional candidate areas, some already suggested by the Forest Department, found outside the list of protected areas, mainly in reserved forests.  The choice of where to target the program will be made on the basis of agreed site selection criteria (see additional discussion below).  Implementation will be carried out under the aegis of an inter-ministerial agreement and will utilize local NGO services for community-oriented organizational development and alternative income generation activities.  The services of a technical assistance contractor with a small resident team and short-term consultants to guide and further develop this approach will be procured through an RFP.

This is clearly a pioneer initiative in co-management of forest resources in this country and will not be a follow on from other projects.  However, indigenous knowledge, lessons learned from and the best practices developed under all previous community-based natural resources management initiatives will be adapted.

4.		PROGRAM IMPLEMENTATION STRATEGY

4.1		Building a Coherent Model and the Capabilities to Implement it

Before launching into a detailed discussion of the forestry program component, a number of special features of this design are worth noting.  This design represents the best efforts of a team of experienced consultants and wide-ranging consultations with those knowledgeable about forest resources and conservation in the country to develop a plan for promoting co-management of natural resources, including particularly, the Forest Department and its parent Ministry of Environment and Forest.

Much of what follows here is both typical and rational for a co-management of natural resources program focused around protected areas, watershed management, and biodiversity conservation.  However, what is set out below deliberately seeks to avoid a priori and perhaps even ad hoc decision-making about some of the critical choices and steps essential to ensuring that the full implications of the co-management model are widely understood and can be effectively internalized.  It seeks to overcome the unavoidable limitations of a restricted design effort in which although the different key parties have agreed to take part, they may not have had sufficient time or inputs to fully realize exactly what they are getting into.  Furthermore, it is a premise of this design that this "process orientation" will greatly facilitate the important learning process and institutional strengthening that will lead to and facilitate the eventual replication of the model elsewhere in Bangladesh.

4.2		Institutional Framework for Program Implementation

Although it may not readily appear so, what is most different about this design must be the institutional framework for its implementation.  Among the most salient of these differences is the agreement to work in an integrated format for resolving the problems of unsustainable use of protected areas that provide important environmental services and shelter the remaining terrestrial biodiversity assets of the country and whose contribution to local development could be enhanced.

For example, the watershed management premise immediately suggests the need for working both within the protected areas that are found typically in the headwaters of the catchments and in other areas within the watershed that may not be under the tutelage of the Forest Department.  These could include Khas lands managed by the Ministry of Land, areas within the Tea Estates adjacent to some of the protected areas, and on private and community lands also found within the watershed.

Similarly, many of the solutions for the present unsustainable use patterns within the protected areas may require actions in these other areas as well in order to ensure that local people are not disadvantaged by conservation imperatives.  Working with local communities may necessitate different skills typically embodied by NGO programs in the rural countryside such as community organization and the development of alternative income generation activities.  In essence then, the integrated approach embodies cross-sectoral efforts involving various governmental agencies, multi-disciplinary solutions for land-use problems, and the involvement of civil society in the transformation of local governance arrangements for natural resources management.

The following is the proposed institutional framework for the implementation of a co-management of tropical forest resources program funded by USAID/Bangladesh.

Program Steering Committee: This program is authorized under the Strategic Objective Grant Agreement (SOAG) between USAID and the Economic Relations Division (ERD) of the Ministry of Finance for Improved Management of Open Water and Tropical Forest Resources.  It will be overseen by a Program Steering Committee chaired by the Secretary, Ministry of Environment and Forest (MOEF). USAID and ERD will also be represented on the committee.  Given the wide-ranging scope of the integrated program, representation from other key ministries such as the Ministry of Lands, the Ministry of Local Government, Rural Development and Cooperatives and the Ministry of Water Resources is also anticipated.  It is suggested that because of the profound implications of this program for the activities of the Forest Department, they must also be represented on the committee, ideally by the Chief Conservator of Forests.

Because of the innovative nature of the co-management model that this program seeks to develop and promote, it is the hope of USAID that the Program Steering Committee will meet regularly and take on a proactive advisory, decision-making and policy role as the program gets started and evolves.  It is at this first level of oversight that some of the key choices regarding program implementation mentioned above can hopefully be scrutinized and decided.  It will be incumbent on the Committee to address the practical realities of institutional mandates for joint implementation.  Leadership and decision-making at this level will doubtless reinforce the internal learning and institutional capacity building goals of the program.

The committee will meet every six months or more frequently at their own discretion or as required for decision-making.  The venue for these Program Steering Committee meetings will be in Dhaka although it is hoped that on several occasions over the life of the program that they might meet in a venue near the field activities and invite local government representatives to take part.

Because of the high level participation in the Program Steering Committee, it will be incumbent on the program to ensure that they are provided with the information and documentation they require for effective and efficient decision-making.  Accordingly, the next tier of the organizational structure, described immediately below, is foreseen.

Technical Working Group:  The fundamental reasons for the suggested formulation of the Technical Working Group are several.  On the one hand, it is this group that will provide a type of secretariat services for the Program Steering Committee, preparing the agenda and supporting documentation essential to their deliberations.  This will include routine reporting (annual reports and work plans) and action-type notes.  The latter are specifically intended to facilitate the decision-making mentioned above and would typically present an issue for consideration, outline the options for addressing it and analyze the advantages and disadvantages of each option.  These presentations are intended to facilitate informed decision-making among the members of the Program Steering Committee.  Early and likely examples of the type of action-memos to be prepared might include: ratifying the methodology of site selection and choice of targeted areas; development of a policy agenda and issues papers related to it; a consideration of the institutional development strategy for co-management.

The Technical Working Group would be formed by those directly leading field implementation of the forestry program component and thus, the other key role of the Technical Working Group would be on-the-ground coordination.  The Group would be co-chaired by the National Project Coordinator, designated by the Forest Department, and the Team Leader of the Technical Assistance contractor.  Their role would also be to ensure the timely preparation and technical validity of the documentation required by the Steering Committee, including annual work plans and reports and the action memoranda.  Other members of the Technical Working Group would include: the DFO(s) in the Division(s) where the program is operational; field-based representatives (one each) of other concerned ministries; and the program leader of the NGO(s) involved in the program.  The USAID Cognizant Technical Officer would be encouraged to attend as possible.

In all likelihood, this Group would also serve as the forum for discussing and debating other issues and deliverables of a technical nature (e.g., vetting consultant reports) prepared under the aegis of the program. Finally, their role includes responsibility for ensuring that the monitoring and evaluation requirements are being met.  The venue and timing of these meetings would be at the discretion of the joint chairpersons although it is anticipated that they would meet at a minimum on a quarterly basis.

Local Government Committees:  Building directly on the effective MACH experience, the forestry program component will also seek to interact with and engage the Upazila Technical Development Committee by means of a Local Government Committee.  This committee will serve as the link between the Resource Management Organizations, the concerned Union Parishad Chairpersons and the officials of appropriate governmental departments posted in the area.  The role of the Local Government Committee will center on public consultation and oversight of program planning and implementation, advisory services, support for brokering community consensus at higher levels and policy advice.

Community-Based Resource Management Organizations:   It is intended that the Resource Management Organizations (RMO's) will be the organizational personification of the empowerment of the local communities to be engaged in co-management.  Here again, as in the MACH Project, these RMO's will represent the interests of those community members living in and around and currently using the resources of the protected areas.  Their primary role will be to: broker the agreements necessary for actively participating in the preparation and ratification of the co-management plans for each area; express the consensus view of the communities regarding their needs and expectations; and working with their members and the general public to fulfill the conservation imperatives critical to safeguarding the sustainability of the natural forest and its biodiversity assets.  RMO members will be elected in the process of organizational development at the grass roots level with the communities residents in and around the protected areas.

4.3		Program Implementation Staff

The remainder of this section discusses the roles and responsibilities of those who will actually serve under the aegis of the different partners on the Program Team and be responsible for its implementation.  The overall design foresees two clusters (discussed in further detail below under the heading of Indicative Implementation Plan) of activity centers--one in the northeast and the other in the southeast.  Sharing of staff roles within the clusters for specialized services will lead to greater effectiveness and efficiency.

Forest Department- Roles and Responsibilities for Program Implementation:  Because they are the present stewards of the protected areas, the Forest Department will play a crucial role in the implementation of co-management development activities (described further below). It is hoped that building a co-management agreement, within the framework of existing acts, with the concerned communities will lessen the incursions into the forest.  This will release staff and staff time to undertake other duties identified in the management plan, for example, receiving the public, nature interpretation and environmental education, monitoring biodiversity assets and forest ecology, limited efforts at silvicultural interventions designed to enhance the quality of the natural environment, and the provision of extension services off-site for forestry related development activities among the participating communities.

The Forest Department will provide many of the core staff members, as part of the GOB contribution in-kind, for the implementation of the forestry program component.

NGO Services- Roles and Responsibilities:  From the outset, the responsibilities of the NGO Service providers will center on being the interface with the local communities, primarily through their roles in promoting community level resource management organizations and a program of alternative income generation activities.  The ideal local NGO to participate in this program would be one with both natural resources management and community organization/alternative income generation skills and experience.  In addition, as mentioned above, the program will look to the local staff of the Forest Department to provide training and guidance for forestry development related activities among the communities but there will still be a need for NGO staff capable of promoting sustainable agriculture, soil and water conservation, and the provision of outdoor recreation and ecotourism services.

Technical Assistance Contractor:  This design envisages the need for a Technical Assistance Contractor procured by means of a Request for Proposals (RFP) among the qualified U.S. based development consulting firms.  The technical proposals will be evaluated by a Technical Evaluation Committee comprised of USAID staff and an appropriate representative of the Ministry of Environment and Forest, preferably the Forest Department. It is suggested, furthermore, that the successful contractor will establish a consortium of corporate skills and capabilities that will include sub-contracting relationships with the local NGO whose services are described above, and because of the conservation focus of this program, with an experienced international conservation organization.

The roles and responsibilities of the T.A. Contractor will include: provision of technical assistance services (both long-term and short-term) and guidance on the development and promotion of the co-management model for USAID, the GOB agencies involved; overall leadership of the other implementation partners; liaison with the GOB agencies, in particular, the Forest Department; overall control of administrative and management support services including financial management, commodity procurement, arranging and supporting all program related training; close collaboration with USAID/Bangladesh in the development and execution of an effective monitoring and evaluation system; administration of credit and grant facilities; and the timely production of all reporting and documentary deliverables.

4.4		Candidate Sites for Program Activities

USAID believes that is both essential and logical to begin this program in areas where the GOB has already demonstrated its conviction and commitment to biodiversity conservation.  The aim is to continue to develop this vital commitment, helping to take the pressure off of declared protected areas by identifying and implementing usage solutions based on a full measure of community participation known as co-management.  In the main, the sixteen (16) existing Protected Areas have been created by official notification of their status as such and involve areas that were once part of officially gazetted Reserve Forests.  These areas are the last refuges of biodiversity in the country although many of the larger mammalian species (leopards, wild dogs, sambar, bear, rhinos, Indian bison, and wild buffalo) have been extirpated.  Doubtless, there have also been serious inroads into the floristic biodiversity assets as well although the picture there offers more hope.  Many of these areas are found in hilly zones and as such also provide important watershed related environmental services.

The present list of protected areas includes national parks, game sanctuaries and game reserves, each with a slightly different set of conservation and management rules established under the Wildlife (Preservation) Act.  All of these protected areas were established after 1980 and like the Reserve Forests from which they were carved, sometimes include forest villages within their boundaries or usage rights for neighboring villages.  During design consultations, the Forest Department has also pointed out that there are other areas of significant natural beauty and biodiversity outside the existing P.A. list, mainly in Reserve Forests.

Although the question of which areas might be considered is important, the matter of how to make the choice is even more fundamental because it serves to reinforce the strategic approach to the development of co-management and to the likelihood of ease of understanding and eventual replication.  The intent of the present program is to promote the formulation of a readily implementable and replicable co-management model and the relatively modest resources available from USAID suggest that this should take precedence over attempts to achieve wider physical impact.

Therefore, one of the starting premises of the program is the need for site selection criteria to identify targeted sites for program investments.  The following table provides suggested site selection criteria as something that could be further discussed and decided among the partners and perhaps even tabled in an early meeting of the Program Steering Committee.

Figure 3: Site Selection Criteria

| Proposed Criteria | Discussion |
| --- | --- |
| Management Status--Part of the existing Forest Department system of Protected Areas. | At least at the outset, and in order to facilitate a rapid start-up, the P.A.'s should be given higher priority for selection. However, this does not preclude choosing sites proposed for notification, reserve forest areas and even ungazetted state forest areas. |
| Conservation Value—Unique examples of tropical forest ecosystems or habitat for important biodiversity assets. | Measuring this value could be a matter of percentage area remaining in natural forest vegetation or the presence of keystone biodiversity species. |
| Watershed Role and Environmental Services—Related to the overall integrated water resources management theme. | There would be a preference for hilly areas that are at the top of the watersheds of important wetlands. Other water related values could include as catchments for reservoirs or as forests sheltering adjacent communities from storm surges and cyclone impacts. |
| Public Awareness Value--Sites likely to attract visitors who would benefit from nature conservation and environmental education. | Accessibility must be such that the general public (and possibly even foreign tourists) can visit the areas for outdoor recreation and nature viewing. |
| Efficiency Considerations--Areas need to be of sufficient size. | A minimum size of 1000 hectares is proposed as the cut-off. Each of the sites will have certain development overhead requirements and costs and this minimum would be sufficient to warrant an effective and efficient investment. |
| Effectiveness Considerations--Neighboring areas to sites already chosen by the program | The intention is to develop two clustered areas of co-management sites, one in the northeast and one in the southeast. This will make for more effective implementation, as it will be easier to share staff and program resources. |
| Relative Potential for Success--The "win-win" situations, especially at the outset where there are some assurances of implementation success. | Avoiding areas of entrenched social conflict, either among communities themselves or with the Forest Department, sites likely to be targeted for other development initiatives, and areas where local communities and authorities express an early willingness to participate. |

4.5		Illustrative Description of Activities

As might be expected, the investments and interventions of the program will be organized in five principal and complementary components congruent with the five intermediate results and their indicators for the SO.  The illustrative description of the activities which follows has also been developed based on an in-depth analysis of the issues and opportunities for co-management of protected areas in Bangladesh which was prepared as part of a working document for this design effort (see Annex C for a tabulation of the Issues and Opportunities).  It was also based on a thorough review of the most pertinent literature from the environment sector in Bangladesh (see Annex D for the list of references used in this design).  Although first generally comes first, the list of activities is not intended to convey absolute priorities or sequencing.

Component No. 1-	Development of a Co-Management Planning and Implementation Model

The activities under this component will be directly responsive to Intermediate Result 6.1-- Effective Community Based Resource Management Mechanisms Implemented and its Indicators.  Anticipated illustrative activities include:

- The Forest Department and its counterparts in the Program Team (Technical Assistance Team and Partners) agree on a select list of Protected Areas as priority options for a phased approach and obtain the concurrence of the Program Steering Committee and USAID based on an agreed site selection criteria.

- Program Team (F.D. and Technical Assistance staff) carry out reconnaissance surveys on status of forest and its biodiversity assets and identify zones of influence (buffer zones) for each protected area (P.A.).  This will involve the development of certain planning tools including a forest biodiversity survey instrument and the definition of a potential zoning code (e.g., ecosystem management zone or core zone, village use/sustainable use zone, resource rehabilitation zones, adjacent critical watershed areas, buffer zones, etc.)  Updated maps of each targeted protected area with important topographical features, infrastructure and present land-use will be prepared.

- Establishment of a GIS/GPS based mapping and monitoring facility as a key planning and performance tracking tool.  These services could be subcontracted to a local private sector institution.

- Identify adjacent areas that are parts of the watershed between the protected area (usually at the top of the watershed) and the lower riparian/wetlands areas they serve to ensure comprehensive watershed management planning and actions.

- Program Team led by the NGO specialists begins a Participatory Rural Appraisal (PRA) process with the local communities living in or adjacent to the Protected Area to identify their needs and opportunities.  These PRA's will use tools such as community mapping and needs assessment.

- Program Team led by the NGO specialists begins community organization process identifying resource management committees and potential interest groups.  The RMO's will adopt the methodology used by the MACH Project for this purpose although it may have to be adapted for terrestrial applications.

- Work with neighboring stakeholders (e.g., Tea Estates, private land owners, the Ministry of Land) to identify their constraints and opportunities for protecting natural forest areas within their boundaries.  Ensure that Tea Estate workers are informed of the goals of the co-management approach and its requirements if they are not part of the communities involved in co-management.

- Develop and apply the rules and methodology of sustainable use zoning within the protected areas where necessary to accommodate established and recognized forest villages and their inhabitants.  Give particular emphasis to garnering traditional knowledge about forest-based farmacopia.

- A Draft Co-Management Plan will be prepared with annual operational targets discussed and agreed with the communities through the intervention of the RMO's for each of the targeted protected areas under the program.

- Study the opportunities for the possible expansion of the protected areas into adjacent contiguous areas of reserve forests and work with the Forest Department to secure their official notification as such.

- Communities and RMO's assess their achievements in light of the annual work plan (monitoring and evaluation) with the Program Team and perhaps adjust expectations in the out-years.

Component No. 2--	Interventions and Investments for Improved Ecosystem Management

The activities under this component will be directly responsive to Intermediate Result 6.2-- Select Habitats and Ecosystems Restored, and the Sub-IR's 6.2.1--Innovations and Best Practices Adopted and 6.2.2--Alternative Incomes Realized for Target Groups and their Indicators.  Anticipated illustrative activities include:

- Ensure that the recognized boundaries of each targeted P.A. are clearly and permanently marked and that suitable and prominent signage regarding their special status is placed at key access points.  In cases where the limits may be in dispute, work with the local authorities and community leaders to re-establish the limits, registering them in the field with a GPS and later plotting them on official maps.

- Program Team prepares habitat restoration manual as a guide to the rehabilitation of areas within the Protected Area in need of improvement.

- Restoration and watershed management activities get underway with community assistance in designated forest compartments where they are required for watershed management and biodiversity conservation purposes.

- Determine the potable water supply circumstances of forest villages and consider development of safe, piped water in return for their agreement to protect watersheds.

- Forest resource development, agricultural improvement, soil and water conservation activities get underway in buffer zones, including with private sector interests (Tea Estates) in order to begin to ensure the sustainability of the watershed.

- Develop a methodology for transparently quantifying human impact on the protected areas as a key to gauging the compensatory measures that may be required to achieve conservation imperatives.

- NGO personnel, perhaps with technical assistance, undertakes feasibility studies for alternative income and employment generation activities.  Companion studies on the micro-economics or business planning and market access elements are carried out to ensure that participants are fully likely to benefit from their participation in these activities.

- Program Team develops an annotated action-reseach oriented issues agenda as the basis for a modest program of research grants to be contracted with institutions like the BFRI and others, focused on forest ecology, natural forest management, biodiversity assessment, watershed management, co-management and other germaine topics.

- Alternative income and employment activities get underway among the target communities.  Lead participants in each of the categories of AIG activities are chosen and their efforts monitored carefully as an indicator of successful performance for monitoring and evaluation purposes.

- Possible community support and working credit program elements are operationalized (e.g. water supply, seed supply, etc.).

- Identify keystone forest tree and plant species that might be re-introduced or whose populations need enhancement within the P.A.  Study the methods for their regeneration including the possibility of direct seeding and the feasibility of planting seedlings.

- Develop a response to possible issues of crop-raiding by animal inhabitants of the protected areas.

Component No. 3--	The Enabling Policy Environment for Co-Management Enhanced

The activities under this component will be directly responsive to Intermediate Result 6.3-- Select Policies Implemented that Support IR's 1 & 2 and its Indicators.  Anticipated illustrative activities include:

- Regular twice yearly inter-ministerial Program Steering Committee meetings with the Technical Working Group providing secretariat services (meeting agenda, issues papers and follow-up actions).

- Program Team assists in the organization of the Local Government Committee and uses this mechanism to present and explain the co-management approach, its activities and implications to the local government level decision-makers (Union Parishads and the Upazila Development Committees).

- Program Team prepares a “white paper” on the local and national policy agenda for co-management for submission to Steering Committee and as the basis for continuing policy dialogue about the enabling environment for the promotion of co-management of natural resources.

- As a result of the decisions of the Program Steering Committee, the Team commissions policy studies to enhance the quality of the informed debate among the program decision-makers.  For example, one such study might address the  macro-economics of biodiversity conservation and co-management of protected areas.  Another might address the institutional strategy for integrated natural resources management and its implications for the ministries concerned.

- Develop a policy and process for a permit and fee structure for day visitors to the P.A.'s.  In selected P.A.'s, there may be future opportunities for limited, low impact camping facilities but this needs further study and a sound policy established.

- Co-management of tropical forest resources operations manual prepared and vetted by the Program Steering Committee and all of the participating GOB departments.  This draft manual provides the substance for a national workshop on the topic.

- Mid-term evaluation carried out; lessons learned identified and any reformulation of program objectives and indicators along with necessary reprogramming of activities, staffing needs or financial resources considered.

Component No. 4-	Laying the Foundation for a Conservation Constituency in Bangladesh

The activities under this component will be directly responsive to Intermediate Result 6.4-- Public Awareness of Key Issues Raised and its Indicators.  Anticipated illustrative activities include:

- Public Awareness Strategy developed by the Program Team perhaps with short-term technical assistance.

- Invite local authorities on one day visits to the P.A.'s in their areas to explain and demonstrate program actions and the co-management approach--to include district, upazila and union parishad authorities and the officers of the security forces (e.g., the BDR detachments) stationed in the area.

- Co-Management Plans presented at national workshop along with approach and specifics of community involvement.

- Inter-Community study visits encouraged and facilitated, including between upstream communities and downstream (wetland) communities and local authorities with the cooperation of the MACH Project.

- Prepare a brief illustrated brochure for each targeted P.A., explaining the forest, its natural components, biodiversity assets and the co-management approach for sale to visitors (in Bangla and English).

- A limited number of community members selected and trained as nature guides for protected area visitors.  Nature guides successfully completing the training course would be authorized by the Forest Department to escort visitors.  A certificate and perhaps a shirt and cap with suitable insignia could be provided to them.  A fee structure established for these services and a brochure in Bangla and English prepared for circulation among travel agencies in Bangladesh.

- Environmental education activities identified and promoted to serve recreation and tourism users.  This will include signage in each of the areas as well as the development of a nature walk through the forest led by trained members of the participating communities.  Nature trails may include limited and rustic structures to accommodate visitors (benches for resting along the way, foot bridges over wet areas and chharas, a latrine).

- Develop a conservation-oriented training package for local elementary schools and provide teacher training in its use.  Sponsor visits by school children from adjacent areas to the protected areas.  Seek private sector (corporate) support for modest funding to finance these visits.

- Work with avid local birdwatching groups to develop an illustrated guide to the birds of the Protected Areas of Bangladesh.  Seek private sector sponsorship for its publication with the proceeds going to investments within the P.A.'s.

- Regular program of media messages promoted and prepared with Team assistance.  One or two high level governmental study tours to working co-management areas and media coverage of these events facilitated.

Component No. 5--	Towards an Exit Strategy--Ensuring Institutionalization of Co-Management

The activities under this component will be directly responsive to Intermediate Result 6.5-- Improved Institutional Capacity and its Indicators.  Anticipated illustrative activities include:

- Training needs assessment carried out for Forest Department, other Ministries and NGO staff involved in the Program and a comprehensive training plan developed.

- Team develops model and methodology for training Local Government staff under a co-management of tropical forest training program.

- Establish a re-invigorated regime of beat patrols by Forest Department staff (consider the provision of radio communications) with special reference to monitoring biodiversity assets.

- Assist the Forest Department to develop a rapid response policy and protocol (disaster prevention) for addressing problem issues like forest fire, illegal logging, flash floods, land invasions, etc.

- Assist the Forest Department authorities in the preparation of staffing position descriptions related to protected areas and co-management.

- Program assists the local environmental and forestry schools (such as the Institute of Forestry and Environmental Sciences, University of Chittagong) to develop curriculum elements for training in the Co-Management Approach to Biodiversity Conservation and Natural Resources Management.

- Strengthening of the Wildlife and Nature Conservation Circle, aiming at establishing a Protected Area Management System as part of its organizational structure.

- Program Team makes a presentation about their achievements to the multi-lateral development banks (ADB, World Bank) with a view to attracting investment level resources for wide scale replication of co-management in Bangladesh.

4.6		Indicative Implementation Schedule

The program leadership will be charged early on with preparing a detailed work plan for the program and thus many of its details must be omitted until that time, however, several premises of the design should be taken into account in the implementation planning exercise; they include:

Careful Adherence to the Biological Calendar:  For one thing, any natural resources management related implementation plan must take into account the biological calendar which dictates when certain activities, related to both forest management interventions or the agricultural production year, must take place.  Thus the overall planning is directly linked to when during the year that the program is approved and becomes operational.

Allowing Sufficient Time for Mobilization:  Implementation will get underway when the Team Leader and the National Project Coordinator are appointed and take their posts.  However, it is likely that a 3 month period will be required to allow all elements of the program to be put in place and start operations.  At the end of this mobilization phase, the Program Team should be ready to share a program work plan cum inception report with the Program Steering Committee and USAID/Bangladesh.  This plan will also include a detailed work plan for the first full year of implementation.

Cluster Approach to Implementation:  As was mentioned above, the design foresees a cluster approach to implementation in order to achieve greater effectiveness and be able to use program resources, especially staffing, in an efficient manner.  Two clusters are suggested, one in the northeast centered on Sylhet Forest Division and another in southeast, centered on Chittagong.  In each cluster, it is probable that 1 to 3 protected areas could be targeted for program interventions and investments.

Incremental Build-Up to Program Activities:  The design consultants believe that a phased approach to implementation is essential so as to ensure that capabilities can be incrementally improved as the program moves forward.  Accordingly, the proposed activities and their targets (performance indicators) will be structured in phases: mobilization/inception phase; development phase; expansion phase; consolidation/exit strategy phase.  The latter assumes that this program duration of five years will not be extended although further insight into this matter is unlikely until at least after the mid-term evaluation scheduled for month 30.

- The mobilization/inception phase has been briefly described above.  During the development phase, it is likely that activities will be limited to 1 to 3 protected areas in one region--the northeast--of the country (although reconnaissance activities in anticipation of expansion to a second region--the southeast--may begin during this period).  More importantly, during the development phase (months 4 to 30), every effort will be made to ensure a comprehensive understanding and implementation of the co-management model is addressed and that human resources development and training as well as institution-building requirements are well underway so as to facilitate effective operations.

- During the expansion phase (months 31 to 48), it should be possible to increase the pace of implementation given the understandings of the model.  Several important caveats, however, must be borne in mind, namely that in the southeast, protected areas are likely to be larger, that the social and economic situation of the communities is quite distinct from the rest of the country, and access to protected areas is generally more difficult.

- During the final consolidation/exit strategy phase (months 49 to 60), barring any significant programming decisions between USAID and the GOB, the focus will logically be on consolidation of the model and handover of the responsibilities under the institutional strategy mapped out for its replication.

Figure No. 4, which follows, provides a graphic indication of the likely implementation plan for the program as a whole. An optimistic start date for the forestry program component would be January 2003 and the implementation calendar in this graphic has been prepared with that in mind, i.e., beginning implementation as a whole year.

Figure 4: Indicative Implementation Plan

| Overall Implementation Calendar—Years | Year One |  |  |  | Year Two |  |  |  | Year Three |  |  |  | Year Four |  |  |  | Year Five |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quarters | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Mobilization/Inception Phase | ---- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Program Team Assembles-- T.A. Contract in place & National Project Coordinator Appointed | ---- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Program Work Plan Prepared & Presented to First Meeting of Steering Committee | ---- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Commodity Procurement Commences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First Protected Area chosen and reconnaisance survey begins | ---- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development Phase |  | ------------------------------------------------------------------ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Co-Management Plan Development begins around the first protected area (* = draft plan ready) |  | --------------------------* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Co-Management Plan Development begins around the second protected area (*= draft plan ready) |  |  |  | --------------------------* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Both resource management and AIG interventions begin within co-management areas |  |  | --------------------------- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Next Steering Committee Meeting |  |  | sc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Established RMO's (2) assess program achievements/Team prepares a report on findings |  |  |  | xx |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarters | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Draft habitat restoration manual prepared |  |  |  |  |  | xx |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First Annual Report due and next Steering Committee Meetings |  |  |  |  | ar |  | sc |  | sc |  |  |  |  |  |  |  |  |  |  |  |
| Training Needs Assessment carried out/preliminary training plan drafted |  |  |  |  |  | xx |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Planning efforts get underway to establish second cluster of sites in southeast |  |  |  |  |  |  |  |  | --------------------------- |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary policy agenda formulated/commission first analytical study |  |  |  |  |  |  |  |  | xx |  |  |  |  |  |  |  |  |  |  |  |
| Second Annual Report due- |  |  |  |  |  |  |  |  | ar |  |  |  |  |  |  |  |  |  |  |  |
| Outdoor recreation/tourism promotion efforts get underway |  |  |  |  |  |  | --------------------------- |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mid-term Evaluation takes place |  |  |  |  |  |  |  |  |  |  | xx |  |  |  |  |  |  |  |  |  |
| Expansion Phase |  |  |  |  |  |  |  |  |  |  | ------------------------------------------- |  |  |  |  |  |  |  |  |  |
| Co-Management Plan Development begins around the third protected area/second cluster (*= draft plan ready) |  |  |  |  |  |  |  |  |  |  | --------------------------* |  |  |  |  |  |  |  |  |  |
| Action-Research agenda prepared/Grants program begins |  |  |  |  |  |  |  |  |  |  |  | xx |  |  |  |  |  |  |  |  |
| Draft institutional development strategy paper |  |  |  |  |  |  |  |  |  |  |  | xx |  |  |  |  |  |  |  |  |
| National Workshop on Co-Management held |  |  |  |  |  |  |  |  |  |  |  |  | xx |  |  |  |  |  |  |  |
| Co-Management Plan Development begins around the fourth protected area/second cluster (*= draft plan ready) |  |  |  |  |  |  |  |  |  |  |  |  | --------------------------* |  |  |  |  |  |  |  |
| Quarters | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Third Annual Report due/Steering Committee Meetings- |  |  |  |  |  |  |  |  |  |  | sc |  | ar |  | sc |  |  |  |  |  |
| Exit Strategy/Consolidation Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | --------------------------- |  |  |  |
| Fourth Annual Report due- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | xx |  |  |  |
| Co-Management Plan implementation continues in all sites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | --------------------------- |  |  |  |
| Final two Steering Committee Meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | sc |  | sc |  |
| Study on economics of co-management prepared |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | xx |  |  |  |
| Efforts to establish Protected Area System within Forest Department |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ----------- |  |  |  |
| Exit/Handover Strategy document prepared as Final Annual Report presented to Steering Committee, Forest Department & USAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | xx |

4.7		Reporting Requirements

The Program Team will be expected to produce a series of regular reports and technical documents (deliverables) over the life of the program.  These will include:

- Annual Work Plans and Annual Performance Reports:  This will be initiated by the end of the first quarter of implementation with the preparation of proposed overall implementation plan for the program, including a detailed Annual Work Plan for year 1 and more indicative work plans for subsequent years of the program.  At the end of each calendar year, the Program Team will present an Annual Performance Report along with a revised Detailed Work Plan for the coming year.  If possible, these plans and reports should coincide with the calendar year rather than the fiscal year to facilitate annual planning and implementation.  These plans and reports will be submitted in ten copies, to be circulated to USAID/Bangladesh and to the Program Steering Committee members.

- Quarterly Progress Reports:  Not later than two weeks following the close of each quarter, the Program Team will prepare and submit quarterly progress reports to USAID.  This report will summarize progress in relation to agreed upon milestones contained in the Annual Work Plan and will specify any problems encountered and indicate how these were resolved through corrective actions.  For each such action, the Team will specify which of the responsible partners is taking charge and the proposed timetable for their completion.  The Quarterly Report will also succinctly note key activities being proposed for the next quarter and specify if they deviate from the agreed Annual Work Plan.  Until all program procured commodities are received and put into use, the Quarterly Progress Report will include an update on the procurement plan.  The update should provide information on tenders in preparation, tenders out for bid, awards, shipments, carrier name and expected arrival date where pertinent.  The last quarterly progress report of each year will be part of the Annual Report and hence only three Quarterly Reports will be due each year.

- Minutes of Steering Committee Meetings:  The Program Team in the role of Technical Working Group will also be responsible for maintaining and reporting on the workings of the Program Steering Committee.  These minutes will record the agenda for the meeting, identify the participants and their affiliation, register the action responsibilities and who was designated to follow them up and the time frame for that action; report on completion of these follow-up actions from the previous meetings; briefly summarize the discussion of each of the meeting's agenda items; and indicate the date, timing and venue for the next meeting.  Copies will be furnished no later than two weeks after the Program Steering Committee meeting on which they are reporting and ten copies will be made available for USAID and the Steering Committee members.

- Technical Documentation (Anticipated Deliverables):  Because this program is designed to develop a model for co-management, a series of working documents and technical reports will be prepared.  The likely preparation of these deliverables will be identified in each of the Annual Detailed Work Plans, including an indication of the number of copies that will be required.  Similarly, all short-term consultants, both expatriate and locally hired will be required to present five copies of a report of their activities and recommendations; these consultant reports will be presented in draft form to the Program Team Leaders and reviewed in-house before the departure of the consultant.  The final version of these reports will be prepared and submitted in ten copies to the Program Team no later than 30 days after completion of the assignment.  They will be submitted to the USAID CTO and to other parties as deemed appropriate.

4.8		Performance Monitoring and Evaluation

USAID's re-engineered approach to development programming presupposes a business-like arrangement between the Mission and its partners.  This is especially manifest in the performance monitoring agreements between them.  Partners, led by the lead contractor are asked to achieve identified intermediate results but the basis for measuring their performance against indicators is ideally negotiated and agreed with them.  Accordingly, the Technical Assistance contractor will collaborate with the Mission to define/refine Performance Monitoring Plan (PMP) indicators as appropriate and to assure that the indicators are adequately defined, including suitable disaggregation by gender, age, region and ethnic group as appropriate.  The contractor will also carry out a rapid appraisal or similar type of assessment as necessary to establish baselines and targets for IR level indicators defined in the PMP based on the program timeline.

In light of the above, the table that follows constitutes only a first approximation of likely indicators that might be applied in measuring the performance under the forestry program component.

Figure 5: Summary Performance Data Tables (Proposed)

| Indicator | Target | Base | 03 | 04 | 05 | 06 | 07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator 6.1b - Number of protected areas and overall total area in which sustainable management plans are being implemented | 4 | 0 | 1 | 2 | 3 | 4 | 4 |
|  | tbd |  |  |  |  |  |  |
| Performance Data Specifications: The unit of measure will be both number of protected areas as well as their cumulative total area in hectares. The indicator will be a measure of physical impact as well as proof that the co-management approach can be successfully used to improve tropical forest resources. Innovative presentation of this data in the format of a user-friendly GIS applications should be employed for this indicator. |
| Indicator 6.1c- GOB agreements to expand protected areas as appropriate | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: The details of this unit of measure could be either physical achievement in terms of hectares added to existing protected areas through notification and/or percentage increase in the size of the area under protection. Here again, GIS applications could facilitate measurement. This indicator can only be calibrated once a more reasonable list of targeted protected areas has been chosen by the Mission and its partners, including the Forest Department. |
| Indicator 6.1d- Declining incidences of illegal use of protected areas | 80% overall | 0 | X-20% | X- 30% | X-50% | X-70% | X-80% |
| Performance Data Specifications: While the baseline is zero, meaning no reduction so far in incidences of unsustainable use of protected areas, the approach mentioned in the design foresees calibrating in realistic terms the incidence and impact of unsustainable use due to traditional use of core sanctuary areas and/or cases of timber theft by illegal loggers. Calibrating the baseline (X) will have to await greater efforts at management planning for individual targeted areas. |
| Indicator 6.2b/c- Upland forest habitat improved in targeted areas (%/ha) | 100% | 0 | 10% | 30% | 40% | 60% | 100% |
|  | tbd | Tbd | --- | --- | --- | --- | --- |
| Performance Data Specifications: Certain portions of the likely protected areas will benefit from proactive attempts to enhance vegetative cover as a result of past use. This indicator will measure impact in achieving this improvement, measured in terms of the percent realized of the area requiring such treatment. While total hectares so treated will be tracked, the percentage of total area requiring treatment is a better measure of the effectiveness of the program. Here again, calibrating the baseline in actual area terms will have to await greater efforts at management planning for individual targeted areas. |
| Indicator 6.2.1d- Watershed management and/or buffer zone plans and practices operationalized | tbd | Tbd | --- | --- | --- | --- | --- |
| Performance Data Specifications: At a minimum, each targeted protected area is likely to have watershed and/or buffer zone management plans and practices associated with the overall co-management plan. This indicator will measure the number of them that can be successfully operationalized out of the total identified. In some cases, because of geographical spread of areas to be managed and communities involved in co-management, there could be more than one such plan per P.A. Further refinement of this indicator must therefore await detailed management planning to get underway. |
| Indicator 6.2.2b- Increased income of targeted beneficiaries (number of beneficiaries achieving satisfactory IRR) | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: The unit of measurement of this indicator will be the number of selected participants in the alternative income generating activities who actually achieve a positive internal rate of return, suggested as 22%, for their investments and activities. As mentioned in the program design, the team will identify a select group of participants for each different type of alternative income generating activity and track their financial progress using a simple format directly related to the idealized business plan for that activity. |
| Indicator 6.3c- Number of formalized co-management agreements in place with communities surrounding targeted protected areas (no. and %) | tbd | 0 | --- | --- | --- | --- | --- |
|  | tbd | 75% | 75% | 75% | 75% | 75% | 75% |
| Performance Data Specifications: Co-management plans may require separate simplified co-management agreements with villages, groups of communities living close to one another and/or individual communities in order to realistically desegregate roles and responsibilities in achieving co-management objectives for a given P.A. Some attempts at co-management may fail initially or even over the life of the program for a variety of reasons. It will, nevertheless, be critical to reach a majority of the concerned communities if the co-management objectives are to make sufficient progress, and potentially attract non-cooperative communities once the benefits become apparent. |
| Indicator 6.3d- Inter-Agency agreements in place allocating usage rights to local communities | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: In many cases, achieving the conservation goals within the P.A. or their core sanctuary areas may only be realized with arrangements that make it possible to replace traditional needs once satisfied there with other sources of forest products. Neighboring khas lands and perhaps even tea estates could provide the sites for these interventions/investments but will likely require a formal inter-agency agreement between the Forest Department/MOEF and the Ministry of Lands and others. Achieving such agreements is considered a critical indicator of achievement in reaching the integrated approach that may be necessary to allow co-management to flourish around P.A.'s. This will likely be a mid-term indicator that can only be calibrated once the co-management planning begins. |
| Indicator 6.3e- Co-management policy agenda established and being acted upon by GOB | Agenda + actions | 0 | 1 | 1 | 2 | 3 | 4 |
| Performance Data Specifications: This indicator is designed to measure the degree of success in ensuring that the appropriate enabling environment of policies, rules and regulations for co-management have been put in place. The indicator is cumulative but calibrating it will first require the study on potential policy reform topics be established based on the working experience in attempting to apply the co-management model. Policy reform achievements could be either local or national in nature. |
| Indicator 6.4b- Number of communities and beneficiaries that participate in training cum planning sessions resulting in co-management agreements for protected areas | Total No. | 0 | --- | --- | --- | --- | --- |
|  | Percent participa-ting | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: This indicator is expected to measure the effectiveness of the public awareness, training and organizational promotion efforts among the user communities. A large number of communities (and beneficiaries) may participate in the programs but the measure of performance success will be gauged by the percent of those participating in these programs who go on to establish RMO's and viable intervention programs. |
| Indicator 6.4c- Growing public awareness and understanding of the importance of biodiversity conservation and environmental services | No. of articles | 0 | --- | --- | --- | --- | --- |
|  | Quality | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: The number and quality of the articles appearing in the media discussing co-management and/or biodiversity conservation or similar themes related to the goals of the program will be tracked as a proxy measure of the success in raising public awareness. |
| Indicator 6.5b- Forest Department skills and experience to promote co-management of protected area improved | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: Once the program gets established, and as part of the institution building efforts of the program, the Team will work with the Forest Department to develop position descriptions for participating staffmembers. The performance of these staffmembers will be analyzed annually by means of staff evaluation reports aimed at institutionalizing accountability as an important element of real acceptance of co-management. |
| Indicator 6.5c- Enhanced GOB Agency capabilities for working together on integrated NRM programs | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: This indicator will monitor cases where outside the program the ministries concerned replicate the principles of integrated approaches to natural resources management. |
| Indicator 6.5d- Local Govt. w/ improved land-use and NRM planning & governance capabilities | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: As part of their efforts, the program team assisting the Local Government Committees will work with them to define co-management, biodiversity conservation, land-use planning and similar natural resources management discussion and issues agendas. This indicator will measure their success in addressing these issues among themselves. |
| Indicator 6.5e- Improved local NGO capabilities to support ICDP | tbd | 0 | --- | --- | --- | --- | --- |
| Performance Data Specifications: Similar to the staff evaluations discussed above for Forest Department staff, NGO personnel performance will also be analyzed. In this case, the emphasis will be on both accountability and the likelihood that they could carry on with the program once technical assistance is withdrawn. |

USAID/Bangladesh will reserve the right, and has set aside separate funding, to commission an independent mid-term evaluation of the program.

Annexes:

Annex A- Participatory Forestry Modalities in Bangladesh

Annex B- Issues and Opportunities for Biodiversity Conservation in the Hills

Annex C- Reference List

Annex A- Participatory Forestry Modalities in Bangladesh

Forest Villages:  In a number of cases in Bangladesh when a forest area was gazetted as a reserved forest by the Government, there were already people living there.  Explicit agreements between these villages within the reserve forests and the Forest Department were drawn up recognizing their rights as traditional users of the lands in the area and identifying their responsibilities as forest villagers.  Typically, they were allowed to cultivate a certain amount of flat lands suitable for paddy within the area around their villages and may also have been given rights to raise certain crops (e.g., bidi leaf) under the canopy of the standing forest.  They are also supposed to assist the Forest Department staff by protecting the forest and also participating as paid labor in plantation programs.

Social Forestry:  This is a somewhat generic name for the wide variety of very common plantation efforts seen in Bangladesh involving a number of parties and local people.  Typically, the scenario involves the Forest Department promoting a scheme for planting trees on so-called "waste lands", such as embankments, railroad right-of-ways, or along roads.  The Department may supply seedlings and fencing materials.  Local people provide the labor and particular stretches or patches of the plantation are identified to be protected by chosen individuals.  These are usually quick growing tree species and the intention is to harvest them for sale at the end of a short rotation.  The money obtained from the sale of these wood products will be distributed according to a predetermined benefits scheme (percentages) established among the local people and organizations involved.  Shares may go to the land owner, be they private people or government organizations, to the Forest Department to cover the costs it invested, and to the person who has guarded the trees in question.  Occasionally, NGO's promote similar programs and are involved in the benefits scheme as well.  Permission and guidance from the Forest Department must be obtained before this type of plantation can be cut.

Homestead Forestry:  Truly participatory forestry in Bangladesh at its best, this simple formula is observed by local people all over the country.  It is that situation where men and women plant trees around their homes and house plots.  They typically buy the seedlings although in some cases these could be provided by the Forest Department, an NGO or a development project on a concessional basis.  Often, these tree gardens around the home include many different species and many species with multiple uses, including food, fruit, fodder, wood, fiber, medicines and fuel.  Those who have planted them are free to cut them at their own discretion and they need not share the benefits of them.  Homestead forestry is flourishing around the country and the floodplains are covered with a green patchwork of these plantings almost everywhere.  Additionally, as the trees mature, many of them become small logs highly sort after by local sawmills and carpentry shops; for example, Jackfruit trees are often converted to timber once they become big enough.

Participatory Forestry Plantations:  This is a newer modality which the Forest Department has been introducing of late which seeks to involve communities and villages adjacent to reserved forests in replanting them.  The land and the trees remain under the control of the Forest Department but the community members work as labor to plant and maintain the trees for several years.  Typically, the species used are longer rotation species (although there may be some short-term ones as well).  The plan is that the proceeds of the eventual timber sale will be shared with the participating communities according to a predetermined formula and after allowing for costs to be repaid to the Department.  What makes this modality novel is that it takes place within the reserved forests.  Communities are expected to be vigilant about the need to protect the young plantations from livestock and other threats.

Annex B- Issues and Opportunities for Biodiversity Conservation in the Hills

| Identification and Discussion of Issues | Opportunities for Addressing the Issues |
| --- | --- |
| Macro-Economic Issues |
| The Economic Implications of the Culture of "Command and Control" Approaches to Conservation: A preference for using a regulatory approach for protection and conservation of biodiversity by creating rules and/or enforcing existing rules can lead to a perverse reaction on the part of those seeking to use them. As demand for the products of these forests is likely to remain constant, an attempt to apply regulations will limit supply and/or be perceived as curtailing supply and thus causing prices to rise or a willingness to take the risks to obtain an increasingly scarcer but needed commodity. | - Using program-based learning to improve the understanding of policy and decision makers about the realities of the macro-economics of supply and demand for natural resources. - Participatory forest management program can and should reduce the costs of public administration of the protected areas and reserved forests because the local people perceive tangible values for themselves in these forests. This in turn would reduce the unit costs of land management that a department like the Forest Department would require for their programs and allow for further program expansion. |
| Funding for Biodiversity Conservation: Although the larger world has recognized the global significance of biodiversity and has begun to provide considerable funding for programs of this nature, the donor community is rarely responsive in situations where the host government appears unwilling or unable to provide at least part of the financing required (at a minimum, the establishment budget requirements) because it suggests that once their funding ceases, the programs will not be sustainable. | - Host governments must recognize that the conservation of biodiversity at home has value for the country and is a worthwhile investment option. NRM accounting procedures should be instituted that begin to build a case for valuing biodiversity, in terms of its real value to the nation (e.g., as a present and future source of needed natural products or in terms of national heritage and pride) and also take account of the environmental services associated with protected areas (the watershed function, storm protection). |
| Illegal Activities within Protected Areas: If local communities are to be convinced to relinquish their use rights (legal or otherwise) on protected areas, government must ensure that outsiders (illegal loggers, those harvesting fuel for brickfields, those seeking to take over such lands) also do so. | - If there is demand for scarce supply, the ingredients are there for an investment program. Why not stimulate communities to make preparations to supply industry with the raw materials it needs? For example, would brick-field owners be willing to pay for fuelwood from plantations, particularly if supply is very short in the area of operations? Ibid for sawmills or carpentry shops which already buy many logs from planted trees. This won't work, however, if there is a continuing perception that supply from natural areas or through illegal activities is available. |
| Socio-Economic Issues |
| Unrelenting Demographic Pressure on Hill Forest Areas: Farmers and rural people are as aware as anybody of the limitations of the natural resources base because they live the dilemma day in and day out. However, in the absence of choices or plans to the contrary, they chose the only course of action open to them--trying to meet their basic needs wherever they can. All concerned, including the GOB agencies and the communities need to understand that the costs of NRM rehabilitation and socio-economic development in the face of widespread degradation are orders of magnitude higher than a proactive program of prevention and wise management. | - Engaging the communities in a discussion not just about the problems (awareness raising) but about the alternatives and the benefits they might derive from improved stewardship of the natural resource base. Similarly, demographic pressures on a protected area are too anecdotal in nature. There is also a real need to quantify the actual usage and value of how local people use the forests in order to determine how to proceed in alleviating the pressure. E.g., how many steres of fuelwood are being removed for subsistence use or for local sale and can these removals be met with other strategies? |
| Poverty and a Lack of Alternative Sources for Basic Needs and Employment Opportunities: Subsistence collection of fuelwood and poles is an economic deadend. Where there is demand for these products, however, there is scope for action as has been repeatedly demonstrated by the very successful homestead plantations so common to the flood plains. | - Local communities and local people often have priorities such as the need for basic social services and rural infrastructure that could stimulate local development far more than access to natural resources on fragile or protected areas. - production trade-offs, particularly for forest harvesters (both legal and illicit) will need to be offset by introducing alternative production and/or employment activities |
| Land Tenure Constraints: Two issues are prominent in this regard: in some cases, villages have been established before protected areas or even reserve forests were gazetted, often involving indigenous peoples. How can they be accommodated? Second, if neighboring khas lands are available, do they not represent an opportunity to find solutions for the landless or for those who must degrade the forests to survive? | - Can tensions with existing villages be mitigated and if so, how? What potential is there for relocation of villages, on adjacent reserve forest areas or khas lands and what would be required to get people to move? Or can resident villages be convinced to stay within their defined boundaries and if so, in return for what? Such arrangements already exist between the communities and FD which employs villagers for management operations. Can protected areas provide similar opportunities? |
| Lack of Local Organizational Capacity to Broker Community NRM Conflicts: Villages are rarely egalitarian social structures but there is a certain amount of social justice required to avoid conflict. Conservation programs have best succeeded where they can create local organizations to ensure that the needs of all segments of society (including landless, women, indigenous peoples) are increasingly taken into account in designing natural resources management-- an inherently social (rather than technical) act involving decision-making about how to use, reserve and share resources. | - Local resource management organizations can fill the need for community understanding, conviction and consensus that it is possible to reverse these trends and acceptance of use restrictions in protected areas; and for promoting/allowing and organizing communities to participate in the decision-making about conservation/management measures. |
| Institutional Issues |
| Conventional Single Sector/Single Agency Approach: Protected areas cannot be dealt with in isolation of their surroundings, particularly in a densely populated country. To maintain the integrity of an ecosystem often requires off-site solutions. Sharing the responsibilities for addressing the challenges among different concerned govt. partners makes better sense and lowers program costs. This requires an appropriate institutional development strategy. | - An integrated approach to dealing with the pressures on protected areas is needed but the key is planning and prioritizing. There are too many things that can be done but the challenge is to know what should be done. Departmental policies, plans, programs and budgets are made in advance so planning is the key. A much more dynamic use of the conventional Project Steering Committee approach is required, based on a secretariat type function that prepares the members of the committee to take informed decisions and track progress in achieving them. |
| Institutional Set-up and Capacity including Skills and Understanding: At present, all protected areas are under the mandate of the territorial staff of the concerned Forest Department Circle, Division, Range and Beat. Staff is routinely and regularly transferred among these sites and may not even be fully aware of the rationale, importance, limits or management requirements of protected areas. | - The principal paradigm of the Forest Department is production and staff have not had the training required to understand the value of protected areas and the environmental services they offer (biodiversity conservation, watershed protection, recreation and ecotourism). The recent decision to create a Wildlife and Protected Areas Division within the FD represents an opportunity to build skills important for conservation. |
| The Need for a Protected Area System: Experience worldwide has demonstrated that a genuine system of protected areas provides a center around which to organize and strengthen institutional capacity for conservation. Furthermore, because a protected area system targets values appreciated by society in general and not just those who consume forest products, it reaches a wider audience and can improve the image of the department responsible for providing these services. It also helps to create a national understanding and growing constituency for environmental conservation. | - A protected area system works better than isolated P.A.'s under territorial mandate, especially in terms of enhanced institutional capabilities (increased opportunities for staff specialization, learning and experience; the development of internal organizational capabilities specific to protected areas; & career development options for staff). - There is also an opportunity to distinguish between different types of protected areas and their functions including biodiversity conservation but also outdoor recreation and environmental services (watershed functions). |
| Technological Issues |
| Inappropriate Land-Use Choices and Practices: The essence of natural resources management is matching land-use to land capability. The protected areas of Bangladesh are for the most part in hilly areas where the options for use are more limited because of the fragile nature of these areas. Even if the protected area can be safeguarded, actions are needed to ensure that surrounding areas of similar conditions are not degraded and depleted as this will only lead to greater pressures on remaining forest areas. | - The key to addressing inappropriate land-use lies in knowing more about the land and not just the technology. Land capability studies must be prepared but these are relatively simple, involving slope and soil depth measurements and soil typing. There are a wide variety of improved management methods for hilly areas that have not been much applied in Bangladesh. They include: soil and water conservation engineering measures for agriculture; cut and carry fodder systems; agro-forestry; composting; green manures for soil fertility improvement; etc. - Similarly, collateral development activities around existing protected areas take pressure off national biodiversity assets. |
| Need for Watershed Management : There is very little mention of the needs for watershed management in sector programs and even fewer program efforts (if any) to address it. Yet each year, flash floods during the early monsoon damage the boro rice crops in the Haor areas. Siltation running off of neighboring hills is causing blockages of watercourses damaging embankments and filling in fish habitat. Similarly, low season flows into the beels limit their utility as brood areas for fish. | - A lack of watershed management programs is not surprising although the country is very aware of the issue because of the damages wrought by conditions in the extra-territorial watersheds of the Bramaputra and Ganges Rivers. There are opportunities to address similar issues, albeit on a smaller scale, in the northeast and southeastern hilly regions that could mitigate the adverse impacts felt downstream. Many of the protected areas are by definition watersheds for neighboring wetlands and need attention to guarantee the sustainability of proactive, ongoing wetlands programs (MACH and others). |
| Knowledge Gaps about Biodiversity Assets: Good data and information about the status of biodiversity in the country is lacking, contradictory or not up-to-date which hampers sound planning for its protection. | - A good set of baseline data and information on the condition of protected areas, habitat integrity and the species found on these areas will be fundamental to sound program planning and subsequent monitoring of program performance.. - There are any number of competent professionals who could be engaged in basic survey and studies to develop targeted information on the status of biodiversity which will serve for M&E purposes but also provide the substance for awareness raising, additional program planning |
| Biodiversity Sensitive Choices of Forest Management Technology: Because many of the protected areas were once part of Reserved Forests, their natural stand structure has been altered by the Forest Department through production plantation programs. | - Encouraging natural regeneration of degraded protected areas should be a preferred methodology for restoration. - There may be occasional need for modest enrichment planting of keynote species important to forest ecosystems and/or wildlife that can be accomplished with minimum site disturbance. |
| Need for Connectivity with other Natural Areas: The long-term sustainability of certain premier animal species (e.g. elephants) may depend on their ability to move over larger areas than available under the protected area system. In some cases, it is possible to conceive of program plans that view Reserved Forest areas or even unclassified state forest as potential corridors for animal migration. | - There is some potential for promoting proactive management choices within Reserved Forest areas, particularly in the southeast of the country (CHT) that could accommodate elephant migration routes. This might reduce the present problem of crop raiding and conflicts with local villages if the animals had a forest corridor extending beyond the boundaries of the P.A.'s. |

Annex C--REFERENCE LIST

MOEF 1995.  National Environmental Management Action Plan (NEMAP), Volume II: Main Report.  Published by the NEMAP Secretariat, Ministry of Environment and Forest, Dhaka, 1995, pp.- 153 + appendices.

FPCO 1995.  Specialist Study- Wetland Resources- Final Report.  Flood Action Plan--Northeast Regional Water Management Project (FAP 6).  Flood Plan Coordination Organization, Bangladesh Water Development Board, prepared by SNC, Lavalin International, Northwest Hydraulic Consultants and Associates with funding from CIDA, Dhaka, October 1995, pp.- 114 + figures.

FPCO 1995a.  Specialist Study- Wetland Resources- Annexes- Final Report.  Flood Action Plan--Northeast Regional Water Management Project (FAP 6).  Flood Plan Coordination Organization, Bangladesh Water Development Board, prepared by SNC, Lavalin International, Northwest Hydraulic Consultants and Associates with funding from CIDA, Dhaka, October 1995, pp.- various.

Forest Department 1996.  Forestry Sector Study: Final Report (Vol. 2, Appendices).  Prepared for the Forest Department, Ministry of Environment and Forest by Fountain Renewable Resources Ltd. & Desh Upodesh Ltd., Dhaka, March 1996, pp.- various + maps.

Farooque, M. 1997.  Law and Custom on Forests in Bangladesh: Issues & Remedies.  Bangladesh Environmental Lawyers Association (BELA), with support from the Ford Foundation, Dhaka, April 1997, pp.- 308.

MOEF 1997. Towards Sustainable Development: The Bangladesh National Conservation Strategy.  Ministry of Environment and Forest with Bangladesh Agricultural Research Council (BARC) and support from IUCN, Dhaka, August 1997, pp.- 205 + appendices.

Gain, P. (ed.) 1998.  Bangladesh Environment: Facing the 21st. Century.  Society for Environment and Human Development (SEHD), Dhaka, pp- 306.

Gain, P. 1998b.  The Last Forests of Bangladesh.  Society for Environment and Human Development (SEHD), Dhaka, pp- 176.

Md. Kamal Hossain 1998. The Potential Role of Plantations on the Rehabilitation of Native Forest Biodiversity in Degraded Hilly Areas of Bangladesh. Proceedings of the 20th. Bangladesh Science Conference, Bangladesh Association for the Advancement of Science, Dhaka, 1998, Part- 2, pp. 99-104.

Arcadis Euroconsult 1999. Sundarbans Biodiversity Conservation Project.  Technical proposal to Asian Development Bank and Government of Bangladesh, Arnhem, The Netherlands, May 1999, pp.- various.

USAID/Bangladesh 2000.  USAID/Bangladesh Strategic Plan FY 2000- FY 2005: A Focus on Sustainable Economic Growth.  Dhaka, June 2000, pp.- 47 + appendices.

Forest Department 2000. Compendium of Conservation Area and Biodiversity Conservation Inputs to Feasibility Studies.  Forestry Sector Project (ADB Project BAN No. 1486), prepared for Forest Department, Ministry of Environment and Forest, by TECSULT International Ltd. in association with SODEV, NRP, HCL & EPC, Dhaka, November 2000, pp.- various.

Forest Department 2000a.  First Five Year Management Plan for Lawachara National Park; Volume 1: Management Plan & Volume 2: Background and Support Material.  Forestry Sector Project (ADB Project BAN No. 1486), prepared for Forest Department, Ministry of Environment and Forest, by TECSULT International Ltd. in association with SODEV, NRP, HCL & EPC, Dhaka, June 2000, pp.- various.

Forest Department 2000b.  First Five Year Management Plan for Rema-Kalenga Wildlife Sanctuary; Volume 1: Management Plan & Volume 2: Background and Support Material.  Forestry Sector Project (ADB Project BAN No. 1486), prepared for Forest Department, Ministry of Environment and Forest, by TECSULT International Ltd. in association with SODEV, NRP, HCL & EPC, Dhaka, November 2000, pp.- various.

ADB 2000. Bangladesh: Environment Operational Strategy (revised draft). Asian Development Bank (ADB TA 3269-BAN), Dhaka, February 2000, pp.- 84 + appendix.

WARPO 2000. Annex O. Regional Environmental Profiles (Volume No. 11- Draft Development Strategy).  National Water Management Plan Project, Water Resources Planning Organization, Ministry of Water Resources, with Halcrow/Mott MacDonald and Associates, Dhaka, August 2000, pp.- 128.

WARPO 2000a.  Annex F: Social Analysis & Annex G: Environment (Volume No. 6- Draft Development Strategy).  National Water Management Plan Project, Water Resources Planning Organization, Ministry of Water Resources, with Halcrow/Mott MacDonald and Associates, Dhaka, August 2000, pp.- various.

Gain, P. (ed.) 2001.  Critique: The Forest (Amendment) Act, 2000 and the (draft) Social Forestry Rules, 2000.  Society for Environment and Human Development (SEHD), Dhaka, pp- 58 + annexures.

Tod, I., Chowdhury, A., Zahirul Islam, Md., & Mahmood, A.S. 2001.  Report of Mid-Term Review: Management of Aquatic Ecosystems through Community Husbandry (MACH) Program. Project of the GOB sponsored by USAID.  Winrock International, BCAS, CNRS and Caritas Bangladesh.  Dhaka, December 2001, pp.- 20 + appendices.

Chemonics 2001.  The Bangladesh Tropical Forest Conservation Fund: Preventing and Arresting Accelerating Species Loss in Bangladesh.  Prepared for USAID/Bangladesh under a task order (No. 806) for the Biodiversity & Sustainable Forestry (BIOFOR) IQC, by Chemonics International Inc., Washington, April 2001, pp.- various + appendices.

Forest Department 2001.  Participatory Conservation Management Planning for Chittagong Forest Division--Chunati Wildlife Sanctuary.  Forestry Sector Project (ADB Project BAN No. 1486), prepared for Forest Department, Ministry of Environment and Forest, by TECSULT International Ltd. in association with SODEV, NRP, HCL & EPC, Dhaka, June 2001, pp.- 39.

Forest Department 2001.  Participatory Conservation Management Planning for Chittagong Forest Division--Teknaf Game Reserve.  Forestry Sector Project (ADB Project BAN No. 1486), prepared for Forest Department, Ministry of Environment and Forest, by TECSULT International Ltd. in association with SODEV, NRP, HCL & EPC, Dhaka, June 2001, pp.- 19 + appendices.

WARPO 2001.  Guidelines for Environmental Assessments of Flood Control, Drainage and Irrigation Projects.  Water Resources Planning Organization, Ministry of Water Resources, prepared by Halcrow/Mott MacDonald & Associates, Dhaka, November 2001, pp.- 31 + appendices.

Giesen, W. Choudhury, J.H., Wahab, M.A., Khanum, S.M. & Jamir, J.A. 2001.  Biodiversity Management Plan for South Chittagong Forest Areas including Chunati, with Special Emphasis on Management of Teknaf Game Reserve.  National Conservation Strategy (NCS) Implementation Project- 1, Ministry of Environment and Forest, funded by NORAD, February 2001, Dhaka, pp.- 87 + appendices.

UNEP 2001. State of the Environment Bangladesh 2001.  prepared by UNEP with collaboration of MOEF, DOE, BCAS, SACEP & NORAD, distributed by the UNEP Regional Resource Centre for Asia and the Pacific, Pathumthani, Thailand, pp.- 121 + appendices.

Shamsul Huda, ATM 2001.  Institutional Review of Selected Ministries and Agencies. Report (PDO-ICZM Paper No. 08) prepared for the Program Development Office, Integrated Coastal Zone Management, Dhaka, November 2001, pp.- 130.

Chowdhury, Q.I. (ed.) 2001.  Bangladesh: State of Environment Report 2000.  Forum of Environmental Journalists of Bangladesh (FEJB), Dhaka, June 2001, pp- 341.

WARPO 2001.  National Water Management Plan: Volume No. 1-- Executive Summary.  Water Resources Planning Organization (WARPO) under National Water Management Plan Project, with assistance of Halcrow/Mott MacDonald & Associates, Dhaka, July 2001, pp.- 35.

UNDP 2001.  Coastal and Wetland Biodiversity Management Project (BGD/99/G31)--Management of Cox's Bazaar and Hakaluki Haor.  Project Document  United Nations Development Programme, Dhaka, 2001, pp.- 38 + annexes.

MACH 2001.  Management of Aquatic Ecosystems through Community Husbandry-- Second Annual Report.  A project of the Government of Bangladesh sponsored by USAID, prepared by Winrock International, BCAS, CNRS & Caritas/Bangladesh, Dhaka, February 2001, pp.- 57 + appendices.

MACH 2001a.  Management of Aquatic Ecosystems through Community Husbandry-- Semi-Annual Report 2001.  A project of the Government of Bangladesh sponsored by USAID, prepared by Winrock International, BCAS, CNRS & Caritas/Bangladesh, Dhaka, August 2001, pp.- 79 + appendices.

MACH 2001b.  Management of Aquatic Ecosystems through Community Husbandry-- Project Profile.  A project of the Government of Bangladesh sponsored by USAID, prepared by Winrock International, BCAS, CNRS & Caritas/Bangladesh, Dhaka, August 2001, pp.- 19 (with Bangla translation).

USAID/Bangladesh 2001.  USAID/Bangladesh's Strategic Plan for Improved Management of Open Water and Tropical Forest Resources. Dhaka, pp.- 21.

Chowdhury, Q.I. (ed.) 2001.  State of Sundarbans.  Forum of Environmental Journalists of Bangladesh (FEJB), Dhaka, September 2001, pp- 143.

Seyler, J.R. 2002.  Strengthening the Arannayk Foundation: Draft Site Selection, Inventory and Monitoring Report.  Prepared for USAID/Bangladesh by Chemonics International Inc., Washington, April 2002, pp.- 53 + annexes.

King, D. 2002.  Proposed Long-Term Implementation Strategy for the Arannayk Foundation(draft copy for comment only).  Chemonics International under the Biodiversity and Sustainable Forestry IQC contract for USAID/Bangladesh, Washington, April 2002, pp.- 73 + annexes.

TECSULT 2002.  Forestry Sector Project-- Quarterly Progress Report: January - March 2002.  Prepared for the ADB Project BAN No. 1486, by Tecsult International Ltd., April 2002, Dhaka, pp.- 12 + appendices.

MACH 2002.  Management of Aquatic Ecosystems through Community Husbandry-- Third Annual Report.  A project of the Government of Bangladesh sponsored by USAID, prepared by Winrock International, BCAS, CNRS & Caritas/Bangladesh, Dhaka, April 2002, pp.- 79 + appendices.

Miscellaneous Unpublished/Informal Background Documentation

- Memorandum of Association of the Arannayk Foundation, also known as the Bangladesh Tropical Forest Conservation Foundation, Final 1-11-02, pp.- 11.

- Articles of Association of the Arannayk Foundation, also known as the Bangladesh Tropical Forest Conservation Foundation, Final 1-11-02, pp.- 13.

- Agreement Between the Government of the United States of America and the Government of the People's Republic of Bangladesh Concerning the Establishment of a Tropical Forest Fund and a Tropical Forest Conservation Board, downloaded from the US Department of State website, September 12, 2000, pp.- 9.

- Brochure: National Water Resources Database.  Water Resources Planning Organization with the assistance of Environment and GIS Support Project for Water Sector Planning (EGIS), no date, pp.- 16.

- Brochure:  Bangladesh Environmental Management Project, a Department of Environment Project funded by a CIDA grant.

- Brochure: SEMP- A NEMAP Follow-Up.  Sustainable Environmental Management Programme, Ministry of Environment and Forest with funding from UNDP.

- Brochures & various flyers of the EGIS.

- Unpublished tables from DFID regarding Environmental activities supported by GoB and donors (1998- onwards).

- Bangladesh Forest Research Institute-- An Information Brochure, 1999.

- Institute of Forestry and Environmental Sciences, Chittagong University (IFESCU) brochure, December 2001.

# Footnotes

The other elements of the USAID/Bangladesh Strategic Plan include strategic objectives for: SO 1- Fertility Reduced and Family Health Improved; SO 5- Growth of Agribusiness and Small Businesses; SO 7- Improved Performance of Energy Sector; SO 8- Improved Food Security for Vulnerable Groups; and SO 9- Strengthened Institutions of Democracy.

“Open access” is strictly de facto in case of forests, where FD has clear jurisdictions.  In case of open water, it is combined de facto and de jure.

The MACH activity is currently being implemented under SO6.  In collaboration with the Ministry of Fisheries and Livestock (MOFL), Winrock International in conjunction with three local partners is implementing the program at three representative aquatic ecosystems of the country.

The matter of watershed concerns when it is discussed in Bangladesh almost always centers on the dilemma of these mega transnational watersheds which extend into India, Nepal, China and Bhutan.  There is some middle ground, however, wherein smaller watersheds overlap the border with India.  The activities being proposed here could serve as a precursor to possible transnational programs of watershed management between India and Bangladesh in areas such as Sylhet/Tripura and Sherpur/Meghalhaya.

# The sites mentioned here are potential sites and actual sites will be selected based on the “Site Selection Criteria”.  The term ‘site’ has been taken as an ecological concept and not as a purposefully demarcated geographical landscape.  To maximize the chance of success of this pilot co-management initiative, the site selection process must take serious cognizance of the importance of taking an ecosystems approach.  In order to develop a successful protected area co-management model, the program must intervene in a geographical (or topographical) area far beyond the geographic limit of a defined protected area.  Interventions will, therefore, also include a buffer zone as well as the surrounding communities.

An ideal site will represent a “mini-watershed” where interventions with an integrated approach can be made proportionately to create an ecosystem-level effect.  Since the intention of the program is to treat ecosystems as holistic entities, a multiplier effect can be realized by integrating both the terrestrial and aquatic ecosystems’ aspects.  It makes the most programmatic sense since the program will operate in the face of limited natural resources.

The Strategic Objective Grant Agreement (SOAG) to implement the Strategic Objective, Improved Management of Open Water and Tropical Forest Resources provides for a SOAG Steering Committee. By definition, the SOAG Steering Committee should include secretary-level representatives from the MOEF and the MOFL, as well as senior USAID representation.

Among the areas suggested by the Forest Department for consideration are Madhobkunda-Muraichhara Waterfall area in Moulvibazar District and Ratargul Wetland Wildlife Sanctuary (proposed) in Sylhet.

# Text boxes

SO 6: Improved Management of Open Water & Tropical Forest Resources

IR 6.3: Select Policies Implemented that Support IR 6.1 & IR 6.2

IR 6.1: Effective Community Based Resource Mgmt Mechanisms

Implemented

IR 6.2: Select Habitats & Ecosystems Improved

IR 6.2.2: Alternative Income Generated for Targeted Groups

IR 6.2.1: Innovative Best Practices Adopted

IR 6.5.1: Foundation Established (Forestry)

IR 6.4: Public Awareness of Key Issues Increased

## X-Cutting IRs

IR 6.5: Improved Institutional Capacity