CHAPTER VII

BUSINESS APPLICATIONS OF

PARAMETRIC ESTIMATING

CHAPTER VII

BUSINESS APPLICATIONS OF PARAMETRIC ESTIMATING

INTRODUCTION

Recent initiatives affecting government procurement practices have further stressed an already fragile world-wide estimating capability.  Competition, accuracy, flexibility, and method-proven credibility dictate reformation in the estimating process, especially for new business pursuits.  Parametric estimating methods for planning and strategizing new business cost issues is a critical element in the reform of traditional bottoms-up approaches.

A paper written by Roy Summers and Bruce Fad summarized here discusses the need for parametric modeling in the new business development process.  The arguments are based on experience gained through use of parametrics in this type environment.  The role of parametric modeling is examined along with the presentation of a process in which parametrics and bottoms-up estimating are complementary.  Organizational conditions leading to effective use of parametrics are also considered.  The questions of job responsibilities, management interface, and functional structures are treated from the practitioners' viewpoint.  Finally, the issue of credibility includes perspectives from both the using and auditing organizations, with emphasis on calibration and the use of testable databases.

PARAMETRIC ESTIMATING IN NEW BUSINESS DEVELOPMENT

Why do programs die?  Why do CEO's, Boards of Directors, DoD, or Congress kill or cancel technically superior projects?  There are many examples, and, generally, it is not due to technical viability.  Even though millions or even billions are lost, the program graveyard claims many projects.  Sommers and Fad suggest that these events happen partly because of an inattention to future cost issues during program development.  There is a need to recognize and react to help solve the cost problems.  Technical success can often mask future cost issues.

The authors propose that an organization responsible for costing use parametric techniques early on, and that cost and technical objectives be treated together.  Parametrics are perfect for cost estimating during a program's conceptual phase, and the tools connect technical and cost parameters together in a very effective way.

New business development actions can attack the problem.  These actions include:

1)  Parallel and coordinated development of technical and programmatic (cost, schedule and quantity) concepts from requirements.

2)  Iterative and continuous cost improvement

3)  Develop cost targets (bogeys) as the result of 1 & 2, above.

4)  A review/reconciliation process that focuses on cost/risk analysis.

The authors go on to suggest that organizations not put off the cost estimating activity, and that cost analysts immediately begin to explore technical/cost alternatives.  They also suggest that the parametric function belong to an independent department and not reside within another function outside the organization that owns new business development.

To effectively integrate parametrics into an organization, upper management needs to be involved.  Upper management involvement will insure the creation of a cooperative team spirit, and more effective management and customer acceptance including estimate credibility.

ESTIMATING PRODUCTION BUYS USING PARAMETRICS

A parametric approach can be used to calibrate production cost and then estimate future production buy(s) and options using a commercial model.  The benefit here is a simpler cost proposal with no bill of material and no labor hours roll-up.  The model can be calibrated and estimates derived at any level of the WBS, hence useful for spare parts pricing.  In either case, the CERs or cost models can be used as the basis of estimate, and delivered to a proposal pricing system via a post processor, or a spread sheet.  In either event, the cost estimating process is greatly simplified, and resource economies of scale can be realized.

Example:  Estimating Production Buys Using Parametrics

What follows is an example of the comparative or analogous estimating approach.

RFQ And Historical Data

PDQ Inc., has received an RFQ for 84 XYZ-L Systems to be built and delivered in 1995. A 120-lot of this same system was delivered in 1993, so recent cost history exists.  The cost history yields the following data:

Manufacturing labor (Hands-on) of 42,000 hours divided into:

Plant A - 18,000 hours

Plant B - 12,000 hours

Plant C - 12,000 hours

Purchased parts: $9,000,000

Manufacturing Support Labor: 17,280 hours which was generated from 1 Mechanical Engineer, 1 Quality Engineer, and 1 Test Engineer at each of the three plant locations.

Engineering Support Labor: 7,680 hours generated by 2 Engineers at Plant A, and 1 Engineer each at Plants B and C.

Tooling Costs: $15,000

Test Equipment Costs: $25,000

The Interview Process

How will the proposed 84-lot be different from the historical (baseline) 120-lot?

VECP - AB123 has altered the system configuration.  Mechanical Engineering has estimated the VECP will reduce the assembly time at Plant A by 5 hours per system.

Plant B is over-capacity so five of the parts in the system will be resourced to Plant C.  These parts are similar in assembly and take 3 hours each to build.

Part number XYZ456, previously assembled at Plant A, is being purchased from an outside vendor.  Assembly time for this part at Plant A was 4 hours.  It is currently being purchased for $200.

Preparation Of The Estimate

Manufacturing Labor Calculations:

Plant A:	150  Hours	Historical Baseline unitized

-5  Hours	Adjustment for VECP-AB123

-4  Hours	Make to Buy Change for P/N XYZ456

141  Hours	Proposed Unit Hours Estimate for 84-lot

Plant B:	100  Hours	Historical Baseline unitized

-15  Hours*	Five parts (@ 3 hours per part) resourced to Plant C

85    Hours	Proposed Unit Hours Estimate for 84-lot

Plant C:	100    Hours	Historical Baseline unitized

+17.5 Hours	Five parts resourced from Plant B

117.5 Hours	Proposed Unit Hours Estimate for 84-lot

*	The 15 hours for the 5 parts were adjusted to account for performance differences between Plants B and C.  Performance factor (inverse of efficiency) at Plant B was 1.5.  The current performance factor at Plant C is 1.75.  Adjustment: 15 hours divided by 1.5 times 1.75 equals 17.5.

Purchased Parts Calculations:

$75,000	Baseline Costs unitized (purchased 50% in 1992 and 50% in 1993)

Material for 84-lot will be purchased in 1994.  Escalation is 3% per year.

$39,784	Baseline (50%) escalated from 1992 to 1994

$38,625	Baseline (50%) escalated from 1993 to 1994

$200	Make to Buy Change for P/N XYZ456 (not in baseline)

$78,609	Proposed Unit Base Estimate for 84-lot

Manufacturing Support Labor Calculations:

Support labor has historically followed a semi-variable pattern; i.e., when the production quantity is halved, support can be reduced by 25%, or when production is doubled, support cost is increased by 50%.

The proposed 84-lot is 60% of a halving of the baseline 120-lot.  Therefore, the support labor adjustment is -15% (60%  X  25%  =  15%) .

9.00	People Baseline

7.65	People 	Baseline Adjusted (-15%)

14,688	Hours Proposed support labor @ 1920 hours per person/year

Engineering Support Labor Calculations:

4	People	Baseline

3	People Adjusted Baseline (Management Challenge)

5,760	Hours Proposed engineering labor @ 1920 hours per person/year

Tooling And Test Equipment Calculations:

$40,000	Baseline costs

$  1,200	Adjusted for escalation from 1994 to 1995 (3% per year)

$  4,120	Adjusted for age of equipment

$45,320	Proposed tooling and test equipment costs

Summary Of Direct Costs

Manufacturing Labor:

Plant A	141.0 Hours  X  84 Systems  X  $75.80 per Hr.	= $   897,775

Plant B		85.0 Hours  X  84 Systems  X  $81.50 per Hr.	= $   581,910

Plant C		117.5 Hours  X  84 Systems  X  $77.10 per Hr.	= $   760,977

Subtotal Manufacturing Labor	= $2,240,662

Purchased Parts:

Base		$78,609  X  84 Systems				= $6,603,156

Normal Material Production Allowance (NMPA) 5.0%		=    $330,158

Raw Material 2.5%							=    $165,079

Material Overhead (Applied to Purchase Parts Only) 8.0%		=    $528,252

Sub-Total Purchased Parts:						= $7,626,645

Manufacturing Support: 14,688 Hours  X  $74.75 per Hr		= $1,097,928

Engineering Support:		5,760 Hours  X  $83.00 per Hr.	=    $478,080

Tooling & Test Equipment:						=      $45,320

TOTAL DIRECT COSTS:				 $11,488,635

ESTIMATING SPARES AND CHANGE ORDERS

Parametric techniques can sometimes be used for estimating spares and change order proposals.  Using a calibrated system model for spares, select the WBS element that represents the spare part(s) that need to be estimated.  Then exercise the model at that point, either a commercial version or one developed for the specific program.  The estimate can be exercised very quickly, and the calibrated model will yield accurate results.

Engineering Change Proposals (VECPs) or other change proposals have to be accounted for by adjusting the actuals or a delta to the current estimate.  The comparative approach is normally well supported by history, as accurate as any other technique.  It is much easier to do "what if" analysis and compute option prices, and the proposals are less complex and smaller in volume and more "user friendly", with significantly reduced preparation, review, audit and negotiation time.

Table VII-1 indicates the potential parametric applicability for various firm business proposals.  Appendix G contains a parametric estimating system checklist.

PARAMETRIC ESTIMATING APPLICATIONS FOR FIRM - BUSINESS PROPOSALS

| Type of Proposal | Engineering | Manufacturing | Test | Support |
| --- | --- | --- | --- | --- |
| 1. | New Business Development | VA | VA | VA | VA |
| 2. | Production | VA | VA | VA | VA |
| 3. | Follow-on Production | VA | VA | VA | VA |
| 4. | Development Contract Change-Order | NVA | NVA | NVA | VA |
| 5. | Production Contract Change-Order | NVA | NVA | NVA | VA |
| 6. | Spares | MBA | MBA | MBA | VA |

NOTE:

Use of parametric estimating may be very applicable for new business development proposals/RFPs; their application may not be as good for unique development contract change orders with little, if any, relevant history to use for CER development or Cost Model calibration. In addition, change order data is collected at too low a level in the WBS for meaningful utilization.

KEY:

VA = Very Applicable; NVA = Not Very Applicable; MBA = May Be Applicable

TABLE VII - 1