| ACTION | TARGET DATE |
| --- | --- |
| Agencies meet to begin EA | April 8 |
| All agencies provide requested background materials and mailing lists to Amy | April 16 |
| FWS (Amy) delivers draft public involvement letter for agency review/comment. DMG reviews letter in April Mtg. | April 16 |
| Agencies provide feedback on public involvement letter to FWS (Amy) for revisions. | April 30 |
| FWS (who?) issues public involvement letter. Allows 4 weeks for public comment | May 3-7 |
| Consultation with Tribal Leaders Initiated | May 3-7 |
| FWS (Amy) delivers preliminary draft Purpose and Need statement and alternatives description to members of the workgroup for their agency review and comment. | May 7 |
| Agencies (workgroup members) provide FWS (Amy) with feedback on Purpose and Need and Alternatives | May 21 |
| “Final” Purpose/Need/Alternative Sections to Workgroup | May 28 |
| Interagency meeting in Moreno Valley | June 4: 0900-1500 |
| Workgroup Members provide their draft sections to Amy | June 25 |
| FWS (Amy) provides preliminary Draft EA to workgroup | July 7 |
| Agencies/workgroup members provide comments to FWS (Amy) on Draft EA | August 8 |
| Interagency meeting in Moreno Valley | mid August? If needed. |
| FWS (who?) issues Draft EA to public (30 day comment period) | September, first week |
| Public Comment Period Closed | First week of October |
| FWS (who?) conducts informal consultation on effects on desert tortoise | October |
| Public Comments Compiled and sent to workgroup for review Revised EA to agencies | Mid October (maybe later if lots of comments) |
| Interagency Meeting in Moreno Valley BLM: Agencies assist FWS with responses to comments. Agencies review EA and draft Decision. | Early November |
| Revised EA, w/ Comments, draft decision for internal review | Early December |
| FWS prepares final EA and final decision, other agencies prepare their own decision documents | Mid December |
| Lead (and cooperating) agencies sign and issue final decision to public | Mid January |

Raven Management EA Preparation Schedule

Raven Management EA Team Organization and Responsibilities

The NEPA lead will be Amy Fesnock, Joshua Tree Ecologist, 760-367-5578, amy_fesnock@nps.gov

The Interdisciplinary Writing Team will be the following:

Compiler/Editor			Amy Fesnock		NPS

Wildlife (Raven)			??? (from Mickey)	NTC

Wildlife (Tortoise/other wildlife)	Brent Husung		DOD

Wilderness				Chris Roholt		BLM

Waste 					John Key		BLM

Native American Concerns		Joan Oxendine		BLM

GIS					Al Stein		BLM

NEPA Review, socioeconomics,	Shannon Hebert	APHIS-WS

urban environment/resources

Bill Boarman will be writing monitoring plan to evaluate the impacts of the proposed action alternative on ravens and DT

Administrative support (e.g., maintaining mailing lists, reproducing documents, mailing document, maintaining and admin record) will be performed by Amy Fesnock and Clarence Everly.

Each cooperating Agency will assign an individual to serve as the agency to contact to

- respond to specific requests for information from the interdisciplinary writing team

- coordinate agency review an document on the draft document

- to respond to public comments as assigned