November 2004

Evaluation Plan for the 
National Cancer Institute’s Community Networks Program:
Phases I and II

Final Report

Prepared for

Ken Chu, Ph.D.

Center to Reduce Cancer Health Disparities

National Cancer Institute

6116 Executive Boulevard

Suite 602 MSC 8341

Rockville, MD  20852

Prepared by

Debra J. Holden, Ph.D.

Brenda Stone-Wiggins, M.P.H.

LaShawn Wordlaw-Stinson, Ph.D.

RTI International

3040 Cornwallis Road

Research Triangle Park, NC  27709

RTI Project Number 09293.000

RTI Project Number

09293.000

Evaluation Plan for the 
National Cancer Institute’s Community Networks Program:

Phases I and II

Final Report

November 2004

Prepared for

Ken Chu, Ph.D.

Center to Reduce Cancer Health Disparities

National Cancer Institute

6116 Executive Boulevard

Suite 602 MSC 8341

Rockville, MD  20852

Prepared by

Debra J. Holden, Ph.D.

Brenda Stone-Wiggins, M.P.H.

LaShawn Wordlaw-Stinson, Ph.D.

RTI International

3040 Cornwallis Road

Research Triangle Park, NC  27709

*RTI International is a trade name of Research Triangle Institute.

Contents

Executive Summary	ES-1

1.	Introduction	2

2.	Evaluation Plan Development	2

2.1	Overview of Evaluation Planning	2

2.2	Steps Completed for Evaluation Planning	2

2.3	Engage Stakeholders in the CNP Evaluation (Step 1)	2

2.4	Describe the CNP (Step 2)	2

2.4.1	Program Building Blocks	2

2.4.2	Focus of Activities	2

2.4.3	Outcomes of Interest to the CNP	2

2.5	Focus the CNP Evaluation (Step 3)	2

2.6	Next Steps	2

References	2

Appendix A:  Planning Matrix	A-1

Exhibits

Exhibit 1.	CNP Phases and Accompanying Goals	2

Exhibit 2.	CDC’s Framework for Program EvaluationAdapted Steps for CNP Evaluation Plan Development	2

Exhibit 3.	Proposed Interconnectedness of the Local Community Advisory Groups and the National Evaluation Advisory Committee	2

Exhibit 4.	Comparison of Conventional and Participatory Evaluation Approaches	2

Exhibit 5.	CNP Draft Conceptual Framework	2

Exhibit 6.	Nine Principles of Community-Based Participatory Research	2

Exhibit 7.	Possible Data Collection Methodologies for the CNP	2

## Executive Summary

Cancer mortality has been declining for most populations in the United States, but this benefit is less obvious for some racial and ethnic groups, as well as others defined by geographic region or income.  As an example, African-Americans are more likely to develop and die from cancer than persons of any other racial and ethnic group (ACS, 2003).  Through a closer examination of the literature and of statistical trends, it is clear that the benefits of current knowledge about state-of-the-art cancer care are not shared equally by all members of our society (Aziz and Rowland, 2002).  When survival rates are broken down by race/ethnicity, significant differences exist across ethnic minority and medically underserved populations with respect to the risk of developing and dying from cancer.  Many reasons for these disparities are known, while some are still under study, such as the biological bases that could be contributing to the disparities.  These causes include limited access to health care (e.g., increasing numbers of uninsured Americans, decreasing resources for Medicaid coverage, geographic location of health facilities), differences in medical practices provided to patients, lack of knowledge among people about the types of care that are of greatest benefit, and others.  Many of these causes are grounded within the local community where these groups live and can best be addressed in that setting.

Through the development of the Community Networks Program (CNP), the National Cancer Institute (NCI) has emphasized the need to systematically address these health disparities with regard to cancer care.  NCI plans to fund up to 22 initiatives to conduct community-based participatory research, training, and education programs that are focused on reducing local cancer disparities.  Groups of individuals who may benefit from these efforts include those of different racial and/or ethnic backgrounds (e.g., African-Americans, Asians, Hispanics) and/or those belonging to underserved populations (e.g., Appalachia, rural).  The primary goal of this program is to “significantly improve access to and utilization of beneficial cancer interventions in communities with cancer disparities.”

RTI International (RTI) worked with staff from the NCI’s Center to Reduce Cancer Health Disparities (CRCHD) to conduct a feasibility study for evaluating the CNP.  The purpose of this study was to better understand the goals and objectives of the CNP and to explore mechanisms for conducting a comprehensive evaluation.  The CNP is comprised of three phases:  one to develop and increase local capacity, a second to create community-based participatory research and training programs, and a third to establish credibility and sustainability of the CNP.  Through this effort, RTI has designed a program evaluation plan for Phases I and II of the CNP.  In conducting the feasibility study, RTI sought answers to the following questions:

- What is the purpose and scope of the evaluation?

- What evaluation questions are important to NCI?

- What practical issues need to be addressed in planning for program evaluation (e.g., political, cultural, financial, and methodological constraints)?

- What will be the interface between the grantees and the evaluators?

- What is the best evaluation approach, both philosophically and practically?  For example, it is not practical to expect to see reductions in cancer morbidity and mortality within 5 years.  Therefore, what is the ultimate hope for achievement through this effort?

- What are the ultimate outcomes for the CNP effort?

This report summarizes RTI’s approach to developing the Phase I and II evaluation plans, as well as the theoretical foundations that were used to organize and support the evaluation approach.  The report also provides tools RTI created, such as a CNP conceptual framework, that NCI can use to implement a comprehensive national evaluation plan of Phases I and II of the CNP.  Exhibit ES-1 presents a compliance matrix summarizing how this report addresses each of the technical requirements of this project.

Exhibit ES-1.  Compliance Matrix of Final Report to Technical Requirements of the Evaluation Plan Project

| Detailed Technical Requirement | Description | Report Section Where Addressed |
| --- | --- | --- |
| A. Identify data elements and information necessary to assess each of the CNP objectives. | Discuss the types of data elements that could be assessed through the evaluation of the CNP. | 2.5, Appendix A (Possible Data Sources) |
| B. Give the design of the data collection system that can be used to collect these data. | Describe how the data could be collected for the CNP evaluation of Phases I and II. | 2.5, 2.6 |
| C. Indicate the types of qualitative and quantitative measures that will be used on the data and information for each CNP objective. | Describe types of measures that could be used for evaluating the CNP. | 2.2, 2.4.3, 2.5 (Exhibit 7), Appendix A (Possible Data Sources) |
| D. Describe the scope of work for the evaluation. | Overview of how Phases I and II could be evaluated, including a description of the role of the national evaluator. | 2.3, 2.4.1, 2.6 |

## 1.	Introduction

Cancer-related health disparities reflect the disconnect between research discovery, system development, and service delivery (NIH/NCI, 2001).  Identifying and eliminating the barriers to cancer prevention and control, treatment, and communication is a necessary step to achieving the Healthy People 2010 and the National Cancer Institute (NCI) Director’s 2015 goals of reducing these disparities (USDHHS, 2003, 2004).  An interdisciplinary community science model that integrates prevention science and community-centered practice is one strategy for bridging that gap (Wandersman, 2003).  In April 2005, the NCI will invest $24 million per year for 5 years to fund up to 22 community cancer networks that will collaborate with local cancer control partners and NCI’s Centers, Divisions, and Offices to improve access to and utilization of preventive cancer care.  A key component of these local programs is to engage their community in every aspect of development and implementation, from identifying cancer care needs and priorities, to addressing gaps in cancer care prevention in their local environment, to evaluating their efforts for program longevity.  Because disparities exist particularly among the four leading causes of cancer-related deathsbreast, cervical, prostate, and colorectaleach Community Networks Program (CNP) will address some aspect of care (e.g., encouraging health preventive behaviors, such as smoking cessation; increasing screening rates for early detection; improving access to clinical trials) for at least one of these cancers.  CNPs can also elect to address other needs that are identified by their community partners as important with regard to cancer care.  As shown in Exhibit 1, the CNP will consist of three phases.  Each phase is dedicated to a goal for the overall development and implementation of the program.

Exhibit 1.  CNP Phases and Accompanying Goals

| Phase | Goal |
| --- | --- |
| I | Develop and increase capacity building to support community education, research, and training to reduce cancer disparities. |
| II | Increase community-based research and training programs to reduce cancer disparities. |
| III | Establish credibility and sustainability of the Community Networks Program. |

The CNP is a complex, multifaceted cancer control program that aims to create change through community-based participatory research.  Levels of change that will be incorporated into a comprehensive evaluation of the CNP have been organized at three socio-ecological levels:  individual, community (including organizational and system-level changes within a community), and policy.  The diversity of the economic, cultural, social, and political context within which these networks will function requires flexibility to design and implement initiatives that are relevant and capture the distinctive characteristics present in the disparate communities (e.g., the type of cancer on which each focuses).  Consequently, each CNP will differ in focus and evaluation capacity.  These factors present unique opportunities and challenges that necessitate technical assistance for improving the programs and evaluating the effectiveness of the CNP.  It is critical that all CNPs successfully implement culturally-relevant, community-based, and evidence-based prevention, early detection, treatment, and communication interventions if they are to effectively address cancer care for disparate populations.  Therefore, it is important to provide for all stakeholders a “road map” that defines outcomes at several points and provides linkages between the socio-ecological levels and the expected levels of outcomes.

The NCI Center to Reduce Cancer Health Disparities (CRCHD) worked with RTI International (RTI) to develop the “best overall approach and most appropriate measures” for conducting a comprehensive CNP evaluation.  RTI’s initial step in developing a comprehensive national evaluation plan is to understand NCI’s philosophy and expectations for the evaluation.  In conducting this feasibility study, RTI sought answers to the following questions:

- What is the purpose and scope of the evaluation?

- What evaluation questions are important to NCI?

- What practical issues need to be addressed in planning for program evaluation (e.g., political, cultural, financial, and methodological constraints)?

- What will be the interface between the grantees and the evaluators?

- What is the best evaluation approach, both philosophically and practically?  For example, it is not practical to expect to see reductions in cancer morbidity and mortality within 5 years.  Therefore, what is the ultimate hope for achievement through this effort?

- What are the ultimate outcomes for the CNP effort?

In collaboration with NCI, RTI identified several principles to guide the CNP evaluation planning process:

	It must be a community-focused, participatory, and collaborative process.  In other words, the CNP must be active participants in all aspects of planning and implementing the evaluation.

	It must provide feedback to the grantees throughout the program to strengthen and improve their evaluation capacity.  For example, each project will be measured against its progress from baseline and not against the progress of other sites.

	It must demonstrate to NCI if the CNP worked as planned.  In other words, were CNPs successful in accomplishing what they set out to do?

This report summarizes RTI’s approach to developing the evaluation plan, as well as the theoretical foundations that were used to organize and support the evaluation approach.  The report also presents tools that NCI can use to implement a comprehensive national evaluation of Phases I and II of the CNP.

## 2.	Evaluation Plan Development

### 2.1	Overview of Evaluation Planning

Evaluation planning and implementation is an important process to utilize in program development.  Its ultimate goal is to determine what components of a program are effective and impact health outcomes.  As specified in the concept statement for the CNP, NCI takes a comprehensive approach to decreasing health disparities related to cancer by addressing three main goals (see Exhibit 1).  As summarized above, these goals encompass such community-based participatory research principles as capacity building, partnerships and collaboration to engage community members and researchers in a joint process with equitable contributions, system development and improvement, and a balance between research and action (Israel et al., 1998).  Each of the funded programs will work to address these goals through objectives specified by the NCI.  The complexity of the CNP raises a number of important questions that must be addressed by a comprehensive national evaluation:

	To what extent are the three goals of the overall program being met?

	Does the CNP impact disparities in breast, cervical, prostate, and colorectal cancers?

	Is each CNP able to improve access to primary and secondary prevention services among the targeted communities?

	What are the characteristics of the programs that effectively impact individual, community, and/or policy changes?

	What level of capacity is required at the community level in order to effectively address education, research, and training needs related to impacting cancer disparities?

Answering these questions is critical to implementing a comprehensive evaluation of the CNP.  In this section, we provide an overview of how we have begun to organize and create a comprehensive evaluation plan for CNP.  This process of plan development incorporates the evaluation’s objectives within a conceptual framework that depicts the activities and direct impacts and outcomes of each program component, as viewed by key stakeholders.  The plan developed to date is comprehensive, yet relies on existing data sources where possible and provides an approach that is feasible.  In this report, we present the evaluation plan developed for Phases I and II.  A similar process will need to be completed for Phase III.

### 2.2	Steps Completed for Evaluation Planning

Exhibit 2 is adapted from CDC’s “Framework for Program Evaluation in Public Health” (1999).  Based on this framework, we have developed a series of steps, accompanied by tools, that have guided the development and implementation of a comprehensive national evaluation plan for the first two phases of the CNP.  In the remainder of this section, we describe the steps completed to date and provide an overview of how this step-by-step approach can result in a comprehensive plan that meets the needs of CNP key stakeholders.

Exhibit 2.  CDC’s Framework for Program EvaluationAdapted Steps for CNP Evaluation Plan Development

Source:  Centers for Disease Control and Prevention (CDC).  1999.  “Framework for Program Evaluation in Public Health.”  Morbidity and Mortality Weekly Report 48(RR11):1-40.

The framework in Exhibit 2 highlights six steps in the process of developing an evaluation plan.  For this study, steps 1 and 2 were completed for Phases I and II of the CNP.  Step 3 was initiated for these two phases but will need to be addressed further, as will steps 4 through 6, once the CNPs are awarded funding and evaluation planning is completed.  The next section provides an overview of the process followed to complete steps 1 through 3.

Step 1—Engage Stakeholders

The RTI team initiated the evaluation planning process with a face-to-face meeting among key stakeholders of the CNP staff and RTI team leaders to review the goals of the evaluation planning process, answer questions about NCI’s concept of how the program would work locally, and collect any documents that needed to be reviewed.  Key stakeholders are defined as those individuals who have a “stake” in the program under study and/or the evaluation findings (Patton, 1997).  So far, these stakeholders have included a number of staff within the CRCHD who will be involved in overseeing and managing the CNP once it is underway.  Stakeholders are important team members in the development of an evaluation plan because they are generally experts in the program itself and understand how it can or should impact the local community.  During the conduct of this feasibility study, drafts of the evaluation planning matrix and conceptual framework, presented below, were presented to NCI team members for review and comment.  These documents were then revised to incorporate team members’ perspectives into the final documents.  As this evaluation planning process moves forward, other key stakeholders, such as the CNP Principal Investigators (PIs) or their designated evaluator, will need to be included in developing the evaluation plan for Phase III.

Step 2—Describe the Program

After meeting initially with key stakeholders, the RTI team reviewed program documents to gain a deeper understanding of the program and its phases.  Based on this understanding, we developed a draft conceptual framework to examine and explain the relationships that exist among program goals, objectives, and outcomes (CDC, 1999).  We then developed an evaluation planning matrix that specifies the program’s goals and objectives and begins to state potential evaluation outcomes that may be of interest to the NCI team.  This matrix also includes details about data sources that will be required to measure program activities and outcomes specified in the evaluation planning matrix.  Below, we provide an overview of the process followed to date to develop a comprehensive evaluation plan for Phases I and II of the CNP.

Document Review

Members of our interdisciplinary team reviewed all existing documents of the CNP (e.g., the Concept Statement for the CNP, Program Announcement, notes from meetings with CRCHD) and worked together to integrate this knowledge into the conceptual framework and evaluation planning matrix, which provided the basis for development of the evaluation plan.  At this stage of evaluation plan development, we do not know which local programs will be funded or what their proposed activities will be.  However, once that determination is made, the evaluation planning matrix can be updated and refined to better match what activities are to be developed at the local level.

Conceptual Framework

Conceptual frameworks typically include a visual depiction of how the program is expected to impact change.  A conceptual framework is generally more theoretically based and conceptual than a logic model.  A logic model tends to be program specific and provides a more detailed description of the planned activities and outputs of a program.  A key advantage of a conceptual framework, in the context of a multifaceted program such as the CNP, is that it identifies the proposed interrelationships across major program phases and activities (e.g., capacity building, partnership and collaboration development) and the expected relationship between these and the program’s outcomes.

Evaluation Planning Matrix

An evaluation planning matrix of activities, outcomes, and data sources is a useful organizational tool for evaluation planning that flows from the conceptual framework.  We created a matrix that relates to appropriate “program building blocks” and begins to specify both short-term (or process) and intermediate (or impact) outcomes that might be expected from the community-based programs.  The evaluation planning matrix developed for Phases I and II of the CNP is presented in Appendix A.  Each section of the matrix is described below:

	Goal:  The stated goals for Phases I and II are taken directly from the Request for Applications (RFA) for the CNP respondents.

	Objectives:  NCI specified objectives for each of the program goals in the RFA that are provided in the first column of the matrix.

	Activities:  Activities are those tasks that would typically need to be conducted to meet a stated objective.  Many of the activities in the current matrix were stated in the RFA prepared by NCI (those appear in bold in the matrix).  However, for some objectives, all of the activities that seemed necessary to accomplish an objective were not specified and have been incorporated into the matrix as much as possible at this time (in regular text).  The activities of the current matrix will need to be further refined once we know which programs received funding since some of the specified activities will likely not be addressed by any of the CNPs.

	Outputs/Products:  Based on details from the RFA for the CNP and other documents, outputs were specified for each of the program objectives.  Outputs are those tangible products specific to an objective that indicate that an activity was completed (e.g., educational materials, curriculum for trainings, organizational chart with CNP staff specified).

	Process Outcomes:  These outcomes are measures that assess how well activities are being accomplished.  These measures are often referred to as “formative” because they focus on assessing how well a program is being implemented, what is going well or not, and what lessons have been learned that could inform ongoing program improvement.  These outcomes are often the most feasible to collect since they focus more on “program-level” measures, which is a more accessible sample than those they serve (e.g., the community members the program impacted).  In the matrix, initial process outcomes have been specified for each objective.

	Impact Outcomes:  These outcomes are measures that assess the extent to which the activities have resulted in change.  For the CNP, the types of change that are of greatest importance are at the individual (e.g., change in screening behaviors), community (e.g., changes in how community-based organizations interact, local referral practices), and policy (e.g., changes in eligibility for Medicaid coverage) levels.

	Possible Data Sources:  For the matrix, we have begun to specify some possible data sources that can be used to assess the outcomes for each of the program objectives.  These sources are described in detail in Section 2.5.  However, much of the work to determine which data sources are the most applicable for and feasible to the CNP will need to be completed after the programs have received funding.  This work is part of the process to “focus the evaluation,” which is described in detail below.

Step 3—Focus the Evaluation Plan

The evaluation must be focused to assess the issues of greatest importance to stakeholders, given the available resources dedicated to evaluation and surveillance (CDC, 1999).  To focus the evaluation, NCI and the future evaluator will need to work with other key stakeholders to prioritize needs to address in the evaluation plan.  Based on these priorities, feasible evaluation strategies can be developed and integrated into the CNP evaluation plan.  During this process, it will be important to incorporate both qualitative and quantitative data elements into the evaluation plan to obtain a comprehensive overview of the CNP.  Examples of these types of data elements are described below.

The methods that could be used to understand the effectiveness of the CNP include multilevel or hierarchical models that can account for how multiple levels of influences can directly impact behavior, either independently (e.g., a provider’s recommendation to obtain screening) or in combination with another level(s) of influence (e.g., a provider’s recommendation in combination with a local mobile mammography made available to increase access).  The evaluation would apply these methods to develop complementary evaluation designs to address the proximal and distal outcomes of the program.  We recommend formative, process evaluations to explore the fidelity and quality of program implementation and outcome evaluations of progress toward proximal and distal outcomes.  In the following subsections, we describe how quantitative and qualitative methods could be incorporated into the final comprehensive national evaluation plan for the CNP.

Quantitative Methods

The heart of our quantitative strategies focuses on the notion that individuals will differ in their exposure to various program activities (e.g., pilot projects, research, training).  By relating these exposures to outcomes (by way of the conceptual framework), quantitative methods can be used to better understand how program components work independently and jointly to contribute to the attainment of program goals.  For example, a local cultural competency training held for area gynecologists could lead to a number of local practices scheduling appointment times during hours after work.  This training then impacts both the cultural compassion that providers have for their patients and access to services among local community members.

By making use of the mix of program activities across communities and organizations, the evaluation can better measure the impact of each program component on key outcomes to determine program successes and failures.  In assessing program effectiveness, the evaluation must also attend to the possibility that the context within which these program activities occur will influence program outcomes.  Sociodemographic characteristics and the capacity of the communities to organize and deliver education, research, and training to disparate populations may influence program effectiveness.

Multilevel models (hierarchical linear models) are a multivariate tool to relate individual outcome measures to exposure to program activities that occur in organizations, communities, and society at large.  These models can also account for the context within which the program activities occur.  Individual outcomes of interest include

	improvement in attitudes about obtaining cancer screenings,

	reduction in negative health behaviors (e.g., smoking, not using sunscreen),

	increase in survivors obtaining care through clinical trials, and

	increase in access to screening services among members of disparate populations.

For measures that are reliably captured in community-based surveys, as an example, we can rely on self-reported data on program activities (to the extent feasible).  However, to get a more complete understanding of the program’s effects, it is also desirable to gather quantitative data on program activities and policies from local organizations and provider practices, as well as the communities, to understand the context within which individuals make decisions about their cancer care.

These quantitative methods can help derive measures of program effectiveness for many of the program efforts.  Quantitative measures can also be used to assess changes at the community and policy levels.  We recognize the limitations of quantitative methods, however, and suggest complementary qualitative methods to strengthen the quantitative data conclusions.  The aim of these efforts is to better understand the context within which change may be occurring and the “how” and “why” of program implementation.

Qualitative Methods

Qualitative methods generally consist of three kinds of data collection:  (1) in-depth, open-ended interviews; (2) direct observation; and (3) review of written documents (Patton, 1990).  In evaluation research, qualitative methods are typically used to study programs for the following reasons:

	Process or formative evaluation of a program to inform improvement of its development or to provide understanding of contextual factors that could be impacting its successful implementation

	A complement to quantitative methods to provide validation or a richer explanation of the results

	An in-depth exploratory tool for use in cases where quantitative methods are either not feasible or inappropriate

Qualitative tools for a comprehensive evaluation should be interwoven across program phases or components to understand how program activities may be mutually reinforcing.  To illustrate, focus groups could be conducted with a diverse representation of community members to explore a variety of topics related to the program, such as how involved they have been in each aspect of program implementation, what their exposure to the program has been, how their access to services has changed (or not), and other relevant issues across each of the CNP phases.  Data from these focus groups could be combined with other data from key stakeholder interviews, record abstractions, network analysis, and various ethnographic techniques to further elucidate changes relating to the key program areas of capacity building, education and training, or partnership development.

Evaluation research stresses the importance of developing measures that provide for a “triangulation” of methods to ensure that the conclusions drawn from qualitative analysis are reliable (Patton, 1990).  Our experience has taught us that this triangulation of data provides for a much more in-depth overview of how the program has impacted change.

Steps 4 through 6

As shown in Exhibit 2, CDC recommends that six steps be completed for evaluation implementation.  Since this is an evaluation planning effort, Steps 4 through 6 are beyond the scope of this project and are not addressed here but should help guide the process for evaluation implementation once that work begins.  In the following sections, we provide an overview of how the evaluation plan for CNP has been completed to date and  recommendations for developing and implementing a national evaluation.

### 2.3	Engage Stakeholders in the CNP Evaluation (Step 1)

As shown in Exhibit 2, the CDC’s “Framework for Program Evaluation in Public Health” provides “a systematic way to improve and account for public health actions by involving procedures that are useful, feasible, ethical and accurate” (1999, p. 4).  Step 1 in the evaluation process involves engaging stakeholders.  So far, the key stakeholders that have been involved in developing the current evaluation plan represent the national level, through the CRCHD.  It is also important to identify and engage local key stakeholders.  Early in the program planning, NCI will need to give the grantees guidance in (1) determining which local key stakeholders should be involved and (2) to what extent they will be involved in planning, implementing, and evaluating local efforts.  This subsection provides discussion points relevant for the process of engaging stakeholders for the CNP.

Engaging stakeholders is a fundamental component of community-based participatory research that can occur throughout the process of program implementationfrom identifying program goals and objectives to conducting the evaluation.  However, the depth of involvement from the community should be discussed prior to or in the early stages of the program.  The role of the community can best be thought of as a continuum.  This means that involvement can range from not being very involved (such as providing feedback on materials and research developed by the program) to being very involved (such as completing tasks that have a direct impact on what the program does and accomplishes).  Since the CNP is required to have a community-based, participatory approach, it is likely that each Community Advisory Group (CAG), a required component of Phase I, will play an active role in every stage of program development, implementation, and evaluation.

The evaluation process begins with an investment from the stakeholders in what will be learned and what will be done with the evaluation.  For the local-level evaluation, to be conducted by each individual CNP, the stakeholders to engage in this process will likely be members of the CAG.  However, some CNPs may decide that additional, guest members need to be invited to participate in order to provide additional expertise on evaluation.  Prior research has identified three principal groups of potential stakeholders to include in evaluation planning and implementation (Mathie and Greene, 1997):

	Those involved in program operations (e.g., partners, collaborators, funding officials, administrators, managers, and staff)

	Those served or affected by the program (e.g., individuals, researchers, providers)

	Primary users of the evaluation (e.g., NCI)

In a community-based participatory approach, key stakeholders include community members, organizational representatives, and researchers who work in partnership on all aspects of the research process (Israel et al., 2003).  Since the “communities” differ for each level of evaluation (i.e., national, regional, or local), the stakeholders for the national evaluation, to be conducted through the CRCHD, will likely belong to different groups than those involved with each local CNP evaluation.  The “community” for the national evaluation includes the programs themselves, since they will be supplying the measures for the national evaluation.  Key stakeholders in the national evaluation will include each PI or his/her designated replacement and CRCHD staff members.  Other stakeholders may be invited experts on program evaluation and/or cancer control and representatives from some local communities involved in CNP.  To be truly “participatory” at the national level, the key stakeholders should include a mix of people with different backgrounds and perspectives.  Given the size of the CNP, the number of stakeholders involved will need to be streamlined and a communication plan will need to be developed to ensure that the stakeholders working with the national evaluators are effectively relaying progress to all of their counterparts.

One structure to consider for ensuring cross-collaboration and a participatory approach at the national level is to convene a group of stakeholders for the national evaluation fairly soon (ideally within 90 days) after award of the CNPs.  NCI and the evaluator could work with the (up to) 22 CNPs to determine who will be members of this group, using a list of criteria developed in collaboration with the PIs (e.g., two members are to represent the management from local CNPs, two should be community members of CNPs).  The purpose of the initial meeting will be to provide an overview of the work that has been completed to date and engage the group in establishing a mechanism to obtain their ongoing input in the national evaluation plan.  One structure that has worked well for several other national evaluations is the development of an Evaluation Advisory Committee (EAC).  These Committees tend to include key stakeholders of the program, as well as experts in program evaluation, to ensure that the resulting evaluation plan is feasible for the programs and will realistically achieve outcomes of interest (Patton, 1997).  It is ideal for these groups to have approximately 10 to 12 regular members in order to provide productive meetings that result in direct guidance to the evaluation plan.  During the first year of CNP implementation, this Committee should probably meet fairly regularly to complete such tasks as

	reviewing versions of the conceptual framework as it is revised to better incorporate local efforts,

	providing guidance on research methods to use at the local and national levels,

	prioritizing evaluation efforts so that the outcomes of greatest importance are incorporated into the evaluation design, and

	critiquing evaluation instruments and tools to be used in the field.

Another role of the EAC would be to ensure adequate communication between what is happening with each local CNP and the national evaluation.  The people designated from each CNP to be members of the EAC should be willing to report regularly to their own CAG about what is being advised for the national evaluation.  Data that are collected locally will be used to inform the national evaluation, so the CAG’s input and guidance into what is done for evaluation will be important.  The ideal model for interaction is depicted in Exhibit 3 with overlapping circles.  One circle depicts the national EAC, and the others

Exhibit 3.  Proposed Interconnectedness of the Local Community Advisory Groups and the National Evaluation Advisory Committee

Local CAG Local CAG Local CAG National Evaluation Advisory Committee Local CAG Local CAG

illustrate how each local CAG would potentially be contributing members to that national group.

Ideally, these groups would be interchanging information so that each is aware of what is expected but also knows what is realistic and of interest to local community members so that their thoughts can be taken into consideration in designing the national evaluation.  The national evaluator could help to facilitate this communication by convening monthly conference calls among all of the CNPs and using these calls to inform stakeholders of the progress being made.  An additional strategy for obtaining input is to create a Web-based “bulletin board” where draft tools and instruments for the evaluation are shared so that each stakeholder can provide input.  This board could also be used as a place for each site to post their local evaluation efforts if they are in need of input and technical assistance.  This model is somewhat different from the conventional approach to program evaluation.  As shown in Exhibit 4, there are distinct differences in how a community-based participatory evaluation would occur and who would be involved, as opposed to conventional approaches to evaluation research.

Exhibit 4 summarizes the stark contrast between the two approaches; however, a mixed method approach can be used, with varying degrees of input from the community.  For the national evaluation, because the need for outcomes of accountability may be greater, the focus may be more on conventional approaches to evaluation, whereas at the local level, the focus may be more on participatory evaluation, since this is required by the RFA.  NCI will need to decide early on in the process of program implementation which of these approaches to use in guiding the CNPs on their evaluation and in overseeing the work for the national evaluation.

Exhibit 4.  Comparison of Conventional and Participatory Evaluation Approaches

| Issues for Consideration | Conventional Evaluation | Participatory Evaluation |
| --- | --- | --- |
| Who | External experts conduct the evaluation | Community leads the efforts, supported by project staff |
| What | Predetermined indicators of success are measured, primarily cost and health outcomes | People identify their own indicators of success |
| How | Focus is on “scientific objectivity,” uniform and complex methodologies, and delayed access to results | Focus on self-evaluation with the use of simple methods adapted to local culture; open, immediate sharing of results |
| Why | Accountability of funding, usually impact related, to determine if the funding should continue | To empower local people to initiate, control, and take corrective action |

Source:  Adapted from Springett, 2003.

### 2.4	Describe the CNP (Step 2)

As described in Section 2.2, the second step in the evaluation process is to describe the program that will be evaluated.  For this project, we reviewed all available documents about the CNP and met with CRCHD staff to discuss the overall program goals and objectives.  We developed two tools for the evaluation plan.  First, we presented a draft conceptual framework for the overall program to NCI team members for their input and feedback.  Individuals who were involved in providing feedback included those who will serve as Project Officers to the funded programs and/or those with specific expertise in one or more of the areas of outcomes (e.g., community, policy).  Based on their feedback, the framework was then revised and has been used extensively in our evaluation planning work.  The resulting conceptual framework (Exhibit 5) is described in detail in the following sections.

The CNP conceptual framework provides a “top of the trees” view of how the CNP is proposed to work.  It shows the relationship between its three major program components:  the Program Building Blocks or foundation that the local initiatives will draw from; the primary Focus of Activities that the Program envisioned; and the desired short-term, intermediate, long-term, and ultimate Outcomes.  It provides a logical sequence of how the resources invested by the CNP will lead to program improvements and the desired results.

Second, we created an evaluation planning matrix that is presented in Appendix A.  This matrix provides details on how Phases I and II of the CNP are expected to be implemented and what the resulting outcomes may include.  The matrix is much more detailed than the conceptual framework and can be mapped directly to the structure of the CNP.  In the following sections, we describe each of the three major program components as depicted in the CNP conceptual framework.  For each component, we describe how the details from the

Exhibit 5.  CNP Draft Conceptual Framework

evaluation planning matrix should be used to guide the addition of Phase III to the evaluation plan and the implementation of the evaluation once awards have been made.

#### 2.4.1	Program Building Blocks

The Program Building Blocks (see Exhibit 5) consist of the infrastructure, partners, and collaborators that will direct and facilitate development and implementation of the Program activities.  These interrelated conceptual building blocks link directly to the first three objectives of Phase I, in the left-hand column of the evaluation planning matrix (see Appendix A, pp. 1-4) and are described separately below:

	Objective I.1:  Develop core organizational infrastructure for local CNP (p. A-1)

	Objective I.2:  Develop partnerships with communities experiencing cancer disparities and organizations that can aid in reducing cancer disparities (p. A-2)

	Objective I.3:  Have at least four collaborations with NCI Centers/Divisions/Offices (p. A-4)

In order for the CNPs to successfully address each of these objectives, they will need to be versed in the principles of community-based participatory research.  The value of participatory research lies in its ability to improve evaluations, utilize evaluations, and empower participants (Patton, 1997; Gergen and Gergen, 1991; Morgan, 1983; Papineau and Kiely, 1996; Reason, 1988).  The characteristics of successful participatory research are based on recognizing and planning for the challenges that accompany it.  Such challenges include overcoming power differences (Israel et al., 1998; Greene, 2000; Mathie and Greene, 1997), determining what is considered program success, adequately documenting success, gaining access to data to measure outcomes (Nichols, 2002), and juggling the differing perspectives and priorities of the community and funding sources of the researcher (Schulz et al., 2003).  However, proponents of participatory research suggest that the “active engagement of those who will be affected by the research is necessary in order to challenge power differentials that currently exclude some from the process of creating knowledge” (Schulz et al., 2003, p. 295).  Therefore, if the challenges are addressed in the planning stage of the programs, and a supporting infrastructure provides a solid foundation for community work, then a climate of program success can ensue and thrive.

Infrastructure

The first Program Building Block in the CNP conceptual framework (see Exhibit 5) corresponds to the infrastructure created by the CNP, stated as “establish and maintain an infrastructure for addressing cancer disparities.”  The CNP model assumes an asset perspective to create participatory, collaborative relationships between the researchers and cultural and/or racial/ethnic minority and underserved communities.  The infrastructure brought to the community by CNP will provide the foundation for conducting local research, training, education, and other initiatives.  However, studies have shown that engaging community residents in the design, implementation, and evaluation of interventions in their communities can substantially contribute to efforts to improve health.  As the programs build their infrastructure, they will need to plan a structure that lends itself to supporting community-based participatory research efforts.

The coalition development literature provides some insight into essential structural components to support community-based participatory research.  In their review of 252 collaborative partnerships, Roussos and Fawcett (2000) identified seven interconnected and modifiable structural components that enhanced their individual and population-level health outcomes:

	A clear vision and mission of what they wanted to accomplish

	Effective leadership

	Regular time to plan what they want to do and strategies to accomplish their goals

	Regular communication to update partners on progress

	Technical assistance

	Ongoing funding mechanism

	A comprehensive evaluation plan

Leadership was the most important organizational factor that contributed to partnership effectiveness.  Effective leaders are able to engage broad and active participation, ensure broad-based influence and control, and facilitate productive group dynamics.  Communication, facilitating meetings, negotiating with partners, and networking were identified as core skills of effective leaders (Roussos and Fawcett, 2000).

During Phase I, each grantee must hire and maintain core administrative and evaluation staff who will provide the CNP leadership.  These staff members include a PI, project manager, research coordinator, policy analyst, and program evaluator and two to three administrative staff.  Only the project manager and administrative staff are full-time.  Additionally, the grantees must also create a Project Steering Committee, Regional Advisory Committee, and a CAG as formal structures to ensure community participation.  The CNP will determine who will participate and the mix among these groups; however, NCI will expect the local CAG to have a strong presence in each CNP.  A formal structure of the CAG will likely be required, such that community members are afforded the opportunity to provide ongoing input and direction to the CNP.  To accomplish this, regular meetings and communication plans will need to be established early on by each CNP to ensure ongoing CAG involvement.  To transition to Phase II, the grantees must demonstrate that they have developed the necessary infrastructure to support the CNP.

Ongoing management processes include collaborating with NCI to provide training and technical assistance to CNP staff, advisory group members, and community partners; updating the strategic plan; observing and communicating progress toward benchmarks; and attending CNP and NCI meetings.  The third column of the evaluation planning matrix (see Appendix A) presents some possible outputs and products from these infrastructure-building activities, including resumes, organizational charts, budgets, cost reports, strategic plan, communication plan, annual progress reports, written communications (e.g., e-mails, memos, faxes, meeting minutes), membership lists, and a CNP database.

To evaluate how well they build and maintain this infrastructure, evaluation questions of interest for the CNPs include the following:

	What is the climate within the CNP?  And within the larger lead or institutional agency?

	What is the local community context that could be impacting how well the CNP can function?

	How are the values of the CNP and lead agency similar or dissimilar?

	How do these values facilitate or impede CNP efforts?

	How are funds administered?  What proportion of funds are provided directly to the community?

	What is the timeline on which organizational structure was established and operationalized?

	What are the turnover rates for the staff and advisory groups?

	What is the structure and size of the CNP?

	How were the advisory group members recruited?  How were they selected?

	What is the structure and size of the CAG?  What is the interrelationship between the CNP and CAG?

	What are the skills, experiences, and worldview of the CNP leadership and staff?

	What are the roles and responsibilities of advisory groups?

Partnerships

The second and third Program Building Blocks in the CNP conceptual framework (see Exhibit 5) relate to partnerships.  Since partnerships are the most essential component of the CNP, a distinction has been made between two groups of partners.  The first is partnerships with community-based organizations (CBOs) and local community leaders, particularly those who work directly with members of the disparate populations.  These partnerships would focus on assessing local community resources and identifying the gaps in services that are impacting cancer care among disparities.  CBO partners would likely be members of each CNP’s Community Advisory Group (CAG) and would help to facilitate leveraging of local resources to address needs in the community.  The second type of partnership (or the third Program Building Block) is with the organizations that can aid in reducing disparities.  These organizations may include representatives from local hospitals, private foundations and business groups, government entities such as the local health department, and policy makers.  These partnerships are essential to impacting change and would also be ideal members to include on each CAG.  As the community identifies its assets and needs, these partners can potentially provide the infrastructure, resources, and funding needed to fill any gaps in services.  The following provides an overview of key elements to consider in establishing and evaluating these partnerships.

Partnership, coalition, network, and alliance are all terms used to describe the goal of community-based initiatives, such as the CNP.  Developing since the 1980s, coalition development literature provides extensive case studies on the ideal structure and process of these partnerships.  For both the structure and process, the Program Building Blocks represent the need for the CNP to identify, create, and/or renew partnerships with different groups of people in their community.  However, establishing these partnerships is just the beginning of the process and will need to be followed with ongoing efforts to nurture the relationships and ensure “buy in” from all essential partners.

The community researcher is a central member of the community-based partnerships.  Participatory researchers share their knowledge and expertise, serve as facilitators of the process, and coach in developing the capacity of the community members (Small, 1995).  But each partner shares their “unique strengths and shared responsibilities” (Green et al., 1995, p. 12) in order to better understand the social and cultural dynamics of the community, and integrate this knowledge with action to improve the local health and well-being (Schulz et al., 1998).  Experts in community-based participatory research have identified nine principles that should be followed and integrated into their work to develop partnerships (Exhibit 6).

These nine principles provide a list of ideals for community-based researchers to strive to achieve in establishing their local partnerships.  However, there are many challenges to this process of partnership development.  After an in-depth review of community-based participatory research, Wallerstein (1999) identified several difficulties with putting this methodology into practice, including creating a rigorous evaluation design, defining “community,” and measuring “community” due to inadequacies of existing datasets at the community level.  Perhaps even more importantly, Boyce (2001) in his review of 100 health promotion projects found that 41 percent of community members participated in planning activities, 29 percent participated in implementation, 19 percent regularly attended meetings, and only 11 percent participated in evaluation.  These findings suggest that community involvement is easier to accomplish earlier in a project than it is on an ongoing, long-term basis.  Obtaining community buy-in or ownership into a research project requires a long-term commitment to addressing disparities within that community for years to come.  Therefore, it is critical that researchers approach this process with the idea that the CNP is just the starting point (or possibly a continuation) to this partnership and will serve as a building block for identifying resources and additional partnerships to improve the local health.

In evaluating these partnerships, it is important to be aware that they develop over time, and therefore measures to assess their development should be sensitive to this process and the structure within which they are occurring.  According to Butterfoss, Goodman, and Wandersman (1993), coalitions or community-based partnerships evolve through four steps:  formation, implementation, maintenance, and accomplishment of goals or outcomes.  Florin, Mitchell, and Stevenson (1993) proposed a more extensive seven-stage process:  initial mobilization, establishing organizational structure, building capacity for action,

Exhibit 6.  Nine Principles of Community-Based Participatory Research

| Principle | Description of Principle |
| --- | --- |
| CBPR recognizes community as a unit of identity. | Approach incorporates an attempt to identify and work with existing communities of identity and to strengthen a sense of community through collective engagement. |
| CBPR builds on strengths and resources within the community. | Approach is “asset” focused, as opposed to “deficit” focused and starts by identifying and building on strengths, resources, and relationships that exist within communities of identity. |
| CBPR facilitates collaborative, equitable partnership in all phases of the research. | All parties participate and share responsibility for all aspects of the program, including problem definition, data collection, interpretation of results, and application of results to address local needs. |
| CBPR promotes co-learning and capacity building among all partners. | Approach facilitates the reciprocal transfer of knowledge, skills, and capacity or resources. |
| CBPR integrates and achieves a balance between research and action for the mutual benefit of all partners. | Approach involves a commitment to translating and integrating research results with community change efforts underway with the goal of benefiting all partners involved. |
| CBPR emphasizes local relevance of public health problems and ecological perspectives that recognize and attend to the multiple determinants of health and disease. | Approach addresses public health problems that are locally relevant and considers the concept of health from a positive model, incorporating the integration of environmental influences into the research with an ecological, broad-based perspective. |
| CBPR involves system development through a cyclical and iterative process. | Approach seeks to build the competencies within a system in order to enhance learning and sustainability. |
| CBPR disseminates findings and knowledge gained to all partners and involves all partners in the dissemination process. | All partners receive the results of the research and are involved with determining the process of relating the results. |
| CBPR involves a long-term process and commitment. | Approach involves the development of trust in working with the community to reduce disparities, which is a long-term process and involves a longer-term commitment than one research project allows. CBPR highlights the need for communities to find mechanisms for sustainability. |

Note:  CPBR = community-based participatory research.
Source:  Adapted from Israel et al., 2003.

planning for action, implementation, refinement, and institutionalization.  Any evaluation designed to assess both types of partnerships essential to CNP would need to be developed so that the effects of the process are taken into account in interpreting the findings.

Structure can also influence group interaction and dynamics that shape whether the partnership is effective (Schulz, Israel, and Lanz, 2003).  Perceived collective efficacy, a group-level interdependence construct, asserts that people will put forth conjoint effort toward a shared belief to exercise control over community life.  Research findings show that the stronger the perceived collective efficacy, the higher the group aspires, the more motivated the group members are to achieve, the stronger their staying power, and the greater their performance (Bandura, 2001).  Partnership provides an effective structure for collective community action but needs to be planned for and adequately managed by each of the CNPs.

NCI is requiring that the CNP develop at least one partnership with community members, providers, and researchers to progress to Phase II.  The motivation for and purpose of the partnerships will vary according to the community and drive the structure and outcome.  The CNP’s local context will vary significantly in the amount and type of assets available to each community.  The partnerships will undoubtedly reflect that diversity.  During the early phases of partnership development, it will be important for the CAG to assess existing cancer control resources, assets, and needs within the community of interest.  This type of context assessment or study can also identify political, social, cultural, and environmental opportunities and barriers.  Doing this type of assessment would initially help the CNPs to plan relevant and effective interventions for that specific context.  For example, availability of cancer resources may be more of an issue in a rural setting or primary and secondary providers may be available in an urban setting but not accessible due to clinic hours.  Once the CNPs are up and running, this type of effort can be helpful in assessing and understanding factors that influence the Program’s progress toward outcomes.  Engaging broad community participation in this contextual assessment is essential for developing and maintaining the partnership.

Some possible outputs and products from these partnerships are listed in the third column of the evaluation planning matrix (see Appendix A).  Possible outputs/products include a map of existing and new cancer control programs, partnerships, and providers; a matrix of community partners by focus areas; and memoranda of understanding (MOU) and memoranda of agreement (MOA) developed with each CNP partner.

Local relationships and capacity building will affect what the CNP is able to accomplish.  Potential evaluation questions to answer include the following:

	What partnerships exist within the disparate communities?

	What is the history of programs and providers working together?

	Who are the key stakeholders?

	What types of partnerships have been developed?

- What CBOs are involved with CNP?  What is their role?  What has been their contribution, if any?

- What business or government entities are involved with CNP?  What is their role? What has been their contribution, if any?

	How are the CAGs structured?  Are they representative of the community?  What CBOs or local business and government entities are not involved with CNP and possibly should be?

	How was the community involved in the development and implementation of the CNP plan?

	How many MOAs and MOUs are in place?

	What are partners’ perceptions of the strengths and weaknesses of the CNP?

	What are the opportunities and threats from the external environment that could be impacting how well the CNP can influence individual, community, and/or policy changes?

Collaborations

The fourth Program Building Block in the CNP conceptual framework is collaborations, which is to “develop NCI collaborations (including with CIS).”  In some partnership models, collaboration is the most involved, most complex, most difficult stage in a continuum for characterizing relationships among partners (Himmelman, 2001).  It is the ultimate engagement of community members.  Lasker and Weiss (2003) define it as synergy, “the breakthrough in thinking and action that are produced when a collaborative process successfully combines the complementary knowledge, skills, and resources of a group of participants” (p. 25).  These distinctions highlight the error of interchanging the terms “partnership” and “collaboration.”

Lasker and Weiss’ (2003) Community Governance Model provides a conceptual map of the collaborative process.  It hypothesizes that leadership and management are critical to participation and collaboration.  It describes a structured method for identifying who should be involved by focusing on three levels of collaboration:  empowering individuals through their active involvement, building interpersonal relationships with other people who are involved, and creating a synergy through the combined assets of all partners.  The result is the collaborative problem solving that creates social changethe synergy.  Everything in the collaborative process depends on the people and organizations that participate in that process.  Getting and keeping all of the right people at the table is a challenge.

For the CNP, the focus of collaboration is between the NCI and the local program.  Programs are required to establish a collaborative effort with the Cancer Information Service (CIS) and with other NCI entities as recommended by their Project Officer.  NCI will provide guidance as to which collaborations may be best suited for each CNP.  Possible outputs or products of these collaborations may include culturally and linguistically appropriate education materials and procurement of additional funding resources.

To evaluate how well these collaborations occur, possible evaluation questions include the following:

	What factors facilitate or impede collaborations?

	How are collaborative relationships maintained?

	What was NCI’s role in facilitating the collaborations?

	What has been the community’s role in building the collaborations?

	What have been the outcomes of each collaboration?

#### 2.4.2	Focus of Activities

As shown in Exhibit 5, the “focus of activities” relates to the actions the local programs will take to impact cancer-related disparities.  Initially, once the Program Building Blocks are in place, the resulting action will be to “develop, through a community-based participatory process, an understanding of relevant resources, assets, and needs to address cancer disparities by creating a synergy of efforts and leveraging local resources.”  As described in Section 2.2, the Program Building Blocks are hypothesized to result in a synergy of effort at the local level (depicted as an oval in the second column of the CNP conceptual framework [see Exhibit 5]).  This synergy will influence the focus and intensity of activities implemented in the CNP communities.  Many factors can influence how well the CNP is able to inspire their local CAG to implement effective initiatives.  Key factors include whether the CAG provides a broad and deep representation of the disparate community, such as if the local community leaders are involved, the agencies they represent, and/or their peers and family.  Hays et al. (2000) demonstrated that a partnership’s ability to change policy was positively related to having broad sector representation.  Serving as advocate for the partnership and community, this “boundary spanner” plays a critical role in community organizing across diverse sectors and between organizations, by breaking down the boundaries that separate these nontraditional partners (McLeroy et al., 1988; Brinkerhoff, 2002).  This factor implies that a broad array of needs and assets within the community should be identified so that gaps in the cancer care of disparate populations can be targeted.  As the local partners are working together to identify the community’s assets and needs, they will undoubtedly learn about the work of others and the available, additional resources that may be used to leverage the CNP and adequately address gaps in care.  It is through this combined effort that the CNP will be able to identify efforts that need to be implemented to effect local change.  Two objectives of Phase I of the CNP relate directly to this component of the conceptual framework and are outlined in detail in the evaluation planning matrix (see Appendix A, pp. 4-5):

Objective I.4:  Increase the utilization of beneficial interventions to reduce disparities in the community (p. A-4)

Objective I.5:  Obtain non-CRCHD funding for community-based education and training activities directed at reducing cancer disparities (p. A-5)

Possible evaluation questions to answer in order to assess the extent to which these objectives were met include the following:

	What do the local partners have to offer the community?  What interventions were already in place before CNP funding?

	How were interventions created or developed?

	What was the role of the CAG in the development and implementation of the interventions?

	Are the interventions implemented “evidence-based”?

	What additional funds were sought?  What funds were received?

	What is the evidence that the community was able to strategically leverage CNP funding to address local gaps in services?

Once the gaps in the community have been identified, local programs will conduct three levels or types of activities to effect change:  individual, community, and policy.  These levels of activities have been conceptualized through the reliance on existing health behavior theory, using the socio-ecological model as a basis for how these activities can work to effect change.  In general, ecological models direct attention to both behavior and its individual and environmental determinants.  They examine multiple levels of influence and provide the basis of the socio-ecological framework suggested to evaluate the CNP.  These types of models are one of the principles of community-based participatory research in that they take into account the individual, the immediate contexts within which s/he lives (such as family or social network), and the larger contexts in which these are embedded (such as community or society) (Bronfenbrenner, 1990).  Given this attention to multiple units of influence and the complex set of determinants of health, “CBPR efforts strive to achieve broad-scale social changes aimed at eliminating health disparities” (Israel et al., 2003, p. 57).

The typologies of socio-ecological models may vary.  However, they all capture micro, meso, exo, and macro system levels.  Microsystems focus on the face-to-face influences in specific settings or interactions such as within one’s family, informal networks, and work groups.  Mesosystems target the interrelations among the settings that the individual is involved in, such as family, peer groups, and church.  The exosystem refers to the forces within the larger social system in which the individual is embedded, such as economic instability, unemployment, and others.  The macrosystem reflects cultural beliefs and values that influence both the micro and macrosystem (e.g., cultural beliefs about smoking, seeking health care).  Overall, ecological models support the idea of “a reciprocal causation between the individual and the environment” (McLeroy et al., 1988, p. 354; see also Pervin, 1968; Bronfenbrenner, 1979).  Adapting from the McLeroy et al. model (1988), RTI has identified three socio-ecological levels described by the CNPs that may effect change in their efforts to reduce cancer disparities:

	Individual-level change depicts the attitudes, beliefs, perceptions, and behaviors of the people targeted by the local CNP (e.g., the relationship between screening behaviors and attitudes).  At this level of change, as depicted in the CNP conceptual framework (see Exhibit 5), the CNP will “develop and conduct community-based education programs and activities.”

	Community-level change imparts the significance of how system-wide change can influence the health behaviors of local individuals.  Examples of community-level changes relevant to the CNP could include whether organizations within the community work together more effectively to address cancer care or if community norms are influenced to the point of impacting individuals to change their cancer prevention behaviors.  This level of change is referred to in Exhibit 5 and presented similar to policy-level changes, since both are more of a systems-level approach to impacting cancer disparities than the individual-level initiatives the CNP may implement.

	Policy and public advocacy have important implications for communities and can include whether local agencies work together to provide services to low-income, uninsured peoples, or a program changes their eligibility requirements to allow for more people in the community to be served.  This level of change, along with community-level change, is referred to in the final box of the CNP conceptual framework as “develop and conduct community-based provider training, recruitment and training of minority students, and relevant research (e.g., pilot projects).”

Overall, the socio-ecological model provides a framework for examining the focus of the activities to determine their broadness and comprehensiveness in addressing cancer health disparities.  Objectives specifically related to this aspect of activity development are in Phase II of the CNP and include the following:

Objective II.1:  Develop cancer disparities research that focuses on the spectrum of research issues necessary to reduce cancer disparities (p. A-7)

Objective II.2:  Train researchers, particularly those from racial/ethnic minority and underserved populations, in community-based participatory intervention research to reduce cancer disparities (p. A-8)

Objective II.3:  Develop pilot projects in community-based participatory disparities research (p. A-9).

The following evaluation questions are important to consider when assessing progress made toward meeting each of these three objectives:

	What existing sources of data were collected to build knowledge of cancer disparities?

	What research is conducted?  How is the research used to impact future work?

	What was the quality of community involvement in the research?

	What current policies impact cancer control in the community?  What about them needs to be changed?  Has any change occurred over time?

	How many researchers from racial/ethnic minorities attended training?

	Did the training accomplish what was intended (e.g., change in attitude, career goals)?

	What population is targeted by the pilot project?

	How well did the pilot projects identify and/or address the needs of the communities?

	What is the role of the community and the CAG in determining which interventions, research, training, and pilot projects to implement?

#### 2.4.3	Outcomes of Interest to the CNP

The resulting evaluation plan focuses on four different sets of outcomes that are based on their timing.  First, the CNP conceptual framework (Exhibit 5) and the evaluation planning matrix (Appendix A) specify short-term or process outcomes.  These measures focus on the formative aspects of the program that are used to assess the extent to which the program is being implemented as planned.  Common process measures are related to elements of change that are precursors to behavioral or system changes.  To illustrate these types of short-term and intermediate changes, the Precede-Proceed model has been incorporated into the CNP conceptual framework (Green and Krueter, 1991).  This model was originally designed as a program planning model to use in applying underlying theories (e.g., socio-ecological level) to an intervention with the goal of identifying and implementing the most appropriate strategies (Glanz et al., 1997).  The model has its origin in the same principles used in medical diagnosis.  For example, a medical diagnosis precedes a treatment plan; thus, an educational diagnosis should precede an intervention plan and evaluation plan.

The Precede part of the model was developed in the 1970s, and it is an acronym representing factors that influence any given health behavior (Green and Krueter, 1991).  A description of these factors follows:

	Predisposing factors are those antecedents to behavior that provide the rationale or motivation for individual behavior.  As shown in the short-term outcomes in the CNP conceptual framework (Exhibit 5), these predisposing factors might include changes in individual knowledge, beliefs, attitudes, and values with regard to cancer-related issues.

	Reinforcing factors provide the continuing reward or incentive (e.g., reinforcement) for the targeted behavior.  These are generally system- or community-level changes that support individual behavioral change.  Depending on how the community is defined, examples related to the CNP could include increases in health professionals’ knowledge and sensitivity related to cultural compassion, increases in understanding of issues impacting cancer control among disparate populations, and mobilization of the community to support CNP efforts and potentially positively impact community norms related to cancer care (see Exhibit 5, short-term outcomes).

	Enabling factors provide the facilitation of a motivation for behavior change to be realized.  For the CNP, these factors relate primarily to community-based changes, such as improved local referral patterns among providers; improved provider interactions with members of the disparate groups; increased access to preventive, screening, diagnostic, and treatment services among disparate groups; and the leveraging of funding among community partners to effectively address gaps in services.  All of these changes would enable an individual to receive more adequate cancer care and are depicted in the CNP conceptual framework as intermediate or impact outcomes (see Exhibit 5).

The Proceed part of the model was developed in the early 1990s and was added to Precede to highlight the important role of environmental factors as determinants of health and health behaviors.  The Proceed component of the model is more specific to program planning and is therefore not highlighted here but is presented in detail in the 1991 book by Green and Krueter.

In the following sections, we provide a brief overview of the four types of outcomes presented in Exhibit 5.

Short-term (Process) Outcomes

Predisposing and reinforcing factors have been conceptualized as the short-term outcomes desired from the CNP.  These factors/outcomes are precursors to behavior, system, or policy changes that might be accomplished in the 5 years of funding for the CNP.  Many researchers refer to these outcomes as “process” measures since they generally capture program-level activities and the extent to which the program was successful in implementing plans.  For the CNP, short-term measures at the program, individual, community, and policy levels will be important to incorporate into the national evaluation plan.

Within 1 to 2 years of program initiation, individual outcomes such as improvements in knowledge, attitudes, beliefs, and values of community members with regard to cancer issues should be measurable through a national evaluation.  If these individual-level changes are occurring, then we can assume that changes in behavior will likely follow for most individuals.

Community and policy short-term outcomes are also related to the knowledge and values of the local systems.  Within the community, the knowledge and attitudes of local health care providers with regard to cancer care for disparate populations have important influences, for example, on how often patients are able to obtain recommended services.  The evaluation could measure the extent to which local efforts to provide training in cultural competence changed the attitudes of providers and increased their willingness to better accommodate disparate groups through their practice, by including clinic hours after work and on weekends, providing transportation, or opening a new office in an inner-city location because their other office is too far for many people in the community.  Within 2 years, it would also be possible to determine if changes have begun in the community norms related to cancer care.  In some communities, there may be a great deal of fear about obtaining screening for cancers, such as prostate or colorectal screenings.  With ongoing community-based education efforts, people could come to realize the benefits of obtaining this screening so that they are less fearful of the results.  As more people obtain screenings and talk to their peer group about their experience, the result is that the community norms gradually change.  The precursors for changes in community norms are an increased understanding among the community of issues impacting cancer control and information on how the community members can obtain the care they need.

The policy-level change involves those laws, regulations, formal and informal rules, and understandings that are adopted on a collective basis to guide individual and collective behavior (Wallack, 1990).  It has several venues:  policy development, policy advocacy, and policy analysis.  Research suggests that programs that recognize the need to facilitate behavior change by removing policy (see Schmidt, 1995) and/or creating policy can encourage health-promoting behaviors.  The CNP plans to address health-promoting behaviors such as screening for the targeted cancers:  cervical, breast, colorectal, and prostate.  Therefore, examining policy for the CRCHD could yield a worthwhile understanding of the political climate related to cancer research and activities.  Short-term outcomes at this level could include increased awareness among policy makers with regard to policies that impact cancer care and how they can be revised to positively influence the community’s health.  If the local CNPs are working with local policy makers to address cancer issues, the evaluation would be able to capture the extent to which their increased awareness has influenced their willingness to impact change.

Intermediate (Impact) Outcomes

Impact measures, or those measuring change, have been conceptualized as the intermediate outcomes of the CNP.  These outcomes, measured within 3 to 5 years of program initiation, would focus on the extent to which changes have occurred among individuals, the community, and local policy.  When utilizing the concepts of community-based participatory research, the unit of analysis is often the community itself but that level of analysis is often not within the scope of the evaluation being conducted.  When individuals within the community are assessed, impact measures would determine the extent to which local screening rates for the four major cancers (breast, cervical, prostate, and colorectal) have increased; whether people have attempted to change their related health behaviors, such as quitting smoking or using sunscreen; and if local cancer survivors have more readily utilized clinical trials in their treatment regimen.  At the individual level, the issue of causality is difficult to address.  Oftentimes, depending on the evaluation methods used, if increases are noted, they cannot be linked directly to the program under study.  This issue can cause difficulty for funding sources since they generally want to be able to state how their program or funds made a difference within the local community.  For that reason, community or policy-level changes are often the most feasible to ascertain with an evaluation design.

For the CNP, community changes would be those resulting differences in the local norms related to cancer care that are described above.  As people become more knowledgeable about cancer issues, and see their friends and family change their own behavior, there will be a notable shift in the community norms within that area.  More easily measured changes within the community would include the extent to which CNP funds have been used to leverage local resources to address gaps in services that were beyond the scope of this program.  This aspect of the evaluation would ascertain whether there have been increases in local resources from other sources and how the partnerships developed through the CNP have impacted these changes in services.  Additional changes within the community could include providers being more centrally located and providing more accessible clinic hours, people reporting higher levels of satisfaction about their interactions with their providers and perceiving an increased sense of cultural compassion, and an increased number of minority members either seeking or entering the health care profession than prior to the CNP initiative.

Policy-level changes are also more readily accessible through an evaluation design and not as costly to measure as individual-level changes.  As previously described, policy can act as a conduit in support of individual-level behavior change (see Farquhar, 1978; Advisory Board International Heart Health Conference, 1992) and similarly as a barrier to individual-level behavior change.  Intermediate outcomes at the policy level would examine the extent to which policies have been revised, developed, and/or implemented to support the individual and community-level efforts.  An example of this type of outcome includes whether a local political leader influenced organizations to decrease their eligibility levels for services, thereby allowing more people to have access to cancer care.

Long-term and Ultimate Outcomes

Long-term and ultimate outcomes are generally measured over a period of time that is beyond the scope of one initiative.  Since the CNP funding would last for 5 years, it is not likely that long-term and ultimate outcomes can be measured through the national evaluation of the program.  However, in order to conceptualize the overarching goals of the CNP, we worked with the NCI to specify these outcomes so that they could be depicted in the conceptual framework (see Exhibit 5).

Long-term outcomes are those that could potentially occur within 5 to 7 years of program implementation.  The long-term outcome that CNP hopes to achieve is to reduce disparities by

	achieving a shift in diagnosis from later to earlier stages;

	improving cancer survivorship; and

	narrowing the gap between the discovery, development, and delivery of care for disparate populations and other groups.

These particular outcomes relate to ensuring longer survival rates across all populations.  Since the stage of diagnosis among the majority population tends to be earlier in the process of cancer growth, this population is more likely to survive cancer.  NCI has an overarching desire to reduce the disparities across cancers so that minority populations, including those of racial/ethnic minorities, low socio-economic status, or with minimal access to cancer care such as rural or inner-city populations, receive the same level of care as others and therefore find out if they have cancer at earlier stages than is presently the case.  The final long-term outcome of “achieving sustainability of efforts for disparate groups” relates to Phase III of the CNP and to the desire to maintain and even improve positive outcomes over time.  All of these outcomes relate directly to the ultimate outcome to “decrease morbidity and mortality from cancer among disparate populations to equate rates among other groups.”

The remainder of the CNP conceptual framework (see Exhibit 5) illustrates the need for evaluation to be an integral part of program implementation with the arrows drawn from each of the columns in the framework down to the arrow, which is generally thought of as a feedback loop.  A critical role for evaluation research is to provide information that can be used for ongoing program improvement.  As each component of the CNP is evaluated, the lessons learned should be communicated back to the Programs so that they can be implemented, where feasible, to improve local implementation.  Each step illustrated in the model, from whether the Program Building Blocks are in place, to how the synergy has been facilitated or deterred in the community, what activities or research have been conducted, and what the outcomes of each have been, should all be evaluated and findings shared with all key stakeholders.  These stakeholders in turn would help to interpret the findings so that they can be used to guide ongoing program management and improvements for every CNP.

### 2.5	Focus the CNP Evaluation (Step 3)

As described in Section 2.2, Step 3 of the CDC Framework (see Exhibit 2) generally consists of identifying the key measures to be obtained during the evaluation.  During this process, key stakeholders are involved in prioritizing the evaluation questions that should be answered over the course of the project.  Much of the work to focus the evaluation cannot be completed until each CNP has been awarded funding.  Once it is known which CNPs will be funded, aspects of their programs can be taken into consideration to revise the evaluation planning matrix.  In addition, Phase III of the CNP will need to be incorporated into the matrix to thoroughly provide process and impact outcomes over the 5 years of funding.  The goal in using the evaluation planning matrix is to have a document that comprehensively addresses all potential evaluation questions for the program.  It is then during the “focusing” that key stakeholders review that matrix and begin to select those evaluation measures that must be addressed and those that are not as critical to meeting the goals of the national evaluation.

Once the stakeholders have determined the priority evaluation measures, the evaluator would work to develop the data sources necessary to capture each.  At this stage in the development of the evaluation plan, it is somewhat premature to attempt to identify these data sources and elements, but we have provided possibilities in the last column of the evaluation planning matrix (see Appendix A).  As described in Section 2.2, our approach to the national evaluation would be to develop data sources that provide for a triangulation of findings so that one type of data (e.g., stakeholder interviews) can be used to inform the development of a second type of data (e.g., a program monitoring system).  These different data sources can be analyzed in order to combine findings and provide a more comprehensive overview of results than any one data set can on its own.  Exhibit 7 provides an overview of potential data sources and the types of data elements each could capture.

As shown in Exhibit 7, a variety of evaluation methods and data collection strategies could be incorporated into the CNP national evaluation, once it is clear which questions are a priority to answer.  Working with NCI and the EAC described in Section 2.2, the evaluator should finalize these methods and the collection of the data elements to minimize the burden of the local CNPs while still addressing the primary goals of the national evaluation.

Exhibit 7.  Possible Data Collection Methodologies for the CNP

| Potential Methodology | Description of Methodology | Who’s Responsible for Collecting? (Local Program or National Evaluator) | Examples of Possible Data Elements |
| --- | --- | --- | --- |
| Record Abstraction | Review of all written documents that provide some information about one or more program components, including minutes from community meetings, organizational charts, educational materials developed, media articles on program components, program implementation and/or evaluation plan, etc. While reviewing documents, abstract details that are applicable to answering the evaluation questions. | Local program provides e-mail copies to national evaluator for review and abstraction | Composition of local partnership Roles and responsibilities of CNP staff, CAG members, etc. Number of staff hired for CNP Level of effort for local meetings (e.g., how many, what is accomplished) Quality of CNP implementation and/or evaluation plan Details on trainings conducted (who attended, etc.) |
| Program Monitoring System | A Web-based, or other user-friendly data system, such as an Access data file, that is created for the NCI CNP to collect details on ongoing program activities | Local program would enter data quarterly or monthly into a system developed and managed by national evaluator | Annual budget and allocations to local community Progress toward reaching benchmarks in Phases I and II Details on partners invited to participate in CNP and their response Types of activities planned versus implemented and barriers/facilitators for completing each |

(continued)

Exhibit 7.  Possible Data Collection Methodologies for the CNP (continued)

| Potential Methodology | Description of Methodology | Who’s Responsible for Collecting? (Local Program or National Evaluator) | Examples of Possible Data Elements |
| --- | --- | --- | --- |
| Case Study | An in-depth community-based study that collects primarily qualitative data (e.g., through face-to-face interviews, focus groups) from management, partners, recipients, and other key stakeholders to assess lessons learned on critical aspects of program development | National evaluator would conduct annual visits to selected sites, with local programs participating in recruitment for interviews and focus groups | Lessons learned on each aspect of program development Barriers and facilitators to completion of program objectives Quality of local partnerships Extent to which CNP has conducted community-based participatory research Key stakeholder perceptions of program successes |
| Survey instruments | Standardized instruments developed specifically for CNP to capture an important aspect of the program. An example would be to administer an instrument to local partners that measures their satisfaction with the CNP, their level of involvement, and the degree to which synergy has been created | Developed and administered by the national evaluator with guidance from the EAC | Data elements to be captured would depend on the evaluation question to be addressed. The method and data collection strategy would need to be developed for each topic to be studied. |

### 2.6	Next Steps

As previously described, the work completed to date only focuses on Phases I and II of the CNP.  The evaluation plan presented here is comprehensive in scope and will need to be refined once the CNPs have received their awards.  At that point, three major steps will need to be taken by the national evaluator.  First, the evaluator will need to meet with key stakeholders of the national evaluation plan and review the draft CNP conceptual framework.  Using input from these stakeholders, perhaps through the development of an EAC, the framework can then be refined and distributed for additional review by community partners working with each of the local CNPs.  The evaluator should plan to work with NCI to determine the extent of review and input desired from the various groups of stakeholders who will be interested in the outcomes and then establish a process to accommodate their involvement.

Second, as the framework is being revised, the evaluator should revise the evaluation planning matrix (see Appendix A) to incorporate Phase III into the eventual plan.  During this process, it will be important for NCI and the EAC (or similar entity) to state the overall goals of the evaluation.  If the EAC determines that the focus of the evaluation should be on measuring health outcomes, for example, this will have great implications on what types of methodologies and data collection strategies should be used in the national evaluation.  A process similar to the one followed to date could be used to engage NCI stakeholders in first specifying what they see as the outcomes of each objective and then working to provide overarching goals or purposes for the national evaluation.  This input could be incorporated into a revised evaluation planning matrix and comprehensive plan for data collection and analysis.  The complete matrix could then be shared with the local CNP for review and comment on the priorities to address through the evaluation plan and their role in ongoing data collection and analysis.

Third, once the evaluation planning matrix is revised and close to finalized, work can then be done to identify the specific data sources to be used in the national evaluation.  We have begun to identify data sources and methods for Phases I and II in this report (see Exhibit 7) but, as noted, until the overarching purposes and goals of the national evaluation are agreed upon, these aspects of the plan cannot be finalized.  Therefore, the evaluator will need to work with NCI and others to prioritize the evaluation measures of greatest concern and identify the most cost efficient and feasible data sources to develop and implement to comprehensively assess CNP achievements.

## References

Advisory Board International Heart Health Conference.  1992.  The Victoria Declaration on Heart Health. Victoria, British Columbia, Canada: British Columbia Ministry of Health.

American Cancer Society (ACS).  2003.  Cancer Facts & Figures 2003.  Atlanta, GA: American Cancer Society.

Aziz, N.M., and J.H. Rowland.  2003.  “Trends and Advances in Cancer Survivorship Research:  Challenge and Opportunity.”  Seminars in Radiation Oncology 13:248-266.

Bandura, A.  2001.  “Social Cognitive Theory:  An Agentic Perspective.”  Annual Review of Psychology 52:1-26.

Boyce, W.F.  2001.  “Disadvantaged Persons’ Participation in Health Promotion Projects:  Some Structural Dimensions.”  Social Science & Medicine 52(10):1551-1564.

Brinkerhoff, J.M.  2002.  “Assessing and Improving Partnership Relationships and Outcomes:  A Proposed Framework.”  Evaluation and Program Planning 25:215-231.

Bronfenbrenner, U.  1979.  The Ecology of Human Development.  Cambridge, MA:  Harvard University Press.

Bronfenbrenner, U.  1990.  The Ecology of Human Development:  Experiments by Nature and Design.  Cambridge, MA:  Harvard University Press.

Butterfoss, F.D., R.M. Goodman, and A. Wanderman.  1993.  “Community Coalitions for Prevention and Health Promotion.”  Health Education Research 8:315-330.

Centers for Disease Control and Prevention.  1999.  “Framework for Program Evaluation in Public Health.”  Morbidity and Mortality Weekly Report 48(RR11):1-40.

Dalton, J.H., M.J. Elias, and A. Wandersman.  2001.  Community Psychology:  Linking Individuals and Communities, pp. 60-86.  Stamford, CT:  Thomson Learning.

Farquhar, J.W.  1978.  The American Way of Life Need Not Be Hazardous to Your Health. New York, NY: WW Norton & Co.

Florin, P., R. Mitchell, and J. Stevenson.  1993.  “Identifying Training and Technical Assistance Needs in Coalitions:  A Developmental Approach.”  Health Education Research Theory and Practice 8:417-432.

Gergen, K.J., and M.M. Gergen.  1991.  “From Theory to Reflexivity in Research Practice.”  In Research and Reflexivity, F. Steier, ed.  Newbury Park:  Sage Publications.

Gielen, A.C., and E.M. McDonald.  1997.  “Chapter 17:  The Procede-Proceed Planning Model.”  In Health Behavior and Health Education:  Theory, Research, and Practice, 2nd edition, K. Glanz, F.M. Lewis, and B. Rimer, eds., pp. 359-383.  San Francisco, CA:  Jossey-Bass Publications.

Glanz, K., F.M. Lewis, and B.K. Rimer.  1997.  Health Behavior and Health Education: Theory, Research, and Practice, 2nd edition.  San Francisco, CA: Jossey-Bass.

Green, L.W., and M.W. Krueter.  1991.  “Chapter 5:  Educational and Organizational Diagnosis:  Factors Affecting Health-Related Behavior and Environments.”  In Health Promotion Planning, 2nd edition.  Mountain View:  Mayfield Publishing Company.

Green, L.W., M.A. George, M. Daniel, C.J. Frankish, C.P. Herber, W.R. Bowie, and M. O’Neill.  1995.  “Study of Participatory Research in Health Promotion:  Review and Recommendations for the Development of Participatory Research in Health Promotion in Canada.”  Vancouver, British Columbia:  Royal Society of Canada.

Greene, J.C.  2000.  “Challenges in Practicing Deliberative Democratic Evaluation.”  New Directions from Evaluation, 85:13-26.

Hays, C.E., S.P. Hays, J.O. DeVille, and P.F. Mulhall.  2000.  “Capacity for Effectiveness:  The Relationship between Coalition Structure and Community Impact.”  Evaluation and Program Planning 23(3):373-379.

Himmelman, A.T.  2001.  “On Coalitions and the Transformation of Power Relations: Collaborative Betterment and Collaborative Empowerment.”  American Journal of Community Psychology 29(2):277-284.

Israel, B.A., A.J. Schulz, E.A. Parker, and A.B. Becker.  1998.  “Review of Community-Based Research:  Assessing Partnership Approaches to Improve Public Health.”  Annual Review of Public Health 19:173-202.

Israel, B.A., A.J. Schulz, E.A. Parker, A.B. Becker, A.J. Allen, and J.R. Guzman.  2003.  “Critical Issues in Developing and Following Community Based Participatory Research Principles.”  In Community Based Participatory Research for Health, M. Minkler and N. Wallerstein, eds., pp. 53-76.  California:  Jossey-Bass.

Lasker, R.D., and E.S. Weiss.  2003.  “Broadening Participation in Community Problem Solving:  A Multidisciplinary Model to Support Collaborative Practice and Research.”  Journal of Urban Health:  Bulletin of the New York Academy of Medicine 80(1):14-60.

Mathie, A., and J. Greene.  1997.  “Stakeholder Participation in Evaluation:  How Important is Diversity?”  Evaluation & Program Planning 20(3):279-85.

McLeroy, K.R., D. Bibeau, A. Steckler, and K. Glanz.  1988.  “An Ecological Perspective on Health Promotion Programs.”  Health Education Quarterly 15(4):351-377.

Morgan, G.  1983.  “Research Strategies:  Modes of Engagement.”  In Beyond Method: Strategies for Social Research, pp. 11-22. Beverly Hills: Sage Publications.

National Institute of Health, National Cancer Institute (NIH/NCI).  2001.  Voices of a Broken System:  Real People, Real Problems. President’s Cancer Panel.  Report of the Chairman, 2000-2001.  Bethesda, MD:  National Institute of Health, National Cancer Institute.  <http://156.40.135.142:8080/webisodes/pcpvideo/voices_files/PDFfiles/ PCPbook.pdf>.

Nichols, L.  2002.  “Participatory Program Planning Including Program Participants and Evaluators.”  Evaluation & Program Planning 25:1-14.

Papineau, D., and M.C. Kiely.  1996.  “Participatory Evaluation in a Community Organization:  Fostering Stakeholder Empowerment and Utilization.”  Evaluation & Program Planning 19(1):79-93.

Patton, M.A.  1990.  Qualitative Evaluation and Research Methods.  California:  Sage Publications.

Patton, M.Q.  1997.  Utilization-Focused Evaluation:  The New Century Text (Edition 3).  California:  Sage Publications.

Pervin, L.A.  1968.  “Performance and Satisfaction as a Function of Individual-Environment Fit.”  Psychological Bulletin 69:56-68.

Reason, P.  1988.  Human Inquiry in Action.  Newbury Park:  Sage Publications.

Roussos, S.T., and S.B. Fawcett.  2000.  “A Review of Collaborative Partnerships as a Strategy for Improving Community Health.”  Annual Review of Public Health 21:369-402.

Schulz, A.J., B.A. Israel, and P. Lantz.  2003.  “Instrument for Evaluating Dimensions of Group Dynamics within Community-Based Participatory Research Partnerships.” Evaluation and Program Planning 26(3):249-262.

Schulz, A.J., B.A. Israel, E.A. Parker, M. Lockett, Y.R. Hill, and R. Wills.  2003.  “Engaging Women in Community Participatory Research for Health:  The East Side Village Health Worker Partnership.”  In Community Based Participatory Research for Health, M. Minkler and N. Wallerstein, eds., pp. 293-315.  California:  Jossey-Bass.

Schulz, A.J., B.A. Israel, S.M. Selig, and I.S. Bayer.  1998.  “Development and Implementation of Principles for Community-Based Research in Public Health.”  In Research Strategies for Community Practice, R.H. MacNair, ed., pp. 83-110.  NY:  Haworth Press.

Small, S.A.  1995.  “Action-Oriented Research: Models and Methods.”  Journal of Marriage and the Family 57:941-955.

Springett, J.  2003.  “Issues in Participatory Evaluation.”  In Community Based Participatory Research for Health, M. Minkler and N. Wallerstein, eds., pp. 263-287.  California:  Jossey-Bass.

U.S. Department of Health and Human Services (USDHHS), Public Health Service, National Cancer Institute.  125th National Cancer Advisory Board, Summary of Meeting, February 11-12, 2003.  Bethesda, MD:  National Institutes of Health.  <http://deainfo.nci.nih.gov/ADVISORY/ncab/125_0203/11feb03mins.pdf>.

U.S. Department of Health and Human Services (USDHHS).  March 2004.  Making Cancer Health Disparities History.  Report of the Trans-HHS Cancer Health Disparities Progress Review Group.  <http://www.chdprg.omhrc.gov/pdf/chdprg.pdf>.

Wallerstein, N.  1999.  “Power Between Evaluator and Community:  Research Relationships within New Mexico’s Healthier Communities.”  Social Science & Medicine 49(1):39-53.

Wandersman, A.  2003.  “Community Science:  Bridging the Gap between Science and Practice with Community-Centered Models.”  American Journal of Community Psychology 31(3/4):227-242.

# Appendix A:
National Cancer Institute’s Community Networks Program Evaluation Matrix

National Cancer Institute’s Community Networks Program Evaluation Matrix

| Phase I Goal: Develop and increase capacity building to support community-based participatory education, research, and training to reduce cancer disparities (Years 1–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs/Products | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| I.1 Develop core organizational infrastructure for local Community Network Program (CNP). | - Hire and maintain required staff: - Principal Investigator (10%) - Project Manager (100%) - 2–3 Staff (100%) - Research Coordinator (20%) - Policy Analyst (20%) - Program Evaluator (20%) - Develop required advisory bodies: - Project Steering Committee - Regional Advisory Committee - Community-based Advisory Group - Operationalize roles to orient and train community partnership members. - Develop an Implementation Plan for the Project. - Provide needed technical assistance (e.g., logic models, grant writing, evaluation) for local Project staff. - Collaborate with NCI Project Director and National Evaluator to develop “core program evaluation data elements” (RFA: 9). | - Organizational chart - Implementation plan - CNP database - Annual progress reports - Additional reports as specified by NCI Program Director - Written communications (e.g., e-mail, memos, minutes of meetings) | - Leadership style of Principal Investigator - Staff of multidisciplinary professionals to implement program hired and maintained as required (CP: 9, 12) - CNP staffing (% time and position) (CNP: 13) - Composition of Project Steering Committee met - Size and representativeness of the Community-based Advisory Group (role and responsibility) - Number and frequency of meetings (RFA: 9) - CNP office space (square footage per staff) (CNP: 13) - Institutional resources provided (e.g., lower indirect cost, waiving indirect cost for pilots) New organizational structures are established (CP: 5) | Met organizational infrastructure requirement to transition to Phase II (CP: 12) (RFA: 6, 14) | Prior funding history (initial and continuation proposals) CNP grant applications Implementation plans Annual progress reports (RFA: 9) Grant budget and expenditures Semiannual meeting with CRCHD Director agenda and minutes Summit Conference proceedings Program Monitoring System/CNP Database (consisting of data elements as agreed upon by NCI Program Director, CNPs, and the Evaluator) |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase I Goal: Develop and increase capacity building to support community-based participatory education, research, and training to reduce cancer disparities (Years 1–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs/Products | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
|  | - Communicate progress toward benchmarks. - Attend regular Project meetings convened by NCI: - Annual Cancer Disparities Summit (up to 8 conference participants per CNP) - PI meetings with CRCHD Director (semiannual) |  | - Ability to develop infrastructure (CP: 3) - Number, role, and characteristics of individuals sponsored for Annual Cancer Disparities Summit Conference (CP: 12) |  | Criteria for determining “quality” of the Implementation Plan |
| I.2 Develop partnerships with communities experiencing cancer disparities and organizations that can aid in reducing cancer disparities. | - Assess existing cancer control resources for community champions (i.e., survivors), such as: - Lay health workers, community-level organizations (e.g., health services, education outreach groups, faith-based groups, coalitions) (CP: 9) - Primary prevention providers (centers) and programs (e.g., smoking cessation and hepatitis vaccination programs) (CP:9), cessation and hepatitis vaccination programs (CP: 9) | Listing of cancer control programs, partnerships, and providers for each focus area (e.g., primary and secondary prevention, diagnosis and treatment, survivorship, policy) Matrix of community partners by focus areas Memoranda of Understanding (MOU) | - Number and type of MOAs with roles and responsibilities specified (RFA: 3) - Number and type of partnership activities (level of involvement) - Total number of cancer control activities (CP: 13) - Total number of interventions developed (CP: 13) - Quality of partnerships with communities (CP: 3) - CNP budget allocation provided directly to community | - Met partnership requirement to move to Phase II - Increased linkages between partners, including improved communication, coordination, networking, etc. - Effectiveness of cancer awareness activities (CP: 12) - Increased leveraging/sharing of funds among involved organizations | - Survey of key leaders of the organizations of interest - Program Monitoring System/CNP Database - Partnership and MOAs at baseline and benchmarks - Grantees’ Phase II Implementation Plan - Community capacity scale |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase I Goal: Develop and increase capacity building to support community-based participatory education, research, and training to reduce cancer disparities (Years 1–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs/Products | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| I.2 Develop partnerships with communities experiencing cancer disparities and organizations that can aid in reducing cancer disparities. | - Secondary prevention programs (screening/early detection providers [centers] and programs) (CP: 9, 10), NCI-funded research institutions (CP: 9), cancer research organization and/or cancer treatment facilities (e.g., community hospitals) (CP: 9), diagnosis and treatment facilities (providers). Phase II (CP: 12) (RFA: 6), national cancer prevention and control organizations (e.g., ACS); other governmental agencies (e.g., CDC, HRSA, CMMS) (14) - Determine gaps and needs. - Develop and maintain partnerships. - Implement activities and interventions. | Memoranda of Agreement (MOA) |  |  | - Inventory of existing cancer programs, projects, providers in the identified communities Committee and group minutes and attendance rosters |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase I Goal: Develop and increase capacity building to support community-based participatory education, research, and training to reduce cancer disparities (Years 1–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs/Products | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| I.3 Have at least four collaborations with NCI Centers/ Divisions/ Offices. | - a. Establish projects with different Office, Centers, Divisions of NCI. - b. Develop objectives and evaluation strategy for each project | Findings from evaluation of each project | # and type of activities with NCI groups Perception among NCI Project Officers of evaluation of CNP role - Number and types of projects offered by NCI. Number and types of projects facilitated by CNP | - Increase in collaborations among NCI entities and local CNP |  |
| I.4 Increase the utilization of beneficial interventions to reduce disparities in the community. | - Determine the best strategies for collaboration to meet Project objectives. - Establish mandated collaboration with Cancer Information Service (CIS) partnership programs. - Develop at least three additional NCI collaborations, through guidance from the NCI Project Officers. - Implement the collaborative projects. | - Public Service Announcements - Newsletters (CP: 13) - Videos (CP: 13) Awards for presentation (CP: 13) - Addresses of Web sites developed (CP: 13) | - Number and type of activities (e.g., health fairs, annual events, ACS events) - Number and type of community education materials developed (language, community/ individuals targeted) (CPN: 13) | - Increase in collaborations across local programs/ partners Ultimate changes in behavior as specified for Phase III | - Program Monitoring System/CNP Database |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase I Goal: Develop and increase capacity building to support community-based participatory education, research, and training to reduce cancer disparities (Years 1–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs/Products | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| I.5 Obtain non-CRCHD funding for community-based education and training activities directed at reducing cancer disparities. | - Identify unmet cancer control needs in the communities of interest. - Assess funding needs and available resources (local, state, private, public) (CP: 10) - Develop and submit proposals for funding. - Leverage in-kind contributions of space, staff support, materials, etc. | Matrix of the type, amount, and source of funding for cancer control in general and cancer disparities in particular | Number and type of proposals submitted - Proportion of applications won/lost - Assessment of costs and contributions made by sources other than NCI | Increase in non-CRCHD funding (CP: 2) | Award notices State and local funding policies Annual reports and other official communication from Foundations and other funding sources Program Monitoring System/CNP Database |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase I Goal: Develop and increase capacity building to support community-based participatory education, research, and training to reduce cancer disparities (Years 1–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs/Products | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| I.6 NCI to facilitate and support local CNP development | - Work with Projects and National Evaluator to develop “core program evaluation data elements” (RFA: 9). - Assess Project’s achievements to determine if Phase I benchmarks have been met. - Provide ongoing technical assistance (TA) to CNPs. - Identify problems with CNPs that are behind in meeting benchmarks and address deficiencies.. - Organize regular meetings with CNPs: - Annual Cancer Disparities Summit (up to 8 conference participants per CNP) - PI Meetings with CRCHD Director (semiannual) f. Assess with which NCI entities collaboration is feasible and facilitate collaboration between local CNPs and any three NCI entities. | Tools for effectively providing TA to local CNPs | - Amount of TA requested/ received from NCI/CIS Number and types of NCI-sponsored collaborations (CP: 13) | Quality of collaborations with other NCI Centers/Divisions/Offices System change (e.g., geographic and appointment scheduling accessibility) (CP: 3) | Program Monitoring System/CNP Database Interviews with Principal Investigators |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase II Goal: Create community-based research and training programs to reduce cancer disparities (Years 2–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| II.1 Develop cancer disparities research that focuses on the spectrum of research issues necessary to reduce cancer disparities. | - Collect and review baseline data to educate and raise awareness about cancer disparities in the communities, such as - prevalence/incidence of cancer by type, sex, and age; - stage of cancer at diagnosis; - screening behavior patterns by cancer type; - follow-up rates from abnormal screenings; and - treatment utilization practices by cancer type. - Prioritize community cancer control needs. - Determine efficient use of resources to address needs. - Develop participatory community-based research proposals. - Conduct research to identify cancer control-related policies. | Matrix of Health Disparities Research - Report number of disparity research areas addressed - Report type of disparity research areas addressed - Report type of cancers targeted (CP: 14) - Report priority needs to be addressed Community Cancer Profile | Number of research studies proposed and completed Level of involvement of priority populations in developing the research Fidelity of the research plan to what was identified as gaps in understanding and what was ultimately studied Increased understanding of the issues impacting cancer control among disparate populations | Research findings to support new evidence-based cancer control interventions, policies, etc., to address findings from research Translation of research to practice | Hospital (e.g., ER, physician offices) and clinic data BRFSS Community health surveys Program Monitoring System/CNP Database |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase II Goal: Create community-based research and training programs to reduce cancer disparities (Years 2–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities (Organize by perspective: CNP Project Activities, CNP Evaluation Team, NCI-CNP Program Director) | Outputs | Process Outcomes (Formative measures that assess how well activities are being accomplished) | Impact Outcomes (Measures the extent to which the activities have resulted in system, individual, or policy change) | Possible Data Sources |
| II.2 Train researchers, particularly those from racial/ethnic minority and underserved populations, in community-based participatory intervention research to reduce cancer disparities. | - Develop and outline training procedures (CP: 10). - Recruit junior- and senior-(?) level researchers for training program (CP: 10). - Conduct trainings. - Develop mentoring program between junior and senior researchers. | Training curriculum (CP: 14) Training workshops conducted | - Number of those recruited for trainings Increase in provider knowledge about recommendations for care Increase in provider knowledge about the barriers/challenges related to health care services in the community Increase in providers who state they are dedicated to serving disparate populations | Increase in minority/ underserved community-based cancer control practitioners and researchers Increase in minority recruits to medical and health professions in general Change in provider practices - Extended office hours - Mobile/outreach services - Doctor–patient communication strategies Increase in cultural competency of trained providers | Program Monitoring System/CNP Database Pre-training survey/interview Post-training survey/interview Clinic observations |

(continued)

National Cancer Institute’s Community Networks Program Evaluation Matrix (continued)

| Phase II Goal: Create community-based research and training programs to reduce cancer disparities (Years 2–5) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Objectives | Activities | Outputs | Process Outcomes | Impact Outcomes | Possible Data Sources |
| II.3 Develop pilot projects in community-based participatory disparities research (option to fund up to four pilot projects per year). | - Develop criteria for pilot project (e.g., resource). - Prepare a request for proposal document for distribution. - Collaborate and pilot projects of the Community Network Program (CNP) sites (CP: 10). - Determine the focus of the pilot project (e.g., accessibility, follow-up, treatment). - Outline the goals of the pilot project. | Number of pilot project submitted by CNPs Number of papers published/in press based on work of Community Networks Number of talks/ presentations of CNP work at professional meetings % CNPs utilizing evidence-based practice (Community Health Guidelines) | Fidelity of pilot projects to planned events Increase in knowledge of facilities that conduct screenings for free or at low cost to decrease cost barrier Increase in knowledge about effective outreach strategies Increase in cancer awareness and primary prevention (e.g., diet, exercise, smoking cessation) Increase in cancer awareness and secondary prevention (e.g., screening, symptoms) Increase in knowledge related to cancer risk factors | - Increase in development and collaboration of new and existing community-based cancer control programs - Improved access to and utilization of beneficial cancer interventions (CP: 2) Increase in resources (e.g., support groups) for cancer survivors Increase in funding level from other sources for ongoing work with disparate populations | Pilot project reports Program Monitoring System/CNP Database Survey data collected during project (will depend on what’s done) |
| II.4 NCI to facilitate and support local CNP efforts | - Review the proposals for pilot projects. ### Select/notify pilot project awardees. - Award funding for pilot projects. - Monitor pilot projects. - Provide ongoing TA to local programs. - Identify problems with CNPs that are behind in meeting benchmarks and address deficiencies. | - Number of pilot projects approved by NCI - Number of pilot projects funded and completed (with written reports) each year (CP: 14) | Improved knowledge among CNPs of NCI expectations | Improved ability of CNPs to successfully apply for pilot project funding | Program Monitoring System/CNP Database |