Southern Sierra Prototype Area

Fire Program Analysis (FPA) System

Preparedness Module

Prototype Charter

December 1, 2003

TABLE OF CONTENTS

1.	Prototype Overview	3

1.1	Identification	3

1.2	Purpose / Business Need / Scope	3

1.3	Prototype Objectives	5

1.4	Partnerships	5

1.5	Key References	5

1.6         Terminology	6

2.	Project Approach Section	6

2.1	Project Deliverables and Quality Objectives	6

2.2	Project Organization and Responsibilities	6

Insert Organization Chart	7

Prototype Steering Committee	7

Prototype Team	8

Advisors	8

Support Services	8

2.3	Reporting, Oversight, & Review	9

Core Process Workflows	9

2.4	Communications	9

2.5         Protype Schedule	10

2.6	Project Effort/Cost Estimate	11

FY 2003 Costs:	Error! Bookmark not defined.

FY 2004 Costs:	11

2.6a       Mechanism for Transferring Funds…………………………………………...10

2.7	Prototype Benefits	11

3.	Approval Section	12

# 1.	Prototype Overview

## 1.1	Identification

This project is to be known as the Southern Sierra Fire Program Analysis (FPA) Prototype Project, also referred as the Southern Sierra prototype.  The FPA System Preparedness Module is an interagency project of the following wildland fire management agencies:

- Sequoia National Forest

- Bakersfield Field Office, BLM

- Sequoia and Kings Canyon National Parks

- Tule River Indian Tribe

- Pacific Region, BIA

## Purpose / Business Need / Scope

The purpose of creating FPA prototype project areas is to support and contribute to the development of the FPA system through:

- Providing subject matter expertise to be incorporated into the system design and function

- Contributing realistic test data sets

- Providing alpha and beta testing of system elements as they are designed

- Assessing the function and logic of the system as it generates results

- Assisting in creating business practices and procedures needed to implement FPA in an interdisciplinary and interagency framework

- Assist with development of FPA-Preparedness Module training material and initial presentations

## 1.3	Prototype Objectives

The goal of the Prototype effort is to assist the FPA development to produce policies, procedures and supporting application components that will be used by the five federal wildfire management agencies to conduct fire preparedness analysis and develop associated budgets within the context of the Fire Program Analysis System.

The overall objectives for the prototype are to participate and advise in the development of the FPA Preparedness module. Specific objectives are:

- Develop interagency planning partnerships.

- Develop or refine resource management objectives relative to fire, and the full suite of fire management objectives, constraints and restrictions.

- Develop and refine the required data inputs for the preparedness model.

- Test and provide feedback on interim and final products.

- Provide a reality check on model outputs, both costs and fire resources.

- Work closely with the FPA Team and the Design and Build contractor.

- Participate as subject matter experts.

- Periodically travel to the contractors work site for consultations.

- Assist in developing training materials based on lessons learned

## 1.4	Partnerships

The following partnership team will provide executive level oversight.  The members of this team are Fire Directors or designee from the following agencies:

- USDA Forest Service

- DOI Bureau Of Land Management

- DOI National Park Service

- DOI Fish & Wildlife Service

- DOI Bureau of Indian Affairs

- State and Local government agencies

- FPA-PM Development Team

- FPA-PM Implementation Coordination Group

## Key References

References may be found at HTTP//fpa.nifc.gov.  Following are significant documents guiding the FPA process:

- 1995 Federal Wildland Fire Policy

- 2001 Update to the Federal Wildland Fire Policy

- National Fire Plan

- A Collaborative Approach for Reducing Wildland Fire Risks to Communities and the Environment, 10-Year Comprehensive Strategy: Implementation Plan (a.k.a. 10-Year Comprehensive Strategy)

- Developing an Interagency, Landscape-scale Fire Planning Analysis and Budget Tool (a.k.a. “The Hubbard Report”)

## 1.6	Terminology

The team will use terms consistent with those defined in the Glossary of Wildland Fire Terminology, published by the National Wildfire Coordinating Group (NWCG).

# 2.	Project Approach Section

The Fire Planning Unit (see attached map) will include all the Sequoia and Kings Canyon National Parks (KNP), the Bakersfield Field Office, Bureau of land Management (BBD), Sequoia National Forest including the Giant Sequoia National Monument (SQF) and the Tule River Indian Reservation (TIA).  The Pacific Region BIA (PAA) is responsible for funding the TIA, and is also a partner agency.  These five agencies (KNP, BBD, SQF, TIA and PAA) will be the prototype “partner” agencies for testing purposes.

The other agencies that will be viewed as “cooperators” for testing purposes will be portions of the Sierra and Inyo National Forests (SNF & INF), California Desert District, Bureau of Land Management (CDD), Kern County Fire Department (KRN), and the California Department of Forestry and Fire Protection, Tulare Unit (TUU) and Fresno/Kings Units (FKU).  Additional cooperators may become involved as the process unfolds.  Aircraft resources from Fox Field Air Attack Base (Angeles NF) will be utilized.

## 2.1	Project Deliverables and Quality Objectives

Primary deliverables from the project will include:

- alpha and beta test evaluations;

- review of and comments on white papers and other documents related to system design and development;

- participation in periodic prototype symposiums.

## 2.2	Project Organization and Responsibilities

### Southern Sierra Organization Chart

Prototype Steering Committee

Steering committee responsibilities:

- Provide direction regarding fire preparedness business strategy.

- Provide guidance on prototype business requirements

- Review project plans and deliverables especially business requirements.

- Help the Prototype Team make decisions regarding scope, time, quality and cost tradeoffs.

- Ensure that the deliverables of the project will meet the business needs of the sponsoring agencies.

- Establish dispute or conflict protocols.

The Prototype Steering Committee members include:

Aaron Gelobter, Fire Management Officer, SQF (Chair)

William Kaage, Fire Management Officer, KNP

Tony Sarzotti, Fire Management Officer, BBD

Shannon Alto, Fire Management Officer, TIA

Ron Recker,  Fire Management Officer, PAA

### Prototype Team

Members include representatives from participating agencies. This team is responsible for:

- Develop Prototype Charter and submit for approval.

- Establish fire preparedness planning and budgeting business process and procedures for all participating wildland fire management agencies.

- Coordinate with technical support groups, advisors and FPA liaison (Jeff Manley).

- Verify requirements for the new preparedness planning application system.

- Provide feedback on user interfaces, data structures and models to support preparedness planning.

- Test resulting application components to ensure they conform to business and system requirements.

- Train users.

- Present project information to peers, associates and managers.

- Successfully produce the prototype deliverables in a timely manner and within budget.

Prototype Team Members include but are not limited to:  Shannon Alto (TIA), Anne Birkholz (SSGIC), Bob Burnham (BLM), Aaron Gelobter (USFS), Bill Kaage (NPS), Ron Recker (BIA), Brian Rueger (TIA), Tony Sarzotti (BLM), and Diane Travis (USFS).

### Advisors

Advisors serve the Prototype Team providing periodic input on specialty subjects. Members may include:

- Liaisons from other fire business areas, e.g. Fire Operations, Fire Planning, Fuels, Prevention, Education, providing input for consideration of interfaces, shared data/resources and to coordinate planning.

- Subject Matter Experts in economics, GIS, research; science, etc. may be called upon periodically throughout the project.

- Liaison from States, Tribes and Federal Agencies.

Advisors include:  Liz Wright (USFS), Larry Hood (USFS), Steve Larrabee (BIA-NIFC), Bill Molumby (FWS), and Richard Smedley (NPS).

### Support Services

SSGIC Program – Data

Pat Lineback, Principal Investigator (NPS)

Anne Birkholz, SSGIC Program Manager (NPS)

Orlando Raez, GIS Specialist (NPS)

GIS Program

Karen Folger, Park Service (KNP)

Heidi Hosler, Forest Service (SQF)

Larry Vredenburgh, Bureau of Land Management (BBD)

(Acting) Fire Ecologist

Tony Caprio, Park Service (KNP)

Fire Planning

Diane Travis (SQF), serves as the prototype “Fire Planner”

## 2.3	Reporting, Oversight, & Review

Reporting, oversight and review will ensure that the prototype stays within scope, on budget and on time.

Oversight is provided by the FPA-PM Core Team.

### Core Process Workflows

The Steering Committee will be responsible for assembling data as needed for the Preparedness Module.  An identified “fire planner”, will facilitate the gathering of data from all the agencies and input it into the Preparedness Module.  The fire planner is responsible for tasking agency planners with data needs and due dates for timely implementation of prototype testing.  The fire planner will document processes used in developing the inputs for the Preparedness Module.

The fire planner has the responsibility of informing the Prototype Steering Committee of discrepancies of data between agencies, discrepancies in assumptions and gaps in data that may lead to inconsistent outputs.

The Prototype Steering Committee has the responsibility of providing oversight to the fire planner in developing assumptions that best represents “real world” fire operations for their individual agency and as a collective unit.

The fire planner will report directly to FPA liaison on completion of data sets.

The fire planner will work directly with the FPA liaison to ensure that the prototype stays within scope and on time.

## 2.4	Communications

Prototype Team

The following mailing list of the Southern Sierra Prototype Area participants has been sent out to the participants including the FPA core team liaison (Jeff Manly).  Communication is encouraged within the prototype team to unearth issues in a timely manner and to provide information when needed.

#### Name			Agency			Phone Number		Email Address

Shannon Alto		Tule River Tribe		559-784-0124		rezdv10@aol.com

Bob Burnham		BLM consultant					ertech@covad.net

Aaron Gelobter		USFS, Sequoia NF	559-784-1500 x1121	agelobter@fs.fed.us

Bill Kaage		NPS, SEKI		559-565-3160		bill_kaage@nps.gov

Pat Lineback		NPS, SEKI		559-565-3725		pat_lineback@nps.gov

Jeff Manley		NPS, NIFC		208-947-3778		jeff_manley@nps.gov

Bill Molumby		FWS			619-669-6651	bill_molumby@r1.fws.gov

Ron Recker		BIA			916-978-6065		mail373002@pop.net

Brian Rueger		Tule River Res.		559-781-4271		prueger@ocsnet.net

Tony Sarzotti		BLM, Bakersfield	661 391-6096		asarzott@ca.blm.gov

Diane Travis		USFS, Sequoia		559-784-1500 x1122	dhtravis@fs.fed.us

Anne Birkholz		SSGIC			559-565-3704		anne_birkholz@nps.gov

Richard Smedley		NPS					Richard_smedley@nps.gov

Steve Larrabee		BIA-NIFC		505-842-3870		steve_larrabee@nifc.gov

Elizabeth Wright		USFS, Region 5		619-445-6235		ewright@fs.fed.us

Larry Hood		USFS, Region 5		530-252-6633		lhood@fs.fed.us

Brent Skaggs		USFS, Sequoia NF	559-784-1500 x1120	bskaggs@fs.fed.us

## 2.5  Prototype Schedule

Timelines for Prototype activities:

October 2003 – June 2004

- Enter data.

- Test iterations.

- Complete and analyze outputs.

July – September 2004

- Finalize product

- Assist in preparing training materials and training the trainers from a “Lessons Learned” perspective.

*See Appendix A for Workplan details

## 2.6	Project Effort/Cost Estimate

One full time FPA “dedicated” fire planner position is required for the Southern Sierra prototype to function as the prototype coordinator/lead planner and primary contact.  The FPA-PM project will fund up to half of the planner’s salary to guarantee it is a dedicated position. Travel and miscellaneous costs related to the prototype area will be incurred by the participating agencies and have been included in the allocation.

### FY 2004 Costs:

- Salary:    	 $43,000.

- Travel:		 $12,000

- Miscellaneous: 	$5,000 per site (GIS, OT, small contracts, data, etc.)

- Total FY04 = $60,000

2.6a   Mechanism for Transferring Funds

FY04 funding from the FPA-PM is $60,000 for the Southern Sierra Prototype.  It has been agreed that each partner agency in this prototype effort may need some reimbursement of funds for the project workload.

Payments and Invoices

- Payment of $60,000 will be given to Sequoia and Kings National Parks as a depository for money transfer.

- The process for agencies to receive the money is as follows:

- To the Forest Service and to Bureau of Land Management.  Billing invoices shall be directly submitted through the NPS under the SSGIC Agreement (No. 855801002) Article VI.6.1.

- To the BIA.  Billing invoices shall be directly submitted through the NPS for standard procedures of transfer of money between NPS and BIA.

- To the Tule River Indian Tribe.  Billing invoices shall be directly submitted to BIA through standard procedures of transfer of money between tribal lands and BIA.  BIA will then submit billing invoices as described above.

C.  The commitment of reimbursing funds to agencies shall be authorized by unanimous approval by the steering committee as identified in section 2.2 of this document.

## 2.7	Prototype Benefits

Assist in design and development of the new national fire planning and budgeting system.  Help develop processes and standards for interagency collaborative wildland fire planning.  Help shape future policy and direction relating to wildland fire management.

# 3.	Approval Section

This charter is effective as of the date of signature. By signing, the signatories indicate their agreement and support of the project charter and their commitment to the project.

____________________________________	_______________

ARTHUR L. GAFFREY	Date

Forest Supervisor

USDA Forest Service

Sequoia National Forest

____________________________________	_______________

JOHN SKIBINSKI 		Date

Acting Field Office Manager

USDI Bureau of Land Management

Bakersfield Field Office

____________________________________	_______________

RICHARD MARTIN		Date

Park Superintendent

USDI National Park Service

Sequoia and Kings Canyon National Parks

____________________________________	_______________

NEIL PEYRON		Date

Chairman

Tule River Tribal Council

____________________________________	_______________

CLAY GREGORY		Date

Acting Regional Director

USDI  Bureau of Indian Affairs

Pacific Region

# Text boxes

Southern Sierra Prototype

Steering Committee

Agency Administrator

Prototype Team

Prototype Lead

Support

List Names

Etc.