“Lessons Learned from the ASAP Centers” Panel:

The purpose of this session is to review some of the lessons we have learned in the ASAP program that are useful to keep in mind.  Some of the lessons may seem obvious (and the panel will add concrete examples) and some of the lessons took several years to learn.

- Highlights included:

Management and Leadership

- Creating a truly multidisciplinary Center in a university environment is often perceived as an “unnatural act”.  But, organizing a multidisciplinary Center in “stovepipes” will not work; the organizational emphasis must be on integration (of codes, theory and experiment, and for PSAAP even more on V&V and UQ).

- Defining a single, overarching problem is needed for conducting research across different university departments because managers can ask what has been done lately for the overarching problem.

- Central resource allocation (versus distributing funds to individual faculty accounts) keeps attention focused on solving the overarching problem for the center. (The Golden Rule strongly applies.)

- Open communication is essential. It is important to include all project personnel in the communication chain.

- Having well defined goals and clear responsibility for their leadership is very important.

Staffing

- There can be an inherent disconnect between university scientists who are theoretically oriented and the Center’s need to develop full-system simulation code.  This must be overcome if the Center is to succeed; annual strategic planning involving all key Center personnel is one way to address these different perspectives.

- Be wary of involving “loner” faculty members (however brilliant they may be) because the ultimate success of the Center will depend on the success of the entire personnel team.

- Post docs and grad students do not typically work on the time scale of a five-year or ten- year program.  Therefore, it is important to have long term staffing so they can train the incoming students and post docs.  This can be a difficult balancing act.

- Over time some faculty, and/or subcontractors, may make less than expected contributions to the overarching problem.  As a result, tough decisions will have to be made by the Center Director.

- Full time staff such as Post docs and Research Assoc can be half or more of a Center’s staff for the type of work required by ASAP and PSAAP.

Balancing Science and Code Building

- Use V&V as a way to balance science and code building; V&V will help to identify what is critical to full-scale problem simulation.

- A roadmap for the overarching system identifying end-to-end simulations that the center will run over the next six to twelve months is one key way to focus on integration.

- Science and code development should take place under the same roof.  The difference between PSAAP and other university centers is that a code has to be delivered and science has to be brought into the code and brought in according to the software engineering framework of the Center.

Integration

- It is important to put the full system (problem) put together (even with less details initially) so that Center personnel wrestle early on with the science of integration. Integration goals are critical from day one.

- Weekly meetings of key Center personnel help to keep a focus on the next planned simulation and can serve as a catalyst for code and model integration.

- Allowing scientists to build special “research codes” is OK (to a point) because it builds in a level of science that can be used as a check against the overarching application.  But Center personnel should understand - from the outset - how such side efforts might be (or not) folded into the overarching application.

- Algorithms are important when coupling diverse codes.

Software Engineering

- The requirement for software quality assessment and engineering practices is non-negotiable.

- Establishing someone on the Center staff as the code architect is highly recommended.

- It is important to have a good software development process in place (and make it clear to those who want to work outside of it that it is not in their best interest).

Other Areas

- Storage of Center calculation/simulation data is a critical issue (and often a surprise when calculations produce terabytes of data).

- Because the Center will (hopefully) exist for five years the success of graduate students’ work should not be tied to Center deliverables (but can be associated with Center research-oriented tasks that are not on the critical path).

- Association with ASC Alliance Center programs led to many successful tenure track advancements for junior faculty during the ASAP phase of the program.

- It can be useful to figure out who is doing work at the DP labs comparable to the Center research and communicate via workshops and visits.

- It is important to see the interaction of the experimentalist with simulations – this produces insights for the simulations and also for the experimentalists.  (It also creates a “super” grad student who understands computation, software engineering, algorithms and the importance of experiments).

- Very difficult to perform V&V with historical data.

- Ties to outside communities for V&V can attract significant funding opportunities to extend core program.

- Annual reviews are a lot of work but are invaluable because they lead to self-examination and improved planning.