| FEMA-1786/1792-DR-LA Operation GUSTAV Louisiana JFO- 415 North 15th St. Baton Rouge, LA 70802 |  |
| --- | --- |

| Operations Section Geographic Operations | Date: September 15, 2008 | Time 2215 hrs. |
| --- | --- | --- |

| BRANCH 1 | Patrick L. Kidder Branch Director |
| --- | --- |

| Division A | Rick Kuss - Division Supervisor | Gail Tate |
| --- | --- | --- |
| Orleans |

Power – 0% Outage; minimal outages New Orleans East/Algiers

Generator - no issues

Political Temperament – Good, Gail Tate meets multiple times each day with the City’s Recovery Director; Gail and Rick Kuss are in constant contact with the Emergency Management Director.

Commodities - no issues – No PODs ; City distributing blue tarps Monday outside the Library DRC. The distribution is extremely slow. City commenced baggage repatriation program at the Dream Center on Monday, Sep 15.

FEMA Programs

- Individual Assistant – City establishing one DRC at the main library (219 Loyola, New Orleans). This site opened on Monday Sep 15. Early in the am approximately 40 people were waiting for the library to open up. 75% of those in line were evacuees from Texas.  The Library DRC hours to be from 0900 to 1800, City has identified an additional DRC site, the Cutoff Community Center, at 6600 Belgrade St. and is working with State and FEMA to inspect the location.  City has set a tentative Friday Sep 19 as the date to open this DRC. (The Cutoff Community Center DRC site may not be activated will update with more information)  City is establishing 6 information centers throughout the city and is looking for flyers and brochures to put in them. These sites will open Wednesday Sep 17.

- Public Assistant - PDAs are complete for the City of New Orleans

- Community Relations - Team in the field working at the DRC in the AM

Blue Roof Program – Blue Roof POC contacted Division personnel and this operation is currently at the main library DRC.  Most pressing issue was to get the DRC open.  CR was present as people arrived prior to the opening.  Many were from Texas; displaced by Ike.  Most pressing issue was to get the DRC open.  CR was present as people arrived prior to the opening.  Many were from Texas; displaced by Ike.

Parish President contacted today by: Gail Tate in constant contact with the Recovery Director, Dr. Blakely.  Rick Kuss and Gail Tate attend planning, tactical and Unified Command Group meetings at the City EOC.

Limiting factors: none

Other issues: Search and Rescue continues through regular 911. Road to Venetian Isle passable to the public. Floodgates are opened.

| Division A | Rick Kuss – Division Supervisor |
| --- | --- |
| St Bernard Parish |

# Power – 0% outage

# Generator - no issues

# Political Temperament - Good

# Commodities - no issues.

# FEMA Programs:

- Individual Assistance – IA Branch will not be supporting St Bernard Parish’s request for personnel to staff a phone bank in place of a DRC.

- Public Assistance – PDAs complete.

- Community Relations–No teams in the field.

- Blue Roof Program – Blue Roof POC contacted the Parish Emergency Management Director.  ROE Collection Center for St Bernard Parish will be at the St. Bernard Community Center.  Opening date will be determined Monday.

Parish President contacted today by: CR met Col Dysart.  The Parish President wants us to work through Col Dysart.

Limiting factors – Report from John Raham: There are still areas that have minimal flooding.

Other issues – John Raham St Bernard Ops Chief stated the St Bernard is in much better condition than expected. Good outlook with recovery in progress.

| Division B | Cindy Janacke- Divison Supervisor | Keala Hughes |
| --- | --- | --- |
| Jefferson Parish |

Power: 2% Outrage

Generators: May be requested by Parish through Web EOC due to lack of electricity due to storm surge from Hurricane Ike in the Jean Lafitte Area (including Crown Point and  Barataria) and Grand Isle.

Political Temperament: Good.

Commodities: Parish officials hope to reopen PODs tomorrow in Lafitte and Grand Isle area tomorrow. The Parish has requested and confirmed receipt of request with the state.

FEMA Programs:

- Individual Assistance – Standing down today due to dewatering of Grand Isle and Lafitte, which includes Crown Point and Barataria. No DRCs established in the parish, the state has the DRC requests. Can begin visiting both areas for assessments, if coordinated with the Jefferson Division Supervisor.

- Public Assistance – Standing down today due to dewatering of Grand Isle and Lafitte, which includes Crown Point and Barataria. Can begin visiting both areas for assessments, if coordinated with the Jefferson Division Supervisor.

- Community Relations – Standing down today due to dewatering of Grand Isle and Lafitte, which includes Crown Point and Barataria. Discussed CR activities with the parish to determine when teams can visit these areas damaged by Hurricane Ike. Will begin visiting both areas for outreach on 09/16/08, through coordination of the Jefferson Division Supervisor. The Parish as requested Community Relations to visit four hotels they are housing residents in to inform them of the registration process. Keala Hughes, IGA with the TRO, would check with Parish officials as to where CR should do outreach.  Hughes is also asking CR to assist evacuees in hotels with their FEMA registration.  Keala Hughes, IGA with the TRO checked with Parish officials as to where CR should do outreach.  Hughes is also asking CR to assist evacuees in hotels with their FEMA registration.

- Blue Roof – Right of Entry Collection Center opened today from 10am-5pm at the Westwego Library, 635 4th Street, Westwego, LA 70094. Parish President has requested two additional centers in the Grand Isle and Lafitte area. Working with USACE to gain approval on the two additional sites.

Limiting Factors:  Finding a method to register residents with out transportation for FEMA and other assistance to gain access to temporary housing The Parish has requested four DRCs and none have been scheduled to open

Parish President contacted today by: Met with the Parish President Broussard regarding his concerns of housing the residents of Grand Isle and the Lafitte area, which includes Crown Point and Barataria.  Parish President mentioned requesting a cruise ship.  Division Supervisor reiterated other housing solutions may be more viable. Begin with using Community Relations to encouraging people to register for FEMA assistance. Assessing damages of hotels in the area for housing eligible FEMA applicants until repairs are completed on homes. He was agreeable to the parish leasing generators for hotels only lacking electricity to result in housing residents. President Broussard views the cruise ship as ideal for the use of the neighboring coastal parishes damaged by Hurricane Ike and plans to ask for the support of other Parish Presidents and Mayors. A letter was sent to Governor Jindal requesting the cruise ship and there are ships are awaiting state inspection. Additional information is available on this issue through the Jefferson Parish Division Supervisor.

Met with Mayor Camardelle of Grand Isle, major concern is the power because it may not be restored to the island until 10/01/08. He noted the majority of the homes in the area are elevated approximately 15 feet on pilings; therefore structural damage may not be as critical as electricity restoration. Requested assistance with registering residents for FEMA assistance Residents will be allowed into the area tomorrow at 8am.

Met with Mayor Kerner of Lafitte, his major concerns are to house residents as there are approximately 500 homes damaged. The residents of this area do not have the financial resources to live away from this area. Residents are fishermen and need to be housed near Lafitte to support their households. He noted major concerns with returning PODs to the Jean Lafitte area, including Barataria and Crown Point and to Grand Isle. This area is under a boil order and residents were able to return to the area as of noon today. Pumps are prepositioned to assist with the dewatering of the area.

Councilmember Chris Roberts, his main concern was to get FEMA and other aid to the constituents in his community. He would like to see residents registered for FEMA under both Hurricane Gustav and Ike.

There was a Jefferson Parish meeting with several of the State, local and Federal entities available for Mayor Kerner and Mayor Camardelle to ask questions of these entities regarding assistance for the residents. In attendance were representatives from the Jefferson Parish Council, Senator Landrieu, Senator Vitter and Congressman Melancon’s office.

Other Comments: Shelters have been established for residents of Lafitte and the parish moved 101 of those residents from shelters into four area hotels as of 09/14/08. Parish hopes to have a DRC established soon in the area to begin registering the displaced residents. Many of these residents were evacuated via buses and have no transportation.

| Division B | Cindy Janacke - Division Supervisor |
| --- | --- |
| Paquemines Parish |

Power: 18% Outrage

Generators:  Most of the generators are not needed and are being pulled back.

Political Temperament: Parish officials are optimistic about stopping the flooding soon.  They have begun to assess the damage.  They have identified three levee breeches – two along the Myrtle Grove area near where the Gustav breech occurred and another near Port ala Hache.  They are still coordinating efforts to save cattle and other livestock trapped by the flood waters and have saved a few hundred. GOHSEP is coming to assess the levee breach today.

Commodities: The parish will open three PODs  - Davant, St. Patrick’s and the Boothville Volunteer Fire Dept.  The parish does not need additional commodities but has requested distribution assistance from the National Guard.  The Guard had issues getting to staff the POD due to having to travel on the river levee and the long delays that it occurred.  The parish will re-open the St. Patrick and Davant site tomorrow.

FEMA Programs: Some branch activities regarding FEMA’s Gustav recovery FEMA programs are suspended due to hurricane Ike.

- Individual Assistance –

- Public Assistance –

- Community Relations –  CR was at the Belle Chasse High School shelter today assisting the residents/

- Blue Roof –

Limiting Factors: The parish is still sandbagging at key spots in the parish along the non-federal levee system flood waters began to seep into the Conoco Phillips Refinery and the parish sandbagged parts of the perimeter roads. Hwy 23 is still impassable and completely closed to all traffic below Myrtle Grove.  The parish is allowing light and necessary traffic to drive along the river levee to the southern end of West Bank.  It does not appear that houses have flooded, although the parish has not been able to fully assess yet.  Schools in the lower part of the parish are closed tomorrow.

Parish President contacted today by: Liaison is embedded in the EOC and has daily, frequent contact with to President Nungesser. President is actively assisting to direct the flood fighting and animal rescue efforts. President Nungesser, Phil Truxillo, EOC Director, and the Sheriff, held a meeting with the EOC team at 0700 today.

| Division C | Jim Huff - Division Supervisor |
| --- | --- |
| St Johns Parish |

Power:  6% outrage

Generators:  No issues

Political Temperament: Very good toward FEMA and its program areas.

Commodities:  Parish has closed their POD site as most of the retail and commercial eateries/suppliers are back in business.  Two trailers for Tarp Commodities are still on a request to LA GOHSEP.  Tarps are needed to protect from further damage of rain caused by Hurricane Ike.

FEMA Programs:

- Individual Assistance – It has not been determine if a DRC location will be established in the Parish.  That decision will be made next week.

- Public Assistance – State and FEMA PDA Teams finished their assessments with Parish Applicants.  Teams still gathering review information.

- Community Relations – Team hit the localized flooded area today and visited neighborhoods and individual residents.  They handed out information on available programs that residents can apply for.

- Blue Roof – Sign up process went well and very well organized by USACE with local support from Parish Government and Sheriff’s Office. Reopened today at the Parish Government Complex in La Place location is central to Parish and was very well organized.

Limiting Factors: State Hwy 51 remains closed due to flooding Lakes Maurepaus and Pontchartrain remain high until the wind moves to a westerly and northerly direction.  Water level has decreased one foot in the last 24 hours.  High water continues to block Interstate 10 at the La Place exits.  Neighborhoods continue to have flooded streets as the flood water level is very slowly and gradually decreasing with the wind changing to the west.  Five subdivisions remain flooded with water over streets.  Many homes that suffered tree damage remain exposed as the blue roof teams are just starting the roofing program.

Parish President contacted today:  Met with Parish President and EOC Director today.  They still want the truck load of tarps that has been requested from LA GOHSEP delivered.  There is a definite need for residents with damaged roofs to protect from further rain damage.  Assessment of flooded homes and businesses is continuing.

Other Comments- Parish Government leaders have stated that by Monday 15 September 2008, 100% of Parish services will be on line.  Curfew was placed last night from 12 midnight to 0600hrs.  Approximately 25 homes outside of the protected levee system were severely flooded and about 150 homes had moderate flooding of up to 1 foot of water.

| Division C | Jim Huff – Division Supervisor |
| --- | --- |
| St James Parish |

Power:  0% Outrage

Generators:  No issues

Political Temperament:  Generally good toward FEMA Program areas.  Community Relations team members continue to increase visibility of FEMA and its available programs to the community which the local elected officials appreciate; having eyes and feet on the ground continues to make a difference.

Commodities:  None needed at this time

FEMA Programs:

Individual Assistance – DRC location lease in the old Lions Home (also used for Hurricane Katrina) is being negotiated by GSA. Potential opening tomorrow if lease agreement is worked out USDA and State of LA re-opened food stamp program today.

- Public Assistance – PDA Teams have finished assessments with Parish Applicants.  The EOC placed a request through WebEOC for a portable health clinic to replace the Parish Public Health Clinic that had its roof blown off last week during Hurricane Gustav.

- Community Relations – Team visiting neighborhoods today to speak to residents about available FEMA Program areas. Ops Div Supervisor states the DRC is still on hold until negotiations are complete

- Blue Roof – USACE re-opened program today with residents signing ROE forms.

Limiting Factors: Tarp Program was requested through WEBEOC but appears it hasn’t happened.  Many homes that suffered tree damage remain exposed as the blue roof teams are just starting the USACE roofing program

Parish President contacted today:  I spoke with Director of EOC today.  Tarp commodity is still badly needed.  Parish was not adversely affected by Hurricane Ike.  Parish should be back to normal operating procedures by Monday, 15Sep08.

Other Comments- None

| Division D | Robert Price – Division Supervisor |
| --- | --- |
| St. Charles Parish |

Power: 0% Outrage

Generators: No issues at this time

Political Temperament: Good

Commodities: There are no POD sites or commodity request outstanding

FEMA Programs:

- Individual Assistance – The contract has been signed for the DRC location.  The building owner is completing repairs for the site to open.

- Public Assistance – There is a kickoff meeting scheduled.

- Community Relations – There was a community relations team working in the Parish.

- Blue Roof – There is one site operational in the Parish at this time.  The Parish would like to consolidate the DRC and Blue Roof in one location.

Limiting Factors: None

Parish President contacted today by: I have a Perish contact (Susan Wilson) with whom I am in contact with on a daily basis.  Susan is coordinating efforts between the Parish President and FEMA.

Other Comments: The Parish is requesting PA assistance for hurricane IKE under category B.  This information has been submitted by the state regional coordinator.  The Parish has expended considerable resources in shoring up levees to prevent Parish flooding.

| Division D | Robert Price – Division Supervisor |
| --- | --- |
| Lafourche Parish |

Power: 21% Outrage

Generators:

Political Temperament: Moderate

Commodities:  Thibodaux and Golden Meadow sites were up and running today. The Thibodaux site was moved to.  Thibodaux site will close at the end of business today.  The Parish will have commodities at the Central Lafourche High School.  There will be no distribution from this site, and all commodities will be for school use.

FEMA Programs:

- Individual Assistance – The DRC opened today.

- Public Assistance – The kickoff meeting is scheduled for Friday.

- Community Relations – There was a community relations team working in the Parish.

- Blue Roof – There are 2 Blue Roof sites operational in the Parish.

Limiting Factors:

Parish President contacted today by: I have a Perish contact (Eric Buois) with whom I am in contact with on a daily basis.  Eric is coordinating efforts between the Parish President and FEMA.

Other Comments:

| Division E | Mark Landry – Division Supervisor |
| --- | --- |
| Assumption Parish |

Power – 16% Outrage

Generator issues – None

Political Temperament – Positive, Making progress on difficult challenges

Commodities – Platteville site did not operate today due lack of staffing and security.  Matter being addressed by parish greatest need continues for ice and water for future POD support.

FEMA Programs

- Individual Assistance – No report received on status.

- Public Assistance –   Applicant briefing scheduled for September 19th, 2008

- Community Relations – No report received on status.

- Blue Roof Program – Program active taking applications and obtaining ROE’s.  USACE has lead.

Parish President contacted today – At Parish request, today’s activity, especially regarding POD status, was coordinated through Parish EM. No contact with President.

Limiting factors – None.

Top Parish Concerns –Parish water purification is not fully functional while on backup generator power; limited production capacity directly impacts ability to meet local need.

Schools – Will open Monday, September 15th, 2008

Comments:  Parish continues to make steady progress; remaining big hurdle is impact of limited water production.

| Division E | Division Supervisor Brian Ellis and Jeffery Sinchak |
| --- | --- |
| Terrebonne Parish |

Power – 21% Outrage

Generator issues – None

Political Temperament – Outstanding

Commodities –   POD sites operational today.

Houma: (4) Water, (4) Ice, (2) MRE, (2) Tarps

FEMA Programs

- Individual Assistance – Fixed DRC #1 open at 805 Barrow St, Houma.  Facility is old “Town Hall”

- Public Assistance –  Plan to be determined

- Community Relations – Cr active in parish

- Blue Roof Program – Program active taking applications and obtaining ROE’s.  USACE active lead.

Parish President contacted today – Participated in public and private meetings and media availabilities with Parish President and other Parish leadership.

Limiting factors – None

Top Parish Concerns– Ongoing SAR operations, lower Parish flooding, and dealing with displaced residents and their future housing needs.

Schools – Plans to open on or about September 16th, 2008.

Comments:  Continued dewatering of the parish.  26 pumps delivered from the state to assist with effort.  40 total pumps strategically placed for dewatering throughout the parish.  Water has moved up the Houma Navigation Canal resulting in flooding of the Gibson and upper Dularge areas, particularly at the intersection of the Houma Navigation Canal and the Inter-coastal Waterway.  10,500 people remain without electricity, 6500 of which were shut off due to high water.  Water is dropping in the northern part of the parish.  Shelter population as of 1500 hours was 308.  Two shelters moving to new locations to accommodate school re-openings Parish beginning to transition from response to recovery, and in process of developing recovery unified command structure.  EOC has stood down.  PDA team in the division conducting site survey of impacted areas

| BRANCH 2 | A.D Hill Branch Director |
| --- | --- |

| Division F | Fred Wehrenberg – Division Supervisor |
| --- | --- |
| Livingston Parish |

Power status – 0% Outage

Generators – No known generator needs/no new requests.

Political climate – Parish President pleased with FEMA support.

Commodities – No PODs open in Livingston Parish.

FEMA Programs

- Individual Assistance – DRC open in Denham Springs. Telephone registration also continues.

- Public Assistance – PDA complete. Project worksheets have begun. Applicant Briefing Scheduled for tomorrow, 9/16. Debris removal continues.

- Community Relations – CR Teams deployed and conducting outreach.

- Blue Roof – ROE Collection site open and operating in Denham Springs.

Limiting factors

Fuel – Fuel available commercially where power is on.

Natural gas/Propane – No known issues.

Parish President Contacts – Met with the following today in Livingston Parish:

OEP Director Parish President OHSEP Regional Coordinator French Settlement Police Chief Maurepas Fire Chief Councilman Ronnie Sharpe

Other Comments

Flood waters have begun to recede, but homes in low-lying areas near Lake Maurepas, Amite River, and Tickfaw River are still surrounded.

Toured flooded areas with Parish OEP Director and OHSEP Regional Coordinator today to scope impact  as a result, OHSEP will request IA PDA for flooded areas of southern Livingston Parish.

Division F Supervisor interviewed by Channel 2 news regarding flooded areas.

| Division F | Fred Wehrenberg – Division Supervisor |
| --- | --- |
| Ascension Parish |

Power status – 2% outage (as of 1400 – except Donaldsonville). Some power remains out in the community of Donaldsonville (projected restoration by 9/24/08).

Generators – No known generator needs/no new requests.

Political climate – Parish President and other elected officials remain pleased with support by FEMA.

Commodities – No PODs open in Ascension Parish.

FEMA Programs

Individual Assistance – DRC relocating to Gonzales and expected to open on Wed. 9/17. Telephone registration continues.

Public Assistance – PDA complete. Project worksheets have begun. Applicant Briefing scheduled for tomorrow, 9/16. Debris removal continues.

Community Relations – CR Teams deployed and conducting outreach.

Blue Roof – ROE Collection sites operational in Donaldsonville and Gonzales.

Limiting factors

Fuel – Fuel available commercially where power is on.

Natural gas/Propane – No known issues.

Parish President Contacts – Met with OEP Director and Planning Chief today.  No outstanding issues.

Other Comments:

- Some flooding from storm surge has occurred in southern portions of Ascension Parish. Water level in New River Canal reported at 4.17feet.  Evaluation of potential impacts continues.

- Food stamp distribution ongoing.

| Division G | Harold Handke – Division Supervisor |
| --- | --- |
| West Baton Rouge Parish |

Power:  0% Outrage

Generators: Not an issue.

Political Temperament: With each passing day, the political climate keeps getting better.

Commodities: POD closed as of 9/13/08.

- Water – 1 Truck Load.

- MREs – 1.35 Truck Load.

- Ice - 0

- Tarps - .85 Truck Load.

FEMA Programs:

- Individual Assistance – Working to get the DRC re-located.

- Public Assistance – Scheduling all PDAs.

- Community Relations – Continuing Outreach Program. Met with the Div Supervisor and Port Allen EM to map areas of damage and outline CR outreach activities.  Met with the Div Supervisor and Port Allen EM to map areas of damage and outline CR outreach activities.

- Blue Roof – The Corp is continuing the program.

Limiting Factors: The Parish had a MDRC It was closed because of mosquitoes.   It closed on 9/11/08.  They are still waiting for establishment of another DRC.  People are going to the old site looking for help and no one is there and nothing telling them what the situation is.

Parish President contacted today by: Spoke with the Parish President’s secretary today.  They were concerned with the closure of the emergency shelter at Enterville at 2:00 today.  They were able to re-locate the 15 individuals to another shelter in the east part of Baton Rouge.  Their other concern is the lack of a DRC.  People are calling the President asking where they can go and get answers concerning registering with FEMA.

Other Comments: The EOC opened today after being closed over the weekend.

| Division H | George Mark Bezou – Division Supervisor |
| --- | --- |
| West Feliciana Parish |

# Power: 0% Outrage

# Generators: No issues

# Political Temperament: Good

# Commodities: No pods in service No commodities needed

# FEMA Programs:

- Individual Assistant- available but negotiating a new area of operation

- Public Assistant- Project worksheets have begun

- Community Relations- CR’s are not travelling today due to weather.

- Blue Roof- Authorized but not started yet

- PDA’s- None

Limiting Factors: Small population spread over large rural area

# Parish President contacted today by: Spoke with Frank Jones, EOC director and informed him that we are in negotiations with leasing the Dollar Store in order to resume DRC operations.

Other comments: Comments: Received a few calls from citizens in reguards to the closed DRC and explained that we were in the process of relocating

| Division H | George Mark Bezou –Division Supervisor |
| --- | --- |
| East Feliciana Parish |

# Power: 3% Outrage

# Generators: none

# Political Temperament: Very Good

# Commodities: No issues as the POD were closed.

# FEMA Programs:

- Individual Assistant- Site in negotiations

- Public Assistant- Project worksheets have begun

- Community Relations- Available

- Blue Roof- In operations at this time

- PDA’s- completed for this parish

# Limiting Factors: Being able to disseminate information through the media

# Parish President contacted today by: No meetings scheduled for today.

Other comments: Susie Joyce, from CR and I visited the Police jury and the St Francisville Development Director to talk programs available and secure maps of the area. I spoke with Ambrose Sims, the Parish business manager and he informed me that he had a lease for the Community Health Center and would be sending it back soon.

| Division I | Steve Tippit – Division Supervisor |
| --- | --- |
| Pointe Coupee Parish |

Power: 2% Outrage

Generators: No issues with generators

Political Temperament: Very Good

Commodities: PODs are closing and parish will handle locally. No commodities today.

FEMA Programs:

- Individual Assistance – MDRC to reopen 9/15/2008

- Public Assistance – Project Worksheets beginning

- Community Relations -  Will be distributing flyers Monday door to door

- Blue Roof – ROEs being collected

Limiting Factors: Being able to disseminate information through the media

Parish President contacted today by: CR met with parish president.

Other Comments: None

| Division I | Steve Tippit – Division Supervisor |
| --- | --- |
| Iberville Parish |

Power: 5% Outrage

Generators: No issues with generators

Political Temperament: Good

Commodities: Consolidated Plaquemine POD to White Castle POD.  Need 1 truck of water and 1 of ice.

FEMA Programs:

- Individual Assistance – DRC opened at 1300hr.

- Public Assistance – Project Worksheets beginning

- Community Relations - Distributing FEMA fliers

- Blue Roof – ROEs being collected

Limiting Factors: Small population spread over large rural area

Parish President contacted today by: Division Supervisor spoke to Michel Ours0.

Other Comments: None

| Division J | Darrell Balsamo – Division Supervisor |
| --- | --- |
| Tangipahoa Parish |

Power: 2%

Generators: 0

Political Temperament:  Good

Commodities: Water, Ice, MRE- Not at this time

FEMA Programs:

- Individual Assistant –Not at this time

- Public Assistance – Not at this time.

- Community Relations – working in parish.  Water is receding; the most damaged areas were Mandeville lake front, Madisonville  along the water and Slidell along the water.  The Mandeville DRC was open today.

- Blue Roof – Contacted about registration sites will start after IKE

Limiting Factors:  No issues at this time

Parish President contacted today by: Darrell Balsamo no issues at this time

Other Comments: No issues at this time

| Division J | Darrell Balsamo-Supervisor |
| --- | --- |
| St. Tammany Parish |

Power: 0% Outrage

Generators: 0

Political Temperament:  Good

Commodities: Water, Ice, MRE- Not at this time

FEMA Programs:

- Individual Assistant –Not at this time

- Public Assistance – Not at this time

- Community Relations – Working in parish. Water is receding; the most damaged areas were Mandeville lake front, Madisonville along the water and Slidell along the water.  The Mandeville DRC was open today.

- Blue Roof – contacted about locations start after IKE

Limiting Factors: None

Parish President contacted today by: Dexter Accardo Emergency Director Will let me know of any issues.

Other Comments: Water residing thru out Slidell, Lacombe, Mandeville, Madisonville some roads still closed thru out the parish with water across them. DRC location 1100 Mandeville high blvd soft open today

| Division J | Darrell Balsamo - Division Supervisor |
| --- | --- |
| Washington Parish |

Power: 0% Outrage

Generators: 0

Political Temperament:  Good

Commodities: No commodities needed at this time.

FEMA Programs:

- Individual Assistant –Not at this time

- Public Assistance – Not at this time

- Community Relations –Not at this time

- Blue Roof – Not at this time

Limiting Factors: No issues at this time

Parish President contacted today by: Thomas Thiebaud Emergency Director no issues at time

Other Comments: No issues at this time

| Division S | Jon Bajon - Supervisor |
| --- | --- |
| East Baton Rouge Parish |

Power: 0% Outage

Generators: No issues with generators

Political Temperament: Excellent

Commodities: Parish has enough commodities

FEMA Programs:

- Individual Assistance – working to stand up DRC’s

- Public Assistance – Project Worksheets beginning

- Community Relations - Distributing FEMA fliers.  The meeting held today with CR, IGA, Ops Division Supervisor and the Parish EM was very successful.  The EM is pleased with the proposed CR outreach activities for the Parish.

- Blue Roof – ROEs being collected

Limiting Factors: None

Parish President contacted today by: No

Other Comments: EOC closed.

| Division S | Jon Bajon – Division Supervisor |
| --- | --- |
| St. Helena Parish |

Power: 0% Outrage

Generators: No issues with generators

Political Temperament: Excellent

Commodities: Parish has enough commodities

FEMA Programs:

- Individual Assistance – Waiting  to set up  DRC;s

- Public Assistance – Project Worksheets beginning

- Community Relations - Will be distributing flyers Monday The meeting held today with CR, IGA, Ops Division Supervisor and the Parish EM was very successful.  The EM is pleased with the proposed CR outreach activities for the Parish.

- Blue Roof – ROEs being collected

Limiting Factors: None

Parish President contacted today by:  I met with EOC Director today to discuss standing up DRC in his parish.

Other Comments: Traveled to St. Helena today with Darry Madden, External Affairs, and Marily Cortez, CR to meet with the EOC Director Harrell. Our discussions included DRC sandup, media, and community relations.

| BRANCH 3 | David K. Nelson Branch Director |
| --- | --- |

| Division K | Brice Acosta – Division Supervisor |
| --- | --- |
| St. Mary Parish |

Power: 3% Outage.

Generators: None

Political Temperament: No issues

Commodities: Verified POD of water only (Amelia Recreation Center).

FEMA Programs:

- Individual Assistance – No confirmation about progress on DRC’s per IAP work assignment No.4.

- Public Assistance – No confirmation on PDA being in the area.

- Community Relations – Contact was made and coverage had in all parishes.

- Blue Roof – Collections have resumed.

Limiting Factors: Highway 90 blocked near Franklin, water on road still

Parish President contacted today by: No contact today.

Other Comments: At the time of visit, it appears a press conference was going on, cameras, lights, etc. Interaction was limited.

| Division K | Brice Acosta- Division Supervisor |
| --- | --- |
| St. Martin Parish |

Power: 1% Outage, 2 dozen homes are without power in lower St. Martins

Generators: None needed

Political Temperament: No issues.

Commodities: Possible need for water distribution pending water quality

FEMA Programs:

- Individual Assistance – DRC locations selected, web EOC request numbers 16070, and 16076 ready for site inspections and lease.

- Public Assistance – Ready for State sponsored PDA

- Community Relations – Contact was made and coverage had in all parishes.

- Blue Roof – Collections began today.

Limiting Factors: None

Parish President contacted today by: No contact today.

Other Comments: Parish is prepared with data on both Public and Individual Assistance needs and is more than ready to receive teams. Stephensville/Belle River is accessible, flood waters have receded.

| Division K | Brice Acosta – Division Supervisor |
| --- | --- |
| Iberia Parish |

Power: 0% outage due to flooded/flood damage homes and businesses. No infrastructure damage visible at this time so power should return one

Political Temperament: Governor Jindal visited the area today.

Commodities: POD site conflict.

FEMA Programs:

- Individual Assistance – (1) Hurricane Ike Preliminary Damage Assessments (State, FEMA, SBA present) began today focusing on the flooded areas of Delcambre, Rynella, Port of Iberia, Lydia. (2) Still awaiting contact for a DRC.

- Public Assistance – Applicant Briefing is needed. PDA’s were completed and submitted.

- Community Relations – CR staff traveled to the town of Jeanerette, Lydia and Rynella to be the Face of FEMA while handing out flyers and information.

Limiting Factors: Some areas still inaccessible because of standing water

Parish President contacted today by: All workers in the area (PDA team, Community Relations, Division Supervisor) met with the Emergency Management Director and the Parish President. All involved presented a unified and well organized team.

Other Comments: Coordination was seamless today. A great show of force, team work, and dedication to the mission!

| Division L | Bob Lonergan-Supervisor |
| --- | --- |
| Vermillion Parish |

Power: 25% Outrage

Generators: No FEMA assets operating in parish.

Political Temperament: Good working relationship with Parish President and OEP Director.

Commodities:

- 6 Truck loads of Ice, 2 Truckloads of water, 0 Truckloads of MRE and 3.5 Truckloads of tarps.

- Requesting replacement commodities as needed.

FEMA Programs:

- Individual Assistance –

  - DRC Location has been identified and reported to WebEOC.

  - Fruit of the Loom POD closing to public at 1800. Will resume operations tomorrow as staging area for changing POD site needs.

  - Delcambre POD being supplied through Iberia parish.

  - Extensive damage to agricultural and aqua-cultural operations in the region.

- Public Assistance –

- Holding on PDA Until Rapid Damage Assessment is complete and water recedes.

- Contacted by PDA Team and advised them that area is unsafe and no parish officials or resources are available to accommodate their request.

- Drowned livestock has been observed, exact numbers not known at this time.

- Flood waters slowly receding.

- Community Relations – CR Teams continue to work at POD sites and areas that are not flooded.

- Blue Roof – In contact with ACOE to locate ROE site. Planning to locate in Courthouse lobby until DRC opens.

Limiting Factors:  Extensive flooding in all areas south if Hwy 14.

Parish President contacted today by: FEMA Division Supervisor. Actively involved as part of Unified Command Group on Hurricane Ike recovery activities

Other Comments:

- Parish has received it’s requested DMORT tasking to recover, identify and restore damaged cemeteries. A fourth cemetery was identified today as breached.

  - Parish official that coordinated this operation after Hurricane Rita will be managing this operation. He advised that he will be contacting Congressional delegation regarding issues encountered in the past for costs related to re-interring remains.

  - This issue appears to be that they are rural cemeteries located on private property in the 1700 – 1800’s but available to the public. There is no land grant or transfer of title records available anymore. FEMA refused to reimburse the cost of reinterring after Hurricane Rita.

  - One of the cemeteries is known to be an old slave cemetery.

- The parish is being contacted by evacuees from Texas looking for shelter and other assistance. They are being referred to the FEMA 800 number and ARC.

- A new apartment complex is available for leasing and will be ready to occupy in 2 weeks. This is the Tiffany Apartments on Rodeo Rd in Abbeville.

| Division M | David Conner – Division Supervisor |
| --- | --- |
| Calcasieu Parish |

Power: About 200 homes with power, remainder of 3500 homes without power

Generators: Too early to know, parish wide flooding

Political Temperament: Internal tension is building a little.  I have been working closely with State and EOC to keep the tension down.

Commodities: USAR provided food, water and ice to Big Pasture residents isolated by two draw bridges out of commission.  No PODS yet, most residents still out of Parish.

FEMA Programs:

- Individual Assistance – Too early for teams

- Public Assistance – Too early for teams

- Community Relations – Too early for teams

- Blue Roof – Too early for teams

Limiting Factors: Flood waters and road hazards continue as EOC continues with road blocks at Parish line.

Parish President contacted today by: Contacted the EOC director only

Other Comments:  We must stay in close contact with EOC director to limit access until further notice.

| Division M | David Conner – Division Supervisor |
| --- | --- |
| Cameron Parish |

Power: Approximately 20,000 without power

Generators: None needed

Political Temperament: Very good; progress going well; repatriation boosted morale

Commodities: No PODS – no commodities

FEMA Programs:

  - Individual Assistance – (Include any pertinent information about DRCs) PDA tp be performed Tuesday

  - Public Assistance –  No programs started yet

  - Community Relations – Noe started in Calcasieu

  - Blue Roof – Not started in Calcasieu, Faith Based  issuing blue tarps

Limiting Factors: None

Parish President contacted today by: Contacted Dick Gremillion, OEP Director, Kelly Fontenot, Comptroller; Lawrence Hennigan, Mayor of DeQuincy; and Randy Roach, Mayor of Lake Charles.

Other Comments: USAR completed today,  Debris Specialists from FEMA, State and Corps met with Parish officials, Repatriation substantially complete.

| Division M | David Conner – Division Supervisor |
| --- | --- |
| Jefferson Davis Parish |

Power: 468 homes (6%) without power

Generators: No requests

Political Temperament: EOC Director upset with POD coordinator.  Issue resolved with lead

Commodities: PODS closed in Roanoke and Topsy

FEMA Programs:

- Individual Assistance – (Include any pertinent information about DRCs) PDAs completed today

- Public Assistance – Unknown

- Community Relations – CR worked Parish today

- Blue Roof – None requested yet

Limiting Factors: None

Parish President contacted today by: None

Other Comments:

| Division N | Bob Lonergan – Division Supervisor |
| --- | --- |
| Acadia Parish |

Power: 0% Outrage

Generators: No issues

Political Temperament: Excellent working relationship with FEMA.

Commodities: None

FEMA Programs:

- Individual Assistance – GSA working on DRC leasing

- Public Assistance – Debris cleanup is ongoing.  Some of the cities have received an email telling them that they can begin the PA Paperwork using the same ID Number that they used from Hurricane Rita. Contacted GOHSEP Liaison, he was checking with his chain of command. Advised parish to wait for clarification.  Parish still very anxious to begin PA process.

- Community Relations - CR outreach operations have resumed and are ongoing.

- Blue Roof – Planning on collocating in DRC, waiting for info on opening date.

Limiting Factors: None at this time

Parish President contacted today by: Division Supervisor. No issues other than stated above.

Other Comments: None at this time.

| Division N | Bob Lonergan-Supervisor |
| --- | --- |
| Lafayette Parish |

Power: 0% Outrage

Generators: No issues

Political Temperament: Willing to reach out as needs are identified.

FEMA Programs:

- Individual Assistance – DRC is in the process of opening.

- Public Assistance – Ready for PDA. Requesting CAT A Declaration for IKE

- Community Relations – CR Outreach team working n the parish.

- Blue Roof – Planning to collocated ROE center with DRC.  Waiting for a date to move in.

Limiting Factors: None

Parish President contacted today by: Spoke with Parish President’s assistant. They are grateful that their community was spared and have offered assistance to their neighboring parishes.

Other Comments: Numerous State and Federal assets staged at Cajun Dome for Post Landfall response.

| Division O | Ron Zuber – Division Supervisor |
| --- | --- |
| Allen Parish |

Power: 4% Outrage

Generators: None needed

Political Temperament: Currently happy

Commodities: Parish received 1 Ice, 1 MRE and 1 water and broke them down for redistribution.  Ice and water being given out by LANG

FEMA Programs:

- Individual Assistance – ESF 6 PDA Team was scheduled to be in parish today but they did not call to let me know.

- Public Assistance – Nothing to report

- Community Relations – CR Team back in the area today and Team Leader made a courtesy visit to OEP Director

- Blue Roof – Coordinated with supervisor back in the JFO to strategize on placement of team in parish. Recommended he get with ESF 6 DRC Manager to possibly work out a partnership and utilize the same place in Oberlin. The facility is huge.

Limiting Factors: None at this time

Parish President contacted today by: Contact in parish made by CR Team Leader.

Other Comments: Food stamp office opened today.

| Division O | Ron Zuber – Division Supervisor |
| --- | --- |
| Beauregard Parish |

Power: 8% Outrage

Generators: None needed at this time

Political Temperament: Happy to be moving into recovery (again).

Commodities: Received and broken down for distribution by parish.

FEMA Programs:

- Individual Assistance – ESF 6 PDA Team entered OEP Office as I was leaving. They did not call to coordinate.

- Public Assistance – Mrs. Cunningham is ready to get going on PWs.

- Community Relations – The CR Team will be working in southern Beauregard parish tomorrow.

- Blue Roof – Recommended to Corps Rep that they look at setting up an ROE point somewhere in south Beauregard or North Calcasieu Parishes (DeQuincy). That way those hardest hit in Beauregard can utilize the same office as those in North Calcasieu.

Limiting Factors: None at this time

Parish President contacted today by: Contact in parish with OEP Director and Parish Administrator by Louis Press and myself.

Other Comments: Faith based shelter in DeRidder with 100 people from Cameron is still open.  No updated population count.  Most of the damage is in the lower end of the parish.

| Division P | Ron Zuber – Division Supervisor |
| --- | --- |
| Evangeline Parish |

Power: 0% Outrage

Generators: None needed at this time

Political Temperament: Unable to visit today

Commodities: None planned for today

FEMA Programs:

- Individual Assistance – Housing inspections being conducted by contractors.

- Public Assistance – Parish has collected debris on the side of the roads.  I don’t know whether the Corp or the parish will do the pick-up.  They seem ready to move forward with the PA process soon.

- Community Relations – No CR Teams in this parish today

- Blue Roof – Those needing Blue Roofs are encouraged to visit the sign-up location in Opelousas, St. Landry Parish.

Limiting Factors: None at this time

Parish President contacted today by: Unable to visit today.

Other Comments: Most debris piles on the side of the road were from Gustav and seemed undisturbed. Those with blue roof and tarps seemed unaffected by Ike.

| Division P | Ron Zuber – Division Supervisor |
| --- | --- |
| St Landry Parish |

Power: 0% Outrage

Generators: None needed at this time

Political Temperament: Good

Commodities: None seen in the Parish

FEMA Programs:

- Individual Assistance – Housing inspections being conducted by contractors.

- Public Assistance – Parish is ready to start PA process

- Community Relations – CR Team in lower part of parish today. They also stopped by the Corps ROE desk for blue roofs for a visit.  CR Team is assessing the need and reporting their findings to their supervisor.

- Blue Roof – Open and collecting ROEs. They will remain open as long as they have enough people coming in.

Limiting Factors: None at this time

Parish President contacted today by: Parish OEP Director was contacted by CR Team Leader.  No issues were reported.

Other Comments: Most debris piles on the side of the road were from Gustav and seemed undisturbed. Those with blue roof and tarps seemed unaffected by Ike.

| BRANCH 4 | Thomas M. Webb Branch Director |
| --- | --- |

| Division Q | Mick Terich – Division Supervisor |
| --- | --- |
| Sabine Parish |

Power: 1% Outrage

Generators: No issues

Political Temperament:  No issues.

Commodities:  PODS have been closed.  OHSEP Director and S.O. are distributing commodities to areas without power.

FEMA Programs:

- Individual Assistance – needed

- Public Assistance – PDA assessment began today.

- Community Relations – Team has been assigned to the Parish

- Blue Roof – No issues

Limiting Factors: None

Parish President contacted today by: OHSEP director was contacted today

Other Comments:  Are trying to get Texas evacuees repatriated back to Texas

| Division Q | Mick Terich – Division Supervisor |
| --- | --- |
| Vernon Parish |

Power: No Issues

Generators: No issues.

Political Temperament:  No issues.

Commodities:

FEMA Programs:

- Individual Assistance – Assessing need for DRC

- Public Assistance – PDA began today

- Community Relations – Team has been assigned to the Parish

- Blue Roof – Recently approved.

Limiting Factors: None

Parish President contacted today by: No contact with OHSEP director today

| Division R | Mick Terich – Division Supervisor |
| --- | --- |
| Rapides Parish |

Power: 0% Outrage

Generators: No issues

Political Temperament: Fair and getting better

Commodities: Parish has requested 2 pallets of tarps. No other issues known.

FEMA Programs:

- Individual Assistance –  DRC lease is in process with GSA

- Public Assistance – Applicant briefing scheduled 9/17

- Community Relations – Team assigned and active in the Parish.  The Pineville Wal-Mart manager is requesting equipment be relocated.  The manager believes the equipment belongs to FEMA contractors.

- Blue Roof – No issues. Flyers being distributed

Limiting Factors: None at this time

Parish President contacted today by: Talked with OHSEP director today but not to Parish President

Other Comments: Getting DRC open is critical

| Division R | Mick Terich - Supervisor |
| --- | --- |
| Avoyelles Parish |

Power: No Issues

Generators: No issues

Political Temperament: No issues

Commodities: POD is closed.  Warehouse is stocked.  Water and MRE’s being distributed at fire station

FEMA Programs:

- Individual Assistance – DRC opened at 1 p.m. today

- Public Assistance – PDA occurring

- Community Relations – Team has been assigned to the Parish is canvassing area and working DRC and Food Stamp center

- Blue Roof – Flyers being posted

Limiting Factors: None

Parish President contacted today by: Contacted OHSEP director but not Parish President

Other Comments:

| BRANCH 5 | Thomas M. Webb Branch Director |
| --- | --- |

| Division T | Derek Joe Tennant – Division Supervisor |
| --- | --- |
| La Salle Parish |

Power: 0% outrage

Generators: No issues known

Political Temperament:  We are working on turning around the poor opinion of FEMA

Commodities: Has requested tarps

FEMA Programs:

- Individual Assistance – DRC has been requested

- Public Assistance – Applicant Briefing is set for 17 September

- Community Relations – Team contacted OHSEP Director, received permission to begin work within the Parish

- Blue Roof – Not approved at this time. Will verify if there is a need.

Limiting Factors: None

Parish President contacted today by: New DivS contacted OHSEP Director. Will contact Parish President later this week

Other Comments: Mosquito Abatement Program requested through webEOC

| Division T | Derek Joe Tennant – Division Supervisor |
| --- | --- |
| Grant Parish |

Power: 0% Outrage

Generators: No issues known

Political Temperament: No issues, but Police Jury not fond of FEMA.

Commodities: No issues known

FEMA Programs:

- Individual Assistance – DRC has been requested

- Public Assistance – Applicant Briefing is set for 17 September

- Community Relations – CR team will establish contact

- Blue Roof – Not approved at this time. Will verify if required

Limiting Factors: None

Parish President contacted today by: OHSEP director was contacted, new DivS introduced. Director requested he be the POC for the Parish.

Other Comments: Mosquito Abatement program requested through webEOC.

| Division T | Derek Joe Tennant – Division Supervisor |
| --- | --- |
| Catahoula Parish |

Power: No known issues.

Generators: No known issues.

Political Temperament:  No known issues

Commodities: Have requested tarps

FEMA Programs:

- Individual Assistance – DRC needed and has been requested

- Public Assistance – Applicant Briefing is set for 17 September

- Community Relations – scheduled to arrive Wednesday 17 September

- Blue Roof – Not approved at this time. Will verify if needed

Limiting Factors: None

Parish President contacted today by: Contact was made with OHSEP Director.

Other Comments: Mosquito Abatement Program requested through webEOC

| Division U | Derek Joe Tennant – Division Supervisor |
| --- | --- |
| Franklin Parish |

Power: 0% Outrage

Generators: No needs

Political Temperament:  Anxious about need for a DRC.

Commodities: No needs at this time

FEMA Programs:

- Individual Assistance – Please establish a DRC in Winnsboro quickly

- Public Assistance – Schedule the applicant briefing (state task)

- Community Relations – Met the OEP Director and received permission to work within the Parish

- Blue Roof – Currently not in operation in Franklin Parish Will verify this is appropriate

.

Limiting Factors: No known issues

Parish President contacted today by: Contacted OHSEP Director twice today.

Other Comments:  Mosquito Abatement program requested through webEOC.