Investment Analysis Standards and Guidelines

Title:		Risk Metrics for Initial Investment Analysis (JRC 2(a))

Type (Standard or Guideline):	Standard

Approval Date:	Approval  July  2002

Purpose:		The Standard Risk Metrics form the investment risk standards.  They should be used to ensure quality and uniformity of practice, unless there is a compelling documented case to do otherwise.

Applicability:	The Standard Risk Metrics are required to be used by all FAA entities and organizations pursuing an Initial Investment Decision (JRC 2(a)) for any system acquisition.   For a facility acquisition, these standard metrics would need to be tailored and modified prior to beginning the risk analysis.  Work continues on modifying this standard to address facility, security, and environmental issues.   Accordingly, this standard should be viewed as an evolving one, and constantly updated to remain more relevant to the context and nature of all IAs. For the Initial Investment Decision, the Joint Resource Council considers the merits of all investment alternatives which meet the requirements and down-selects to the best candidate solution.

Description:	The standard metrics are the risk facets of technical, operability, producibility, supportability, cost estimating, benefit estimating, schedule, management, funding, stakeholder, information security, human factors, and safety.  Within each facet is a checklist of potential issues to be considered for each alternative.  The number of issues identified as affecting the alternative under consideration is an indicator of magnitude of risk.   This measure of risk forms the basis for the application of a methodology to assess the level, consequence, and mitigation of risk.

Content:  		The Standard Risk Facets, and Risk Checklist are defined and presented below.

Configuration Management:	This Standard will be maintained by the Investment Analysis and Operations Research Directorate (ASD-400) in the FAA Acquisition System Toolset (FAST).  It will be reviewed annually by ASD-400 for currency with acquisition environment.  If any changes are necessary, they will be proposed by

ASD-400 through the normal ASAG/ FAST change process.

## Risk Metrics for Initial Investment Analysis (JRC 2a)

## Terminology: Risk

Risk is defined as an event whose outcome is unknown in advance.  In this context, risk implies some probability that an acquisition alternative will fail to deliver the benefits projected, either in whole or in part, and that failure may have consequences to its success.  The risk can derive from uncertainties in an alternative's concept or problems encountered during design, development, implementation, or operation.

## Risk Consideration During Initial Investment Analysis

For the Initial Investment Analysis Decision (JRC-2a), the critical issue to be answered is which of the viable acquisition alternatives is worth examining in more detail for implementation.  Consequently, the risk assessment for the Initial Investment Decision is necessarily done at the macroscopic, and comprehensive levels.

The process includes

Identification of risk issues,

Development of potential mitigation strategies,

Assessment of investment alternatives, and

Affirmation of mitigation strategies to be examined for cost or benefit estimation impact.

### The Investment Analysis Team (IAT) Alternatives Risk Assessment

In general, within the IAT Alternatives Risk Assessment there are thirteen facets that constitute an exhaustive range of potential risk areas, including: technical, operability, producibility, supportability, benefit estimate, cost estimate, schedule, management, funding, stakeholder, information security, human factors, and safety.  Risk issues may be identified by discussion with program staff, users, stakeholders, or derived from secondary written sources.  Usually, in the course of identifying risk issues, mitigation actions come to mind and are written down as preliminary mitigating actions.  Also at this point, the  discussions or secondary information suggest the likelihood of the issue surfacing and the potential severity of impact of the issue, if unmitigated.

The next step is to convene a broad team of stakeholders, programmatic, investment analysis, union representatives, and other interested colleagues.  A broad team is important because information is needed from multiple perspectives.  Only in so doing is it possible to get an objective assessment.  Together the team reviews the material and by double blind voting and justifying discussions arrives at consensus of each facet’s rating for each alternative, and affirms or complements issue mitigation strategies or actions. In a double blind voting procedure, each group member votes before and after group discussions without knowing how other group members are voting. At the end of these discussions, the relative risk levels of alternative s emerge.

This information is provided to the IAT. In turn, the IAT uses this information and other inputs from cost, benefit, and other analyses, to put together its recommendation for down-selection.

The risk analyst then identifies whether the mitigation strategies are likely to impact the cost estimation or the benefit estimation of the down-selected alternative, and works with appropriate staff to estimate the impact within the appropriate work breakdown structure categories.

The product of this effort may be a technical memorandum, but most often is:

A stand-alone summary section in the Investment Analysis Report;

Solid input for creating cost and benefit high confidence ranges around the most likely numbers, and

Direct input into the Risk Management Matrix in the Initial Acquisition Program Baseline.  The Risk Management Matrix may be found in the FAA Acquisition System Toolset (www.fast.faa.gov , APB Template, Section 6, Table 6.1).

Lastly, the issue ratings are summarized into a matrix for the JRC, and for continued analysis in the Solution Implementation Phase.

## Risk Facets

The life cycle risks are broken down into thirteen components, or facets, of risk, which are used to assess the overall risk.  These risk facets have been selected to reflect the comprehensive risks associated with an acquisition alternative’s development, implementation, operation, in such a way as to achieve the projected benefits.  The facets are intended to facilitate the identification of risk and its quantification.  The thirteen risk facets are defined as follows:

RiskTechnical is the risk associated with (1) developing a new or extending an existing technology to provide greater performance than previously demonstrated, or (2) achieving a level of performance.  It also refers to how well the system operates to design or safety specifications.

RiskOperability is the risk associated with how well the system to be produced will operate within the NAS and interact with other systems.  It addresses NAS or other system interfaces, the degree to which they are known and complete, and the degree to which the operational concept has been demonstrated and evolved to the point of a design baseline.

RiskProducibility is the risk associated with the capabilities to manufacture and produce the desired system.

RiskSupportability is the risk associated with fielding and maintaining the resulting systems.

RiskBenefit Estimate considers the difficulty in estimating the benefits and in realizing benefits.  This risk facet addresses the accuracy and uncertainty of the benefit estimate, including such issues as inadequate methods to estimate the benefits, lack of data to estimate the benefits, uncertainty of assumptions, and whether the alternative is defined enough to estimate the benefits.

RiskCost Estimate considers the difficulty in estimating the cost and in adhering to the cost.  This risk facet addresses the accuracy of the cost estimate, including such issues as inadequate methods to estimate the cost, lack of data to estimate the cost, uncertainty of assumptions, and whether the alternative is defined enough to estimate the cost.

RiskSchedule considers the likelihood that the alternative will be completed within the specified schedule.

RiskManagement refers to complexity of the alternative to manage (e.g., number of sub-tasks and/or number of performing organizations) and considers the risks of obtaining and using applicable resources and activities that may be outside of the alternative's control but can affect the alternative's outcome.

RiskFunding addresses the availability of funds when they are needed and a confidence in management and Congress that those funds will continue to be provided.

RiskStakeholder is the risk associated with various stakeholders supporting the development and operation of the alternative, such as internal FAA organizational users, Congress, airline and general Aviation users, and potential equipment and aircraft manufacturers.

RiskSecurity addresses a system's vulnerability to external threats and the risks likely to occur in employing countermeasures.  This pertains to both information and physical issues.

RiskHuman Factors focuses on the effectiveness and suitability of the human-in-the-loop aspects of the system with respect to both operations and maintenance.

RiskSafety considers the risk associated with the performance (or lack thereof) of appropriate safety risk management activities and in implementing the identified safety requirements. This risk facet shall not be confused with the operational risk of system hazards. The operational risk of system hazards are documented in other analyses.

## Risks Metrics

For the Initial Investment Analysis, measuring risk begins with the identification of the number of specific risk issues for each risk area. The identification of risks is conducted in an organized and comprehensive manner.

Risk identification involves enumerating and describing the risks pertaining to each of risk facet for successfully carrying out each of the alternatives being considered.  The number of risks identified constitutes the measure, or quantification of risk.  The measure of risk is not to be confused with the assessment of risk.  The assessment of risk for each alternative follows a set methodology which considers the probability of occurrence of risk and the severity of impact should that risk materialize.   Assessment of risk will be covered in a subsequent product of the risk standardization effort, called Risk Methodology.

For purpose of risk enumeration, Table 1: Facet Risk Checklist, is included in the following several pages.  For each of the thirteen (13) risk facets already identified as being relevant to the Initial Investment Analysis Decision, a comprehensive set of risk issues are listed.  The analyst should examine each alternative to determine whether each of the bulleted issues is present.  The number of risk issues present and their detailed description determine the metric for risk.   The risk issues that are found to be present are then the basis of further research.  Further research would include a risk assessment to determine the level of risk, usually by understanding the probability of the occurrence of risk, and the severity of their impact.

Table 1:  Facet Risk Checklist

| Technical Risks | Operability Risks | Producibility Risks |
| --- | --- | --- |
| Technology Undue reliance on currently unavailable or unproved technology Possible better new technology may be available by time alternative is implemented System Engineering Technically incompatible with NAS Architecture Inadequate functional analysis Deficient functional allocation Incomplete integration Undefined internal interfaces Vague operational environment Insufficient requirements analysis Unstable requirements Non-compliant or unvalidated requirements Weak or non-existent failure modes analysis Requirements difficult to trace Unidentified safety/security considerations System Design Inadequate capacity Highly complex Lack of design details Insufficient design margins Immature design Unsatisfactory growth potential Undefined physical properties Incomplete hardware design Incomplete software design Inadequate software tools Difficulty of developing real-time, safety critical software Immature software language Ineffective fault detection Inordinate use of unique resources Complex/incomplete man/machine design Undefined technical approach System Test Inaccurate/simplistic modeling Insufficient simulation No or minimal prototype testing Incomplete/inadequate test planning Unsatisfactory OT&E results Technical Documentation Inadequate design documentation Insufficient test documentation Ambiguous/incomplete requirements documentation Undocumented technical details | System Operation Undefined external interfaces Marginal availability Insufficient reliability Inadequate performance Unsatisfactory OT&E results Systems Inter-operability Operationally incompatible with NAS Architecture Incompatibilities with Concept of Operations Incompatibilities with future NAS systems Places undue loads on other systems Incompatible or inconsistent operation with existing systems or regulations Unspecified operational interfaces Marginal inter-operability | Design Production Highly complex design Undeveloped production requirements Inadequate built-in test equipment Non-standard remote maintenance monitoring Novel/unproved technologies Manufacturing Deficient manufacturing plan Novel/unproved manufacturing technologies Speculative manufacturing strategy Custom design and manufacture required Significant special tooling Undefined tooling requirements Unclear production requirements Premature initiation of manufacturing Unavailable or limited manufacturing facilities Inadequate quality assurance program Excessive standards Unavailable equipment Inexperienced contractor Inadequate configuration management process Insufficient skilled labor Shallow industrial base Parts and Materials Undefined long lead items Unavailable government furnished equipment Ineffective incoming materials handling Unidentified hazardous materials Unavailable parts Testing and Documentation Inadequate consideration of special test equipment Insufficient qualification testing Deficient technical data package Ineffective factory acceptance test program Untested design changes |

Table 1:  Fecet Risk Checklist, Cont’d

| Supportability Risks | Cost Estimate Risks | Benefit Estimate Risks | Schedule Risks |
| --- | --- | --- | --- |
| O&M Inadequate O&M concept Undeveloped O&M strategy Specialized O&M equipment Insufficient maintainability Unsatisfactory maintenance interfaces Inadequate maintenance procedures Undeveloped maintenance plan Configuration management not enforced Deficient change process Logistics Insufficient spares planning Spares unavailability Inaccessible site location Inadequate training Unclear Logistics Center responsibilities Testing and Support Insufficient support equipment COTS/NDI - Industry refresh rate not likely to be consistent with FAA needs Undeveloped support requirements Inadequate automated test equipment (ATE) Unidentified field support requirements Poor diagnostics Insufficient testing and support facilities Unskilled/insufficient manpower Support Documentation Deficient technical data Faulty maintenance plan Undefined data rights Inappropriate release cycle System Implementation Deficient implementation approach Uncertain transition strategy Unclear rules and procedures Insufficient personnel/staffing Unspecified/inappropriate standards | Cost Estimation Inadequate cost estimating tools Estimation errors Inaccurate discount rate Faulty BOEs** Insufficient cost margin Unrealistic overhead and G&A rates Relies on scarce resources Speculative life cycle costs Sensitivity analysis to cost drivers not undertaken Cost Management Unsatisfactory cost controls Insufficient cost monitoring Product Cost Undefined government furnished equipment Reliance on unavailable NDI/COTS Unavailable government facilities Unavailable contractor facilities Inadequate budget for tests Undefined hardware costs Hidden software costs Unidentified parts and materials | Benefit Identification Same benefits claimed by other programs Unidentified major benefits Unrealistic identified benefits Difficult to identify benefits Benefit Estimation Benefits not quantifiable Difficult to estimate benefits Tenuous relationship to projected benefits External forces may affect achieving benefits Erroneous benefits estimations Inaccurate inflation/discount rates Speculative cost avoidance Faulty BOEs. Inadequate estimating tools | Schedule Estimation Inadequate schedule estimating tools Erroneous estimations Faulty BOEs Insufficient schedule margin Optimistic schedule duration Inappropriate program schedule Schedule Dependency Unpredictable labor strikes Improper test scheduling Excessive task concurrency Unidentified need for procedures development Unidentified need for regulations development Inordinate number of critical path items Unidentified need for standards development Uncertainties in contractor process Uncertainties in contractor stability Schedule too ambitious for degree of technical complexity Unavailable materials Unavailable parts Unavailable government furnished information Unavailable facilities Unavailable personnel Unavailable tools Unavailable contractor Schedule Management Unsatisfactory schedule controls Insufficient program schedule monitoring Improper contractor/subcontractor schedule monitoring |

Table 1:  Facet Risk Checklist, Cont’d

| Management Risks | Funding Risks | Stakeholder Risks |
| --- | --- | --- |
| Planning Inadequate program plans Incomplete contingency plans Deficient risk management plans Inadequate management approach Unplanned slips in other programs Adverse environmental impacts Unsubstantiated funding profile Unsubstantiated manpower requirements Unidentified personnel skills Minimal resource alternatives Excessive dependencies on other system Unexpected acquisition regulation changes Organizing Excessive span of control Inadequate authority Undefined responsibilities Unclear communications Undefined integration responsibilities Ambiguous organizational interfaces Inadequate contractor organization Implementing Insufficient management tools Inadequate program office staffing Inadequate resource allocation Deficient personnel management Lack of coordination Tenuous top management support Cumbersome FAA contracting process Instability of contractor Uncertainties in procurement Unavailable personnel Deficient change implementation Control Undefined or ineffective change management Unsatisfactory configuration management Insufficient contract evaluation Inadequate planning for contractor monitoring Insufficient financial management Irregular/unscheduled program reviews Insufficient history/records Undefined key metrics Uncontrolled requirements changes Requirements freeze not enforced Inadequate tracking systems | Funding Constraint Unfavorable agency priorities Inadequate funding Unavailable funding Lengthy budget cycle Inadequate OMB marks Constraining unique budget scoring rules for lease-purchases and leases per OMB A-11 Funding Support Inadequate user support Ambiguous operator support Unclear political support Marginal cost/benefits Inconsistent FAA plans Lack of alignment of necessary funding profile with agency affordability profile Fiscal Management Insufficient funding requirements Insufficient fiscal controls Insufficient fiscal tools Insufficient funding plans | Congressional Based Impact of congressional mandates Unfavorable congressional hearings on program Critical GAO report Administration Based Conflicting FAA priorities Conflicting DOT priorities Aviation Community Many different stakeholders Diverse user community Conflicting user demands Conflicting user opinions Conflicting user priorities Inordinate pressure from user groups Marginal user support Strained relationships with users Resistance to avionics equipage requirements Inordinate media attention |

Table 1:  Facet Risk Checklist, Cont’d

| Security Risks | Human Factors Risks | Safety Risks |
| --- | --- | --- |
| Vulnerability Incomplete vulnerability assessment Security policy and procedures not in place Easy access to communication No provision for firewalls between shared networks or Virtual Private Networks Threat Incomplete threat assessment on intent and capability to exploit vulnerability No prioritization of threat severity No provision for penetration testing Threat difficulty not considered Countermeasures Few countermeasures defined Effectiveness of countermeasures on infrastructure not testing Inadequate configuration audit Lack of monitoring and enforcement Insufficient funding tools/controls Ambiguous funding support | Human-in-the-loop Effectiveness Inadequate definition of human-in-the-loop operational objectives Inadequate specification of human-in-the-loop benefits Inadequate analysis of human-in-the-loop system capability to deliver expected benefits or enhancement Human error mechanisms or metrics not fully identified Time required to perform tasks is unknown Automation does not provide the necessary functionality or information to support effective decision-making/problem-solving Human-in-the-loop Suitability Lack of consistency, compatibility, or congruity with operational environment or legacy systems Human-system design/interface induces new/additional human error potential Inadequate incorporation of functional requirements to support user-system performance goals User Acceptability New tasks impose excessive attention, memory, or workload demands Requires new teaming and communication links Operations interface is unacceptable to user Maintenance interface is unacceptable to user | Hazards Hazards and service-level effects not fully identified Inter-relationship of hazard effects not established Hazards not classified per common scheme Hazard class not based on operational environment definition System Safety Interdependence Hazard interdependence poorly understood Interoperability of components on system safety not investigated Systemic approach to safety is lacking one or more components (planning, requirements, procedures, operation, aircraft certification, or user approval) Mitigation Strategies Mitigation strategies not shared Operational and safety objective not established Lack of critical/valid safety information Mitigation strategies not tied to hazards or safety requirements Plan for development and operational assurance not in place |