For the

By

December 12, 2002

table of Contents

Acronyms	ii

Introduction	iii

Special Considerations	1

Budget	1

Staffing	1

Time Commitments	3

Workshop Planning and Logistics	1

Responsibilities	1

Schedule for Planning	1

Participation Policies and Invitation Lists	2

Invitation Materials	5

Facilities	6

Food	7

Signs	7

Equipment and Supplies	7

Workshop Content and Conduct	9

Agenda and Activities	9

Scenario Development and Conduct	11

Workshop Follow-Up	14

Workshop Handout Materials	14

After Action Report	14

Thank You Letters	14

Appendices

Appendix A: Workshop Planning Checklist

Appendix B: Sample Invitation Materials

Acronyms

CST		Civil Support Team

EM		Emergency Management

FAA		Federal Aviation Administration

FBI		Federal Bureau of Investigation

FEMA		Federal Emergency Management Agency

FHWA	Federal Highway Administration

FRA		Federal Railroad Administration

FTA		Federal Transit Administration

HAZMAT	Hazardous Materials

JTTF		Joint Terrorism Task Force

WMD		Weapons of Mass Destruction

Introduction

This guide provides information about how to develop a multi-jurisdictional workshop featuring tabletop exercises focused on disruption of a transportation network through a terrorist related event. It is based on the experiences of the Federal Highway Administration (FHWA) and Booz Allen Hamilton in conducting 10 workshops during the summer of 2002.

The FHWA workshops focused on transportation operations emergency prepared and response. The overall objectives were:

- Increase participant awareness of the critical processes, issues, and activities that may arise during and following an emergency, and of the possible approaches for addressing these.

- Enhance working relationships among personnel from multiple organizations responsible for emergency preparedness and response in each of the 10 regions.

- Identify area for improvement for transportation emergency response planning and readiness in each of the 10 regions. Determine next steps to address these areas.

- Provide input to transportation emergency preparedness guidance material being prepared at the national level.

To achieve these objectives, the workshop featured two-days of tabletop exercise, group discussion, and case study presentations. Participants included executive and operations managers from multiple emergency planning and response agencies within the focus area. The focus area for most of the workshops was the metropolitan area level. However, one workshop was focused on a 60-mile stretch of rural Interstate Highway that is a key freight route.

An important element of the workshops was their multi-jurisdictional nature. Exercises were designed to require interaction among many different jurisdictions and agencies. Effort was made to include participants from as many jurisdictions within the focus area as possible, within the 75-participant limit.

This guide provides instructions on how to plan a workshop similar to those conducted. The guide describes issues that should be considered before planning begins, as well as how to plan workshop logistics, workshop content and conduct, and prepare follow-up materials. Supplemental materials provided on CD-ROM include:

- Workshop Flyer Template

- Registration Form Template

- Scenario Templates 1 and 2 (Situation Manuals)

- Scenario Presentation Templates 1 and 2

- Special Presentation Examples

- Evaluation Form Template

For more information about this product, please contact Mr. Vince Pearce at vince.pearce@fhwa.dot.gov or Ms. Nancy Houston at Houston_nancy@bah.com.

Special Considerations

Planning an emergency preparedness workshop requires significant commitments. It is important to remember that participants will be making significant time commitments to attend, so putting on a quality workshop with valuable results is critical. Organizers should consider a number of factors before deciding to undertake the planning effort.

Budget

Budgets for conducting a workshop can vary significantly based on how the workshop is designed. The number of participants will have a large impact on the budget because it affects almost all budget factors. The following items should be considered when determining a budget:

- Staff support

- Facilities

- Equipment

- Food

- Materials and supplies

- Materials shipping

- Travel

Staffing

Staffing may be the most important factor in the outcome of a workshop. Staff and organizers will be required to perform the following activities:

- Plan the exercise scenario – Scenario planners require knowledge of terrorist and weapons of mass destruction capabilities, emergency response processes, and exercise dynamics. Extensive research may be necessary. Assistance from individuals who are familiar with the local environment is extremely helpful.

- Lead the workshop and present materials – It is good to have a single lead facilitator to emcee or manage the workshop. This individual needs to manage workshop time, provide direction and context for activities, keep the audience focused, present materials, and facilitate large group discussions. Additional presenters and facilitators add variety to the workshop and provide a break for the lead facilitator.

- Facilitate breakout group discussions – Breakout groups should have a maximum of 10 to 15 participants each. Breakout group facilitators have to keep breakout discussions moving and focused. Experience with facilitation and understanding of the subject matter are critical.

- Take notes – A notetaker is needed for every breakout group. A notetaker must be able to record and synthesize information quickly (and often simultaneously) and recognize key points. In the FHWA workshops, notetakers had to have excellent computer skills to assemble a power point presentation in the last 15 minutes of the breakout discussion for use immediately afterward in the brief back presentations. It is not realistic to expect facilitators to take adequate notes while leading the discussion. Asking participants to take notes limits their participation in discussions and, generally, does not result in quality notes. Notetakers will also need to accurately record large group discussions for use in After Action Reporting and follow-up activities.

- Coordinate logistics – Conducting a workshop requires a great deal of logistics coordination before and during the workshop. Before the workshop, logistics coordinators must arrange for facilities, food, equipment, materials and supplies, participant invitations and special accommodations, and often travel. Someone must ensure that all necessary planning activities are on schedule and coordinate between the parties involved. Immediately prior to the workshop, an individual who is familiar with the workshop activities should check the facility arrangements, inventory and test equipment, and communicate expectations to other workshop organizers and facility staff. During the workshop, an individual without other key roles should monitor logistics (lights, temperature, equipment function, food arrangements, etc) and respond to problems.

- Supervise registration – Several individuals will be needed at the beginning of the workshop to greet participants, record their attendance, verify their contact information, and provide them materials and instructions.

Skilled and experienced staff can make the difference between a successful workshop and one that is a waste of participants’ time. Careful consideration should be given to the choice of facilitators. Facilitators must command respect from the audience to keep their attention throughout and make participants comfortable discussing sensitive information. Participants respond best to facilitators who are members of their own peer group and understand the issues they face. Inexperienced facilitators tend to try to participate in the discussions rather than lead them. This tendency is ineffective and turns participants off. It is also important that facilitators not be viewed as having biases or promoting their own agendas; consequently, facilitators from outside the region are often better choices than insiders. Outsiders can also bring perspectives from other regions. This allows them to ask probing questions, which can uncover weaknesses or needs and to provide helpful insights in follow-up reporting.

Time Commitments

Workshop planning requires significant time commitments. It is important that volunteers understand what may be involved when committing to assist. Dedicating staff or hiring consultants may be necessary to ensure that planning functions receive adequate and timely attention. Schedules and time estimates should be determined along with the budget.

Workshop Planning and Logistics

Responsibilities

Workshop planning will most likely be done by a team of people. Determining key workshop objectives, goals and focus should be a group effort. However, many planning activities will fall to individual team members. Responsibility should be assigned for the following tasks (these are also provided in a checklist in Appendix A):

Workshop Content Development

- Develop scenario

- Collect related background and supporting material

- Determine and invite speakers

- Prepare presentations

- Prepare participant materials

Workshop Logistics

- Arrange for facility, food, and equipment

- Make staff travel arrangements

- Ship supplies and materials

Participant Invitations and Registration

- Prepare invitation list

- Prepare and send invitation materials

- Respond to questions and special requests from invitees

- Record and confirm RSVPs

- Follow-up with critical non-respondents

- Prepare participant nametags, name tents, contact lists, and registration materials

Administration/Oversight

- Monitor budget and schedule

- Coordinate staff activities and communicate expectations

Schedule for Planning

Table 1 indicates a suggested schedule for carrying out many of these activities.

Table 1. Workshop Planning Schedule

| Time Period (Prior to Workshop Date) | Activity |
| --- | --- |
| 3-6 Months | Establish planning team and assign responsibilities |
|  | Determine budget and schedule |
|  | Develop workshop goals and objectives, and agenda |
|  | Identify and invite welcome and special speakers |
|  | Begin planning exercise scenario and collecting related and supplemental materials |
|  | Reserve facility; arrange for food and equipment |
|  | Develop invitation list and contact information |
|  | Develop invitation material |
| 2 Months | Send invitation material |
|  | Develop signs or coordinate directional signage with facility |
| 3 Weeks | RSVP deadline for participants |
|  | Follow up with critical participants |
|  | Finalize scenario based on expected participation |
| 1 Week | Create participant lists, nametags, name tents, etc. |
|  | Produce participant materials |
|  | Ship all materials and supplies to the facility |
|  | Confirm facility, food, and equipment arrangements |
| 1 Day | Check facility arrangements |
|  | Test equipment |
|  | Set up materials |
|  | Conduct workshop staff meeting |

Participation Policies and Invitation Lists

Participation in the FHWA workshops was by invitation only. This was necessary to manage the workshop size, ensure attendance by the correct people, and control distribution of potentially sensitive material.

A target invitation list should be determined based on the workshop goals and type of exercise. The FHWA workshops targeted management and specialized staff from a wide cross section of agencies, as described in Table 2. While it is good to be as inclusive as possible, it is also important that all participants have an interest in the exercise. The invitation list should be tailored to the exercise.

Table 2. Potential Workshop Participants

| Agencies | Staff |
| --- | --- |
| State and Local Level Agencies/ Organizations |  |
| Departments of Transportation/Public Works | Operations Managers Maintenance Managers Public Information Officers |
| Fire, Police, Sheriff, and Emergency Medical Services | Incident Commanders Anti-terrorism Coordinators Hazardous Materials (HAZMAT) Response Team Leader Public Information Officers |
| Hospitals | Disaster Planners |
| Transit Agencies/Authorities | Operations Managers Security Managers |
| Bridge, Tunnel, or Toll Authorities | Operations Managers Security Managers |
| Stadium Authorities | Operations Managers Security Managers |
| Metropolitan Planning Organization/ Council of Governments | Transportation Planning Managers Emergency/Disaster Planners |
| Private freight organizations* | Trucking or Rail industry representatives |
| Mayor’s/Governor’s Offices | Emergency Coordinators Public Information Officers |
| Local Media (Optional) | Trusted representative |
| Federal Agencies |  |
| Federal Bureau of Investigation (FBI) | Field Office WMD*/JTTF** Coordinator |
| Federal Emergency Management Agency (FEMA) | State Emergency Coordinator |
| Federal Highway Administration | Division Administrator |
| Federal Transit Administration (FTA) | Regional Administrator |
| Federal Aviation Administration (FAA) | Regional Emergency Transportation Coordinators |
| Research and Special Projects Administration (RSPA) | Regional HAZMAT Safety Assistance Team Leader |
| USDOT Federal Railroad Administration (FRA) | Regional representative |
| National Guard | Civil Support Team Leader |
| Coast Guard | WMD* Coordinator |

*Sources include MPO freight councils or state trucking and rail associations

** WMD – Weapons of Mass Destruction

***JTTF - Joint Terrorism Task Force

Invitation of local media should be based on their relevance to the scenario and existing relationships with local media personnel. Local media have important roles in emergency response. However, planners of the FHWA workshops were concerned that local media participation may stifle open discussion of potentially sensitive information. The decision must be made at the local level.

The FHWA workshops were limited to 75 participants. Factors to consider in determining workshop size include:

- Facility and budget capacity

- Facilitator/breakout group capacity—assume 12 to 15 participants per breakout group

- Workshop goals—the larger a group, the more difficult to accomplish specific tasks or goals

Because capacity will presumably be limited, it will be necessary to balance the number of agencies represented with the number of personnel from each agency. It is important to establish policies regarding participant substitutions and additional participants and to state these policies in the invitation material. It may be necessary to turn away other interested parties.

After the RSVP deadline, it may be necessary to follow-up with invited participants who are key to the exercise scenario but have not replied. Consequently, phone and e-mail addresses should be included when assembling invitation contact lists. Critical participants may include:

Critical Participants

Fire Department Incident Commanders from impacted jurisdictions

State and local police Commanders from impacted jurisdictions

FBI Field Office Representative

State and local Transportation Operations/Traffic Engineering Representative

Transit Authority Representative

Representatives from facilities effected by the scenario (e.g., stadium or port authorities)

County Emergency Management Agency Representative

Medical/Hospital Disaster Preparedness Coordinator

Invitation Materials

Possible invitation materials may include:

- Invitation letter

- Informational brochure

- Registration form

- Maps or directions to the facility

Sample invitation materials are provided in Appendix B.

The process of sending physical invitations and processing RSVPs is time consuming. It is important to automate the process as much as possible through development of participant databases, mail merge lists, etc. Some associations and firms offer automated invitation and registration services, often utilizing totally electronic processes.

Answering participant question is also time consuming. Including the following information in the invitation material is important for reducing potential confusion or questions:

Items to Include in Invitation Materials

Workshop purpose

Workshop date, time, and agenda

Workshop location, address, and directions (or map)

Parking provisions (if necessary)

Workshop sponsors and organizers

Invited organizations and appropriate level of personnel

RSVP procedures and deadline

Policies for accepting participant substitutions

Food provisions (provided, fee, or not provided)

Dress

Whether material presented will be classified

Contact name and information

Note that the sample invitation letter is divided into two pages; all information personal to the participant is on the first page, while the signatures are on the second. This enables the page with signatures to be duplicated and the personalized page to be electronically generated for each participant.

Facilities

The best facility layout is one large room that can accommodate all participants and staff, set up classroom style, and separate breakout rooms for each group. Breakout rooms should be in close proximity to encourage exchange between groups.

If breakout rooms are not available, the available room should be set up in clusters for each breakout group. In this case, it is important that the room be large enough to adequately separate the breakout clusters. Having all groups in one room is not ideal because the room may become loud, making it hard for participants to hear and remain focused.

Many facilities have large rooms with movable dividers. Placing a cluster in each divided section works well. Dividers can then be opened for main sessions and closed for breakout group discussions.

Food

Due to the busy schedule and short time available for lunch, the FHWA workshops had lunch served in (or just outside) the rooms. Providing lunch, or having it available on-site, encourages participant interaction (a key goal of the workshop). In regions where the host was not able to pay for lunches, arrangements were made for a caterer to provided affordable box or buffet lunches on sight (allowance for this should be a consideration in selecting the facility). Hosts also provided food and drinks for continental breakfasts and snacks.

Signs

Directional signing in the facility parking lots and lobbies is helpful. Often the facility can provide this. A large sign at the registration table also helps participants find the workshop and is a good way to acknowledge sponsors.

Equipment and Supplies

Equipment and supplies are a critical part of any workshop. The checklists below indicate equipment and supplies that were used in the FHWA workshops:

Equipment and Supplies

Basic Equipment and Supplies (Available through the Facility)

Table for registration set up outside main room

Easel for workshop sign set up next to registration table

Projection screen in primary room

LCD projector and extension cord in main room

Wireless microphone in primary room

Podium or lavaliere microphone in primary room

Flip charts, easels, and markers in each breakout room

Direction signs

Specialized Supplies (Prepared by Organizers)

Participant exercise manuals and materials

Workshop presentation material

Participant nametags

Participant name tents

Sign for workshop registration table

Workshop registration material (lists of participants, pens)

Evaluation forms

Emergency supplies: pens, markers, tape, extension cord, stapler, paper

Access to printing and duplicating capabilities within the facility is helpful for emergencies (printing nametags of participants who did not register) and special features (providing participants copies of material generating during the workshop).

Workshop Content and Conduct

Agenda and Activities

This section describes the FHWA workshop agenda and each activity and provides tips for conducting a successful workshop. Figure 1 shows a typical workshop agenda.

Figure 1. Typical Workshop Agenda

Welcome – Workshop hosts and local dignitaries (e.g., Mayor’s Office Representative, State Emergency Management Coordinator) were invited to provide a welcome.

Special Presentations – Special presentations provide information of interest to participants. The FHWA workshop featured case studies and information from FHWA and FTA. However, local or regional information (e.g., Introduction to the traffic management center capabilities) is also good material for special presentations.

Breakout Discussions – Breakout groups focused on three functional areas:

- Public Safety

- Emergency Management

- Transportation Operations and Management

Division of breakout groups by functional area reflects the way personnel would be working in an actual emergency and enabled specialization of discussions that would not be possible in mixed groups. Discussion questions were designed to encourage frequent communication among the groups. Participant liaisons exchanged information between the groups during discussions. Because transportation personnel are generally unfamiliar with emergency management procedures, most transportation participants were assigned a “rotation” to one of the other groups for one module. This also provided insights on transportation issues and capabilities to the other groups.

Ideal break-out group size is 10 to 15 participants. Many FHWA workshops had two Transportation Operations and Management Breakout groups due to the large number of participants. Participants were pre-assigned to breakout groups and Assignments were noted on participant nametags.

Breakout group discussions were 1 to 1 ¾ hours per module, depending on the amount of material, and focused on questions provided in the participant manuals and other key issues that arose. The last 15 minutes of each discussion were dedicated to identifying key action items and issues for presentation during the Brief Back Session.

Brief Back Sessions and Discussions - A member of each breakout group was asked to present the key actions and issues from the breakout discussion to the entire group. Presentations were limited to 10 minutes each, allowing approximately 30 minutes for questions and discussion. These sessions are extremely important, because they are the main times in the workshop that participants learn what other organizations do and the challenges they face.

Identification and Discussion of Regional Actions – At the end of the workshop, the Lead Facilitator asked participants to identify 10 or more priority needs or actions for the region based on the exercise results. As time permitted, these were prioritized and notes made about what entity should be responsible for follow-up.

A single presentation was developed to guide participants through all workshop activities (example provided on CD). This saved time in loading and switching presentations. The Lead Facilitator acted as emcee: keeping activities on schedule, introducing speakers, and leading the large group discussions.

Scenario Development and Conduct

The tabletop exercise is based on a pre-planned emergency scenario. Exercises should meet a number of criteria, described here:

- Tailor to local conditions and concerns – Attacks should focus on local landmarks and points of concern. Described impacts (e.g., traffic congestion) should be consistent with past experiences. Correct names of facilities and organizations should be used.

- Impact all participating agencies – Response to attacks should impact all participants. Often multi-incident scenarios are used. Participants can also be included through discussion of impacts on surrounding jurisdictions and provision of mutual aid assistance.

- Provide adequate information for participants to react – Necessary information may include descriptions of blast areas, extent of damage, gas clouds, plume characteristics, weather and temperature conditions, time of day, special events taking place, and victim’s symptoms. These should accurately reflect the type of attack.

- Be realistic – Attacks should reflect actual terrorist threats and patterns of activities.

- Challenge but not overwhelm participants – Attacks should be significantly disruptive, but not incapacitate responders (e.g., complete nuclear destruction of an area may be overwhelming; however, individual dirty nuclear devices may be good exercise material.

Consequently, design of the exercise requires knowledge of the local environment, and understanding of terrorism threats and their consequences. Failure of small details in the exercise design can lead participants to reject the validity of the exercise and render unsuccessful results. The FHWA workshop exercises were designed by WMD/anti-terrorism experts from the consulting firm Booz Allen Hamilton, with support from local public safety and transportation officials. Several exercise scenario templates are provided in the supplemental material to this guide.

The FHWA workshop exercises were divided into three time periods to focus on the three primary aspects of emergency management: preparedness, response, and recovery. A presentation was made at the beginning of each module to describe the event scenario. A description was also provided in participant manuals. Participants were given the manuals at the beginning of the workshop, but asked not to read ahead.

Supplemental material also helped to make the workshop realistic and successful. Background information on the regional transportation network, emergency plans, and other special factors was provided in each participant manual. Large maps of each incident site and the regional transportation network were provided in the breakout rooms and participants were encouraged to use and make marks on them in their discussions. A traffic engineer from the region was provided the scenario in advance and asked to brief the audience on expected traffic conditions at key time intervals (15 minutes, 30 minutes, 1 hour, 2 hours) after the event.

The supplemental materials include two scenario templates that can be used as a basis for planning. The scenario templates can be used as participant manuals and are designed to be used in conjunction with the agenda provided and the presentation templates. The templates present generic scenario and workshop information, leaving placeholders where the scenario planner should insert region-specific information. Placeholders and instructions to the planner are in red text for immediate visibility. Users will need to change the text to the correct color after inserting the required information. Some of the presentation template slides include speaking notes.

The scenarios in the template assume certain regional characteristics (e.g., port facility, rail line that carries toxic chemicals, special events that take place in proximity to other features, limited alternative routes to those attacked, etc.). The scenario may need to be materially altered to represent actual regional conditions. Consequently, simple plugging of information into the scenario is not recommended. The planner should first develop a vision for the scenario based on workshop goals and regional characteristics and then use applicable parts of the template scenarios.

Scenario 1 features detonation of a “dirty” nuclear devise at a port and Scenario 2 features two highway bridge explosions and a chlorine gas leak. Additional features of each scenario are described in Table 3.

Table 3. Scenario Template Descriptions

| Feature | Scenario 1: Port Dirty Nuclear Explosion | Scenario 2: Highway Collapse/Chlorine Gas Leak |
| --- | --- | --- |
| Weapon | Dirty nuclear bomb, explosives | Explosives, Chlorine gas |
| First target | Ship/port | Highway overpass |
| Second target | Highway overpass | Highway rail overpass, train carrying hazardous materials |
| Time of year | Summer, July 4 | Summer |
| Time of day | Morning rush hour | Evening rush hour |
| Special features | Holiday travel | Outdoor festival near second incident scene |
| Modes effected | Freight (port operations), highway | Freight (rail operations), highway |
| Major issues | Radiation preparedness, evacuation, mass hysteria, transportation gridlock, multi-jurisdictional cooperation | Chemical preparedness, evacuation or sheltering for special event, transportation gridlock, multi-jurisdictional cooperation |

Workshop Follow-Up

Prompt follow-up is critical to maintain the focus and momentum generated in a workshop. This section describes important workshop follow-up actions and reports. An organizer or host should take responsibility for ensuring distribution of follow-up materials, planning follow-up activities, and pursuing key actions identified.

Workshop Handout Materials

Any information that can be handed out to participants before they leave the workshop is especially useful. These may include:

- of brief back presentation materials

- Lists of identified issue and action items

- Updated participant contact lists based on actual attendance.

Generating these materials in real time and producing them before the end of the workshop can be difficult and requires capable and prepared staff.

After Action Report

After action reports are reports of key workshop outcomes. Included should be:

- Regional actions identified in the final discussions

- Results of the brief back presentations and discussions

- Key issues or shortcomings identified in the breakout discussions

- Organizer and staff analysis of outcomes and recommendations.

Thank You Letters

It is a good idea to formally thank hosts, sponsors, and guest speakers following a workshop.

APPENDIX A: Workshop Planning Checklist

APPENDIX B: Sample Invitation Material

Sample Invitation Letter

«Date»

«Salutation» «First Name» «Last Name»

«Job Title»

«Organization»

«Street Address»

«City», «State»  «Zip Code»

Dear «Salutation» «Last Name»:

The «Sponsors» request your participation in an invitation-only workshop on Emergency Transportation Preparedness and Response, to be held «Workshop Date» in «Workshop Location». The workshop is intended to assess the «Name of Region» region’s ability to respond to potential terrorist threats and catastrophic events, and to recover critical transportation functions. Participants will work together to develop responses to a realistic terrorist scenario in a two-day tabletop exercise, which has been designed by anti-terrorism «or Other» experts from «Workshop Designer». Invited participants include senior operations managers from area transportation, public works, police, fire, emergency medical services, state and federal emergency management, public health, hospital, military, National Guard and other relevant agencies and organizations.

Your participation is very important to make this a realistic and productive workshop. Due to the sensitive nature of the material, we ask that only the invited participant or a single delegate attend. To notify us of your intent, please return the enclosed registration form by «Registration Deadline». If you have any questions, please contact «Contact's Name»  at «Contact's Phone Number»or «Contact's e-mail address».

Sample Invitation Letter (Continued)

Page 2

This workshop is one of «Number of Workshops» such workshops to be conducted nationwide. The outcomes may be applied to improve national emergency response planning tools, in addition to enhancing the «Name of Region» region’s emergency response capabilities. Enclosed is a flyer with information about the workshop schedule, location, and other logistics. The conference hosts thank you for your attention to this invitation, and we sincerely hope that you will help us make this workshop a success through your participation.

Sincerely,

«Signatory's Name», «Signatory's Title»

«Signatory's Organization»

«Signatory's Name», «Signatory's Title»

«Signatory's Organization»

## Sample Invitation Brochure

Sample Invitation Registration Form

Sample Evaluation Form

Evaluation Form ― Emergency Transportation Operations

Preparedness and Response Workshop ― <Name of Region>

Role:	Observer	Emergency Management	Public Safety	Transportation Operations / Planning

Name / Agency Name (Optional):

I.      Personal Background - Before the exercise: Please circle the appropriate response.

| 1. | Have you received transportation emergency management training previously? | Yes | No |
| --- | --- | --- | --- |
| a. | If yes, when was your last training? (month/year)? | _________ | __________ |
| 2. | Have you been a participant in previous transportation emergency management exercises? | Yes | No |
| a. | If yes, when was your last exercise? (month/year)? | _________ | __________ |
| b. | If yes, did any of these have a WMD focus? | Yes | No |
| Please rate the following on a scale of 1 (strongly disagree) to 5 (strongly agree). |
| 3. | My role in a WMD incident is well defined. | 1 | 2 | 3 | 4 | 5 |
| 4. | My agency’s role in a WMD incident is well defined. | 1 | 2 | 3 | 4 | 5 |

II.  Exercise Design

| Please rate the following on a scale of 1 (strongly disagree) to 5 (strongly agree). |
| --- |
| 1. | Was the scenario realistic and challenging? | 1 | 2 | 3 | 4 | 5 |
| 2. | Was your group actively engaged during the exercise? | 1 | 2 | 3 | 4 | 5 |
| 3. | Was the time sufficient to play the exercise? | 1 | 2 | 3 | 4 | 5 |
| 4. | Were institutional relationships encouraged between tables? | 1 | 2 | 3 | 4 | 5 |
| 5. | Please comment on overall exercise design: |

III.	Facilitators:

| Please rate the following on a scale of 1 (strongly disagree) to 5 (strongly agree). |
| --- |
| 1. | Did the Facilitators keep the table on track and moving forward? | 1 | 2 | 3 | 4 | 5 |
| 2. | Did the Facilitators provide useful, relevant technical advice? | 1 | 2 | 3 | 4 | 5 |
| 3. | Overall comments on Facilitators: |

IV.   Personal Background - After the Exercise:

| Please rate the following on a scale of 1 (strongly disagree) to 5 (strongly agree). |
| --- |
| 1. | Do D Do you have a better understanding of: |  |  |  |  |  |
| a. | Your role in a WMD incident? | 1 | 2 | 3 | 4 | 5 |
| b. | Your agency’s role in a WMD incident? | 1 | 2 | 3 | 4 | 5 |
| c. | The roles, responsibilities, and methods of other WMD responders? | 1 | 2 | 3 | 4 | 5 |
| 2. | Were your personal goals met for the workshop? | 1 | 2 | 3 | 4 | 5 |
| 3. | Please comment on overall exercise design: |

V.	Overall Impression of Workshop:

| 1. | Please comment on the positive aspects of the workshop: |
| --- | --- |
| 2. | Please comment on the areas of the workshop needing improvement: |
| 3. | Were the case studies and reference materials useful? | Yes | No |
| 4. 5. | Did they add value to the exercise? | Yes | No |
|  | Please comment on the case studies and reference materials: |

# Text boxes

Day 1:

7:30 a.m.	Registration

8:00 a.m.	Workshop Introduction and Welcome

8:30 a.m.	New York City September 11 Case Study Presentation and Discussion, Part I: Response Actions

9:15 a.m.	<Special Presentation>

9:45 a.m.	Break

10:00 a.m.	Participant Introductions

11:00 a.m.	Module 1: Pre-Incident Planning and Preparation, Module Introduction

11:30 a.m.	Lunch

12:00 p.m.	Module 1: Breakout Discussion

1:00 p.m.	Group Brief Back and Discussion

2:00 p.m.	Break

2:15 p.m.	Module 2: Initial Response Actions (0 – 24 Hours Post-Incident), Introduction

2:45 p.m.	Module 2: Breakout Discussion

4:30 p.m.	Adjourn

Workshop Planning Checklist

|  | Develop Workshop Content |  |
| --- | --- | --- |
|  | Goals and Objectives |  |
|  | Agenda |  |
|  | Scenario |  |
|  | Background and supporting material |  |
|  | Presentations |  |
|  | Speakers |  |
|  | Arrange Workshop Logistics |  |
|  | Facility |  |
|  | Food |  |
|  | Equipment (see related checklist) |  |
|  | Staff travel |  |
|  | Materials and supplies |  |
|  | Invite and Register Participants |  |
|  | Invitations |  |
|  | Registrations |  |
|  | Prepare Participant Materials |  |
|  | Exercise manuals |  |
|  | Nametags and name tents |  |
|  | Contact lists |  |
|  | Evaluation form |  |
|  | Assign and Coordinate Staff Roles |  |
|  | Lead Facilitator |  |
|  | Breakout Facilitators |  |
|  | Note takers |  |
|  | Registrars |  |
|  | Special speakers |  |

Day 2

8:00 a.m.	Group Brief Back and Discussion

9:30 a.m.	Break

9:45 a.m.	New York City September 11 Case Study Presentation and Discussion, Part 2 (Recovery)

10:30 a.m.	Module 3:  Extended Response and Recovery Actions (>24 Hours Post-Incident), Introduction

11:00 a.m.	Module 3: Breakout Discussion

12:00 p.m.	Lunch

12:30 p.m.	Module 3: Breakout Discussion (continued)

1:00 p.m.	Group Brief Back and Discussion

2:00 p.m.	Break

2:15 p.m.	Identification and Discussion of Regional Actions

3:15 p.m.	<Special Presentation>

3:45 p.m.	Adjourn

DAY 1

DAY 2

## Planning Tabletop exercises for

TRANSPORTATION OPERATIONS PREPAREDNESS AND RESPONSE TO TERRORIST INCIDENTS

Thank you for completing this form.