Manager: Manage Data Development
Work Instruction

Purpose

The purpose of the manager role here is to monitor the workflow progress of the specific data development tasks and their associated QA activities, and to update the cost and schedule information for these tasks.  Once the task status information has been entered, the user has the opportunity to enter any leverage information for the specific tasks.

Prerequisites

- Obligate Project Funds has been completed, and the data development tasks have been assigned to specific organizations/contractors.

- The cost and schedule information for the data development tasks should be updated regularly (at least monthly) by the manager role as work progresses.

Navigation

| Via Menu Path | Home ( Workbench ( Work Items then Manage Data Development |
| --- | --- |

Work Steps

1.	Click on:  to claim the task you want to perform.

2.	Click on:  link to enter the task.

3.	Click on: arrow to expand and review the baseline information.

4.	Click on:  arrow to expand and review information for the QC tasks.

5.	Click on:  arrow to expand and enter information for the Develop DFIRM Database task.

6.	Click on and enter Actual Start Date.

7.	Type 07/03/2007.

8.	Click on and enter Actual Cost to Date.

9.	Type 25000.

10.	Click on and enter As Of date.

11.	Type 07/17/2007.

12.	Click on and enter Percent Complete.

13.	Type 44.

14.	Click on:  to save this information.

15.	Click on and enter Projected Preliminary Date that the map is projected to be issued.

This date is critical!  It will be used to determine projected KPI information by Congress, FEMA HQ, etc.

Note: By clicking Update Status, the EV information is updated in real time to show the impact of the changes made.

16.	Type 09/30/2007.

17.	Click on and enter Comments.

You can use this field to enter any comments about this task.  These will be seen in reports such as the Study Progress Sheet (Quarterly Report).  Clicking the (c) above this box will show an archive of comments.

Note: The icon buttons can be clicked to find more information about the metadata (m), DFIRM QA (d) or the workflow history (i).

18.	Type Project is in Review.

19.	Click on:  to capture the information entered thus far.

20.	Click on:  link to enter the task and add information about the Independent QA/QC of the DFIRM.

21.	Click on:  arrow to expand and see project information.

22.	Click on:  arrow to expand and enter information about the QA/QC.

23.	Click on and enter Actual Start Date of QA/QC.

24.	Type 08/01/2007.

25.	Click on and enter Actual Cost to Date.

26.	Type 10000.

27.	Click on and enter As Of date.

28.	Type 08/06/2007.

29.	Click on and enter Percent Complete.

30.	Type 75.

31.	Click on and enter any Comments.

32.	Type QA complete.  Awaiting final materials from Denver Office.

33.	Click on and enter Actual End Date of the QA task.

34.	Type 08/06/2007.

35.	Click on:  to save this information.

36.	Click on:

You have now scrolled down to the DFIRM database task.  Since it has been a month since you statused tasks, you need to mark this area as complete to advance the workflow.

37.	Click on and enter Percent Complete.

38.	Type 100.

39.	Click on and enter the Final Cost.

40.	Type 50000.

41.	Click on and enter Actual End Date of the task.

42.	Type 08/01/2007.

43.	Click on:

You have now scrolled down, and are ready to enter Leverage information for the Data Development portion of your project.  .

44.	No leverage was provided for QA/QC, so click on:  radio button.

45.	Click on:  to enter this information.

However, there was leverage provided by a mapping partner for the DFIRM database.

46.	Click on and enter Quantity of the leverage (whether dollars or units).

47.	Type 10.

48.	Click on Type and select the type of leverage provided. In this example, select Preliminary DFIRM Panels.

49.	Click on:

50.	Click on Contributed By and select who the leverage was contributed by. If you don't see the organization you are interested in, contact your RMC or MIP Help. In this example, select Colorado Water Conservation Board (CWCB).

51.	Click on:

52.	Click on Federal Fiscal Year and select 2007 from the dropdown.

53.	Click on:

54.	Click on and enter Comments about the leverage being provided.

55.	Type CWCB prepared panels 1-10 and delivered to us.

56.	Click on:  to capture the project leverage. Once complete, you could repeat these steps if multiple organizations have contributed leverage.

57.	Click on:  to move onto the Review screen and take one more look at all of the information entered for data development.

58.	Click on:  to see all information.

59.	After you have scrolled through the information, and verified that it is correct click on:  to complete the task, and advance the workflow.

Note: If any of the information is incorrect, use this back button to make edits.

60.	Click on:

Once clicked, the task will close, and you will no longer be able to make edits.  Any information that needs to be updated must be coordinated through the Region, RMC or MIP Help.

Results

By entering in the actual cost, schedule, and percent complete to date, the SPI (Schedule Performance) and CPI (Cost) are calculated and displayed. Once all Data Development tasks are complete for all areas in the project, the study is able to move on to preliminary mapping.