West Region Technology Workgroup

and Technical Discipline Consortia

Business Plan

FY2008 – FY2009 with Progress as of 10/1/08

West Region Technology Workgroup (WRTWG) Members:

Russ Hatz, Leader for Technology – Oregon, Chair

Mark Weatherstone, ASTC (Technical Services) –   Idaho

Rob Sampson, SCE - Idaho

Ron Nadwornick, SRC – Montana

Chuck Gordon, SSS - Montana

Jerry Jasmer, SRC – Wyoming

Frank Riggle, SRC – Colorado

George Chavez, SRC – New Mexico

Steve Barker, SRC – Arizona

Ron Davidson, SRC – Utah

Mike Odegard, SRC – Nevada

Bill Dollarhide, SSS – Nevada

Diane Holcomb, SRC - California

Charles Davis, SCE – California

Paul Scales, SRC – Washington

Eugene Schock, SRC – Alaska

Anthony Ingersoll, Assistant Director for Technology - Pacific Islands

WRTWG Advisor:

Larry Yamamoto, Director – PIA

WRTWG Coordinator:

John Copeland, NTS, WNTSC - Portland

West Region Technical Consortia/ Chairperson/Mentor:

Agronomists – Rick Fasching – Steve Barker

Biologists – Peter Husby – Jerry Jasmer

Cultural Resource Specialists/Coordinators– Andy Williamson – Mike Odegard

Economists – Julie Nelson – Gene Schock

Engineers – Rob Sampson – Charles Davis

Foresters – Frank Gariglio – Ron Nadwornick

Grazing Lands Specialists – Brendan Brazee – George Chavez

Plant Materials Specialists/PMC Managers – Joe Williams– Frank Riggle

Soil Scientists – Dave Hoover – Chuck Gordon

Water Quality Specialists – Tom Pick – Paul Scales

Past Chairpersons:

FY2005 – Ron Nadwornick, SRC, Montana

FY2006 – Ron Nadwornick, SRC, Montana

FY2007 – Mark Weatherstone, ASTC (Technical Services), Idaho

Role of the West Region Technology Work Group:

- Coordinate technology transfer at the state level

- Coordinate technology needs across state lines

- Coordinate technical support activities

- Assist in determining technology transfer and training needs

- Assure that available and needed technology is delivered to specialists and field staffs

- Coordinate technology needs at the field level

- Facilitate the development of high priority and mission critical technology

Role of the West Region Discipline Consortia:

- Communicate with other State Technical Specialists and identify opportunities for collaboration

- Work together on projects assigned by the WRTWG to find favorable solutions to problems or develop requested products and eliminate duplication of efforts

- Strive for consistent and compatible technical information being utilized in the field.

- Identify research and technology development needs among the states.

- Work to eliminate inconsistencies in the implementation of technology and technical processes across state lines.

- Forward information and technology needs to the West Region Technology Work Group.

- Forward information and regional technology needs to leadership within the consortium.

- Function as a two-way communications mechanism between the WRTWG and the Field, including Technical Discipline Specia1ists.

Relationship to the West National Technology Support Center:

This business plan focuses on coordinating the activities of the Western States to reduce duplication and improve technology delivery.  The activities listed in this plan reflect efforts to be carried out by the States working in partnership with the WNTSC.  The WNTSC is supporting most of the activities in this plan and, for those items for which the WNTSC is providing support, the name of the WNTSC specialist is shown and a reference number to the WNTSC business plan may also be included.

Action items that require a budget have been approved by the WRTWG and are highlighted in green.  Many of the action items will be accomplished by state staff with no additional expenditure of funds.  It is understood that all consortia would benefit from an annual meeting if budgets allow.

| Organizational Activities |
| --- |
| Evaluate WRTWG/Consortia organizational structure | April 2008 | WRTWG/ Consortia | Complete |  | John Copeland |
| Obtain and Develop Technology |
| Objective: Obtain and develop technology needed to promote productive soils, clean air and water, and healthy plant and animal communities. |
| Work with the WNTSC and PMCs to identify appropriate biomass and biofuel crops and the associated resource impacts of growing them in the west. | June 2008 | Frank Riggle/Plant Materials Specialists/ Coordinators Consortium | Included in Los Lunas PMC business plan. Carry over. |  | Jim Briggs |
| Assist the WNTSC Energy Team to develop a process for conducting an on-farm energy audit and identify the role NRCS would play in the audit. | Sept 2009 | Charles Davis/Engineers Consortium | Complete |  | Stefanie Aschmann |
| Evaluate technology needs and identify new priorities such as PDAs, tablets, GIS, etc. that could streamline, enhance, or speed up cultural resources fieldwork and reviews. | 2008 | Marsha Sims/Cultural Resource Specialists/ Coordinators Consortium | Complete. Consortium determined that existing technology could be expanded to incorporate use of Trimble GPS technology, remote sensing into cultural resource investigations and conservation planning. |  | Meg Bishop |
| Explore options for using market based approaches to solve resource concerns. | Mar 2008 | Jerry Schaefer, Hal Gordon/ Economist Consortium | Complete. Jerry published an economics tech note entitled Soil Carbon Sequestration Opportunities for MT Producers and was posted on the economics website. |  |  |
| Develop a proposed NPMM policy regarding seed/plant transfer zones. | July 2009 | Briggs/Pendergrass/ Plant Materials Specialists/ Coordinators Consortium | Complete |  | Jim Briggs |
| Develop a proposed NPMM policy and procedures relative to selection of wildland seed/plant populations. Use of common garden studies, genetic study protocols, etc. | July 2009 | Briggs/ Plant Materials Specialists/ Coordinators Consortium | Complete |  | Jim Briggs |
| Encourage the development of a publication to supplement Tables 11-6, 11-8, and 11-9 in the AWMFH for the Western Region. Participation and coordination in an effort to summarize and evaluate available mineralization, volatilization, and denitrification of organic fertilizer materials (manure) used in the West Region. | FY 2008 | Rick Fasching, Agronomists Consortium | On-going. States have determined which tool they will use. This item may no longer be relevant. | None | Tom Gohlke , Charles Zuller, Dan Sullivan (OSU), Robert Flynn (NMSU), Jessica Davis (CSU), Pettygrove from CA |
| Provide input and review proposals to facilitate the introduction and use of bio-energy crops in the West Region. | FY08 | Agronomists Consortium | On-going. Concerns with increased soil erosion potential! Carry over to 2009-2010 plan. |  | Stephanie Aschmann |
| Explore the idea of an IPA with FWS to help with programmatic consultations | Mar 2008 | Deborah Virgovic/Biologists Consortium | Completed and meetings are planned. |  | Meg Bishop |
| Develop and submit a problems/needs report to Bruce Wight on the use of VEGSPEC forestry practices in the West. | FY 2008 | All States/ Foresters Consortium | Complete |  | Jim Briggs (coordinate with the West Plant Materials Consortium), Lyn Townsend, James Henson, Bruce Wight |
| Cooperate with the WNTSC and NHQ WEPP-RUSLE2 Forest Land Erosion Pilot study by providing site data and WEPP runs to the WNTSC. | FY 2008-2009 | All States using WEPP on forest land applications/ Foresters Consortium | Complete |  | Lyn Townsend, Tom Gohlke, Bruce Wight (CNTSC), Vacant (ENTSC), Andy Mason (NHQ) |
| Determination of the extent, condition, and treatment needs of riparian areas (having a forest potential) in agricultural areas using GIS/remote sensing analysis pilot projects (would include existing statistics from CCRP, CREP, and EQIP accomplishments). | FY 2009 | States?/ Foresters Consortium | Determined to be not feasible. Cancelled |  | Terry Aho, Lyn Townsend, Kathryn Boyer, Wendell Gilgert, Pat Shaver, Jamie Gillum(WRSL), TBD (FIA), TBD (EPA) |
| Develop a process that the WQ Consortium will utilize to provide input on water quality related tools and materials submitted for review by NTSC or other entities. | Dec 2007 | Hudson Minshew/ Water Quality Specialists Consortium | Completed. Prepared request letter and submitted. Process in place and working |  | Shaun McKinney |
| Acquire timely updates on water quality tools and materials under development: Water quality criteria Water quality handbook Nitrogen trading tool Watershed health indices ARS/CSU Nitrogen Index CSP Eligibility Tool Water Quality CSP enhancements MMP WIN-PST Pathogens Pharmaceuticals SPAW SWAT BASINS | Aug 2009 | Becky Challender/ Water Quality Specialists Consortium | Completed Review-feedback provided on: Wq criteria Water Quality Handbook SWET WQ CSP enhancement |  | Shaun McKinney |
| Conduct Tall wheatgrass regional scale intercenter strain trial study to evaluate biofuel potential and develop first year regional report. | On-going | AZ, CA, CO, ID, NV, OR, MT, WA / Plant Materials Specialists Consortium | Complete |  | Jim Briggs |
| Conduct planned ICST’s and develop first year region reports: Alkali sacaton AZ Cottontop | 2008-2010 | AZ, CO, NM, CA, NV PMC’S/ Plant Materials Specialists Consortium | Complete. Squirrel tail and Sandberg bluegrass trials will be established in 2008-2010. |  | Jim Briggs |
| Complete development of a region wide plant materials study plan to address sage grouse habitat needs in collaboration with Biology consortia. | On-going | Plant Materials Specialists Consortium | 50% complete. 2 draft study plans developed. Coordination and input from PM consortia and biologists needed. |  | Jim Briggs |
| Provide peer review of selected new plant release packages and other technical documents as needed | Sept 2009 | Plant Materials Specialists Consortium | Complete |  | Jim Briggs |
| Advance a list of research support needs that will enhance the data gathered for ecological site descriptions (eg, hydrology section of ESDs can use data from RHEM model). | April 2009 | Herman Garcia/ Grazing Lands Specialists Consortium | Working with Ken Spaeth and Grazing land Technology team with development |  | Pat Shaver, Jeff Repp |
| Develop inventory of available benchmark soil characterization data to analyze for potential enhancements to understanding of soil organic matter and related soil property data as they related carbon budget modeling. Develop draft multi-year state and transition model hypothesis benchmark soil sampling strategy for gathering additional data to enhance soil survey database. |  | Soil Scientists Consortium | Delete – add new item in next year’s plan. |  | Terry Aho |
| Refine and Deliver Technology |
| Objective: Ensure that field personnel have technology that is up to date, easily accessible, and designed to meet user needs. |
| Assist the WNTSC develop planning guides for use in the field to improve air quality. | June 2008 | Charles Davis/John Beyer | 75% complete. |  | Greg Johnson |
| Advance a list of research support needs that will enhance the data gathered for ecological site descriptions (eg, hydrology section of ESDs can use data from RHEM model). | Dec 2008 | Jon Gustafson, Jerry Rouse/ Grazing Lands Specialists Consortium | On-going |  | Pat Shaver, Jeff Repp |
| Determine technology gaps in planning tools, such as Comet-VR, available for use by the field for air quality. | Dec 2007 | Frank Riggle | Meeting held in CA on “Comet-VR. |  | Greg Johnson |
| Coordinate development & refinement of biology and wetland assessment models | Dec 2007 | Karen Fullen/ Biologists Consortium | 50% complete. |  | Wendell Gilgert/ Kathryn Boyer |
| Field test Supplements to the 1987 COE Wetlands Delineation Manual. | Sept 2008 | Terri Skadeland, Bill Wood/ Biologists Consortium | Complete-Training was held in CO for CO, WY, & UT on wetland delineation, incorporating supplements |  | Meg Bishop |
| Develop a strategy for what NutBal should be (and be used for) in the West Region. Training, implementation, outreach and Program utility. | Dec 2008 | Lori Metz/ Grazing Lands Specialists Consortium |  |  | Jeff Repp, Arnold Norman |
| Solicit and share success stories from the Western States that have used the Market Based Approach in solving resource concerns. | June 2008 | Gene Schock/Economists Consortium | Completed. Discussed at Economist Consortium teleconference. It was reported that there was a lot of discussion about market based approach theories but very little practical application at this time. |  | Stacy Mitchell |
| Determine if and where Quality Criteria above the sustainable level should go in the FOTG | June 2008 | Mark Weatherstone/ WRTWG |  |  | John Copeland |
| Make recommendations on Dynamic Soil Properties related to their collection, storage, and retrieval. | Sept 2008 | MO Leaders/Soil Scientist Consortia | Complete |  | Terry Aho |
| Evaluate in collaboration with appropriate state specialists consistency of plant materials related state conservation practice standards and specifications across state boundaries. Practices undergoing National revision will be selected*. | Sept 2009 | Plant Materials Specialists/ Coordinators Consortium |  |  | Jim Briggs |
| Develop a strategy for meeting wetland training needs until National training is funded and developed. | July 2008 | Tim Dring/Terri Skadeland Biology Consortium |  |  | Wendell Gilgert |
| Collect photos of Western tillage implements labeled to correspond with the RUSLE2 operations database and send to Joel Poore, WA. | Mar 2008 | Joel Poore, members/ Agronomists Consortium | Carryover to 2009-2010 plan |  | Tom Gohlke |
| Provide coordination for the 2008 National Agronomy Workshop to be held in the Palouse region of WA. | 2008 | Rick Fasching/ Agronomists Consortium | Cancelled for FY 2008. |  | Tom Gohlke, Norm Widman, (National Agronomist) |
| Encourage work towards an inclusion of an irrigation-erosion model within RUSLE2. | FY 2008 | Rick Fasching/ Agronomists Consortium | On-going. Idaho ARS is currently piloting a program. Carryover to 2009-2010 plan |  | Tom Gohlke, Clare Prestwich |
| Form a committee and review common conservation practices and proposed revisions to the energy resource concerns. | FY 2008 | Rick Fasching/ Agronomists Consortium | On-going. Subcommittee has reviewed several common conservation practices. |  | Stef Aschmann |
| Develop an interim standard – Fish and Wildlife Structures | Feb 2008 | Pete Husby/ Biologists Consortium | Draft is complete. Carry over to 2009. |  | Kathryn Boyer/Wendell Gilgert |
| Develop a web page that has all habitat assessment models used in the West Region | Sept 2008 | Biologists Consortium | Sharepoint was set up by Wendell. ~50% of states have entered models. Continue into 2009 |  | Wendell Gilgert |
| Maintain updated point of contact (POC) by discipline: Soil Mechanics – B Ward Construction/ASTMs – M Milani Irrigation – C Prestwich Hydrology/Hydraulic – D Moore, Q Quan Design/Structures –S Durgin Fluvial Geomorphology - R Sampson Engineering Geology - P Pedone CAD - K Dastrup, K Yasumiishi | On-going | John Harrington/ discipline point of contacts/ Engineers Consortium | On-going |  | Kip Yasumiiishi, Charles Zuller, Peter Robinson |
| Develop wild land fire recovery measure BMP guide for use with EWP/ECP applications. | May 2008 | Andrews, Chavez, Davis/ Engineers Consortium | Complete |  | Kip Yasumiishi |
| Combine available CAD details/drawings into one on-line catalog. (Or listing of drawings and location) | May 2009 | Andrews, Yasumiishi/ Engineers Consortium | 25 % complete |  | Kip Yasumiiishi |
| Update six (6) national conservation practice standards annually. | Sept 2006 | TBD/ Engineers Consortium | Complete |  | Kip Yasumiiishi, Charles Zuller, Peter Robinson |
| Support the multi-state design teams. | On-going | Charles Davis (Regional Tech Work Grp member)/ Engineers Consortium | On-going |  | Kip Yasumiiishi, Charles Zuller, Peter Robinson |
| Distribute electronically examples of agreements that include streamlining activities regarding specific structures such as canals for Cultural Resources Management (CRM) | FY 2009 | Marsha Sims/Cultural Resource Specialists/ Coordinators Consortium | 75% completed at end of FY 2008. Cultural Resources Consortium determined greater need for existing example documents to be compiled into an electronic repository for use. |  | Meg Bishop |
| Distribute electronically a summary of technology helpful in recognizance level for completing survey/inventory of CRM | FY 2009 | Marsha Sims/Cultural Resource Specialists/ Coordinators Consortium | Complete. Cultural Resource Consortium included discussion, demonstration of GPS and remote sensing software for use in cultural resource investigations. |  | Meg Bishop |
| Prepare and submit: 1) a national practice standard draft for Road and Landing Closure/Removal; and 2) a revised national practice standard draft for Forest Trails and Landings (655) standard. | FY 2008 | WA, CA, OR/ Foresters Consortium | Complete | $1000 (to support travel expenses for state agency personnel) | Lyn Townsend, TBD (USFS/State Agency), TBD (WNTSC Env. Engineer) |
| Develop a West-wide template for thinning/spacing and slash treatment guidelines for western species including site-level criteria (slope, remoteness, etc.) to determine "effort" intensities and associated costs for use with EQIP and other programs. | FY 2008 | All States/ Foresters Consortium | Complete |  | Lyn Townsend, Hal Gordon |
| Develop a coordination plan to accomplish completion of high priority forest ecological sites in West states including: 1) specifications for using TSPs, universities, and other experts; 2) coordination with biology and range disciplines; 3) a consensus on minimum requirements to formulate and publish ecological site description. | FY 2008 | All States/ Foresters Consortium | Complete |  | Lyn Townsend, Wendell Gilgert, Pat Shaver, George Peacock, Curtis Talbot, Bruce Wight |
| Develop agroforestry case studies: 1) effects of existing windbreaks for air quality improvement around animal feeding operations; 2) evaluation of existing multi-story cropping applications to evaluate the practice under western conditions. | FY 2008-2009 | CA, OR (other states?) / Foresters Consortium | Medium priority - 10% complete – On-going | 1) $5000 2) $2500 | 1) Greg Zwicke (National Air Quality Team), Bruce Wight (National Agroforestry Center); TBD (University) 2) Bruce Wight, TBD (University) |
| Formulate a report to the National Forester consisting of needed changes (from a West perspective) to the National Forestry Manual and Handbook. Note: The NFM-NFH are being revised by a national team in FY 2008-2009. | FY 2008 | OR, WA, MT, PIA/ Foresters Consortium | Complete |  | Lyn Townsend |
| Evaluate water quality modeling tools: Compare west region states’ use of water quality related tools and models and identify gaps/needs for quantifying conservation effects. Invite specialists to present emerging technologies through teleconferences and workshop Request Water and Climate Center update the list of water quality models available, with specific information on use (platform, application, how data intensive, etc.) | Dec 2007 | Dee Carlson/ Water Quality Specialists Consortium | Complete First draft of Comparison Tools document completed 1/08. Add column to tables for documentation req. Presentations made on: WQ trading at Oct. 07 teleconference; pharmaceuticals at proposed WQ meeting. WQ model document sent out; query to states on current wq model use – results drafted 1/08. Report at 08 conference. |  | Shaun McKinney |
| Explore water quality trading: Obtain relevant information on WQ trading (talking points, training/info materials, powerpoints) for use in the western states. Develop a document highlighting the various approaches used in western states concerning WQ trading, including state-specific examples and opportunities and limitations. | Sept 2008 | Tom Pick/Water Quality Specialists Consortium | Will replace with new item for ‘09-‘10 Presentation at Oct. 08 teleconference on Idaho’s Lower Boise River WQ Trading Project; Fact sheets sent out and links to trading topics/env. Credit newsletters online (Carl Lucero) Trading topic on agenda for Sept. conf. in Albuquerque |  | Carl Lucero |
| Prepare a brief summary of west region CIG and CEAP projects related to water quality with objectives/outcomes concerning effectiveness of conservation practices in improving water quality | Feb 2009 | Water Quality Specialists Consortium | Complete. Begun January 2008. Discussion of summation at WQ conference and decide on best way to distribute information gathered. |  | Shaun McKinney |
| Work with biology and forestry consortium on evaluation of new tools and technology available to streamline field data collection. Tools, technology etc. to develop list/costs. | Sept 2008 | Lori Metz/ Grazing Lands Specialists Consortium | Coordinating list for purchase and development of tools for data collection. |  | Pat Shaver, Jeff Repp, Gene Fults |
| MLRA 35 S&T model development workshop. Tentative location in Farmington, NM area. | Sept 2008 | John Tunberg/ Grazing Lands Specialists Consortium | Complete |  |  |
| MLRA 28A S&T model development workshop. Toolle, Utah | Sept 2008 | Shane Green/ Grazing Lands Specialists Consortium | Complete |  |  |
| Continue to act on National Bulletins dealing with Soil Survey or Technical Soil Services. This includes testing of new models and/or interpretations and sharing of the results. |  | Soil Scientists Consortium | Complete |  | Terry Aho |
| Be proactive in promoting education and outreach activities related to soils to our non-traditional and Tribal customers. Examples of non-traditional customers might include landscape architects, members of the American Planning Association, Realtor Consortia, etc. |  | Soil Scientists Consortium | Complete |  | Terry Aho |
| Develop Forage Preference tables by MLRA/LRU to replace individual state lists. | Sept 2009 | John Tunberg/Bob Gallaspy/ Grazing Land Specialists | started |  | Jeff Repp, Gene Fults |
| Incorporation of Forest Visualization Simulator models for stand inventory, assessment, and planning future desired stand conditions. NEW FROM 11/07 WFC TELECONFERENCE | FY 2008 | AK/Foresters Consortium | 10% complete On-going |  | Mitch Michaud |
| Train and Support the Field |
| Objective: Ensure that our employees acquire and maintain the knowledge and skills needed to be successful. |
| Distribute electronically the revised 2008 edition of Ag. Handbook 339 “Grasses and Legumes for Soil Conservation in the Pacific Northwest and Great Basin States” | Sept 2009 | Stannard-WA Ogle –ID/ Plant Materials Specialists Consortium | 66% complete. | $3000 - for hard copy publication | Jim Briggs |
| Train the WR on Supplements to the 1987 Wetlands Delineation Manual. | Sept 2008 | Terri Skadeland, Bill Wood/ Biologists Consortium | Completed. The COE provided training that was open to NRCS people. | Need meeting request | Wendell Gilgert, Meg Bishop, Terry Aho |
| Provide one ESD Conceptual Workshop for Great Basin. | 2008 | Patti Novak-Echenique, Shane Green/Grazing Lands Specialists Consortium | Scheduled for Nov 18-20, 2008 |  | Jeff Repp |
| Develop and implement an agreed-to process for coordinating biology practice standards | Nov 2007 | Biologists Consortium |  |  | Kathryn Boyer/Wendell Gilgert |
| Provide regional Section 106 orientation and introductory training to NRCS staff, focusing on Agency responsibilities and actions | 2008 | Marsha Sims/Cultural Resource Specialists/ Coordinators Consortium | Canceled due to budget concerns. | Need meeting request | Meg Bishop |
| Hold a WRAC workshop in conjunction with a WEPS Train-the Trainer workshop to receive training on new/updated models, develop/share tools, to articulate new/emerging issues from a West Region perspective, and to gauge progress with current WRAC Work Items. | Mar 2008 | Rick Fasching/ Agronomists Consortium | Complete |  | Mike Sporcic, (CNTSC); Tom Golhke, |
| Hold state sponsored pollinator workshops (how many?) | Sept 2008 | Karen Fullen/Terri Skadeland/Frank Fink/Tim Dring/Biologists Consortium | Completed. CO, WA, OR, & CA have scheduled for 2008. CO has one and maybe more for 2009. Keep in plan for 2009 |  | Wendell Gilgert |
| Continue to track biology training needs and courses being offered through the training spreadsheet | Ongoing | Terri Skadeland/ Biologists Consortium | Spreadsheet was started, but not much input or interest. Delete for 2009 |  | Wendell Gilgert |
| Provide listing (by state) of technical training planned throughout the fiscal year. | Nov 2007 | Sampson Harrington & all SCEs/ Engineers Consortium | On-going |  | Kip Yasumiiishi, Charles Zuller, Peter Robinson |
| Promote engineering staff interstate experiences, by promoting detailing/temporary assignment to other states. | On-going | John Harrington & all SCEs/ Engineers Consortium | On-going |  | Kip Yasumiiishi, Charles Zuller, Peter Robinson |
| Hold a Consortium meeting for training purposes | FY 2008 | Cultural Resource Specialists/ Coordinators Consortium | Completed. Meeting held in Colorado, June 2008. |  | Meg Bishop |
| State sponsored Training: Windbreak technology Prescribed burning and fuels management on forest land Silvopasture and multi-story cropping Forest vegetation simulator Forest erosion control and forest water quality Forest ecological site inventory and description Introduction to Conservation Forestry Planning (web-based) | FY 2008 | States: NM, MT, CA, OR ID, OR OR ID OR, WA AZ All States/ Foresters Consortium | High priority - 10% complete 20% 40% 100% Those not complete are on-going. | $1000 per session for meeting rooms and incidental expenses | Lyn Townsend, Bruce Wight, Pat Shaver, Homer Sanchez |
| Plan for a National Water Quality Workshop to coordinate technical assistance and conservation planning across states/regions for water quality resource concerns, budget permitting | May 2008 | Linda Scheffe, Hud Minshew/ Water Quality Specialists Consortium | Cancelled 2008 after being postponed in May due to budget limitations. Will try for national meeting in 2009. |  | Carl Lucero, Bruce Newton |
| Provide input for training module(s) for watershed planning (models, inventory techniques, etc.) | Dec 2008 | Norm Evenstad, Water Quality Specialists Consortium | Complete. Discussion of needs in watershed planning at WQ conference Sept. in Albuquerque |  | Shaun McKinney |
| Coordinate water quality technology training among states: Determine needed WQ training modules or aids for use by specialists or others that could be shared among states Request space on the WNTSC website for WQ Consortium use to post the above information for use by members Notify national water quality list serv when we post new items to WNTSC website Create and use SharePoint site for use by members and advisors | May 2008 Oct 2007 July 2009 | Water Quality Specialists Consortium | Completed Completed Completed COMPLETED. Site created - currently in use to share presentations, joint work products, and document review. |  | Shaun McKinney |
| Prepare justification and seek approval to have regional plant materials workshop early FY 09. | July 2009 | Ogle, Hersdorfer, Davey/ Plant Materials Specialists Consortium |  |  | Jim Briggs |
| Participate in National joint Plant Materials, Biology, State Resource Conservationist meeting in Texas | Nov 2007 | PM staff/ Plant Materials Specialists Consortium | cancelled |  | Jim Briggs |
| Consortium meeting – Lexington, KY | Jan 2008 | Herman Garcia/ Grazing Lands Specialists Consortium | Complete |  | Pat Shaver, Gene Fults |
| Provide Range Ecology II workshop for Great Basin(NEDS Range Ecology II) | Feb 2008 | Patti Novak/ Grazing Lands Specialists Consortium |  |  | Pat Shaver, Jeff Repp, Gene Fults |
| Mojave Desert S&T Workshop Las Vegas, NV. 10/22-26/07 | Oct 2007 | Patti Novak/ Grazing Lands Specialists Consortium | Complete | Need meeting request | Pat Shaver, Jeff Repp, Gene Fults |
| Develop, compile, and share training materials (lesson plans, syllabuses, templates, etc.) used in "Soils Training for Conservation Planners" workshops. |  | Soil Scientists Consortium | Complete |  | Terry Aho |