Minutes from meeting on installation and fitup

With significant contributions to the minutes from Phil Pfund

November 16, 2005  10 a.m.  CDT

In attendance

At Fermilab

Mike Lamm

Tom Page

Tom Nicol

Roger Rabehl

Rodger Bossert

Phil Pfund

Andy Hocker

Sandor Feher

Jim Rife

At CERN

Ranko Ostojic

Peter Limon

At BNL

Peter Wanderer

At LBNL

Joseph Rasson

Ranko:  No change in last few weeks for transport and installation.   Starting on Nov 18th transport first D2,  followed by Q1,Q2 Q3 on the 21st.

There had been discussion about installing the D1 and DFBX at a separate time, but the final decision was to install them at the same time.  Therefore, we will be able to work on the interconnect of d1-dfbx-q3-q2-q1 during our trip in January.

The start time for this January work continues to be January 9th .. therefore traval plans need to be made right away.. no later than Dec 1st for the Fermilab crowd.

Note:  From 22 Nov 2005 email from Ranko, installation and interconnect schedule has been delayed by at least two weeks

Peter Limon told us about the sorts of training needed to have tunnel access.  There is a general safety course given in Building 55, offered twice daily.  You have to pass a (written?) test.  This course covers levels I-II-III.  There is a level IV.   That can be done on the web.   It can all be done in a day.

One needs PPE to work in the tunnel.  Safety shoes (i.e. steel toe) are not required;  work boots would do.  US Labs employees would be wise to bring their own shoes.   Helmets, airpacks, cell phones, will be taken care of by our CERN-stationed collaborators.  Peter will look into this.

There was a discussion about whether it was worth coming in early, say on Friday the Jan 6th in order to get this training.  It was generally felt that spending Monday doing training, with Tuesday in the tunnel would match the CERN schedule.

We discussed “who should go and when”

Plan: send in two “waves”   Rodger B. Bill Mumper and Tom Page go first.   Bossert/Mumper because they are the splice experts.  Tom Page because he is most knowledgeable about the interconnect kits.

Second wave will be Tom Nicol, Jim Rife and Mike Lamm.   This group works on the mechanical interconnect and Lamm looks over the electrical data.  The second group arrives on Jan 16 or Jan 17 so that there is an overlap with group 1.   Each group stays for ~2 weeks.

Joseph Rasson arrives with second wave, as does BNL participants  (probably John Escallier and Steve Plate or John Cozzolino).  This schedule is because we will start with the Q1 and work our way towards the DFBX/D1 interconnect.

There was a discussion about the D1-DFBX interconnect.   The splice fixture for the Quads is being modified for use on the D1-DFBX.  FNAL has never tested it on the BNL cable although a similar fixture is used to splice the KEK-Fermilab bus work.

The D1-DFBX instrumentation interconnect design is minimal.  It follows the letter of the CERN requirement.      This design is similar to the RHIC design.   This has been knows for some time.  Peter Limon volunteered to look into this and make suggestions on how to improve it.

There was also a discussion about the thermal connection on the D1-DFBX. There was a thermal bridge which was discovered during the April fitup to be too long.  Ranko says that this problem has been fixed.

Peter suggested that we should send CERN as set of leak test “clam shells” .  We use fixtures like this on the Fermilab test stand.  The clam shells are strapped over the bellows and sealed with Apiezion grease.   There was a discussion about how useful these would be at CERN.   We cannot spare the ones on our test stand and we don’t have a set for every interconnection.  Still they are relatively easy to make and could prove useful.  Roger Rabehl volunteered to look into the cost and schedule for getting a set for CERN.

There was a discussion about missing components.   Peter gave examples of components that cannot be found at CERN.   I believe the US folk felt that all components were accounted for.

Ranko will ask Ivo and Cedric to make a list of missing components and send this list to Tom Page.

There was a discussion about the procedures.  CERN   is working at CERN to embellish our procedures, integrate them with other CERN tasks and translate them in French.

There is a “detail” with the HTS leads that needs to be put into the procedures.  There is a transport restraining screw that needs be loosened prior to cooldown.  Roger R. and Sandor will write a small document to describe this.

We discussed the need to get all of the tooling at CERN PRIOR to January.   For example the soldering fixtures are still at Fermilab.   Rodger reported that the plan is to send a tested set of soldering tooling by the end of November.  A second set will be manufactured and testing at Fermilab in December, and shift or hand carried to CERN in early January.