Educator Astronaut and Education Flight Projects

Integrated Project Plan

Acting Assistant Administrator							Date

Office of Education

Director										Date

Elementary and Secondary Program

Manager										Date

JSC Elementary and Secondary Programs

Project Manager									Date

INTEGRATED PROJECT PLAN – Educator Astronaut and Education Flight Projects

- PROJECT OVERVIEW

Educator Astronaut Project (EAP) and Education Flight Projects (EFP) are part of NASA’s Elementary and Secondary Education Program.  The Elementary and Secondary Education Program Plan provides guidance for all its projects.

NASA Johnson Space Center (JSC) is the Lead Center in the management of Educator Astronaut and Education Flight Projects.  The scope of these projects is national, and other NASA Field Centers and JPL are involved in the implementation of project activities.  Information on the roles and responsibilities of EAP and EFP Performing Centers is found in Section 2.2 – Resources.

This document is an integrated project plan for Educator Astronaut and Education Flight Projects.  It serves as a controlling document that defines the top-level strategy and the management structure for these projects, and is intended to be a living document.

1.1 Introduction

In the Vision for Space Exploration, NASA outlines its plans for a return to the Moon and a future voyage to Mars.  NASA recognizes that in order to prepare the next generation of explorers who will make these journeys possible, it must continue the Agency’s tradition of investing in the Nation’s education programs and supporting the country’s educators who play a key role in preparing and inspiring their students.

Key to future exploration is the need to provide educators and students with tools, experiences and opportunities to increase interest in and knowledge of science, technology, engineering, and mathematics (STEM).  NASA’s unique resources, including people, facilities, and content, can stimulate students to pursue higher levels of study and future careers in STEM related fields, which can ensure the Agency’s future workforce.

The NASA Office of Education oversees the Agency’s education investments which includes the Elementary and Secondary Education Program.  Educator Astronaut Project and Education Flight Project are integral parts of the NASA Elementary and Secondary Education Program.

Beginning in 2006, NASA will pursue three major education goals:

- Strengthen NASA and the Nation’s future workforce

- Attract and retain students in STEM disciplines

- Engage Americans in NASA’s mission

As part of NASA’s portfolio of education programs and projects, Educator Astronaut and Education Flight Projects can help the Agency achieve these goals.

NASA Education investments are expected to map to at least one of the three overarching NASA Education Outcomes as part of annual performance, to track efforts back to the identified outcome manager, and to contribute to the FY06 (and beyond) annual performance goals (APGs).

Outcome 1: Contribute to the development of the STEM workforce in disciplines needed to achieve NASA’s strategic goals, through a portfolio of investments.

Outcome 2: Attract and retain students in STEM disciplines through a progression of educational opportunities for students, teachers, and faculty.

Outcome 3: Build strategic partnerships and linkages between STEM formal and informal education providers that promote STEM literacy and awareness of NASA’s mission.

As part of the Elementary and Secondary Education Program, Educator Astronaut and Education Flight Projects serve as major links in the student pipeline used to meet the Education Goals from NASA’s 2006 Strategic Plan.  The Elementary and Secondary investments map to NASA Education Outcome 2, “Attract and retain students in STEM disciplines through a progression of educational opportunities for students, teachers, and faculty,” via projects that use NASA content, people or facilities.  Programs are integrated in the Engage and Educate categories of the Education Framework.  Investments to this Outcome are contributed through HQ Education, Mission Directorates, Centers, and strategic partnerships.

The Elementary and Secondary Education Program and its projects are designed to provide students and educators with tools, experiences, and opportunities to further their education and participation in unique NASA learning experiences that enhance their knowledge of science, technology, engineering and mathematics (STEM).  The individual efforts emphasize family involvement, which has been shown to enhance student achievement.  The program also supports the role of educational institutions, which provide the framework to unite students, families, and educators for educational improvement.  This program integrates new components with existing NASA assets into a structure that supports local education efforts to encourage student involvement in STEM.

Figure 1 – Agency Education Goals, Outcomes, and Criteria

The Education Strategic Framework (Figure 1) is a strategic management tool that allows the Agency to monitor participant movement through education activities, with each category leading to the next.  Education programs and projects draw from the category below them – as a key source for participants – and they connect participants to the category above them – providing a more experienced and focused group and creating a measurable pipeline.

Definitions for the four levels of involvement are articulated within the document, “NASA Education Strategic Coordination Framework: A Portfolio Approach.”  Below are the descriptions for Engage and Educate, which the Elementary and Secondary Education Program projects target:

Engage – Education activities that in some manner incorporate participant interaction with NASA content for the purpose of developing a deeper understanding.  Participants are strategically identified and targeted.

Educate – Focused education support that promotes learning among targeted populations.  Educate activities focus on student learners, or pre- and in-service educators, and are designed to develop and/or enhance specific STEM knowledge and skills using NASA resources.  Educate activities promote new knowledge acquisition and strengthen an individual’s skills.  NASA’s elementary and secondary education efforts are supplementary to formal classroom instruction.

In addition to direct contributions to Outcome 2, Elementary and Secondary Education projects, including Educator Astronaut and Education Flight Projects, look for synergy and continuity of efforts with other projects that are mapped to this same outcome as well as to other activities identified as “engage” and “educate.”  Thus, linkage with Informal and Higher Education projects and activities is pursued to support the appropriate progression of education opportunities for learners.  Project managers are expected to demonstrate and collect evidence of where constituents are drawn from and how constituents are moved to other NASA education projects (push-pull concept).

As part of the FY06 NASA Office of Education (OE) realignment process, management of Educator Astronaut and Education Flight Projects will transition to NASA Johnson Space Center (JSC).  Other Centers, listed in Section 1.5 – Project Authority, serve as Performing Centers.  Educator Astronaut and Education Flight Projects offer NASA Education unique capabilities and opportunities to involve educators and students through astronaut training, spaceflight missions, on-orbit education activities, and a variety of education flight projects.

Transition of the projects to JSC offers opportunities to:

- Align and redefine the projects

- Increase efficiency and effectiveness in supporting Outcome 2

- Create push-pull opportunities with other Elementary and Secondary Education projects as well as Informal and Higher Education

- Maximize value in the Office of Education and Elementary and Secondary Education portfolio

The realignment of Educator Astronaut and Education Flight Projects to JSC will necessitate adjustments to management processes and interface mechanisms throughout FY07 and FY08.  The adjustments will be a result of assessment and discussions not only between NASA Headquarters (HQ) and JSC, but also between Centers and Mission Directorates.  Outcomes from these adjustments will present opportunities for refinement to the guidance and policy as defined from HQ and with project management as proposed from the Center.  Full integration of the projects with their associated budgets will not be complete until FY09.  A schedule of key integration activities is found in Section 2.1 - Schedules.

Educator Astronaut and Education Flight Projects and their associated activities will be managed by the JSC Education Office and integrated with Teaching From Space (TFS), a NASA Education office co-located with JSC’s Astronaut Office.  TFS has the experience and expertise needed to manage and support both projects.  Integrating the projects with TFS and utilizing a common management structure has the potential to benefit both projects.  Projected benefits include:

- Established JSC infrastructure to manage and support the projects

- New capabilities and opportunities to engage and educate

- Increased synergy and ability to leverage and integrate resources between this project and other associated projects/assets across the Agency (e.g. NASA education flight projects, reduced gravity flights, Solar System Ambassadors)

- TFS’s ability to facilitate “push-pull” opportunities with other NASA education programs

- Historically strong TFS connection to the astronaut corps which can be leveraged to better engage astronauts in the projects

- TFS’s expertise in managing payloads and on-orbit education activities on both Space Shuttle and International Space Station, and future spaceflight platforms

- Capability to manifest future student payloads on the Space Shuttle, International Space Station (ISS), and the Crew Exploration Vehicle

- Experience with space operations and mission requirements

- Close association with NASA’s unique people, facilities and assets that contribute to the Vision for Space Exploration

- Experience working with ISS partner education offices

- Experienced staff with a strong education background

The JSC Education Office will have a single project manager for Educator Astronaut and Education Flight Projects, and their associated activities, under the TFS umbrella.  For the project transition phase, the following chart (Figure 2) reflects that the two projects are operationally integrated but maintain separate reporting functions.  The chart lists existing TFS responsibilities under Education Flight Projects.  Refer to Section 2.1 – Schedules for additional details.

Figure 2 - Teaching From Space Management Chart

The following organization chart reflects total project integration under TFS.  Refer to Section 2.1 – Schedules for specific information.

Figure 3 – Teaching From Space Fully Integrated Management Chart

Henceforth, EAP and EFP will be referred to in this document and future documents as Teaching From Space (TFS).

  - Objectives

All TFS activities will be designed to support an integrated vision and objectives.  The vision for TFS is to:

Facilitate education opportunities that use the unique environment of spaceflight.

TFS will focus its efforts to meet three objectives:

- Develop and provide NASA-unique experiences, opportunities, content, and resources to educators to increase K-12 student interest and achievement within STEM disciplines.

- Develop and facilitate NEAT-like group of highly motivated educators.

- Build internal and external partnerships with formal and informal education communities to create unique learning opportunities and professional development experiences.

As part of the Elementary and Secondary Education Program, the vision and objectives of TFS support Outcome 2.  This goal and objectives provide the basis for project annual performance goals (APGs) and indicators that must map to and contribute towards these measures.  These APGs support the strategic goal, objectives and outcomes of the Elementary and Secondary Education Program.

Elementary and Secondary Program Objectives are:

2.1  	Educator Professional Development—Short Duration

- Objective (Engage)

Provide short duration professional development and training opportunities to educators, equipping them with the skills and knowledge to attract and retain students in STEM disciplines.

2.2  	Educator Professional Development—Long Duration

- Objective (Educate)

Provide long-duration and/or sustained professional development training opportunities to educators that result in deeper content understanding and/or competence and confidence in teaching STEM disciplines.

2.3  	Curricular Support Resources

- Objective (Engage)

Provide curricular support resources that use NASA themes and content to:

  - Enhance student skills and proficiency in STEM disciplines (Educate).

  - Inform students about STEM career opportunities (Engage).

  - Communicate information about NASA’s mission activities (Engage).

2.4  	Student Involvement K-12

- Objective (Engage)

Provide K-12 students with authentic first-hand opportunities to participate in NASA mission activities, thus inspiring interest in STEM disciplines and careers.

- Objective (Engage)

Provide opportunities for family involvement in K-12 student learning in STEM areas.

TFS inherits two established projects.  Education Flight Projects and its activities primarily align with 2.4, Student Involvement - K-12.  Educator Astronaut primarily aligns with 2.2, Educator Professional Development – Long Duration.  TFS recognizes evaluation of the projects, their activities, and their metrics associated with Outcome 2 is necessary.  This evaluation and review will be conducted continually through the life of the integrated projects.  See Section 1.8 – Project Requirements for additional information on buckets.

The integrated TFS project will have primary and secondary “buckets.”  Primary customers will be K-12 educators and through these educators, TFS will reach their students.  The project will provide sustained and varied professional development activities for educators.  As a result of these activities, educators will be able to provide students rich STEM experiences that utilize unique NASA content.  The primary bucket for TFS will be Educator Professional Development – Long Duration (2.2) and the secondary bucket will be Student Involvement – K-12 (2.4).

FY07 APGs that will be specific to TFS are:

- APG 7ED6 – Conduct 10 Educator Astronaut workshops, involving approximately 200 educators.

- APG 7ED8 – Select 100 student experiments involving 1,000 students, to participate in the Flight Projects program.

In addition, annual performance and data collection for current EAP and EFP activities will measure the following:

- APG 11 – Collect, analyze, and report the percentage of grantees that annually report on their accomplishments.

- APG 12 – Peer review and competitively award at least 85%, by budget, of research projects.

- PART Measure 1 – Percentage increase in number of elementary and secondary student participants in NASA instructional and enrichment activities.

- PART Measure 2 – Percentage increase in number of elementary and secondary educators utilizing NASA content-based STEM materials and programs in the classroom.

- PART Measure 3 – Level of student learning about science and technology resulting from elementary and secondary NASA education programs.

- PART Measure 4 –Level of student interest in science and technology careers resulting from elementary and secondary NASA education programs.

- PART Measure 10 – Number of people reached via e-education technologies per dollar invested.

See Section 4.0 - Appendix A for the complete list of potential outputs, outcomes, and efficiency measures for the Elementary and Secondary Program Objectives.

TFS activities will enable educators to directly engage and educate students in STEM subjects using NASA unique content and resources.  Focused interactions with educators are an efficient, cost-effective, and sound approach to engaging and educating students.  This will be achieved by providing educators with meaningful long duration professional development opportunities.

By equipping educators with appropriate experiences, they can laterally engage their peers.  The targeted educators, and the peers whom they influence, will engage and educate students resulting in a larger quantity of student involvement in the project.  To this end, TFS will provide or facilitate NASA-unique experiences, opportunities, content, and resources.  Additionally, TFS will generate a climate where professional educators can collaborate and share their knowledge and enthusiasm with the broader education community.

TFS will continually look for new opportunities to collaborate with and support existing projects in the NASA education portfolio, especially those that can be used to encourage and increase student involvement.  Of particular interest are the many NASA education flight projects that are currently part of the NASA Education portfolio.

Furthermore, examination of the cross-cutting investments -- dissemination, coordination, research and development, and evaluation -- will be important elements for TFS to see that these investments are folded into efforts in support of continuity and synergism.

In addition, TFS will look for synergy and continuity of efforts with other Elementary and Secondary Education projects that are mapped to Outcome 2 as well as to other activities that are identified as “engage” and “educate.”  TFS will pursue links with Informal and Higher Education projects and activities that support the appropriate progression of education opportunities for participants and their constituents.  TFS management will demonstrate and collect data of where project constituents are drawn from and how the project moves its constituents (push-pull concept).  The Spring 2006 Education Portfolio Inventory Data Call will be used to identify other projects and activities that offer TFS opportunities for synergy and continuity.  The following diagram (Figure 4) shows examples of where NASA Education projects fall in the pyramid and illustrates the potential for TFS push-pull relationships.

Figure 4 – Example of projects mapped to strategic framework

1.3 Mission Description

TFS inherits a suite of established activities.  As part of the realignment and integration process, TFS will evaluate individual activities and redefine strategic outcomes, goals, schedules, and deliverables to increase efficiencies, leverage resources, and to better align with the guidance, policy, and requirements of the Elementary and Secondary Education Program.  After evaluation, activities may be redesigned or eliminated to ensure that all TFS activities contribute to the overall success and value of the project, Elementary and Secondary Education Program, and the overall NASA Education portfolio.

Individual activities will be constructed to support other TFS, Elementary and Secondary Education, and NASA Education activities and will be designed to be part of a seamless pipeline of NASA education programs that encourage students to excel in STEM disciplines and pursue STEM careers.  TFS will seek synergy with and continuity between existing and new projects within the Elementary and Secondary Education Program and across Outcomes 1 and 3.  This deliberate approach to synergism and continuity will help to define and evaluate the project’s direction, activities, and partnerships.

After evaluations and reviews are complete, TFS anticipates that a new description of the integrated projects will be needed and that the current activities may be redefined, eliminated, or additional activities added.  A current list of major project activities follows:

- Educator Astronaut Project – NASA's Educator Astronaut project has helped to infuse into education new content, advanced technological tools, and other educational services such as direct participation in space research and interaction with NASA scientists, engineers, and astronauts.  To date, the project has trained the top tier of Educator Astronaut applicants (190), called the Network of Educator Astronaut Teachers (NEAT), to perform as NASA Education advocates by engaging their schools and communities across the country in NASA education activities and informing them of NASA resources. Current activities include:

  - Educator Astronaut Support:  Support is provided to Educator Astronauts for K-16 education related public appearances.  In addition, assistance with education related questions that Educator Astronauts receive from educators, students, and the general public is available.  Spaceflights of Educator Astronauts are supported during the pre-mission, mission, and post-mission phase.  Assistance with planning key components (ground-based and on-orbit education activities) of an Educator Astronaut flight is provided.  Information on current NASA education programs and projects, and support for the Astronaut Office Education branch are provided.

  - Network of Educator Astronaut Teachers (NEAT):  During the initial Educator Astronaut selection process, approximately 190 teachers were rated Superior. The NEAT group is comprised of these teachers.  As part of this group, the teachers are provided professional development through national conferences and Center workshops.  They receive NASA resources, special training, and are offered unique NASA experiences.  NEAT members serve as advocates for NASA and promote NASA Education efforts.

  - Educator Workshops:  As part of NEAT, professional development workshops are provided both on a national and Center regional level.  The workshops are normally 2-3 days in length and offer selected educators unique NASA content and experiences.  Additional educator workshops may be planned as one component of a suite of education activities associated with Educator Astronaut spaceflights.

  - Product Development Facilitation:  Astronaut and astronaut candidate training provide rich content for NASA education products.  The project facilitates the use of astronaut related content for a variety of NASA customers, including the NASA web site (portal) and NASA Explorer Schools (NES).  Support for NASA education product producers is provided in the form of connection with subject matter experts, video, and still imagery.

  - STS-118/Future Spaceflights:  STS-118 is the first flight of an Educator Astronaut and is currently scheduled for June 2007.  Education efforts, both ground-based and on-orbit, are key components for the flight.  Support for the development, planning, integration, and implementation of education activities during the pre-mission, mission, and post-mission phases is provided.  The education initiative associated with STS-118 will serve as a model for future spaceflights, including but not limited to flights of Educator Astronauts.

  - Educator Astronaut Recruitment/Selection:  Outstanding educators are recruited to join the Astronaut Corps to have a special responsibility for education.  In 2004, three educators were selected to become astronauts.  They completed astronaut candidate training in early 2006.  They are currently serving in Astronaut Office technical assignments while awaiting flight assignments.  Support will be provided for future recruitment and selection of additional Educator Astronauts, possibly as early as 2008.

- Education Flight Projects -  Provides: The project provides opportunities for K-12 students to gain hands-on experience as payload investigators using NASA flight platforms such as the Space Shuttle, the ISS, sounding rockets, reduced gravity aircraft, and scientific balloons.  EarthKAM, the Amateur Radio on ISS (ARISS), and the ISS Education Downlinks are three activities under EFP that have enabled the platform of ISS to have an international reach to educational communities and to inform the public of the excitement and value of space research.  Current activities include:

- Astronaut Support:  Support in the form of resources and consultation is provided to astronauts for K-16 education related personal appearances.  In addition, assistance with education related questions that astronauts receive from educators, students, and the general public is available.  Astronauts preparing for spaceflight seek support and assistance with planning on-orbit education-related activities.  Current information on NASA education programs and support for the Astronaut Office Education branch are provided.

  - Education Payloads:  Education payloads are designed to support NASA Education outcomes by focusing on demonstrating science, technology, engineering, mathematics, or geography principles in a microgravity environment.  Education payloads are referred to as Education Payload Operations (EPO).  Video recording of the demonstrations and/or still photographic documentation of a crewmember operating EPO hardware while on-orbit achieve EPO goals and objectives.  NASA Education projects and the informal education community design these education payloads.

  - On-orbit Education Activities:  On-orbit educational demonstrations designed to use only hardware already on-board the ISS are referred to as EDAs – Education Demonstration Activities.  EDAs are intended for K–12 audiences and support national standards.  They are designed to enhance existing NASA education products and programs.  Educators, students, and NASA Education projects suggest activity topics.  Activity video is provided to the informal and formal communities, ISS partners, and NASA education programs and projects.

  - In-flight Education Downlinks:  Live in-flight education downlinks on-board the ISS and during selected Space Shuttle flights, typically 20 minutes in length, allow students and educators to interact with the crew as they answer questions and perform simple educational demonstrations.  Members of the informal and formal education communities, NASA Centers and Education Programs, and the ISS partners host these events.  Hosts make downlinks part of a comprehensive education package that supports national and state education standards and initiatives.  Education downlinks are broadcast live on NASA Television.

  - Amateur Radio on the International Space Station (ARISS):  ARISS is an educational outreach program, sponsored by NASA, in which students engaged in a science and technology curriculum are given the opportunity to speak with an astronaut orbiting the Earth on the ISS.  Using amateur radio, students ask questions about life in space and other space-related topics.  Students fully engage in the ARISS contact by helping set up an amateur radio ground station at the school and then using that station to talk directly with the on-board crew member for approximately ten minutes, the time of an ISS overhead pass.

  - ISS EarthKAM:  ISS EarthKAM is a NASA education program that enables students, teachers and the public to learn about Earth from the unique perspective of space. At the core of the program is a spectacular collection of digital images of Earth.  The image collection and accompanying learning guides and activities are extraordinary resources to support classes in Earth science, space science, geography, social studies, mathematics, communications and even art.  ISS EarthKAM images are unique because they are taken by middle school students.  During EarthKAM missions, registered middle schools use the EarthKAM web site to request images real time based upon their classroom investigations.

  - Sub-Orbital Flight Platforms:  Flight Opportunities include: Small-scale Educational Rocket Initiative (SERI) - dedicated rocket designed for one school to experience building and launch capabilities; Student Experiment Module-Balloon (SEM-Balloon) - potential for over 600 students to experience a flight opportunity in one launch (a balloon carries 2 suitcases per flight; each suitcase contains 10 experiments, potential 30 students per class); Student Experiment Module-Sonde (SEMsonde) - weather instrument balloon designed to gather data and permit students to participate through mission control center by tracking and reporting data in real time; provided to maximum 30 students, 5 schools at one time; FreeSPACE - provides up to 10 experiments with maximum 8 student projects per free space; provides opportunities for 80 students in hands-on activities;   Sounding Rocket - most advanced capability with a larger-scaled sounding rocket; maximum of four experiments per rocket impacting over 30 students.  The various platforms for flight projects provide educators and their students with a greater opportunity to develop and hone their skills in project design and development.  While each flight opportunity provides direct hands-on experience for a specific number of students, its potential impact for engagement reaches far beyond the on-site experience.  All flight project experiments carry the enhanced capability to engage thousands of other students and educators through Control Center in the Classroom and web casting.

In addition to the activities listed above, TFS will solicit other internal and external partnerships throughout the project lifecycle.  All potential partnerships will be evaluated by TFS through a proposal and review process.  TFS is particularly interested in developing internal partnerships with projects and activities, supported by existing facilities at other Centers that offer additional K-12 student flight opportunities.

EFP Portfolio Management Report (December 2004) lists a variety of NASA flight platforms including the ISS, the Space Shuttle, Expendable Launch Vehicles (ELV), Scientific Aircraft, Scientific Balloons, Sounding Rockets, and Small-Scale Rocketry.  See Appendix B for a complete listing of NASA Flight Platforms, NASA Education Flight Platforms, and NASA Mission Directorate/Field Center Education Flight Projects.  Detailed information on each project or platform is found in the complete EFP Portfolio Management Report (December 2004).

TFS is committed to providing a variety of meaningful flight opportunities to the Nation’s diverse education communities.  TFS will work to develop and continue internal partnerships (e.g. Wallops, Space Grant, Reduced Gravity Flights, Team America Rocketry Challenge, Student Launch Initiative, etc.), and will strive to maximize education community awareness and access to NASA flight platforms effectively and efficiently.  By providing hands-on experience with NASA flight platforms to the elementary, secondary, higher, and informal education communities, TFS will play a critical role in the Office of Education’s endeavors.

TFS plans to continue the Portfolio Management Approach that was developed by EFP.

This approach enables project oversight via performance metrics, promotes communication and collaboration, and ensures that investments are based on program ability to strengthen the entire portfolio.  This approach provides a means to measure and respond to the impact of education flight projects on NASA’s STEM student pipeline and workforce development efforts and ensures a coordinated, non-duplicative set of activities that work together to achieve NASA’s education goals.  The portfolio management approach includes:

- An inventory of all approved NASA education flight projects

- A rigorous evaluation of proposed projects

- Periodic progress reports on performance metrics

- Annual performance evaluation using common criteria

- Access to performance information for the entire portfolio

- Performance improvement plans

Education flight projects may be initiated and managed by any one of a number of organizations including TFS, a NASA Mission Directorate, or a NASA Field Center.  If a project is managed by an organization other than TFS, TFS will:

- Ensure management level awareness of all education flight projects

- Analyze and report project performance

- Encourage the incorporation of the education program operating principles

- Advise education and project management on:

  - Exemplary programs

  - Duplicative programs for consolidation

  - Resources to strengthen the education flight projects portfolio

If a project is managed by TFS, TFS will:

- Prioritize and allocate resources in the budget process

- Increase functional and organizational interoperability

- Provide a central repository for performance metrics and the basis for a Balanced Scorecard

- Streamline processes to ensure timely delivery of management reports and data calls

- Support development and maintenance of Pathfinder Initiatives

Using the established EFP management structure, TFS will organize its portfolio according to flight platform and education division.  This structure will allow TFS to design, assess, and adjust projects to construct and maintain a seamless pipeline of flight opportunities for each platform.  TFS is responsible for portfolio-wide analysis and subsequent recommendations to management regarding strategic planning for the long-term attainment of Agency goals and Mission Directorate objectives via education flight projects.

Strategic Approach

TFS will assess current activities and seek additional activities that support its vision and objectives.  The following considerations will be used to help guide this process:

- Results of the 2005 Program Analysis and Evaluation Report (PA&E):  A Review of the NASA Education Program ( specifically recommendations for EAP)

- NASA Education Operating Principles

- Opportunities for “push-pull” and synergy within the TFS portfolio  (e.g. NEAT involvement in Wallops sub-orbital education flight projects)

- Benchmark with successful K-12 projects/activities to look for opportunities for project improvements (e.g. NASA Explorer Schools)

- Retirement of the Space Shuttle in 2010

- Future flight opportunities on manned launch vehicles, including the CEV

- Existing unmanned flight platforms and education flight projects

- Mission Directorate education activities, including flight projects

- Education opportunities as part of the ISS National Laboratory plan

Internal Relationships

TFS recognizes the value of relationships with other NASA Education projects and activities.  These relationships are often mutually beneficial, have the potential to increase the worth and reach of all associated projects and activities, and result in enhanced continuity between elements in the NASA Education portfolio.  TFS activities support and/or are supported by a variety of NASA Education projects and activities.  These established relationships include, but are not limited to:

- Educator Astronaut Support

Center Education Offices, AESP, NES, DLN, Mission Directorates, CORE, ERCN

- Educator Workshops

AESP, DLN, Center Education Offices, Mission Directorates

- NEAT

AESP, Center Education Offices, Mission Directorates, NASA web site (portal),

- Product Development Facilitation

NASA web site (portal), DLN, NASA Education, Mission Directorates

- STS-118/Future Spaceflight

Mission Directorates, Formal Education, Informal Education, eEducation, NES, 	CORE, ERCN

- Educator Astronaut Recruitment/Selection

NASA Education

- Astronaut Support

AESP, ERCN, Center Education Offices, DLN, CORE, ERCN

- Education Payloads

Informal Education; Mission Directorates, NASA web site (portal), ISS partners

- On-orbit Education Activities

AESP, NES, ERCN, NEAT, Formal Education, Informal Education, DLN, NASA 	web site (portal), ISS partners, CORE

- In-flight Education Downlinks

AESP, NES. NEAT, ERCN, Solar System Ambassadors, Formal Education, 	Informal Education, Higher Education, Mission Directorates, ISS 	partners, 	NASA web site (portal)

- ARISS

AESP, NES, NEAT, Formal Education, Informal Education, Higher Education, 	NASA web site (portal), ISS partners

- ISS EarthKAM

AESP, NES, NEAT, Formal Education, NASA web site (portal), ISS partners

- Sub-Orbital Flight Projects

NES, NEAT, Formal Education, Informal Education, Higher Education, Learning 	Technologies Project (LTP), Space Grant, NASA web site (portal)

1.4 Customer and Stakeholder Definition and Advocacy

Elementary and Secondary Education projects are managed at NASA Field Centers.  Center education offices work closely with their regional customer base in support of systemic reform initiatives in formal education, assist with the generation and communication of knowledge for their unique research and technology development requirements by involving colleges and universities across the country, and establish linkages with informal education networks in support of Agency national STEM education initiatives.

As part of the Elementary and Secondary Education Program investments, TFS will use NASA content, people, or facilities to reach the education community, as identified in Outcome 2.  The project will utilize key internal and external stakeholders to identify, engage, and educate its customers.

TFS will seek to engage and educate these key participants:

- Primarily certified teachers who will be provided professional development in STEM subject areas.

- Through their teachers, K – 12 students who become involved in a variety of NASA STEM activities.

As a result of these professional development experiences, educators will engage and educate their students using NASA unique content and resources.  Educators and their students will be introduced to and become involved in a variety of NASA education opportunities.  These experiences will result in a continuous pipeline of NASA education experiences for professional educators and their students.

TFS will involve educators, astronauts, engineers, scientists, mathematicians, and subject matter experts (SMEs) from the NASA workforce, and the public and private sectors, to address NASA’s related disciplines and topics and to enhance learning in the K-12 formal education community.

NASA Customers

- Aeronautics Research Mission Directorate (ARMD)

- Exploration Systems Mission Directorate (ESMD)

- Science Mission Directorate (SMD)

- Space Operations Mission Directorate (SOMD)

- Center Education Offices

- Office of Strategic Communications

- NASA education product developers

- NASA formal and informal education program managers

- Astronaut Office

- Existing NASA education flight projects (Refer to Appendix B)

Other Federal and External Customers and Stakeholders

- Non-Governmental Organizations (NGOs)

- Academia

- Professional Education Organizations

- Federal Agencies

- Members of Congress

- NASA’s partners and collaborators

- Informal and formal education communities

- Network of Educator Astronaut Teachers (NEAT)

- ISS partners

To effectively strengthen the Nation’s STEM workforce, NASA must implement activities that are useful to the education community and that strengthen their ability to engage and educate students in the STEM pipeline.  TFS ascertains customer satisfaction by soliciting and analyzing customer feedback as reported through:

- NASA Education Evaluation & Information System (NEEIS)

- Beta, pilot, usability, and field-testing specific project elements

- Independent evaluation

Outcome reviews will employ a variety of mechanisms to assure that activities associated with Outcome 2 align with the education operating principles, yield demonstrable results, and reach intended audiences.  Use of external reviewers will be an integral part of outcome reviews to provide NASA with credible information regarding how well TFS efforts meet customer needs.

1.5 Project Authority

The project authority and guidance is taken from the FY06 – FY08 Program and Resources Guidance for the Elementary and Secondary Education Program.  The Elementary and Secondary Education Program plan defines authority and guidance for all projects in its portfolio.  The following diagram (Figure 5) illustrates the flow of authority.

Figure 5 – Educational Portfolio Coordination Framework

TFS project management resides at NASA Johnson Space Center (JSC).  The line of authority for the project runs through the JSC Education Office where the TFS project manager reports to the JSC K-12 Education Manager.   The JSC K-12 Education Manager directly interfaces with the JSC Education Director and the Elementary and Secondary Education Program Manager.

TFS management is responsible for making and executing decisions within its authority. This includes budgets, schedules, staffing, and capital assets that fall under the sole purview of TFS.  The project manager works across organizational lines to perform appropriate integration functions and identify “push-pull” relationships.  The Elementary and Secondary Education Program plan outlines specific responsibilities of TFS management to develop project plans, requests for proposals and other contract-related documents, reports associated with major reviews, and other key activities.

Performing Centers

JSC serves as the Lead Center for TFS.  Performing Centers are:

EAP – ARC, DFRC, GRC, GSFC, KSC, LARC, MSFC, SSC

EFP – ARC, GSFC, JPL

Performing Center roles and responsibilities are listed in Section 2.2 – Resources.  Performing Centers will be involved in the redefinition of project activities. JSC will work with HQ and Centers to determine the most efficient way to combine EAP and EFP into TFS to utilize and leverage the best efforts of each project.

As part of its portfolio of activities, TFS has established or will need to establish a coordinated management structure and approach with Performing Centers and with internal and external partners.  Successful communication is needed to ensure the success of project activities.  TFS is responsible for providing information and guidance on expectations and evaluation for activities.

TFS will use the following strategies to work with and support Performing Centers:

- Identify primary TFS point of contact

- Communicate important and relevant information through regular emails

- Schedule regular telecons with activity management

- Provide evaluation information and guidance, as required

- Monitor and track activity through established reporting systems

- Conduct annual site visits

Each Performing Center lead will develop annual performance goals/milestones that support the overall TFS project outcomes, goals, and deliverables.  The reporting process will include a monthly report, a quarterly review, and an end of the year performance report to the TFS project manager.

1.6 Management

Management structure for TFS is outlined in the Elementary and Secondary Education Program plan. TFS will participate in all review processes and adhere to all requirements stated in that document, including Outcome Level Metrics and Reviews, and Project/Activity Evaluations.

NASA uses objective and verifiable performance metrics, regular management insight and review processes, and defined tools to assess its performance at all levels - portfolio, outcome, and the individual program/project/product/activity.  Each level of management participates in setting performance targets, consistently evaluates performance against those targets, and reports the results to the Education Coordinating Committee (ECC).  If performance measures are carefully and thoughtfully chosen and applied, the regular performance evaluation at each level becomes one of our most important means of identifying problem areas and opportunities for better management, leading to greater organizational effectiveness and guiding investment strategies.

Outcome-Level Metrics and Reviews

Outcome reviews will assure that activities align with the education operating principles, yield demonstrable results, and reach intended audiences.  External reviewers will be an integral part of outcome reviews to provide NASA with credible information regarding how well its education efforts meet customer needs. Outcome reviews include the results of individual program, project, product, and activity evaluations within the portfolio. These results should be used to guide funding organizations in making adjustments in the portfolio where appropriate.

Program/Project/Activity Evaluation

Management of education programs/projects, as with all NASA programs/projects, complies with the NASA policy NPR 7120.7 - NASA Institutional/Infrastructure Program/Project Management Processes and Requirements.

Education evaluations are based on a common set of criteria including performance alignment with the Education Overarching Philosophy and Operating Principles.  Evaluation plans will measure intended impact and be scaled appropriately to the size of the investment—“one size does not fit all.”  Mission Directorates, Centers and the Office of Education regularly monitor and evaluate their programs, projects, products and activities and report the results to their funding organizations and the OE for review by the ECC.

  - Governance Structure

For the TFS project, annual performance planning and reporting is required and annual performance goals are measured and monitored throughout the fiscal year.  Monthly reports will be submitted and quarterly reviews will be held. At the end of each year, an annual review will be completed and results of the review will be used to develop an improvement plan for the upcoming year.  This approach includes:

- Rigorous evaluation of projects/deliverables as matched to TFS annual performance goals (APGs) and targeted Elementary and Secondary Education Program outcomes and sub-elements

- Periodic progress reports on performance metrics

- Annual performance evaluations using common criteria

- Access to performance information for the entire Elementary and Secondary Education Program portfolio

This approach provides information necessary for reallocation of resources and sunsets to projects or activities, if necessary.  It also ensures a coordinated, non-duplicative set of Elementary and Secondary Program projects that work together to achieve NASA’s education goals.

Additionally, the NASA Office of Education has established operating principles.  Every NASA-sponsored education project or activity is to be developed, implemented and evaluated according to these principles.  TFS projects will keep to these Education Program Operating Principles/Criteria:

- Relevance

- Content

- Diversity

- Evaluation

- Continuity

- Partnerships/Sustainability

  - Project Requirements

TFS project management will adhere to the guidance, expectations, and requirements outlined in the Elementary and Secondary Education Program plan.  The project manager will input to the Education database, NEEIS, to capture annual data and metrics to support Agency-wide roll up and reporting.  The project manager will periodically review input to assess progress of activities, make necessary adjustments to project implementation, and meet necessary reporting/reviews requirements.

The TFS project manager will complete the following tasks and deliverables.

- Annual performance goals are to be identified, measured and monitored throughout the fiscal year.

- Quarterly reports accounting for progress towards the APGs, status of projects to cost, schedule, and deliverables.

- Annual review with results of the review used to develop an improvement plan to be integrated within next fiscal year.

- Submissions to the online Weekly Activity Report and Education 90-Day report are encouraged.

- Continuous input to the Education database, NEEIS, for capturing data and metrics to support Agency-wide roll up and reporting is expected.

Information on project review and evaluation is found in Section 3.8 – Reviews.

Breaking Programs & Projects into Elements

In order to categorize a large project encompassing many activities it will be necessary to disaggregate.  In some cases it may be appropriate to aggregate similar activities from one or more projects or programs into an element for categorization.  In cases where an element, regardless of size, could be categorized in two or more buckets, the primary intent of the element should guide its categorization.

The following “buckets” have been identified under Outcome 2 and projects under the Elementary and Secondary Education Program can be expected to fall within and support one or more of the buckets.  Performance measures regarding the development of specific measures under each bucket will serve as further guidance to projects in development of collecting, tracking and reporting progress.  The primary TFS bucket is 2.2, Long Duration Educator Professional Development.  The secondary bucket is 2.4, K-12 Student Involvement.  Information on the primary and secondary buckets for TFS is contained in the following chart:

Bucket Overview

| OUTCOME 2 | K-12 focused, although some junior and community college educators may participate in Educator Professional Development experiences. |  |
| --- | --- | --- |
| 2.1 Educator Professional Development--Short Duration | Short-duration professional development experiences at Centers, ERCs, etc. primarily for K-12 educators. | Includes only one-time, short duration professional development for educators, typically short workshops and activities lasting less than 2 days. |
| 2.2 Educator Professional Development--Long Duration | Longer-term or sustained professional development experiences offered via distance learning, through series, partners, etc. for primarily for K-12 educators. | Includes professional development experiences lasting longer than 2 days or offered over an extended period of time. |
| 2.3 Curricular Support Materials | Development and distribution of educator resources for use in formal education settings; Educator Guides, Briefs, wallsheets, textbooks, web-based lesson plans and activities for K-12. | Includes printed and electronic materials intended for use in formal education and linked to national standards. This includes tools for educators (briefs, guides, etc.), wall sheets, text book collaborations, web-based lessons, web challenges, etc. |
| 2.4 Student Involvement K-12 | Opportunities for K-12 students to actively participate in instructional NASA opportunities and capitalize on unique NASA facilities and personnel. | Includes active instruction and engagement of K-12 students with specific learning objectives, typically associated with classroom teams and/or teachers. This includes summer "intern" activities (e.g. INSPIRE), challenges, flight payload opportunities, competitions, etc. |

The NASA Education Portfolio Data Call Report (May 2006,  Institute for Global Environmental Strategies) lists current EAP and EFP activities and associates each activity with specific buckets.  The document identifies push/pull opportunities for each activity.  The complete document is found at http://www.strategies.org/Portfolio/FinalReport.html.  Information on current push/pull opportunities for EAP is contained in the following chart:

Educator Astronaut Buckets Showing Push/Pull

| 1. Bucket Number/Name | 2. Element Name | 6. Purpose | 12a. Pulls Participants from: | 12b. Pushes Participants to: |
| --- | --- | --- | --- | --- |
| 2.2 Educator Professional Development--Long Duration | Network of Educator Astronaut Teachers (NEAT) | Project provides professional development and support for teachers through content development, web interaction, and the NEAT. The professional development workshops provided training on NASA Education opportunities, sessions for exchanging innovative lessons and teaching techniques, special access to world-class facilities and scientists, and opportunities to interact with the 2004 astronaut class and NASA Education personnel. Participants received detailed training to engage their classrooms and communities in NASA Education in an unprecedented way. This element is part of NASA’s Educator Astronaut Project. EAP develops original educational content based on Educator Astronaut training and flight activities in formats that are usable either directly by students or by teachers in a classroom setting | NEAT members were initially recruited from a nationwide campaign directed at K-12 teachers through informal networks, such as internet resources, as well as professional networks such as NSTA. | Members of NEAT are “plugged into” NASA Education, and are therefore very likely to become involved laterally in other areas within the NASA Education Strategic Framework, namely NASA Explorer Schools, Digital Network, FIRST, and other K-12 NASA activities for teachers and students. |
| 2.4 Student Involvement K-12 | STS-118, First Spaceflight of an Educator Astronaut (EA) | The STS-118 education and public engagement plan aims to capitalize on the interest surrounding the first spaceflight of an educator, and has three phases: 1) Pre-Mission Phase - Use EA and crew training for education content and public engagement; well developed ground–based education content and public engagement; 2) Mission – Link mission objectives to education content and public; on-orbit activities to enhance ground-based activities; and 3) Post-Mission – capitalize on excitement about and interest in mission and continuation of education-public activities | The participants for this activity are primarily informal education participants through the internet, as well as existing NASA participants such as those engaged in the Educator Astronaut Program Earth Crew and NASA Explorer Schools, NEAT member regions, communities with in ERCN reach, NGO partner communities/networks. | 7-12 Education and Higher Education strategic investments will draw participants from this activity due to their increased interest in NASA and STEM, as well as pursuing STEM fields and careers. |
| 3.1 Materials | NASA Space Act Agreement with AOL | Non-reimbursable Space Act Agreement between NASA and America Online, Inc. was formed 1) to educate kids about science and space exploration in a fun and interactive environment; 2) increase interest and awareness in NASA space exploration and Earth Crew; 3) provide opportunities to increase membership in Earth Crew; 4) create an interactive learning experience via “Crew Missions” | The participants for this activity are primarily informal education participants through the internet, as well as existing NASA participants such as those engaged in the Educator Astronaut Program Earth Crew and NASA Explorer Schools | Through the dissemination network of the Edspace website and the content provided by both Edspace and AOL, participants will be directed toward other NASA content providers and opportunities: DLN, NES, SON, etc. |
| 1. Bucket Number/Name | 2. Element Name | 6. Purpose | 12a. Pulls Participants from: | 12b. Pushes Participants to: |
| 4.1 Dissemination | Edspace Website | The Educator Astronaut Program website aims to provide an exciting, interactive program linking students, teachers, and the public to space related educational activities. It features opportunities to interact with NASA on ground-based opportunities and meet NASA astronauts/employees through webcasts, other DL activities and live programs. | The Edspace website draws participants from Informal Education and other websites. | The Edspace website and associated activities push participants/users into other NASA programs/resources through providing information and links. |

Information on current push/pull opportunities for EFP is found in the following chart:

Education Flight Project Buckets Showing Push/Pull

| 1. Bucket Number/Name | 2. Element Name | 6. Purpose | 12a. Pulls Participants from: | 12b. Pushes Participants to: |
| --- | --- | --- | --- | --- |
| 2.4 Student Involvement K-12 | Amateur Radio on the International Space Station (ARISS) | ARISS is an educational outreach program, sponsored by NASA, in which students engaged in a science and technology curriculum are given the opportunity to speak with an astronaut orbiting the Earth on the ISS. Using amateur radio, students ask questions about life in space and other space-related topics. Students fully engage in ARISS by helping set up an amateur radio ground station at the school and then using that station to talk directly with the on-board crew member for approximately ten minutes, the time of an ISS overhead pass. Preparation for the experience motivates the children to learn about radio waves, space technology, science, geography and the space environment. In many cases, the students help write press releases and give presentations on the experience to their fellow students and to the local community. Through this hands-on experience, students are inspired to learn more in STEM fields, and to pursue STEM-related careers. | NASA Explorer Schools; Informal Education | Workforce-students who have participated in ARISS have gone on to pursue aerospace and engineering careers. Some are now engaged in NASA-related careers. |

| 1. Bucket Number/Name | 2. Element Name | 6. Purpose | 12a. Pulls Participants from: | 12b. Pushes Participants to: |
| --- | --- | --- | --- | --- |
| 2.4 Student Involvement K-12 | ISS EarthKAM | ISS EarthKAM is a NASA education project that enables students, teachers and the public to learn about Earth from the unique perspective of space. At the core of the program is a spectacular collection of digital images of Earth. The image collection and accompanying learning guides and activities are extraordinary resources to support classes in Earth science, space science, geography, social studies, mathematics, communications and even art. ISS EarthKAM images are unique because they are taken by middle school students. During EarthKAM missions, registered middle schools use the EarthKAM web site to request images real time based upon their classroom investigations, 30 undergraduate students support the program per quarter primarily via web design and maintenance activities. | NASA Explorer Schools; Informal Education; JASON | Many students are selected for NASA internships and center job based on their EarthKAM experience. |
| 2.4 Student Involvement K-12 | Teaching From Space | The Teaching From Space office is co-located with the Astronaut Office at NASA’s Johnson Space Center. In addition to supporting public appearances by astronauts at educational events, the office is responsible for facilitating ISS downlinks, Education Demonstration Activities (EDAs), and Education Payload Operations (EPO). Live in-flight education downlinks on-board the ISS and during selected Space Shuttle flights, typically 20 minutes in length, allow students and educators to interact with the crew as they answer questions and perform simple educational demonstrations. EDAs, innovative on-orbit education activities, capture video of ISS crewmembers conducting STEM-related education demonstrations. EDA topics are suggested by the NASA education community to meet an identified need, and they support NASA education products and national education standards. Payloads (EPOs) flown on behalf of the Office of Education, are designed to support NASA Education outcomes by focusing on demonstrating science, mathematics, engineering, technology, or geography principles in a microgravity environment. | NASA Explorer Schools, Informal Education, Educator Astronaut Program, Elementary and Secondary Education, Higher Education | Work to get customers to use other NASA Education resources, specifically efforts under eEducation; and ERCN, AESP, DLN, Center Education Offices |

The annual performance plan for projects is to be submitted no later than the first week of November in each fiscal year to the identified HQ Elementary and Secondary Program Manager and the Mission Directorate Education Lead.  In turn, these persons will review and share with the Deputy Assistant Administrator for Education Programs for additional comment.  Program Directors and Project Managers will then discuss any necessary revisions and each Project Plan should then be approved no later than final week of November

  - Technical Summary

TFS is not a technical project.  It does not currently attempt to develop hardware, software, facilities, or similar assets.  Periodically the project will facilitate the process of manifesting education payloads and associated operating procedures, however, the technical aspects of these efforts will be fully documented through established payload review processes and reports.

  - Implementation Approach

TFS will be implemented by a mix of civil service and contractor personnel.  The JSC Education Office K-12 program manager is a civil servant providing oversight to the TFS project manager.  The remainder of the team will consist of contractor WYEs and fractional FTEs as required.  TFS will enlist other Centers to support the project and will provide funding for additional fractional FTEs and WYEs if needed.  Performing Center roles and responsibilities are listed in Section 2.2- Resources.

A well defined short-term and long-term approach is essential to the project’s success.  TFS will develop a separate detailed implementation plan.  The implementation plan will be completed by the beginning of the third quarter of FY07.  The plan will be reviewed by the Elementary and Secondary Program Manager and other NASA Education personnel as identified by the Elementary and Secondary Program Manager.

1.11 Project Dependencies

The major dependencies for TFS involve formation of relationships to support sustainability for the project.  In order to form such partnerships, the project must bring to the table internal and external education programs and organizations that are capable of supporting and enhancing the objectives of the project.  Establishing and leveraging internal and external mutually beneficial partnerships is essential to project success and to offset a reduction in FY07 funding.

As stated in the Elementary and Secondary Education Program Plan, project dependencies could also include:

- Legislative actions, such as the 2005 NASA Authorization Bill, the Deficit Reduction Act of 2005 (establishment of the Academic Competitiveness Council (ACC)), and Congressional-directed mandates, will further influence and shape existing projects and the expansion, consolidation, or cancellation of activities supported under Elementary and Secondary Education.  See Appendix C for additional information on the ACC.

- Expected recommendations as a result of the 2006 National Research Council’s review of NASA’s Pre-college Programs will serve as another near term resource for refining direction and focus of the Elementary and Secondary Program and potentially, have an effect on projects.

TFS will attempt to use the push-pull concept to pull participants into the project and move them into other projects providing a more experienced and focused group and creating a measurable pipeline.  Close and effective consultation, coordination, and cognizance among all entities – Education Divisions, Mission Directorates, and Centers – as aligned towards Outcome 2 will allow TFS to pull or push participants which is critical to the optimal fulfillment of NASA’s objectives relative to overall education investment.

TFS will consider strategic internal and external partnerships, cooperative agreements, and entrepreneurial relationships, and utilize announcements of opportunity that contribute to the overall project goal and objectives.  Included under this area could be agreements with ISS partners, other NASA education flight projects, and development and implementation of educational endeavors.

TFS strategic alliances, formal partnerships, and customized activities and events will be continuously strengthened and new ones sought.  All will be monitored and reported towards accomplishment of the project goal and objectives.

The offices of Legislative, Public Affairs, and External Relations will be appropriately involved in external endeavors.

  - Logistics

TFS project staff will work with internal and external partners to accomplish tasks aligned with project objectives.  These tasks include planning, coordinating, and facilitating new and existing education opportunities and initiatives.

TFS inherits numerous education activities from EAP and EFP.  TFS staff will oversee the logistics associated with these existing activities as well as the logistics of integrating new and innovative education activities into the TFS project.  In all cases TFS will solicit and manage participation from internal and external partners to ensure project objectives are met or exceeded.  Key to the success of the TFS project is coordination and communication with the NASA Centers that serve as the project’s Performing Centers.

- PROJECT BASELINE

2.1 Schedules

Plans

In compliance with NPR 7120.7 Institutional/Infrastructure Program/Project Management Processes and Requirements, TFS will submit an annual performance plan no later than the first week of November each year to the Elementary and Secondary Program Director who will review and share with others as appropriate.  The program director and the TFS project manager will then discuss any necessary revisions and each project plan should then be approved no later than the final week of November.

Reviews

Projects have a defined schedule for review and reporting.  See Section 3.8 - Reviews for complete descriptions of these elements.

Grants and Services

Grants, cooperative agreements and contracts can be expected as part of the overall operations and contribution of performance by the Elementary and Secondary Education Program and its projects.  Rules, requirements, and regulations as outlined by NASA Grant and Procurement Offices are to be followed.

TFS has identified the following major grant activities over the next 24 months.  Grantees shall provide annual progress reports to NASA, which are examined and approved or disapproved by the project managers.  Grantees are expected to provide additional input for the purpose of OMB and Congressional reporting requirements.

Project: Educator Astronaut Project (EAP)

Grantee/Cooperative Agreements: Oklahoma State University

Purpose: Program Support (1 contractor) to provide administrative and management support to the EAP at the HQ level

Performance Period: July 1, 2005 – June 30, 2006.  A 12-month extension from July 1, 2006 to June 30, 2007 has been approved.

Project: Education Flight Project (EFP)

Grantee/Cooperative Agreements: Oklahoma State University, Teaching from Space

Purpose: Provide unique educational content and experiences based on spaceflight

Performance Period:  February 1, 2006 – January 31, 2007.  Technical officer function is being transferred from Headquarters to JSC.

Grantee/Cooperative Agreements: University of California – San Diego (UCSD) for ISS EarthKAM

Purpose: UCSD oversees and manages the entire project. The UCSD Mission Operations Center operates 4 EarthKAM missions per year.

Performance Period: 5-year grant, ending August 31, 2006; however, a 3-month no-cost extension has been approved (thru November 2006) in order to complete independent evaluation and transition from HQ to JSC as technical officer

The TFS schedule can be summarized in three phases:  Project Transition, Project Start-up, and Project Implementation.  These phases and major activities are:

Project Transition (FY06 Fourth Quarter through FY07 Second Quarter)

TFS was augmented by merging two existing NASA Education projects, Educator Astronaut and Flight Projects.  Since these efforts were previously managed from Headquarters, it is necessary to transition them to JSC.  Some of the key transition tasks will focus on areas of assessment, business model, and partnerships and will include the following tasks/actions:

- Begin and/or complete third party, independent assessment of existing activities (i.e., ARISS, ISS EarthKAM, Education Downlinks, NEAT)

- Benchmark existing NASA K-12 professional development projects and networks (i.e., SEMAA, NES, Solar System Ambassadors)

- Investigate existing Elementary and Secondary and Outcome 2 projects and activities to identify and explore possible synergy/continuity

- Identify existing Outcome 1 and 3 projects that show potential for “push-pull” relationships

- Evaluate and define role of Centers in support of specific activities and projected future FTEs by Center

- Begin to communicate and work with Performing Centers

- Evaluate EdSpace and potential NASA web site (portal) migration issues

- Establish dialogue with NEAT group

- Develop a communications plan for NEAT (distribution list and forum)

- Assess TFS web needs and develop web strategy

- Investigate role of ISS partners in supporting and utilizing a variety of flight platforms for education activities

- Develop near and long-term (10 year) project implementation plans

- Co-chair the planning and deployment of STS-118 education efforts

- Lead the education sub-team for STS-118

- Assist with the development of an evaluation plan for STS-118

- Ensure files (e.g., budget information, historical documents, etc.) are properly transferred from HQ to JSC

- Complete the formal transfer of project management responsibilities and ensure internal partners are notified of changes

- Establish communication with other Centers regarding project direction and collaboration

- Address TFS staffing/hiring needs

- Develop internal processes for data collection and reporting (i.e. Weekly Activity Report (WAR), 90 Day Reports, etc.)

- Evaluate project and activity assessment tools (i.e. NEEIS)

During this phase, it is expected that the current schedule of activities and events under ARISS, ISS EarthKAM, and ISS Education Downlinks will be maintained.

Project Start-up (FY07)

After most of the transition efforts are complete, JSC will engage in a number of activities to build momentum for full implementation of project objectives.  The start-up phase will allow TFS to focus on high priority matters and activities that will generate short term wins for the project.  These activities will depend to some degree on when transition efforts are complete, but TFS anticipates the transition phase will begin in fall 2006. The results and recommendations from assessments and benchmarking efforts will contribute towards the following major tasks and start-ups during FY07:

- Revise the project plan

- Write an implementation plan (short-term and long-term)

- Complete independent external assessment of project activities

- Develop a plan for an internal partnership call

- Continue to look for push-pull opportunities

- Explore opportunities to collaborate with existing  NASA education flight projects

- Renew the Teaching from Space grant

- Complete development and begin implementation of a TFS web strategy

- Recompete the ISS EarthKAM cooperative agreement

- Redefine ARISS

- Redesign the NEAT element

- Continue support, integration, and deployment of STS-118 education efforts

- Evaluate STS-118 education activities, document lessons learned, and compile a revised framework for future education spaceflights

- Facilitate the engagement of other Centers in TFS activities

- Continue communicate and work with Performing Centers

- Establish partnerships with other NASA education flight projects that offer student involvement (i.e. Wallops, Team America Rocketry Challenge, Space Grant)

- Investigate partnerships with external education organizations, private industry, and other federal agencies

- Propose new starts, new business model, new interfaces (between projects, outcomes, and partnerships) to:

  - Reshape FY08 Elementary and Secondary Education Program and Resource Guidance for EAP and EFP and

  - Contribute to FY09 Education Program and Resource Guidance

- Implement new TFS web strategy

- Redesign assessment tools to capture push-pull data

- Reevaluate APGs for FY08

- Work with the Office of External Relations and the International Programs Specialist assigned to NASA Education to explore funding options for education flight projects

TFS must explore creative ways to continue student flight opportunities as the Space Shuttle is retired and the next generation vehicle is developed.  The variety of existing unmanned NASA flight platforms and education flight activities offer exciting opportunities to continue student engagement in flight projects.  TFS is actively supporting efforts to identify education opportunities for students as part of the ISS as a national laboratory effort.  TFS plans to hold discussions with other federal agencies and their education offices, non-governmental organizations, and professional education organizations to solicit ideas for innovative ways to engage students in education flight projects.

Project Implementation (FY08)

After start-up activities are well underway, TFS will implement additional activities to support all three project objectives.  TFS will basically be fully functional at this point and will implement activities as funding and personnel resources permit.  Some of the key activities TFS will conduct in this “normal” mode may include:

- Revise the project plan

- Issue an internal call for partnerships

- Continue to seek push-pull opportunities

- Continue to work with Performing Centers to evaluate project activities

- Facilitate the redesigned NEAT group of educators

- Manage the implementation of national education efforts tied to space exploration activities, similar to the education efforts planned for STS-118 (i.e., Pre-Mission, Mission, and Post-Mission education concept)

- Support selection processes for upcoming educator astronaut candidates, if required

- Enhance and facilitate education flight activities on board the ISS and identify unique on-orbit opportunities

Review and Reporting Schedule

TFS will utilize the online Weekly Activity Reporting tool to communicate key events/activities that have happened during the week or key events expected to happen in the near term.  A 90-day report is assembled for the NASA Administrator on a monthly basis and items that look forward over the 90-day period are compiled into this report for the Administrator and shared with the Agency Senior Leadership.  Monthly reports are due on the Monday proceeding the last Wednesday of each calendar month.  Quarterly reports are required on a similar schedule at the end of months 3, 6 (serves as semi-annual review), 9 and 12 (serves as annual report).  Reviews and site visits will be scheduled by the Elementary and Secondary Education Program officer.

2.2 Resources

NOTE:  Until Education Project Realignment is complete, the information contained in this section to include Centers and civil service workforce, is fluid and estimate only.

Budget – Educator Astronaut Project

|  | Educator Astronaut Project -FTE |
| --- | --- |
|  | Total | HQ | ARC | DFRC | GRC | GSFC | JPL | JSC | KSC | LARC | MSFC | SSC |
| FY06 | 2.48M | 0 | 0 | .3 | 0 | .4 | 0 | 1.1 | .6 | 2.7 | 1.6 | .4 |
| FY07 | 2.87M | 0 | .3 | .2 | .5 | .2 | 0 | 1.4 | .3 | .5 | .5 | .2 |

NASA Centers receiving EAP funds will be expected to report performance and activities to the TFS project manger, in accordance with the project management plan.  Performing Center FTE roles and responsibilities are:

ARC -Ames Research Center (FTE = 0.3) – NEAT.  ARC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

DFRC – Dryden Flight Research Center (FTEs = 0.2) - NEAT.  DFRC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

GRC – Glenn Research Center (FTEs = 0.5) - NEAT.  GRC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

GSFC – Goddard Space Flight Center (FTEs =0.2) - NEAT.  GSFC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

JPL – Jet Propulsion Laboratory (WYEs = .1) - NEAT.  JPL will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

KSC  - Kennedy Space Center (FTEs = 0.3) - NEAT.  KSC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

LARC – Langley Aeronautics Research Center (FTEs = 0.5) - NEAT.  LARC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

MSFC – Marshall Space Flight Center (FTEs = 0.5) – NEAT.  MSFC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

SSC – Stennis Space Center (FTEs = 0.2) - NEAT.  SSC will provide feedback to JSC and other Centers on program activities; Centers will communicate to NEAT members in their regions offerings of opportunities and professional development.  Further guidance for FTEs supporting the program will be available after project redefinition.

Budget – Education Flight Projects

|  | Education Flight Projects - FTE |
| --- | --- |
|  | Total | HQ | ARC | DFRC | GRC | GSFC | JPL | JSC | KSC | LARC | MSFC | SSC |
| FY06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| FY07 | 2.01M | 0 | .5 | 0 | 0 | .1 | 0 | .8 | 0 | 0 | 0 | 0 |

NASA Centers receiving EFP funds will be expected to report performance and activities to the TFS project manger, in accordance with the project management plan.  Performing Center FTE roles and responsibilities are:

ARC - Ames Research Center (FTEs = 0.5) – A staff member will assist JSC in their efforts to expand the EFP portfolio to include student flight opportunities on platforms in addition to the ISS and Space Shuttle.

GSFC – Goddard Space Flight Center (FTEs = 0.1, WYEs = 0.4) – Staff members assist JSC with examination of the Agencywide flight platform/services, cost for services, customer-base, and in depth analysis of the educational elements/value of platform by educators/students.

Staff members perform tasks including technical support for development of ground and flight hardware, school contact coordination and operations, coordination of the international ARISS technical team with JSC’s Mission Operations Directorate, and communication of key events and activities within the team and to TFS.  ARISS activities are coordinated with NASA’s Space Operations Mission Directorate.

JPL – Jet Propulsion Laboratory (WYEs = 0.7) – A staff member supports ISS EarthKAM activities related to image processing and associated tools that support image analysis expanding the educational value of the digital images through annotation, captioning, and organization, as well as by creating informational resources using the images.

  - Acquisition Management

TFS project is composed of educational activities that target students and educators at the engage and educate levels of involvement in the Office of  Education (OE) Education Framework.  The primary TFS focus is long-duration educator professional development and K-12 student involvement.  TFS will encourage new partnerships through established NASA processes and through a project specific internal call for collaboration.  TFS will use competitive sourcing to provide opportunities for potential partners.

The TFS acquistion strategy will maximize its abilities to meet project goals and milestones in support of the OE Education Framework and Outcomes.

  - Performance

Annual performance planning and reporting for TFS is required and annual performance goals will be measured and monitored throughout the fiscal year.  TFS will submit monthly reports and hold quarterly reviews.  At the end of each year, an annual review will be completed and results of the review will be used to develop an improvement plan to be integrated within the project’s next annual performance plan.

TFS will conduct a rigorous evaluation of its activities/deliverables as matched to APGs and targeted Elementary and Secondary Education Program outcome and sub-elements.  It will submit periodic progress reports on performance metrics and annual performance evaluations.

- SUBPLANS

3.1 Communications Plan

The portfolio approach to the management of NASA’s education efforts provides a holistic view of all NASA education programs, projects, products, and activities. It also facilitates performance evaluation, assessment, and accountability reporting, as well as communication of program status within NASA and to external stakeholders.

The report requirements provide a uniform system of documentation and assures clear and consistent communications throughout the program community on project progress, status, and issues.  The integrated operation of these functions furnishes the means to determine the harmony of actual and planned cost, schedule, and performance goals during development and implementation by verifying whether everything is occurring in accord with baseline plans.

Communication between TFS management, the project’s activities, Performing Centers, and the Elementary and Secondary Program Manager is key to the success of this plan.  The project manager will communicate with the Program Manager via email and a monthly videoconference or telecon to receive guidance for the project activities and to report progress of project activities.

The TFS project manager will ensure that pertinent information from the Elementary and Secondary Program Manager, JSC’s Director of Education, JSC’s K-12 Manager, and other higher-level management sources is promptly and accurately communicated to the TFS project staff and relevant partners.  Similarly, the TFS project manager will compile and communicate important information from project staff to upper management.  The latter will be achieved, in part, through timely submission of established reporting tools as outlined in Section 3.10 - Reviews.

3.2 Control Plan

The Elementary and Secondary Education Program plan provides TFS with guidance on control and compliance processes and plans.

The Elementary and Secondary Education Program control and compliance process includes reporting and reviewing performance against baselines (as detailed in this document); evaluating alternatives; developing disciplined processes for considering, approving and implementing changes to official baselines; and assuring positive feedback on all directions and decisions.  The program also provides a uniform system of documentation and assures clear and consistent communications throughout the program community on project progress, status, and issues.  The integrated operation of these functions furnishes the means to determine the harmony of actual and planned cost, schedule, and performance goals during development and implementation by verifying whether everything is occurring in accord with baseline plans.

The TFS project manager must request, in writing, deviations from the Project Plan or from the project-specific guidance including center-to-center or inter-center transfer of funds.  The TFS program manager reports major changes as reported to Elementary and Secondary Education Program Manager.

Ultimate responsibility for the effectiveness of management control rests with the TFS project manager.  Delegation of authority, definitions of roles and assignments of responsibilities carry with them the terms of accountability.

TFS funding shall be evaluated mid-year (prior to start of third quarter of the fiscal year) relative to the demonstrated performance of the project team and to the educational value of the project’s activities. Projects not meeting their deliverables, schedule or other commitments, or having insufficient alignment with NASA outcomes and objectives, may have their funding reduced or eliminated.

This portfolio management approach will provide information necessary for reallocation of resources; sunsets to projects, if necessary; and ensure a coordinated, non-duplicative set of Elementary and Secondary Education Program projects that work together to achieve NASA Education Outcomes.

3.3 Risk Management Plan

TFS is a relatively low risk project.  The primary risk is a loss of affiliation with principal participants resulting in the loss of opportunity to reach targeted audiences. Loss of affiliation is most often attributed to a lack of informational material currency, to funding disruption or stoppage, or to issues related to technology deployment.

TFS will monitor and mitigate program risk through continual evaluation of project content and delivery methods, adjusting the content and deployed technology to assure currency.  Also, the project manager will carefully monitor funding levels and flow to ensure continual engagement with current and intended funding recipients.

TFS will work with the Office of External Relations and the International Programs Specialist assigned to NASA Education, to explore funding options for education flight projects.

Continued or increased funding reductions that are a result of Congressional earmarks may result in risk to the project.  Future funding reductions may impact project activities and result in decreased scope, cancellation, or postponement of existing or new activities.  The impact of decreased funding could include:

FY07

- Delay in third party evaluation for project activities

- Decrease in support for STS-118 activities

- Reduction in new support for education flight projects

- Reduction in web site development

FY08

- Reduction in staff or postponement of future hires

- Decrease in support of internal and external partnerships

- Decrease in support for NEAT workshops and activities

- Reduction in support and/or funding for new education flight projects

TFS will continue to evaluate and address potential risks to the project due to funding shortages.

A robust performance process will be applied across TFS that is consistent with Elementary and Secondary Program requirements.  This process will be designed to provide Office of Education management with timely data to anticipate potential areas where project performance goals and milestones may not be met with the current funding or schedule.  This risk management process will provide management with timely data in order to institute project schedule, cost, and/or content corrections.

3.4 Technology Strategy or Insertion

The TFS project manager will build a technology strategy, beginning with review of current activities to see where future efficiencies, reach, and impact might be gained through technology-based applications and infrastructures.  TFS will consult with and link with the eEducation Program and Project Managers as strategy is developed.

Budgeting for IT-related infrastructure (e.g., web sites, portal) and electronic dissemination (e.g., 508 compliancy and meta-tagging of products) has been considered and is included in the project’s budget.  TFS will investigate the role/function of technology; how it can serve this project, and this links to inspire, engage, education, and employ categories.  TFS will also investigate how the development of a technology strategy will or can be used to enable the project to better push-pull (engage and educate) with Informal and Higher Education.

Existing technology-based tools used by the project include:

Inspire – NASA portal features

Engage – Downlinks, ARISS, EarthKAM, STS-118, DLN, AOL Space Act Agreement

Educate – K-12 curriculum support materials (NASA web site features, Learning Launchers 	and teacher notes, etc.)

The eEducation Program portfolio includes the assets of the NASA Learning Technologies (NLT) research and development (R&D) and evaluation; the education file on the NASA TV Public Services channel and the NASA Education Services channel; Web services, including the NASA public portal (www.nasa.gov) and education home pages; the suite of television and Web-based instructional series; and electronic, and site-based dissemination networks such as the Central Operation of Resources for Educators (CORE). Mission Directorate and NASA Education program-funded projects contribute to the overall portfolio of activities under eEducation.

The eEducation portfolio provides TFS with tools and expertise that can be utilized to promote the project and its activities, disseminate its content, and cross-cut with and between NASA Education divisions, including Informal and Higher Education.  Specific ways where collaboration with eEducation might support the TFS project include:

- NASA Education Technology Services (NETS) to review, adapt, produce, and disseminate TFS project content on the NASA Web site (portal) in the educator, student, and kids sections.  (Engage and Educate)

- Highlight TFS activities (ISS education downlinks, on-orbit education activities, STS-118, education flight projects, etc.) through the NASA TV education channel and use of the Web, including podcasting.  (Engage and Educate)

  - Cooperation and Commercialization

TFS will build strategic partnerships and linkages between STEM formal and informal education providers that promote STEM literacy and awareness of NASA’s mission.  TFS will target the following efforts:

- Pursue partnerships to support TFS and Outcome 2 through talents and resources of government, industry, and private foundations.  Dividing the work into manageable activities built around clearly articulated goals and tightly integrated objectives.

- Leverage technology infrastructures to deliver content related to exploration, science, and aeronautics to audiences; and partner with Mission Directorates, professional education organizations and others to create rich, effective learning experiences and connections for K-12 audiences.

NASA will release, at least twice a year, a request for entrepreneurial offers, seeking one or more unfunded collaborations with organizations that would enhance NASA’s ability to achieve its educational goals. Specifically, NASA will seek proposals for creating and managing innovative activities, events, products, services, or other types of formal or informal education methods for the purpose of disseminating information nationally about NASA’s projects and programs. It is intended that this request for entrepreneurial offers will result in the establishment of one or more non-reimbursable Space Act Agreements that will define the full roles and responsibilities of NASA and the proposing organization(s).  TFS will use these processes as one mechanism to identify potential external partners.

With guidance from the appropriate NASA offices, TFS will also work with ISS partners and their education offices to pursue cooperative education initiatives.

3.6 Safety and Mission Success Plan

Before any other Agency or organizational goal or objective, safety is the first consideration.

The TFS project adheres to standards of mission safety that are promulgated for all employees of NASA and its Centers.  TFS project activities that relate to spaceflight will adhere to all NASA regulations and NASA Policy Directives (NPDs) concerning both hardware and software.

TFS will develop safety and mission assurance plans as needed that will identify all activities such as safety, reliability and maintainability, quality assurance, software assurance (including IV&V), environmental related design and test including orbital debris mitigation, program surveillance, failure detection, isolation, and recovery, and failure reporting or resolution, and hazard analysis and mitigation, which are used to ensure the success and safety of the spaceflight.

  - Environmental Management Plan

The TFS project manager and project team members adhere to environmental compliance requirements, which are promulgated for all employees of the National Aeronautics and Space Administration and its Field Centers.

3.8 Systems Engineering Plan

Although TFS will not undertake engineering or highly technical projects, a systems engineering approach may be invoked on some project activities.  The types of activities where systems engineering might be used within TFS could include coordinating payloads for manned flight platforms such as Space Shuttle, ISS, and CEV, and unmanned platforms such as sounding rockets, scientific balloons, and the like.  Systems engineering processes might also be used when planning and coordinating complex efforts such as conferences or large educator professional development workshops.  The systems engineering processes used with these types of activities will primarily fall within the scope of what is commonly referred to as project management principles and methodologies.

The technical standards to which all education flight projects and payloads must adhere to are defined by the applicable flight platform’s program office.  TFS will ensure that all education payloads and flight projects comply with flight safety requirements.  Furthermore, TFS will process all education payloads and flight projects through the required safety review panels.

3.9 Verification and Validation

Verification and validation processes for the TFS project are outlined in the Elementary and Secondary Education Program plan.

Managing each of the three Outcomes within the Agency education portfolio requires a cross-cutting review that encompasses all projects, products, and activities, whether originating in the Office of Education, the Mission Directorates, or the Centers.  The Office of Education will assign a staff member for each Outcome to conduct strategic analysis and planning, establish measurable metrics, and implement an evaluation plan.  The staff member for each Education Outcome will report on the Agency’s progress toward achieving that Outcome to the Assistant Administrator and the ECC.  TFS will work with this staff member to ensure that the project continues to contribute to the appropriate Outcome.

Outcome reviews will employ a variety of mechanisms to assure that activities associated with each Education Outcome align with the education operating principles, yield demonstrable results, and reach intended audiences.  Use of external reviewers will be an integral part of outcome reviews to provide NASA with credible information regarding how well its education efforts meet customer needs.  Outcome reviews include the results, findings, or conclusions of individual program, project, product, and activity evaluations from within the portfolio.  TFS will use external reviewers as needed.

3.10 Reviews

TFS will regularly review the project’s activities, using external reviewers and internal NASA review processes.  Reviews will provide TFS with credible information regarding how well its education efforts meet customer needs.  TFS will use these evaluation results to make adjustments in the program where appropriate.

TFS will perform the following reporting and review activities:

- Annual performance planning and reporting is required and annual performance goals are to be identified, measured and monitored throughout the fiscal year.

- Monthly reports are submitted and quarterly reviews are held.

- Annual review with results of the review used to develop an improvement plan to be integrated within its next annual performance plan.

- Submission to the online Weekly Activity Report is encouraged.

- Continuous input to the Education database, NEEIS, for capturing annual data and metrics to support Agency wide roll up and reporting is expected.

More complete description of the review and reporting elements are listed, below.

### Weekly Activity Report (WAR)

Projects are encouraged to utilize the online Weekly Activity Reporting tool to communicate key events/activities that have happened during the week or key events expected to happen in the near term.  A 90-day report is assembled for the NASA Administrator on a monthly basis and items that look forward over the 90-day period are compiled into this report for the Administrator and shared with the Agency Senior Leadership.

### Monthly Status

By the final Wednesday of each month, each project shall submit a status brief. The brief shall provide explanation within the four areas of Cost, Schedule, Technical, and Management Issues and using the (green, yellow, and red) color key, provide status with explanations. In addition, accomplishments for the time period should be listed.  This status will be used to input progress into ERASMUS and to assess overall monthly status of the Elementary and Secondary Education Program to report to the AA for Education.

### Quarterly Review

The projects shall undergo review each quarter of the progress. Quarterly reviews shall be conducted by the program/project Manager.  The reviews shall consist of a demonstration of the state of the project’s technology and deliverables, an assessment of the project’s status relative to its schedule, and an evaluation and possible adjustment of the project’s direction and deliverables.

### Semi-annual Review of Performance

Project funding shall be evaluated mid-year (prior to start of third quarter of the fiscal year) relative to the demonstrated performance of the project team and to the educational value of the project’s technology.

- Annual Review of Performance

Reviews will be based primarily on written documentation summarizing the goals, objectives, organization, resources, and accomplishments of each Project.  The results of the review will be used to develop an improvement plan to be integrated within its next annual performance plan.

The final review will address the six criteria.  These principles are:

- Relevance: To effectively strengthen the Nation’s STEM workforce, NASA must implement activities that are useful to the education community and that strengthen their ability to engage students in the STEM pipeline.

- Content: Education investments use NASA content, people or facilities to involve educators, students, and/or the public in NASA science, technology, engineering, and mathematics.

- Diversity: NASA strives to ensure that underrepresented and underserved students participate in NASA education and research programs to encourage more of these students to pursue STEM careers. Programs and projects are representative of American demographics, engage underrepresented and underserved minorities, women, and persons with disabilities, and reflect an atmosphere of equity, balance, and inclusiveness.  NASA will continue to focus on enhancing the capabilities of Minority Serving Institutions to contribute to the research needs of the Agency.

- Evaluation: Education investments document their intended outcomes and use metrics to demonstrate progress toward and achievement of these outcomes and annual performance goals. Evaluation methodology is based on reputable models and techniques appropriate to the content and scale of the targeted activity, product, or program.

- Continuity: Projects and activities draw from audiences that have already demonstrated interest in NASA and connect participants to the next level of engagement. A blend of projects and activities encourage continued student affiliation with NASA throughout their academic career.

- Partnerships/Sustainability: Education investments leverage and achieve sustainability through their intrinsic design and the involvement of appropriate local, regional, and/or national partners in their design, development, or dissemination. As appropriate, key aspects of projects and activities are replicable and demonstrate potential for continuation beyond the period of direct NASA funding.

Finally, the TFS project will be subject to review and assessment per NASA Education guidance articulated under the Strategic Framework and as further communicated based on the results of the Education Coordinating Committee working group on evaluation.  The process is illustrated in the following graphic (Figure 6).

Figure 6 – Monitoring and Evaluation

3.11 Configuration Management Plan

The TFS project management team will record and report the status of project elements as documented in Sections 3.10 – Reviews, 3.1 – Communications Plan, and 3.2 - Control Plan. The information will be archived as documented in 3.14 - Knowledge Capture.

3.12 Education and Public Outreach Plan

This project falls under the umbrella of NASA Education and therefore the complete nature of the project and its scope are education and fall under the guidelines and requirements thereof.

3.13 Termination Review Criteria

TFS funding shall be evaluated mid-year (prior to start of third quarter of the fiscal year) relative to the demonstrated performance of the project team and to the educational value of the project.  Projects not meeting their deliverables, schedule or other commitments, or whose technology has or is clearly becoming obsolete, or has insufficient alignment with NASA education goals and objectives may have their funding reduced or eliminated.

.

3.14 Knowledge Capture

Evaluating the effectiveness of NASA Education’s portfolio requires on-line, near-real-time access to planning, budgeting, analytical and programmatic information to enable rapid decision-making, corrective actions, and the ability to respond in a timely manner to Agency and external stakeholder requests.  The decision-making environment requires that project managers:

• Use one common database and format.

• Assess using same database.

• Trace budget and actual costs through the Agency Education Outcomes with linkage to the NASA Strategic Plan.

• Demonstrate link between budget and both operational and strategic planning.

• Utilize the Agency’s Core Financial systems

TFS will centrally aggregate, carefully analyze, and make readily accessible relevant information in order to provide responses to requests from a variety of organizations for information concerning NASA education.  This information will be used to measure the accomplishment of outcomes for NASA management, OMB, Congress, and other stakeholders. The database utilized to centrally aggregate the information will be maintained by the Office of Education and should be readily available to the entire Agency, including mission directorates and centers for decision-making.

The TFS project manager will be held accountable for the continuous input to the Education database, NEEIS, for capturing annual data and metrics to support Agency-wide roll up and reporting.  The TFS project manager is expected to periodically review input to assess progress of activities and to make necessary adjustments to project implementation and to meet necessary reporting/reviews.

For TFS flight projects that will gather and manage data, these will align with all of the requirements as specified in NPR 7120.5D, and will address the data being captured and its availability.

3.15 Waivers/Deviations Log

The Elementary and Secondary Education Program plan lists requirements for waivers or deviations.

3.16 Change Log

| Date | Author | Amendment Details |
| --- | --- | --- |

4.0  Appendix A

NASA Office of Education

Outcomes, Annual Goals, and Measures

FY 06 and FY07

FY06 and FY07 Updated APGs and PART Measures

| FY 06 | FY 07 |
| --- | --- |
| Outcome Two: Attract and retain students in STEM disciplines through a progression of educational opportunities for students, teachers, and faculty. | Outcome Two: Attract and retain students in STEM disciplines through a progression of educational opportunities for students, teachers and faculty. |
| DELETE APG 6ED1 [Conduct 12 Educator Astronaut workshops, involving approximately 240 educators.] | APG 1 Conduct 10 Educator Astronaut workshops, involving approximately 200 educators. |
| DELETE APG 6ED8 [Select and support 50 additional schools to participate in the NASA Explorer Schools program, maintaining the total number at 150.] | APG 2 Select and support 50 additional schools to participate in the NASA Explorer Schools program, increasing the total number to 150. |
| DELETE APG 6ED2 [Select approximately 150 student experiments, involving approximately 1,500 students, to participate in the Flight Projects program.] | APG 3 Select 100 student experiments, involving 1,000 students, to participate in the Flight Projects program. |
| APG 6ED11 Collect, analyze, and report the percentage of grantees that annually report on their accomplishments. | APG 11 Collect, analyze, and report the percentage of grantees that annually report on their accomplishments. |
| APG 6ED12 Peer review and competitively award at least 80%, by budget, of research projects. | APG 12 Peer review and competitively award at least 85%, by budget, of research projects. |
|  | APG 4 Complete a retrospective longitudinal study of student participants to determine the degree to which participants maintain affiliation with NASA through the pipeline. |
| PART Measure 1. Percentage increase in number of elementary and secondary student participants in NASA instructional and enrichment activities. | PART Measure 1. Percentage increase in number of elementary and secondary student participants in NASA instructional and enrichment activities. |
| PART Measure 2. Percentage increase in number of elementary and secondary educators utilizing NASA content-based STEM materials and programs in the classroom. | PART Measure 2. Percentage increase in number of elementary and secondary educators utilizing NASA content-based STEM materials and programs in the classroom. |
| PART Measure 3. Level of student learning about science and technology resulting from elementary and secondary NASA education programs. | PART Measure 3. Level of student learning about science and technology resulting from elementary and secondary NASA education programs. |
| PART Measure 4. Level of student interest in science and technology careers resulting from elementary and secondary NASA education programs. | PART Measure 4. Level of student interest in science and technology careers resulting from elementary and secondary NASA education programs. |
| PART Measure 10. Number of people reached via e-education technologies per dollar invested. | PART Measure 10. Number of people reached via e-education technologies per dollar invested. |
| PART Measure 12. Percentage of programs that have developed and annually measure their effectiveness using performance metrics relating to NASA's mission and education goals. | PART Measure 12. Percentage of programs that have developed and annually measure their effectiveness using performance metrics relating to NASA's mission and education goals. |
| PART Measure 13. Percentage of grants awarded on a competitive basis. | PART Measure 13. Percentage of grants awarded on a competitive basis. |
| PART Measure 14. Percentage of grantees that annually report on their accomplishments. | PART Measure 14. Percentage of grantees that annually report on their accomplishments. |

4.1 APPENDIX B – Education Flight Platforms

The following list of flight platforms and student flight activities is found in the Education Flight Projects Office Portfolio Management Report, December 2004.  Additional information on each platform and activity is contained in that report.  Some of the listed activities have been completed and others are no longer active.  Implementation of other activities has not yet begun.

NASA Flight Platforms

International Space Station (ISS)

http://spaceflight.nasa.gov/sation/index.html

Space Shuttle

http://spaceflight.nasa.gov/shuttle/index.html

Expendable Launch Vehicles (ELV) and Exploration Systems

https://pollux.hq.nasa.gov/elv/

http://exploration.nasa.gov/

Scientific Aircraft

http://www.wff.nasa.gov/~apb/

Scientific Balloons

http://www.wff.nasa.gov/balloons/

Sounding Rockets

http://www.nsroc.com/front/program/prframe.html

Small-Scale Rocketry

Student Launch Initiative

Education Flight Projects Office Portfolio

International Space Station (ISS)

ARISS/SpaceCam

http://msnbc.msn.com/id/3077940/

Earth Knowledge Acquired by Middle School Students (ISS EarthKAM)

http://www.earthkam.ucsd.edu/

Education Payload Operations (EPO)

Node 2 Naming Competition

NASA Spaceflight Education Opportunities (NSEO)

Student Experiment Modules-Satchel (SEM-Satchel)

http://sspp.gsfc.nasa.gov/satchel/index.html

Expendable Launch Vehicles (ELV) and Exploration Systems

Small Payload Launch Initiative (SPLI) The Education Flight Project Office recommends the following education payloads for consideration under the Small Payloads Launch Initiative:

STARSHINE-4/5

http://www.azinet.com/starshine/

Citizen Explorer (CX-I)

http://citizen-explorer.colorado.edu/

National Space Grant Cubesatellite Complement

http://ssp.arizona.edu/sgsatellites/mission.shtml

University Nanosatellite Candidate

http://www.universitynanosat.org/

Get Away Special Program

http://sspp.gsfc.nasa.gov/gas/gas.html

Student Experiment Modules (SEM)

http://sspp.gsfc.nasa.gov/sem/about.html

### Scientific Balloons

Student Experiment Modules – Balloons (SEM-B)

http://www.wff.nasa.gov/semb/

Undergraduate Multi-disciplinary Earth Science Air-Borne Imaging Research Project (UMESAIR)

### Scientific Aircraft

### Student Experiment Modules – DC-9 (SEM-DC9) Proposed Future Education 	Flight Project

Student Experiment Modules – Sounding Rockets (SEM-SR)

Free Suborbital Projects for Autonomous Cooperative Experiments (FreeSPACE)

http://www.wff.nasa.gov/freespace/

### University Rocket Experiments (UREI) Proposed Future Education Flight Project

# Student Experiment Modules – Small-Scale Rocketry (SEM-SSR)

# Scholastic Rocketry Initiative (SRI)

.

Small-Scale Educational Rocket Initiative (SERI)

http://www.wff.nasa.gov/seri/

### Student Rocket Flight Demonstration Initiative (StuRoc) Proposed Future Education Flight Project

Control Center in the Classroom

Space Operations Learning Center

EFPO/National Space Grant Partnership

http://ssp.arizona.edu/sgsatellites/mission.shtml

Space Grant Consortium Involvement with Education Flight Projects

Crawl

Alabama		UAH BalloonSat, Auburn High Altitude Balloon program

Colorado		BalloonSat

Georgia			GSGC High Altitude Balloon Student Experiments

Iowa			HABET

Louisiana		ACES: Aerospace Catalyst Experiences for Students

Michigan		Balloons are Cool

Montana		BOREALIS

Nevada			Teleoperation of CanSat Experiments, High-altitude Ballooning

Oregon			MarsReach

South Dakota		SWAMI

Washington		Access to Space

Wisconsin		High-altitude Balloon Program, Rockets for Schools

Wyoming		High Altitude Balloon Program

Walk

Alabama		Auburn University Student Satellite Program

Arizona			University of Arizona Student Satellite Program

Colorado		DemoSat

Cornell University 	ICE CUBE

Dartmouth College	DartSat

Hawaii			Mea Huaka'i

Iowa			CySat

Kansas			KUTESat

Montana		MEROPE

Pennsylvania		SPIRIT II

Run

Arizona			Arizona State University Student Satellite Program

Colorado		Citizen Explorer Satellite, Three Corner Satellite

Cornell University	Dawgstar

Pennsylvania		Penn State University LionSat Program

Stanford University	SAPPHIRE, OPAL, EMERALD

Virginia			MicroMAPS

Washington		Translife Mars Gravity Biosatellite

Fly

Arizona			MIMIC

NASA Mission Directorates/Field Centers Education Flight Projects Portfolio

International Space Station (ISS)

Agricultural Camera (AgCam)

Expendable Launch Vehicles (ELV) and Exploration Systems

Athena Student Interns Program (ASIP)

Mars Student Imaging Project (MSIP)

Magnetic Field Investigation of Mars by Interacting Consortia (MIMIC)

http://nasa.asu.edu/index.php?pageid=27

Student Dust Counter

Scientific Aircraft

Aerosonde Uninhabited Aerial Vehicle (UAV)

JASON XIV

Reduced Gravity Flight Opportunities

Reduced Gravity Student Flight Opportunities Program (RGSFOP)

Museum Reduced Gravity Flight Opportunities Program

Stratospheric Observatory for Infrared Astronomy (SOFIA)

Small-Scale Rocketry

Student Launch Initiative (SLI)

Students for the Exploration and Development of Space (SEDS)

Appendix C – Academic Competitiveness Council (ACC)

Overview of the ACC

Department of Education Secretary leads an interagency effort to improve the effectiveness of Federal math and science investments.  Consistent with this effort, the 2006 Deficit Reduction Act created the “Academic Competitiveness Council” (ACC).  The Secretary of Education has the lead to:

- Identify all Federal programs with a mathematics or science focus;

- Identify the target populations being served;

- Determine the effectiveness of the programs;

- Identify overlap or duplication; and

- Recommend ways to integrate and coordinate the programs.

Workplan

The ACC is implementing a plan to achieve the goals of the act:

- Developing an inventory of Federal education program.  The ACC has produced a comprehensive inventory that combines the best thinking of the agencies and provides more program details such as the extent to which it has been evaluated.

- Grouping programs into categories based on their purpose and goal.

  - K-12 programs to improve student achievement;

  - Postsecondary fellowships to train future scientists; and

  - Informal education and outreach to enhance awareness of science.

- Developing common, outcome-based performance goals and measures for each program category.  For example, our K-12 investments should be measured by whether they boost student achievement.

- Determining which programs have data to demonstrate results using these measures.  For those that don’t, we need to adopt new evaluation strategies.  This will also be an opportunity to share best practices between programs.

# Academic Competitiveness Council: For K-12 Education

Below are the goals targeting K-12 STEM Education.  These goals were defined by members of the ACC K-12 working group.  Progress toward each one of these goals will be assessed with relevant metrics which are still under development (July 2006).  Each agency’s programs will be targeted toward the realization of at least one of these goals.

# Elementary and Secondary Goals and Metrics

Goals target following three areas:

- Student Learning: a) Quantity – preparing all students with the STEM skills needed to succeed in the global economy, whether in post-secondary education or the workforce and graduating students with the capability and motivation to become STEM professionals, educators, and leaders

- Teacher Quality:  Recruiting and retaining teachers with majors or minors in STEM fields and increasing the content knowledge of current K-12 STEM educators

- Engagement:  Increasing student engagement in STEM and their perception of its value to their lives

Metrics:  The general philosophy behind the following schema is that there need to be both “high level” metrics that serve as a national barometer of the status of math and science education as well as metrics that serve to assess the effects of individual programs or projects.

- National metrics.  The national metrics would provide information on the health of the nation with respect to mathematics and science education and would (arguably) provide information on whether the total national STEM education effort was paying off.  The national metrics should be comparable nation-wide and comparable across time.  A decided plus would be to select metrics that are readily available (i.e., already being collected as part of an on-going data collection program).  These metrics would not show causality—i.e., there would be no way to prove that changes in them were the result of the Federal investment—but they would provide essential data on the state of math and science education.

We have identified metrics for which data are currently available, as well as additional metrics—such as measures of teacher effectiveness and of student interest in math and science—for which we have not yet identified sources or for which agencies should identify strategies for collecting nationally.

- Program metrics.  The program metrics would provide information on the merits of individual projects and programs.  Preferred metrics would provide information on whether programs and projects were improving outcomes, particularly student achievement, for target participants.  However, given the diverse nature of Federal elementary and secondary programs, program metrics could include other, intermediate, outcomes such as whether research is enhancing knowledge about aspects of teaching and learning.  Programs and projects would be encouraged to use experimental or quasi-experimental designs to assess program effects.

In a sense, these metrics are equivalent to the long-term and annual measures used under PART.  Program progress on the program metrics would presumably be reflected in progress on the “national” metrics, although, of course, it would not be possible to directly link the two.

# Text boxes

EDUCATOR

ASTRONAUT

PROJECT

EDUCATION

FLIGHT

PROJECTS

Educator Workshops

Astronaut Support

Educator Astronaut Support

NEAT

TEACHING FROM

SPACE

ASTRONAUT
OFFICE

Educator Workshops

Astronaut Support

Educator Astronaut Support

NEAT

Educator Workshops

Astronaut Support

Educator Astronaut

NEAT

Educator Astronaut Support

NEAT

Educator Workshops

Product Development Facilitation

STS-118/Future Spaceflights

Educator Astronaut Recruitment/Selection

TBD

Astronaut Support

Education Payloads

On-orbit Education Activities

In-flight Education Downlinks

Product Development Facilitation

ARISS

EarthKAM

Sub-Orbital Flight Platforms

TBD

JSC OFFICE OF

EDUCATION

K-12

NASA Education

Mission Directorates

Center Education Offices

Informal Education

ISS Partners

TEACHING

FROM

SPACE

ASTRONAUT
OFFICE

Educator Astronaut Support

NEAT

Educator Workshops

Product Development Facilitation

STS-118/Future Spaceflights

Educator Astronaut Recruitment/Selection

Astronaut Support

Education Payloads

On-orbit Education Activities

In-flight Education Downlinks

EarthKAM

ARISS

Sub-Orbital Flight Platforms

TBD

JSC OFFICE OF

EDUCATION

K-12

NASA Education

Mission Directorates

Center Education Offices

Informal Education

ISS Partners

Elementary/ Secondary

Education

Informal Education

Higher Education

AESP

Explorer Schools

Mars Student Imaging

C-9 Program

Moonbuggy

FIRST Robotics

URC

USRP

GSRP

FAR

NAFP

NPP

JPFP

Space Grant

EPSCOR

URC

C-9 Program

Moonbuggy

USRP

GSRP

FAR

NAFP

NPP

JPFP

Space Grant

EPSCOR

Outcome 1: Contribute to the development of the STEM workforce in disciplines needed to achieve NASA’s strategic goals, through a portfolio of investments.

NSTA

Digital Learning Network

Solar System Ambassadors

PSTI

SEMAA

Educator Workshops

AESP

Explorer Schools

Mars Student Imaging

FIRST Robotics

Outcome 2: Attract and retain students in STEM disciplines through a progression of educational opportunities for students, teachers and faculty.

Conferences

NASA TV

IMAX Movies

Museum Sci Ctrs

NASA Portal

Public TV

Curriculum Support

NASA Connect

Visitor Centers

GSUSA

Explorer Institutes

Outcome 3: Build strategic partnerships and linkages between STEM formal and informal education providers that promote STEM literacy and awareness of NASA’s mission.