Intermountain West Coordinated Bird Monitoring Program

Progress Report

Jonathan Bart and Ann Manning

March 1, 2006

(NOTE:  The permanent IWCBM web site address is given in this document but at present [4 Mar 2006] the web site is still under development; it  may be found at http://iwcbm.dev3.fsr.com/)

Contents

Introduction	1

Aquatic Bird Survey	1

Designated Areas	2

Site Descriptions	2

Existing Surveys	3

Potential additional surveys	4

Collection of Existing Data Sets	4

Specific Management Issues to Address	4

Roles and Responsibilities	4

Conclusion	5

Terrestrial Bird Surveys	5

Data Management	5

Analytic Tools	5

# Introduction

This Progress Report describes the status of the Intermountain West Coordinated Bird Monitoring (IWCBM) program as of March 1, 2006.  An overview of the program is available at the IWCBM home page, http://greatbasin.nbii.gov/iwcbm/.  Since the beginning of the IWCBM project in early 2005, most work has been focused on the Aquatic Bird Survey.  This work is described in the next section; other progress is described in the final section.

# Aquatic Bird Survey

The Aquatic Bird Survey is being implemented using a four step approach (Table 1).  The program overview emphasizes tasks 1 and 2, particularly guidelines for preparing site descriptions.  This document describes progress on identifying designated areas and current and potential surveys.  It then suggests possible management issues to be addressed during the first few years of the Survey.

Table 1.  Approach for initiating the IW Aquatic Bird Survey

1.  Describe general purpose of the survey

2.  Create the needed infrastructure

Focal area and species

Sites to be covered

Site descriptions

Current and potential surveys

Data management system

Organizational support

3.  Choose specific management issues to address

4.  Implement the survey for those issues

## Designated Areas

Collaborators on the program have identified 424 important areas for aquatic birds in the IW (Table 2).  The numbers per State vary from 18 to 52, with Idaho having the largest number.  The IWCBM web site, http://greatbasin.nbii.gov/iwcbm/, has reports for each State.  Careful review of these reports is needed.

Table 2.  Number of designated areas and their importance to aquatic birds.

|  | Number of areas | Number known to be important for… |
| --- | --- | --- |
| State |  | Waterfowl | Waterbirds | Shorebirds |
| Arizona | 42 | 15 | 32 | 13 |
| California | 40 | 20 | 22 | 19 |
| Colorado | 44 | 0 | 29 | 22 |
| Idaho | 52 | 7 | 32 | 4 |
| Montana | 21 | 2 | 12 | 13 |
| Nevada | 48 | 15 | 20 | 2 |
| New Mexico | 37 | 9 | 20 | 12 |
| Oregon | 40 | 30 | 28 | 13 |
| Utah | 41 | 17 | 27 | 20 |
| Washington | 18 | 7 | 4 | 3 |
| Wyoming | 41 | 23 | 1 | 0 |
| All | 424 | 145 | 227 | 121 |

## Site Descriptions

Site descriptions have been prepared for 137 (34%) of the designated areas (Table 3).  Idaho has prepared descriptions for nearly all the areas it has identified.  Montana, Nevada, and Colorado have also prepared descriptions for many of their sites.  Less work has been done on preparing survey descriptions for designated areas, however some descriptions have been prepared for sites in Nevada, Utah, Idaho, and Colorado.  Preparing descriptions for the rest of the sites should receive high priority.

Table 3.  Status of descriptions for designated areas in the IW.

| State | Prepared | Not prepared | Proportion prepared |
| --- | --- | --- | --- |
| Arizona | 0 | 42 | 0.00 |
| California | 0 | 40 | 0.00 |
| Colorado | 17 | 27 | 0.39 |
| Idaho | 50 | 2 | 0.96 |
| Montana | 15 | 6 | 0.71 |
| Nevada | 25 | 23 | 0.52 |
| New Mexico | 0 | 37 | 0.00 |
| Oregon | 0 | 40 | 0.00 |
| Utah | 30 | 11 | 0.73 |
| Washington | 0 | 18 | 0.00 |
| Wyoming | 0 | 41 | 0.00 |
| Grand Total | 137 | 268 | 0.34 |

## Existing Surveys

Decisions about which surveys will be conducted at each site will be made by managers and biologists who have the resources to survey the sites.  To facilitate the decision-making process, we collected information on surveys being conducted at the designated areas.  We defined 5 surveys:

1.  Aerial survey (primarily for waterfowl; any time of year but mainly winter in the IW)

2.  Ground survey (usually for all aquatic species; any time of year)

3.  Secretive marsh bird survey (for rails, bitterns, grebes; breeding season)

4.  Migrating shorebird survey (migration season; shorebirds only)

5.  Colony survey (breeding season; all colonial, aquatic species)

Our current estimate is that 388 surveys for aquatic birds are currently being conducted in the IW including >100 aerial surveys and ground-surveys for all species.  Fewer, but still significant numbers, of the other three surveys are being made.  The reports for each State provide detailed information about where these surveys are being conducted in each State.  This information should be reviewed by groups in each State.

Table 4. Summary of known aquatic bird surveys at designated sites in the intermountain west1.

| Survey | Aerial Waterfowl | Ground-based waterbird | Secretive Marshbird | Migrating Shorebird | Breeding Colonies | All surveys |
| --- | --- | --- | --- | --- | --- | --- |
| Existing survey | 117 | 119 | 44 | 29 | 79 | 388 |
| No survey at present | 28 | 112 | 73 | 93 | 64 | 370 |
| Volunteers could conduct | 7 | 30 | 40 | 30 | 34 | 141 |
| Volunteers could help conduct | 0 | 13 | 4 | 5 | 4 | 26 |
| Staff would conduct | 0 | 46 | 23 | 42 | 24 | 135 |
| Survey would be difficult | 21 | 23 | 6 | 16 | 2 | 68 |
| Information lacking | 263 | 191 | 293 | 276 | 242 | 1265 |

## Potential additional surveys

We also determined what additional surveys might be conducted at each site.  No presumption was made that these surveys should be conducted.  This information was gathered solely to help address questions such as “If we wanted to survey at least 80% of the sites with significant numbers of migrating shorebirds (or any other group), how many new surveys would be needed?”.  We also collected information on whether volunteers could do the survey entirely or in part, and whether the surveys were viewed as extremely difficult by biologists familiar with the sites.  Results showed that there are about as many opportunities for additional surveys as there are current surveys (Table 4).  Most suitable sites for aerial surveys are being surveyed whereas less than one third of the sites suitable for migrating shorebird surveys are being covered.  Based on our results, volunteers could conduct 141 surveys and could help conduct 26 additional surveys.

## Collection of Existing Data Sets

Table 3 above, reporting that 388 surveys of aquatic birds are made each year in the IW provides dramatic confirmation of the need to collect the existing data.  The results of these surveys are undoubtedly useful to the local managers, and some of the data, particularly the aerial survey data, are collected in a central location.  Much of the data, however, exists only on paper and is gradually being lost or at becoming irretrievable.  It thus seems worthwhile to make a substantial effort to collect these data sets and store them in digital and permanent form.  We have recently received one data set and re-formatted it so it can be stored in a data base and would be interested in collecting other similar data sets.

## Specific Management Issues to Address

Participants in the Aquatic Bird Survey should begin considering what specific tasks they would like to work on during the coming few years.  Three possibilities are:

1.  Initiate a long-term trend survey.

2.  Initiative a 3-4 year project to determine distribution, abundance and habitat relationships.

3.  Address one or more very specific issues such as effects of water level on aquatic birds.

Selecting one or more projects, such as the ones above, will make it easier to motivate people to complete the site descriptions and the information on current and potential surveys, and to prepare survey protocols.

## Roles and Responsibilities

The Western Working Group is the primary forum for discussing the IW Aquatic Bird Survey and gaining agreement on major components of the Survey.  A coordinating committee for the IWCBM program holds conference calls 1-2 times per month.  The IW Joint Venture and BCR Coordinators have agreed to lead the effort to encourage increased coordination of existing surveys and decisions about whether to initiate new surveys.  USGS scientists are taking the lead on design.  Many State biologists are playing key roles in establishing ?????

## Conclusion

We recommend that attention be given to the following tasks:

1.  Review and revision where needed of the designated areas and the current and potential surveys at each.

2.  Preparation of site descriptions.

3.  Selection of the management issues to be addressed during the coming 3-4 years.

4.  Decisions about which surveys to continue or initiate.

5.  Acquiring existing, high-quality data sets.

6.  Completion of the data base and analytic tools.

# Terrestrial Bird Surveys

A few conference calls have been held to define objectives of this part of the IWCBM (in particular whether to emphasize a long-term trend-monitoring program or one or more short-term programs).  Work has also begun on a nocturnal bird monitoring program.

# Data Management

Much remains to be done on the data management system.  The web site is functional, though it will be improved significantly in the coming few months.  We have had several conversations with a database designer but serious work has not been initiated yet.  We have developed a proposed design but need to prepare examples of how data from different surveys would be stored in the database.  We anticipate collecting data on spreadsheets which will be e-mailed to us for the next several months or a few years.  We anticipate gradually switching to an internet-based approach but serious questions remain – at the regional and continental scale – about how much to rely on a distributed system and what central repositories will be created.  Thus, we anticipate proceeding slowly on attempting to automate data entry.  Data retrieval and analysis, on the other hand, can be organized as soon as we find the time, hopefully during the next 3-4 months.

# Analytic Tools

Work is only just beginning on this part of the IWCBM program.  See the “IWCBM – Analytic Tools” report for recent accomplishments and plans.