INTERNAL UNOFFICIAL DRAFT  - STILL WORK IN PROGRESS - DO NOT DISTRIBUTE

INTERNATIONAL TECHNICAL REVIEW OF STATUS

KSTAR PROJECT

Coordinated by:

Quantum Technology Corp.

3650 Wesbrook Mall

Vancouver BC V6S 2L2

Canada

tel: 1-604-222-5539  fax: 1-604-677-5826

www . quantum-technology.com

Under contract to KOPEC

Authors:

C. Winter, Ph.D.  			cwinter@quantum-technology.com

J. Miller, Ph.D.     			miller@magnet.fsu.edu

C. Neumeyer, M. Sc. 		neumeyer@pppl.gov

S. W. Wolfe, Ph.D.			swolfe@quantum-technology.com

R. Ivanov, Ph.D.			rouslanivanov@yandex.ru

J. Montani, B.Eng.			jmontani@quantum-technology.com

S.I. Choi, M.Sc.			sichoi@askcorp.co.kr

Date: 2004 Feb. 5

TABLE OF CONTENTS

A) Introduction - Scope of Review

B) KSTAR Objectives

C) KSTAR from an International Perspective

D) Component Analysis

For each component:

- PRESENT STATUS

- TECHNICAL RISK FACTORS

- COMMENTS AND RECOMMENDATIONS

E) Recommendations

F) Conclusions

A) Introduction - Scope of Review

This review has concentrated on project management and scheduling issues.  The review was undertaken as part of the procedure of the annual budget review for the KSTAR project.  The review contract is between Quantum Technology Corp. and KOPEC.

Review methodology: The KSTAR team provided the reviewers with detailed technical reports on the status of the KSTAR design, budget and schedule information which were studied by the reviewers prior to the four-day on-site review.  During the on-site process the review team was able to interview each of the team leaders and examine documents and test results.  The KSTAR team has been very kind in providing written answers to written questions.  The review team received excellent cooperation and assistance from KSTAR personnel.

The primary objective of the review is to clearly communicate the present status and expected future program of the KSTAR project to KOPEC and the Korean Government.  The overall results of the review are very positive.

During the meetings a number of differences between KSTAR procedures and procedures at other international laboratories were noted.  These differences are commented on in this report.  These are positive comments suggesting minor changes in organizational structure and methodology.  The KSTAR project team is clearly very successful and very effective at their job.

B)  KSTAR Mission

The mission of the KSTAR project is to develop a steady-state advanced superconducting tokamak, and thus to establish the scientific and technological basis for the construction of a fusion power reactor as an attractive energy source in the future.  This is an important step in the world-wide fusion energy research program, which aims to find a practical technical method for controlled exothermic nuclear fusion of isotopes of hydrogen, as a peaceful carbon-free source of energy with abundant supply and minimal environmental imact.

The technological aims of the KSTAR project are:

- To build and operate a fully superconducting magnet system

- To explore and achieve steady state operation of a tokamak using non-inductive current drive

- To investigate and optimize continuous divertor operation, as well as  continuous plasma wall interaction. This includes the development of limiters, divertor plates and other important in-vessel plasma-facing elements.

The research objectives in the context of the KSTAR mission are:

- To provide tokamak operation in advanced regimes with high-beta plasmas such as high performance H-mode, reversed-shear mode, and high-lj mode

- To integrate optimized plasma performance during continuous operation, as a step towards an attractive fusion power reactor

- To extend the present stability and performance boundaries of tokamak operation through active control of profiles and energy, and particle transport mechanisms.

KSTAR is a very important project for the scientific community as well as for Korean industry. The project will be the most technically advanced fusion energy device in the world when it is completed. It is designed to incorporate the current, most advanced technologies for plasma confinement, including divertor operation and non-circular plasma configurations.  In addition, the project employs the most up-to-date plasma heating technologies, such as high power, long pulse RF heating at ion cyclotron frequencies, electron-cyclotron heating with state-of-the-art gyrotrons, and powerful neutral beam injection.

C) KSTAR from an International Perspective

The KSTAR project will make critical contributions to the world fusion research and development program. It will:

- Extend advanced tokamak research to high performance and steady-state operating regimes

- Contribute techniques for successful steady-state operation of the international tokamak project, ITER

- Compare advanced tokamak physics results with those from superconducting stellarators and spherical tokamaks.

- Position Korea to make major contributions to ITER.

None of the other countries involved with ITER have recently constructed, or are planning to construct, a device with the advanced ITER-relevant technology of KSTAR.

The KSTAR project is a very ambitious project for Korea given the large number of new technologies involved.  The KSTAR team has already succeeded in creating  the infrastructure -- scientific and engineering skills, research facilities, industrial partnerships, university collaborations and international collaborations -- required to successfully complete this project.  In addition the KSTAR team deserves praise and recognition for doing all of this development work with a severely constrained budget.

The attached table compares the KSTAR project to similar international projects.  Note that KSTAR has the same parameters as the TPX project, which was planned by the US in the early 1990’s but cancelled due to budget cuts.  The key point is that the budget for the KSTAR project is much less than the proposed budget for TPX.  In fact the KSTAR work breakdown scope budget is only one half of the TPX budget!  Furthermore the KSTAR team has been able to use the budget in a very constructive manner to establish facilities and research programs for every major component of the project.

It is our view that the recent cost increases of the KSTAR project as well as the schedule delays are due to an overly aggressive and optimistic projection at the start of the KSTAR project.  Budget increases and schedule extensions are necessary at this stage to ensure the completion of the KSTAR project.  This is also essential because it is part of the infrastructure required for the Korean contribution to the ITER project.

# D)  COMPONENT ANALYSIS

(arranged by WBS)

# T1 – TOKAMAK SYSTEMS

# T11 – Plasma Facing Components

Consists of:

T111	Divertor

T112	Inboard Limiter

T113	Poloidal Limiter & Armour

T114	Passive Stabiliser

T115	Local Instrumentation & Control

T116	Research & Development

Only the inboard limiter (T112) will be installed for first plasma experiments, therefore the discussion considers only this component.

### T112   Inboard Limiter

## STATUS

Development and design are complete

## TECHNICAL PERFORMANCE

Target performance:

Ability to withstand the thermal and mechanical loads of high temperature fusion grade plasma

Attained performance:

Not yet tested

## TECHNICAL RISKS

1) Leak in coolant line and loss of coolant

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Delay | Low | Medium |

Notes:

- Hydraulic pressure tests to 22 bar are planned

- Time to install the inboard limiter:  6 months

- Time to repair a leak:  2 months

2) Quality of vacuum

Properties of tile material and wall conditioning affect vacuum quality and therefore plasma parameters

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Delay | Very low | Low |

Notes:

- The outgassing data for the materials used have all been examined.  The graphite/CFC was tested for outgassing at the national standards institute, due to the fact that the material did not have any available outgassing information.

# T12 – Vacuum Vessel System

T121	Vacuum Vessel

T122	Baking and Cooling Piping System

## STATUS

T121	Vacuum Vessel				Fabrication in progress

T122	Baking and Cooling Piping System	Design complete

## TECHNICAL RISKS

1) Water jacket leak to the vacuum space

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Delay at worst, performance at best | Low to medium | Low to medium |

2) Piping leak

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | Delay at worst, performance at best | Low to medium | Low to medium |

3) Vacuum leak

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Delay at worst, performance at best | Low to medium | Low to medium |

Notes and recommendations:

- Implications are different depending on whether a fluid/gas leak is to cryostat space or to vacuum vessel space.

- Leak specification has been downgraded to 10-6 mbar-l/s because the original specification was seen to be unnecessarily strict.  This agrees with our recommendation.

- The water cooling lines on the vacuum vessel must be helium leak tested to ensure there are no leaks.  A leak in this location could jeopardize the whole project.

- A leak in the vacuum vessel can be distinguished from a leak in the bellows by introducing GHe to the cooling water jacket.

- The gas and fluid supply penetrations into the vessel, and distribution within the vessel, is a complex system. Due to the large number of lines and joints, the large thermal gradients, stresses, and deflections, as well as the magnetic/eddy current forces and deflections, the system is quite challenging from an engineering perspective. Also, ease of installation will be a key issue, considering the very tight space and limitations of in-vessel work. Therefore, this area deserves considerable engineering effort and detailing.

## T123	Vacuum Vessel Thermal Shield

## STATUS

Design complete

## TECHNICAL RISKS

1) Leak in cooling lines

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | Performance | Low | Low |

- There is a redundant set of GHe cooling lines in the design.  To switch between sets in the case of a leak takes about one week of down time.

2) Failure of mechanical supports

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Delay | Medium | High |

- Safety margins in the design of the mechanical mounts must be large because replacement is very difficult and the consequences may be severe.

3) Excessive thermal load

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Delay | Medium | High |

# T13/T14 ( TF/PF Magnet System

Consists of:

T131/T141	TF/PF Magnet Conductor

T132/T142	TF/PF Magnets

T133/T143	TF/PF Local I&C / External Quench Detection System

T134/T144	TF/PF Magnet Bus & Leads

T135/T145	TF/PF Conductor and Magnet Test

T136/T146	TF/PF Magnet Structure

T137/T147	TF/PF Magnet System Research and Development

# T131/T141 – TF/PF Magnet Conductor

Production and qualification of CICC conductor for TF and PF magnets, including: acquisition of superconducting wire (both Nb3Sn and NbTi), plating, cabling, jacketing, and appropriate QA inspections and tests at each stage.

## STATUS

This task has been carried through the prototype stage and is well into the production stage.  However, it is not clear how thorough the QA test program is.  It has been stated that certified wire test data are supplied by the vendors, but no such data were readily available showing scatter and margins relative to the specifications.  Apparently, no CICC current testing has been carried out other than the test of TF00.  Because the test was performed only at approximately 4.5 K, the critical-current limit of the conductor was not approached.  A variety of CICC inspections and tests are planned, including leak testing prior to winding and inspection of CICC witness samples reacted along with coils for evidence of SAGBO.  Acceptance criteria for leak test of CICC are semi-quantitative.

## TECHNICAL PERFORMANCE

The design is based primarily on a minimum critical-current performance of the wire of 750 A/mm2 at 12 T and 4.2 K, and ac-loss performance defined by dissipation of 250 mJ/cm3 of non-copper over a +/- 3T cycle.  It is not clear what are the allowable values for degradation of that performance in the process of fabricating the wire into a CICC, winding the coil, and heat-treating in that form.

## TECHNICAL RISKS

1)	A particular batch of wire does not meet specifications

Critical-current or ac-loss performance lower than expectations

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Substandard coil performance | High (replace coil or operate at reduced level) | Long delay (for replacement) or none (operate at lower level) |

2)	Wire damaged or degraded by cabling and/or jacketing

Critical-current or ac-loss performance lower than expectations

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Substandard coil performance | High (replace coil or operate at reduced level) | Long delay (for replacement) or none (operate at lower level) |

RECOMMENDATIONS:

- Institute tests of wire keyed to production units

- Institute tests of a reasonable number of CICC samples correlated with tests of individual wires.  Tests should include CICCs with credible flaws that might be introduced by the cabling or jacketing processes and be missed during practical inspection procedures.  The reasonable number should be determined by the observed variability of test results among wires and CICCs.

- Develop suitable methodologies and procedures to ensure strict control of materials and processes

# T132/142 – TF and PF Magnets

Fabrication of TF and PF magnets, including QA inspections and tests

## STATUS

A prototype for the TF coils has been built and tested and a prototype for the CS and divertor coils has been built (the BKG coil) and will be tested soon.  The outer PF coils are in production.

## TECHNICAL PERFORMANCE

Coils must reach the design field and retain specified performance margins during all phases of operation.  Although complex, these operating conditions are fully specified.  Testing for these margins is very difficult short of operating the complete magnet system in the defined operating scenarios.

## TECHNICAL RISKS

1)	A coil fails or exhibits degraded performance

Coil has a short, has compromised insulation integrity, has degraded critical-current performance, or excessive ac loss

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | All (failure, delay for repair or replacement, operates with degraded performance, results in damage to equipment or injury to personnel) | High | Extreme delay |

RECOMMENDATIONS:

Either test entire coils (extremely costly and not amenable to fully measuring true performance margins in many cases) or develop the appropriate tests of key components (including witness samples of conductors processed along with coils) that provide confidence in coil performance.

# Develop suitable methodologies and procedures to ensure strict control of materials and processes

# T134-144 – TF and PF Magnet Bus-Line and Leads

This task includes the fabrication and installation of in-cryostat and out-of-cryostat bus systems, including: joints, bus and joint supports, feed-throughs, bus ducts, cryogenic current leads, and current lead boxes.

## STATUS

Several fairly detailed conceptual designs have been produced with sufficient detail in all components to allow accurate cost projections.  Some components have been prototyped to assess fabrication feasibility, cool-down, and high-voltage integrity.

## TECHNICAL PERFORMANCE

Buswork and leads must retain specified performance margins during all phases of operation including normal, off-normal, and fault conditions of the magnet systems.

## TECHNICAL RISKS

- Mechanical/Electrical failure at a joint

The Bus-Line and the Current leads involve a series of strand-to-strand joints, butt joints and lap joints that require care and attention to process detail during installation

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Failure, Delay | Medium | Medium |

## RECOMMENDATIONS

Ensure that processes are well developed, well documented, and extensively practiced to achieve the required results with very low probability of error.

# T135/145 – TF and PF Conductor and Magnet Test

Design and construction of a facility capable of accommodating full-size prototype and production magnets for test.

## STATUS

Facility completely operational and recently used to test prototype and production TF coils to high current.  Preparations underway to augment the facility with a BKG coil that is both prototypical of CS coils and suitable as a facility for testing full-scale conductors to high field and high current.

## TECHNICAL PERFORMANCE

The facility is capable of cooling down and testing TF coils to nearly full current, the current level being limited by structural limitations of the test-coil structure in the single-coil test geometry.  The facility apparently does not have (but could have) provisions for operating the test coil at a higher temperature, thereby testing to operating temperature margins for the full system.

## TECHNICAL RISKS

1)	Operating performance margins not fully tested

A variety of manufacturing processes or untested design features could result in performance margins of completed coils being unacceptable or lower than expected

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Unacceptable or lower than expected performance | High (replacement or repair of low-performing coil) | High (replacement or repair of low-performing coil) |

# RECOMMENDATIONS

- Provide means of testing superconductor performance margins at an acceptably low test current by introducing elevated-temperature operation

- Measure joint resistance accurately, by a method appropriate to the allowed resistance.

- Measure ac losses (combined hysteresis and coupling) by a method appropriate to the allowed values.

- Ensure that analytic models of coil performance are properly benchmarked against prototype tests so that the can be relied on to predict performance and establish allowable operating limits in full scale system

# T136/146 – TF and PF Magnet Structure

## STATUS

Prototype magnet structures for both TF and outer PF magnets have been fabricated.  The TF magnet structure has been tested for cooling performance and extensive mechanical tests (static yield and fatigue crack growth) have been performed on TF case materials.  Manufacturing of four more TF units were begun in January 2004.  The first four units will take one year to complete.  Due to budgetary issues, the remaining twelve TF units will be manufactured over a period of eighteen months after the first four TF units are completed.

## TECHNICAL PERFORMANCE

Strength of the TF case alloy has been demonstrated in mechanical tests to be greater than 1000 MPa in comparison to maximum expected stress of about 500 MPa.  Models for demonstrating techniques for cooling-tube installation show good results.  Case cooling tests have been performed on a model structures with good results.

Manufacturing tolerances on the TF cases provide reasonable margin (5-10 mm) for the fit of TF windings with tolerances obtained there.

Methods of inspection of structures for flaws are under development.

## TECHNICAL RISKS

1)	Leak in the cooling lines

The main concern with the magnet support structure is a leak in the cooling lines that cool the structure.  A leak will deteriorate the integrity of the vacuum thereby compromising the operation of the tokamak.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Fail | High | High |

# T137/147 – TF and PF Magnet R&D

# STATUS

Complete.  See above section T132/T142

Appendix to TF13/14

Recommended QA/QC measures associated with fabrication, heat treatment, and impregnation of a large CICC magnet

- Visually inspect the CICC to be used for surface imperfections and flaws in the conduit

- Perform helium-gas flow test on the CICC and compare to a standard for pressure drop established during the R&D program..

- Reserve a sample of this CICC and the wire used for its fabrication for use as witness samples to be reacted along with the finished coil winding

- Seal the ends of the section of CICC to be wound into the coil and leak test in a vacuum chamber with pressurized helium gas inside the conduit with a clear and quantitative specification of the tolerable leak rate

(These measures reduce the risk that the investment in fabricated conductor and coil-winding effort will not be wasted in the event that an unrepairable leak or flaw is discovered later.)

- Repeat the leak test (to the appropriate quantitative allowable) between each significant fabrication step.  Also repeat the flow test.

- During the heat treatment, include witness samples in the heat-treatment vessel in a way that ensures that these samples are exposed to the same conditions as the coil.  For example, the CICC witness sample should be exposed to the same external vacuum and internal purge gas as the coil.

- Detailed and continuous data records of heat-treatment conditions should be kept.  This is especially important, for example, for a decision of whether or how to recover from an interruption of the heat-treatment cycle.

- After the heat-treatment process, perform the appropriate tests on the witness samples.  Ideally, these tests would be performed before proceeding to the next step but surely before installing the coil, the decision being based on an assessment of cost of the test and schedule delays vs risk.  At a minimum, the wire should be tested for critical current at the appropriate field and temperature and the CICC inspected for unexpected and undesirable changes (both outside and inside the conduit) that might indicate a problem with the heat treatment.  It may not be necessary to test the CICC for critical current if there have been a sufficient number of tests during the R&D program to allow a confident correlation between strand performance and CICC appearance.

- Likewise, if only a visual inspection of the coil terminations is possible, there should exist a detailed, well documented process for producing such joints that is based on a substantial test program during the R&D period.  This test program should include a sufficient number of tests that the termination and joint performance can be related to practical visual inspections with confidence.  Based on a relative assessment of costs and risks, it may be decided that the coil termination and joint processes should, for example, include execution and test of a number of trial joints by the installer before execution of the real termination and joint on the coil (much like qualifying a welder to make a critical, uninspectable weld).

- After installation of the dry insulation and before the VPI, the coil should be electrically tested for turn-to-turn shorts.  At a minimum a measurement of coil resistance will reveal any serious shorts by hidden damage to the insulation or foreign metal shavings, for example.

- After VPI and before putting the coil in a case, repeat the flow test and leak test.  An electrical test for turn-to-turn shorts is also recommended at this time.  This is most easily accomplished by making the coil the open-circuit secondary of a transformer with a separable yoke.  The primary may be fed by an ac source with variable amplitude.  Monitoring the input current and voltage will demonstrate the existence or absence of shorts in the secondary with reasonable precision.

# T17 – Field Error Compensation (FEC) / Resistive Wall Mode (RWM) Coil System

# T18 – In-Vessel Control Coil (IVCC) System

These coils are necessary to improve plasma performance and stability (FEC/RWM), and to provide control of plasma position.

## STATUS

T17	FEC/RWM Coil System		Design in progress

# T18	In-vessel Control Coil System	Design complete

## TECHNICAL RISKS

1) Failure of mechanical supports or coil feedthroughs

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Very low | Delay | Very low | Very low |

- No significant risks identified.  These systems are common in all tokamaks, and therefore world-wide experience will ensure successful implementation.

- These coil sets are not planned for first plasma.  However, position control is often useful for reliable, robust first plasma experiments, and may improve the scientific value of the first campaign, so the IVCC set should be considered at a minimum.

# T2 – AUXILIARY HEATING AND CURRENT DRIVE SYSTEMS

# T22 – Ion Cyclotron Heating (ICH) / Fast Wave Current Drive (FWCD) System

Consists of:

T221	Launchers

T222	Tuning & Matching System

T223	RF Source

T224	ICH Subsystems

T225	ICH Local I&C

T226	ICH R&D

## STATUS

This system is presently under development at KAERI.  It is planned for high performance experiments in the future, and is scheduled to be complete by 2009.

Overall status:

Development and design	85% complete

Prototype fabrication	80% complete

## TECHNICAL PERFORMANCE

Target performance:

- 6 MW (4 x 2 MW sources), 25-60 MHz, 20 s pulses, peak voltage <35 kV

- Upgrade planned to 12 MW for 300 s

Present performance:

- Low power transmitters are presently on hand (300 kW max.) with one 2 MW source on order.

- Tests on antenna:  33 kV (peak) (15 kW forward power) for 60 s; 25 kV (peak) for 300 s

## TECHNICAL RISKS

The following represent risks to the future experimental campaign and not to attainment of first plasma.

1) Loss of coolant in either launcher or transmission line

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Very low | Delay | Very low | Very low |

2) Vacuum feedthrough failure

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Very low | Delay | Very low | Very low |

- Double-redundant ceramic feedthrough has been developed.

# T23 – Lower Hybrid Heating (LHH) / Lower Hybrid Current Drive (LHCD) Systems

Consists of:

# T231	LHCD System Design

T232	LHCD Launcher & Splitter

T233	Waveguide Network

T234	Klystron RF System

T235	Klystron Power Supply System

T236	LHCD Local I&C

T237	LHCD R&D

## STATUS

This system is presently under development.  It is planned for high-performance experiments in the future, and is scheduled to be completed by 2010.

Overall status:

Engineering design:		50%

Preliminary testing of prototype launcher/splitter has been done.

## TECHNICAL PERFORMANCE

Target performance:

5 GHz, 4 x 500 kW (CW) klystrons (to be developed by Toshiba)

## TECHNICAL RISKS

Risks associated with this system only impact future experimental campaigns, and not the achievement of first plasma.

1) Performance does not meet expectations

- High power, high frequency klystrons are state of the art.  There is a risk that they will not perform as expected

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Performance | Low | Very low |

# T24 – Electron Cyclotron Heating (ECH) / Electron Cyclotron Curren Drive (ECCD) Systems

# Consisting of:

# T241	Transmission System

T242	Gyrotron System

T243	Gyrotron Power Supply System

T244	ECH Local I&C

T245	ECH R&D

## STATUS

This system will be used both for pre-ionization of the first plasma as well as for high performance operation in future campaigns.

T241	Transmission System	Design complete

To be manufactured in the US

T242	Gyrotron			Manufactured and tested

T243	Gyrotron Power Supply	Fabrication complete, testing in progress

## TECHNICAL PERFORMANCE

T242	Gyrotron

Target performance:	0.5 MW at 84 GHz for 2 s

Attained performance:	low power testing only

## TECHNICAL RISKS

1) Performance not sufficient for operation during first plasma campaign

- Low power is sufficient for pre-ionization of the first plasma.  Progress has been good, and the only risk to cost or schedule will arise from procurement of the transmission components. The risk to cost or schedule is expected to be low.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | Performance | Very low | Very low |

# T3	FUELLING AND VACUUM PUMPING SYSTEMS

## T31	Fuelling System

Consists of:

T311	Gas Fuel Delivery System

T312	Pellet Fuelling System

T313	Fuelling System Local I&C

T314	Fuelling System R&D

## STATUS

# Design Phase

## TECHNICAL PERFORMANCE

The maximum fuelling pressure in the vacuum space (hydrogen gas pressure) is 10-2 to 10-4 torr with a volume of 55 m3.  The volume of hydrogen involved is about one litre.

## TECHNICAL RISK FACTORS

1) Hydrogen leak

A hydrogen leak into the building could cause an explosion, which might cause damage to the system or pose a hazard to workers.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Safety | Low | Low |

RECOMMENDATION:

Hydrogen safety should be included in all discussions involving overall plant safety.  See also recommendations in WBS T82.

T32	Vacuum Pumping System

Consists of:

T321	Torus Pumping System

# T322	Cryostat Pumping System

T323	Roughing & Backing System

T324	Diagnostics Vacuum Pumping Interface

T325	Leak Detection Systems

T326	Vacuum Pumping System I&C

The pumping system includes two separate pumping systems, each with an RGA, a vacuum pump, a cryopump, and a leak detector.

## STATUS

Design Phase

## TECHNICAL PERFORMANCE

In the event of a hydrogen explosion, the exhaust pipes have been specified to have a wall thickness of 4 mm.

## TECHNICAL RISK

1) Hydrogen Explosion

Main technical risk is a danger of having hydrogen gas at the outlet of the vacuum pump (1 bar). There is also a fear of H2 contamination of the oil of the pumps.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Safety | Low | Low |

# T33	Wall Conditioning System

# Consists of:

# T331	Discharge Cleaning System

T332	Wall Coating System

# T333	Wall Conditioning System I&C

# T334	Wall Conditioning System R&D

## STATUS

Design Phase

## TECHNICAL PERFORMANCE

The vacuum vessel and inside components should have a surface state that minimizes the amount of foreign material in the plasma due to interaction between the plasma and the wall.  Wall conditioning in KSTAR will be performed using glow discharge cleaning.  Effective impurity removal is possible when the discharge current is more than 0.1 A/m2.  Assuming the discharging area is 300 m2, a discharging current of more than 30 A is required.  Discharge electrodes are mounted in two ports (Bay A, Bay I), which are separated by 180( on the torus.  The discharge power supply has a capacity of more than 20 kW.  Hydrogen is the discharge gas for impurity removal, and helium gas is used for fuel gas desorption.  Proper discharge pressure is several mTorr.

## TECHNICAL RISK

1) Poor vacuum

Wall conditioning is essential for good plasma and its purpose is to remove foreign materials on the inner wall and outgassing of the surface materials.  If the wall conditioning is poor the vacuum integrity may be compromised.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Performance | Low | Low |

T4	Power Systems

The following information is based on the documents supplied for this review (originating late 2003) and other information and documents received by the writer during prior reviews, including the Magnet & Power Supply Review of October 2002.

The latest KSTAR power supply scheme is summarized in the table below.

| System | Type | Vramp | Vflat | Imax | Polarity | Units | Quench | Blip |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TF | IGBT | 20V | 20V | 40kA | Unipolar | 1 | yes | no |
| PF1,2,7 | Thyristor | 1800V | 360V | 25kA | Bipolar | 3 | yes | yes |
| PF3,4,5,6 | Thyristor | 1800V | 360V | 25kA | Bipolar | 8(4U,4L) | yes | yes |
| FEC | IGBT/IGCT/GTO | 50V | 50V | 7kA | Unipolar | 2(mid, sad) | no | no |
| ICC | IGBT/IGCT/GTO | 900V | 900V | 7.5kA | Bipolar | 2(V,R) | no | no |

For first plasma the required systems are TF, PF 1,2,7, and PF3U, PF3L, 4L, 5L, 6L, where U=upper and L=lower. Because the first plasma operations will be in the double null configuration, separate control of the upper and lower coil pairs is assumed not required, so the deployment of the outer coil power supplies 4U, 5U, and 6U has been deferred. Whether or not plasma initiation field null conditions can be achieved, and whether or not vertical stability can be maintained without a radial field component (which would be produced by having upper current not equal to lower current in one or more circuits) has not been assessed by the writer.

For quench protection, the plan is to use a two-stage mechanical-thyristor switch (MTS) scheme in series with a redundant back-up DC circuit breaker (DCCB). The MTS involves the commutation of the load current by discharging a capacitor through a thyristor, which creates an artificial current zero in a parallel vacuum circuit breaker and/or mechanical bypass switch. The MTS scheme is essentially the same as that developed by the Efremov Institute for the ITER power supplies.  The technology choice for the redundant back-up DCCB has not been finalized as of yet. The candidates are an explosively actuated DCCB such as the one developed by Efremov for ITER, and a “Pyristor” consisting of a circuit breaker in parallel with a fuse, such as that manufactured by the Ferraz Corporation in France. The former is less complex and therefore less likely to fail than the latter. However, the former is a unique item not commercially available.

For first plasma the electric power demand can be met by the local grid, so that no supplemental source is required. However, the project plans to install a Motor-Generator (MG) set later on for this purpose.

STATUS

Fabrication of the TF power supply is complete, and it has been in use for some time already in the prototype TF magnet testing. This includes the quench protection, although not with the redundant back-up DCCB, and not with the final dump resistor module. While the writer does not consider the power electronic topology chosen for the the TF (AC/DC converter feeding IGBT DC/AC inverter, feeding DC rectifier) to be optimal in terms of cost or efficiency, it will nevertheless function in a satisfactory way as already demonstrated. In addition, it gives Korean industry some experience with the high current IGBT inverter.

The PF3U fabrication is complete. Some testing has already been performed with the ramping power supply driving a copper magnet. The complete power supply will be tested using a superconducting PF coil sometime in the near future. Additional testing has been performed on prototype PF quench protection circuits and other accessories such as the DC current transducers (new to Korean industry).

Less progress is evident in the area of the Field Error Correction (FEC) and Internal Control Coil (ICC) power supplies. These will be of the “switched mode” variety, using IGBTs, IGCTs, or GTOs. However, since these systems are not needed for first plasma, and are less critical in general, their present status is not cause for concern.

The remainder of the first plasma power supply systems are to be fabricated by POSCON and completed by the end of 2005. The full year in 2006 is allocated to the installation and commissioning. This was communicated verbally, and is consistent with schedules shown in October 2002. However, the schedule included with the documentation package for this review showed some of the fabrications not ending until mid-2006.

During various reviews, including this one, various one-line diagrams, schematics, and control wiring diagrams have been presented and included in the documentation. However, the writer has never seen evidence of a fully integrated design that covers all details and which is sufficient to procure, fabricate, install, and commission the entire electrical power system. It should be pointed out that this is no small undertaking, requiring a large number (perhaps of order 1000) of drawings. Based on the telephone conference of February 2, 2004, the intent is to complete the integrated design by the end of this year (2004), including the final selection of items such as the redundant DCCB technology.

## TECHNICAL RISKS

1) Power Electronics Systems

Although the advanced power electronics systems are beyond the current state of the art for Korean industry, they do not exceed the technology of other systems built at other facilities in the US, Europe, and Japan in the past two decades. The Koreans have been very proactive in performing R&D to develop their domestic capabilities in the high voltage, high current, high power regime of power electronics. In doing so they have no doubt gained lots of experience which will be invaluable when it comes time to commission the full system. And the prototype testing which they have performed will significantly mitigate these risks.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Reduced Performance | Medium | Medium |

2) Control and Protection Systems

The fully integrated design must address control and protection. There is evidence of good work in these areas, but the design will continue to evolve as the time of power supply and machine commissioning approaches. The protection issue will be very challenging and absolutely critical because of the superconducting coils. Ground fault and quench detection design details must be developed, and the fault response of the power supplies to internal and external faults must be coordinated. Reliability will be a crucial issue. The essential element, in the end, is the redundant back-up DC Circuit Breaker. The technology choice needs to be finalized, and if necessary, tested to fully characterize it. The overall coil fault detection and protection system should utilize  Failure Mode and Effects Analysis (FMEA).

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Low | Magnet Failure | High | High |

3) Cost, Schedule, and Technical Performance

Success in the end will depend on a sound and well-documented integrated system design that can be efficiently installed and commissioned in the field. The actual time and resources required to complete the work can be  guessed or estimated based on a top-down view, but the bottom-up estimate can only be generated once the integrated design is in place. Although not reviewed by the writer, there is evidence that progress is being made toward the finalization of the integrated design, which was projected to be completed by the end of this year.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | Delay and/or overrun | Medium | Medium |

4) Commissioning and Integrated System Testing

The integrated magnet and power supply system, along with its control and protection, is a complex and critical system. Detailed plans and procedures need to be developed to guide in the commissioning of its component parts, and then the integrated system. This must include suitable engineering instrumentation so that it can be confirmed that the systems are performing as expected as the operating levels are increased.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | Delay and/or Equipment Damage | Medium | Medium |

T5	Diagnostic Systems

## STATUS

Design phase

Recommendations:

DIAGNOSTICS FOR THE FIRST PLASMA  (The basic minimum)

| PLASMA PARAMETER | EQUIPMENT | TIME NEEDED FOR DEVELOPMENT | NUMBER OF PEOPLE NEEDED FOR DEVELOPMENT | COMMENTS |
| --- | --- | --- | --- | --- |
| Plasma current | Rogowski coil | 2yr | 1/3 | Note 1 |
| Loop Voltage | Flux loops | 2yr | 1/3 | Notes 1,2 |
| Plasma shift | Magnetic probes | 2yr | 1/3 | Notes 1, 2 |
| Control of plasma position | In-vessel control coils+ magnetic probes+ distributed digital computer feed back system | 1 yr | 1 physicist, 1 EE, 1 computer engineer | Modern distributed digital control system to be developed which can evolve over the life of the project |
| Average plama density | Mm microwave interferometer | 12 months | 1 |  |
| Control of plasma density and its time evolution | Gas-puffing system + feed-back of MW-interferometer | 12 months | 1 |  |
| Electron temperature on the axis | Thomson scattering of laser beam | 24-36 months | 1-2 | Manufacturing of simulating sector of VV will be helpful |
| Plasma TV | High Speed CCD Video | 3 months | 1 |  |

  - Location, mounting, routing of leads, and feedthroughs are critical

  - In-vessel diagnostics are custom subminiature magnetic probes which must operate at very high temperatures and require high temperature insulated wire

  - Because of difficulty of access, in-vessel diagnostics sufficient for operations beyond first plasma should be included in initial installtion prior to first plasma; they should not be deferred

## T51	Magnetic Measurement Diagnostics

Consists of:

T511	Rogowski Coils

T512	Flux / Voltage Loop

T513	Magnetic Field Probe

T514	Saddle / Locked-mode Coils

T515	Mirnov Coils

T516	Diamagnetic Loops

T517	Vessel Structure Current Monitor

The set of Magnetic Measurement Diagnostics (MMD) includes sensors for measurements of poloidal magnetic flux, loop voltage, local magnetic field, B-fluctuations, diamagnetic flux, vessel current, halo current, etc. This set of diagnostics is quite complete and sufficient both for efficient operation of the tokamak and for evaluation of plasma parameters.

These diagnostics are included in the basic set required for the first plasma operation.

STATUS

The MMD systems are 55-60% complete as reported on 2003.4.1-10.30. This status is quite satisfactory for future implementation and use during the first plasma  experiments. The design and testing of the prototype is satisfactory.

## TECHNICAL RISK FACTORS

- Damage to sensors during operation

The technical risks in this part of the project are related to possible damages to the sensors after the vacuum vessel is closed. Damage to some of these sensors, for example the Rogowski coil, might produce serious problems for the tokamak's operation.  Because of the relatively low price, the number of magnetic probes should be doubled (so that there are duplicates).

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium chance that a sensor may fail, however, redundancy avoids system failure | Performance, Fail | High | High |

# T52	Control and Machine Diagnostics

Consists of:

T521	mm-Wave Interferometer

T522	Hard X-ray Detector

T523	Survey IR TV

T524	Divertor Protection IR TV

T525	Reciprocating Langmuir Probe

T526	Edge Probes (Movable)

T527	Fixed Langmuir Probe Array

The Control and Machine Diagnostics (CMD) consist of a millimeter-wave interferometer, Hard X-ray detector, Survey IR TV, Diverter Protection IR TV, Reciprocating Langmuir probes, movable Edge probes, and Fixed Langmuir Probes array. This set of diagnostics, combined with the magnetic measurement diagnostics, is sufficient for control of the machine operation.

## STATUS

The present status of CMD as reported on 2003.4.1-2003.10.30 is satisfactory. The systems are 30-65% complete and there is enough time left to finish their development and installation before the plasma operation starts.

## TECHNICAL RISK FACTORS

- Sensor damage

The technical risk of a failure is quite different for each of these diagnostics. The highest risk of damage is caused by having the Langmuir probes both movable and rigid. These probes are located inside the vacuum vessel and contact the plasma, so fixing and/or replacing them might be problematic in many cases. There is also a large risk that the plasma will be contaminated during reciprocating and movable probe operation if the probes are damaged.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | Performance, Fail | High | High |

## RECOMMENDATIONS

Since the electric probe measurements at the edge of the plasma are most valuable for fine investigations in well organized plasma, these diagnostics are not recommended for the first plasma experiments. All the other diagnostics are located outside the Tokamak and can easily be repaired or replaced.

The millimeter-wave interferometer is one of the main diagnostics, capable of provide basic information about the first plasma. The unavailability of this diagnostic at first plasma experiments would make the interpretation of results problematic. This diagnostic system was reported as being 65% complete, but no detailed information concerning the status of the development was found. High management attention to this diagnostic is recommended, in order to make it available in the first plasma experiments.

## T53	Vacuum Diagnostics

Consists of:

T531	Torus Ion Gauges

T532	Residual Gas Analyzer

T533	Inspection Illuminator

T534	Fast Neutral Pressure Gauges

The list of vacuum diagnostics includes torus ion gauges, residual gas

analyzer, inspection illuminator, and fast neutral gas gauges, but there is information available regarding the inspection illuminator only.

## TECHNICAL RISK FACTORS

The technical risk related to these elements of vacuum diagnostics is low.

## T54	Passive Visible / IR Diagnostics

Consists of:

T541	Visible Survey Spectrometer

T542	H_alpha Monitor

T543	Visible Bremsstrahlung Array

T544	Visible / H_alpha TV

T545	Diverter Visible / H_alpha TV

T546	Multichord Visible Spectrometer

T547 Visible Filterscopes

T55	Passive UV / X-ray Diagnostics

The set of passive visible / IR Diagnostics consists of Visible Survey spectrometer, H-alpha monitor, Visible Bremsstrahlung Array, Visible/ H-alpha TV, Multichord visible Spectrometer, and Visible filterscopes.

STATUS

The reported completeness is 80-85%, and the design, development and tests are quite satisfactory.

## TECHNICAL RISK FACTORS

The risks may be related to possible vacuum leaks or damages to the view ports, however, the technical risks for the project are low.

T55 Passive UV/ X-Ray Diagnostics

Consists of:

T551	X-ray Crystal Spectrometer

T552	Soft X-ray Array

T553	X-ray Pinhole Camera

T554	X-ray Pulse Height Analyzer

T555	Soft X-ray Spectrometer

T556	VUV Survey Spectrometer

T557	Diverter VUV Spectrometer

T558	Bolometer Arrays

T559	Diverter Bolometer Arrays

## STATUS

The  development, fabrication and testing of the X-ray crystal spectrometer and  soft X-ray array is a well advanced part of the KSTAR diagnostics. A part of the equipment has been successfully tested in different Tokamak experiments. The reported completeness of these diagnistics is over 60%.

## TECHNICAL RISK FACTORS

The risks may be related to possible vacuum leaks or damages to the view ports, however, the technical risks for the project are low.

## T56	Active Laser Diagnostics

Consists of:

T561	Thomson Scattering (Core, Edge)

T562	Diverter Thomson Scattering

T563	Vertical FIR Interferometer

T564	Tangential FIR Interferometer / Polarimeter

T565	Laser Induced Fluorescence (LIF)

## T57	Active Beam Diagnostics

Consists of:

T571	Charge Exchange Spectroscopy

T572	Motional Stark Effect

T573	Poloidal Rotation CES

T574	Beam Emission Spectroscopy

T575	Diagnostic Neutral Beam

T576	Impurity Pellet Injector

## T58	Microwave Diagnostics

Consists of

T581	ECE Heterodyne Radiometer

T582	ECE Grating Polychromater

T583	Diverter Microwave Interferometer

T584	Edge Reflectometer

T585	Microwave Imaging Reflectometer

T586	ECE Imaging System

T587	Electron Cyclotron Absorption (ECA)

## T59	Particle Measurement Diagnostics

Consists of:

T591	Epithermal Neutron Detectors

T592	Multichannel Neutron Collimator

T593	Neutron Fluctuation Detector

T594	Escaping Fast-ion Detector

T595	Charge Exchange Neutral Analyzer

T6	Control and Data Systems

## T61	Tokamak Control System

Consists of:

T611	Central Control System

T612	Main Operation Console

T613	Computer System

T614	Interlock & Safety System

T615	Remote Collaboration System

T616	Tokamak Control System R&D

STATUS:

Procurement stage

International design of the central control system is complete.  The central control system is now in the procurement stage.  The Main Operation Console Design concept has been approved by General Atomic.  The Interface and network research and development is also 100% complete.

## TECHNICAL RISK FACTORS

1) Functional Failure:

The main technical risk factor is if the control system fails to perform its required functions.  With careful programming,esting, and the inherent flexibility of the computer-based control this risk is extremely low.  The following principles shall be followed in this regard:

- the overarching philosophy shall dictate that protection systems local to the controlled equipment (e.g. power supply systems, heating systems, etc.) should be self-sufficient such that no failure or misoperation of the central control system can endanger the controlled equipment or the KSTAR device. The central control system shall not be responsible for protection functions.

- to enhance the reliability and security of the computer-based control, all engineering control systems shall be isolated from outside networks by suitable firewall systems

## T62	Plasma Control System

Consists of:

T621	Magnetics Control System

T622	Kinetics Control System

T623	Discharge Supervisory Control System & Interface

T624	Plasma Control System R&D

STATUS:

Design Phase

General Atomic has approved the concept design so the system is now in the design phase

## TECHNICAL RISK FACTORS

1) Functional Failure

The main technical risk factor is if the control system fails to do its designed task.  With careful programming and testing this risk is extremely low.

## T63	Machine Interface & Network System

Consists of:

T631	Bus Assembly

T632	Closed Local Area Network

T633	Open Local Area Network

T634	Network Management System

T635	Interface & Network R&D

## STATUS

.  The Interface and Network research and development is now 100% complete.

## TECHNICAL RISK FACTORS

- Functional Failure

The main technical risk factor is if the control system fails to do its designed task.  With careful programming and testing this risk is extremely low.

## T64	Data Acquisition System

Consists of:

T641	Database System

T642	Data Acquisition Hardware

T643	Local Data Access & Control System

T644	Data Analysis Software

T645	Data Acquisition System R&D

# T7	System Integration

# T72 – TOKAMAK Assembly

1) Assembly of KSTAR Main System

2) Interface of Subsystems for Main System

3) Precise measurement & Adjustment of KSTAR Main system

### STATUS

The KSTAR team has done an excellent job of planning a detailed assembly sequence.  This includes a 3-D visual simulation of the assembly.

### TECHNICAL RISKS

1) Interference between systems installed. Only minor delays anticipated.

Disassembly/reassembly time due to any magnet fault :

TF coil takes, 17 months to disassemble and reassemble in the event of requiring an upgrade.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| Medium | High | High | 17 months |

T8 - Project Management and Interface Control

## T81 - Project Control and Support

The KSTAR project is divided into areas of responsibility according to physical components of the machine.  Team leaders are responsible for specific Work Breakdown Scope (WBS) (T- numbers) or specific Facility (F-numbers) sections.  Each team leader manages his own part of the project and is responsible for his own budget.

The use of conventional project management tools is inconsistent across the various WBS sections.

RECOMMENDATIONS

1)	The KSTAR team could consider implementing a standardized project management reporting structure.  Such a structure could include:

i)	A construction project manager with overall responsibility for construction and commissioning of all systems required for first plasma;

ii)	Regular periodic reports from each section to the project manager;

iii)	Regular updating of the schedule producing Critical Path and/or Gantt charts;

iv)	Regular updating of the financial status, including for each sector: requested budget, approved budget, expended, committed/encumbered, available funds at present, planned future funds, and computing “earned value” (i.e. “Budgeted Cost of Work Performed” (BCWP), “Actual Cost of Work Performed” (ACWP), “Budgeted Cost of Work Scheduled” (BCWS), “Actual Cost of Work Scheduled” (ACWS);

v)	Regular reporting by the construction project manager to all team leaders of current status and planned activities for the next period;

vi)	Project critical fault analysis done on a project-wide basis based on a probabilistic/deterministic method to list possible faults, identify their consequences, identify systems which can reduce the harm to the project of these faults and to allocate funding or effort accordingly;

vii)	Consistent quality assurance/quality control system (QA/QC) such as 6-sigma measurements of critical component parameters and tracking of those critical components.

This recommendation should not be taken to mean that the review found any problem with the existing project management, simply that that because of inconsistent methods used by the different WBS teams it is difficult for the reviewers to review the overall project planning process.

2)	The KSTAR team considered a critical project fault analysis of all fault scenarios which substantially affect the project schedule or performance, such as a “Failure Modes and Effects Analysis” (FMEA). This should identify and list significant faults, calculate probability of the fault, evaluate cost and schedule delay for the fault, and discuss strategies to avoid the fault within reasonable cost.

Special attention should be made of: helium leaks into the cryostat space, issues such as joints and heat treatment which may affect maximum magnetic field achievable and magnet fault detection and quench protection which are necessary for magnet safety.

superconducting magnet performance.

For example:   (the numbers are for example illustration only, not calculated)

Project critical fault scenario: Flexible helium cooling hoses on the heat shield of the vacuum vessel may pass initial leak test, but leak after repeated bending.

Cost to repair: eg. Won 500,000,000

Schedule delay: eg. 1 month

QA/QC to reduce the probability:

100% test of bellows sections without stress.

100% test of bellows sections while flexing up and down to elastic limit

20% cold test of bellows at LN2 temperature

6 sigma destructive testing of burst pressure of bellows hose based on 10 qualification samples and 10 random samples from delivered sections

Cost of QA/QC program: eg Won 3,000,000

or

Design change to reduce the probability

Replace flexible bellows hose with double walled flexible bellows hose

Cost increase of Won 10,000,000

or

Replace flexible bellows hose with a loop of pre-tested seamless stainless tubing which has enough flexibility

Cost decrease of Won -10,000,000 (reduces cost)

## T82 Project Safety

T82a Radiation Safety, meeting with Dr. Kim Chang Seok February 4, 2004@10:45AM

The reviewers met with Dr. Kim, Chang-Seok, who is the radiation safety officer for the KSTAR project.

### STATUS

An application has been submitted to the Korean authorities for a nuclear facility operating license.  This license is required before the first plasma.  It is anticipated that the license may be approved mid-2004.

The reviewers were not permitted to examine the license application, however they were assured that it includes:

* Radiation dosimeters for personnel

* Safety interlocks to prevent operation when personnel are in the room,

* Shielding (1.2 meters of concrete) around the facility,

* Procedure for waiting a few hours before allowing re-entry to reduce personel exposure to materials activated by radiation,

- Report is in preliminary stage and is not available for viewing.

- Dr. Kim submits regular reports to the Korean nuclear safety governing body.

- KSTAR must get licensing to operate nuclear machine.

- The license will be available by this summer 2004.

- The schedule is covered in the Power Point presentation.

- Half of the budget has been spent to date.

- He is responsible for all of the radiation safety concerns for the new system.

- The budget for safety programs is around 3 million dollars.

- 1.2 m wall thickness for the walls of the main chamber.

Work in progress:

A decommissioning plan is being prepared and should be complete this year.

Design of the safety interlock systems is in progress.

### TECHNICAL RISKS

1)	Radiation Safety

X-ray exposure from high voltage discharges such as the Neutral Beam Injection,

Neutron exposure from nuclear reactions such as the Neutral Beam Injection

Activation, exposure from previously non-radioactive materials which become radioactive after exposure to radiation from the KSTAR nuclear reactions,

Exposure to radiation while KSTAR is operating, contamination exposure by absorbing activated materials including solids, liquids and gases, and other radiation hazards.

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| High | Safety | Low | Low |

Radiation shielding and radiation protection program

As soon as the NBI facilities are implemented in the KSTAR project, induced radiation will emerge as a new factor of tokamak operation. No access into the entire tokamak area will be possible during the 5 – 10 hours after NBI-heated operation, and work on many components of diagnostic equipment will be restricted. Other Tokamaks have radiation shielding be built close to the tokamak facility and NB-injectors to avoid this issue.  KSTAR has chosen simply to wait for deactivation.

Qualified special personnel and appropriate equipment will be needed to provide a radiation safety program.

Comment:

In the case of Neutral Beam Injection, the researchers were not able to provide a radiation survey or radiation safety document.  Due to high currents there may be intense beams of X-rays leaking from the vessel ports or penetrating through the walls.  The KSTAR radiation-safety officer claims this is not his scope of responsibility because it is off site at Korea Atomic Energy Research Institute.

However, because this is a safety issue, the reviewers feel that the KSTAR radiation-safety officer should receive a safety review report from all KSTAR activities, whether on site or off site.  The KAERI staff will do a study and prepare a report.

2) Electrical Safety

The use of high voltage, high current, high power, and high stored energy equipment is an inherent aspect of any magnetic fusion facility. Safe conduct of commissioning, operation, and maintenance requires the incorporation of sufficient design features to ensure that personnel are isolated from these hazards under all circumstances, that all activities are conducted per written procedures, and that all personnel are adequately trained. At the present stage the emphasis should ensure that the design includes sufficient isolating and grounding devices, electrical and mechanical interlocks, energy absorbing barriers and isolation features such that personnel safety can be ensured during all commissioning, operation and maintenance.

# 23	 Non-radiation Safety

The review committee was unable to identify one person who has overall responsibility for Non-radiation safety issues for the KSTAR project.  This may be a serious issue for the organizational structure, because some safety issues may "fall through the cracks" between different groups.  The review committee was unable to obtain a list of non-radiation safety issues for the KSTAR project.  Clearly for such a complex project safety reports and formal committee safety reviews should be implemented.

The US Department of Energy has published a relevant guide, “Safety of Magnetic Fusion Facilities: Requirements,” DOE-STD-6002-96, May 1996 that addresses the diverse issues for safety in such a facility.

In the case of the Brookhaven National Laboratory (BNL), New York USA, there are published safety standards available on their web site for a wide variety of issues.  There is a formal procedure that does not allow any equipment to be operated without a formal safety committee review.  After operation the users must still report to the safety committee.  The safety group performs spot safety checks of each team every year.

Some of the non-radiation safety issues applicable to KSTAR are:

Low oxygen deficiency 	(use sensors, alarms, fans - see BNL standard)

High magnetic field		(use fence, warning signs - see BNL standard)

Windows into vacuum space (do critical failure analysis - see BNL standard)

Electrical equipment	(see Korean standard, UL, CE or CSA standards)

High voltage equipment	(wire cage fence, safety interlocks, formal safety 		committee review, see BNL standard)

Hydrogen gas fire/explosion (use fans, sensors, flash back preventors on vent 	pipes, see pressurized gas standard, BNL standards)

Assessment of risk:

| Probability | Consequence | Cost implication | Schedule implication |
| --- | --- | --- | --- |
| High | Safety | Low | Low |

T83 Project Physics and Modeling: Not reviewed.

## T84 Facility Construction Interface

Items that are part of the KSTAR machine are assigned T-numbers (WBS) and are part of the KSTAR budget.

Items that are not part of the KSTAR machine are assigned  F-numbers and are part of the FACILITY budget.

KSTAR did not provide the review team with a document defining the delimitation of the scope of supply between these two systems.  In many cases it is reasonably clear from the definitions.  In the case of the cryogenic facilities the boundary is the cryostat boundary.

FACILITIES (F numbers not in T number system)

CRYOGENIC FACILITIES

The cryogenic facility is now in the detailed design phase with a contract through Samsung and Air Liquide.

- This process involves re-estimating the heat loads of the entire KSTAR system.  At this time these heat loads are still subject to uncertainty.  The results of this analysis are expected in 2004.

- The vacuum vessel of KSTAR, and consequently the cryostat as well, is designed to have 120 diagnostic and technological ports.  Such a large quantity of ports increases the hot area in the cryostat from 40 square meters (vacuum vessel itself) to 120 square meters, thus considerably increasing the inward heat flux and therefore the consumption of liquid helium.  There is a non-negligible risk that the cool-down and operation of the superconducting-magnet system will not be achieved in this cryostat with the presently specified refrigeration system.  Additional detailed and expert study of the cryostat is strongly recommended prior to the start of assembly of the facility.

- ELECTRIC POWER SUPPLY

- An electric power supply system that is able to provide the KSTAR facility with its required peak power is planned.  This system will eventually utilize an energy-storage device (a motor-generator) to cover power peaks that occur during NBI, ECRH, and ICRH operations.  While an MG system has been envisioned and planned, it is a very long-lead item.  This factor needs to be taken into account in the planning of the research program after first plasma and initial operating campaign.

General Recommendations:

A.	The efforts and financial support should be concentrated on first priority aims.

  - The first priority, in the current state of the project, is to supply KSTAR with appropriate superconducting coils.  This is also the most critical part of the whole project.  It is the superconducting TF and PF magnet systems that make KSTAR unique in the world fusion program.  On the other hand, the future operation of KSTAR with magnetic fields considerably lower than expected, would strongly reduce the scientific and practical value of the whole project.  The present unavailability of manufactured and successfully tested toroidal coils prevents assembly of vacuum vessel, cryostat, and thus the further development of the project.  The situation is complicated by the fact that manufacturing superconducting coils unfortunately has a useful output considerably less than 100%.  In practice the coils should be manufactured and tested one after another, as the real number of manufactured units may be much higher than 16.  In terms of the project development, the above implies that essential delays should be expected.

  - The second priority for this project is the in-vessel equipment, such as control and divertor coils, and plasma facing elements, such as limiters and divertor plates.  These components are extremely complex and challenging, and are critical to plasma performance during future tokamak operations, and can influence the success of the whole project.  The development, design, and testing of this in-vessel equipment should be subject to a high level of attention.  However, at present the manufacturing of these components has not been started, while some parts, such as the FEC / RWM coils, are not even designed yet.  An increase in efforts to develop these components is recommended.  As well, due to the extreme importance of these components, it would be helpful to develop several different versions, using different configurations and materials.

  - The subject that is of next highest priority is the specification of the minimum objectives of the first plasma experiment, and the selection of the required diagnostics set. The first plasma experiment is the critical first step of the research program. Among the aims of the first plasma experiment are:

- To establish adequate vacuum conditions, magnetic field null and loop voltage to obtain a plasma with minimal parameters, such as Ip ~ 500kA, <n> ~1012 - 1013 cm-3 and Te> 200-300 eV

- To provide credible measurements of these parameters.

- To provide radial and vertical position control of the plasma using  closed loop feedback control techniques.

- To obtain experience in wall cleaning  and conditioning procedures and investigate their effects on plasma parameters.

To realize these objectives, a minimal but reliable diagnostic setmust be available for first plasma.

B.	Unfortunately due to budget constraints, the plasma diagnostics preparation has not yet gotten underway.  It should be noted that Thomson scattering is the most reliable technique for measuring the temperature of plasma, and is used on practically all tokamaks operated throughout the world.  This diagnostic will also be needed in the KSTAR first campaign (CALVIN: I’M NOT SURE THAT THIS IS REALLY TRUE???? FIRST PLASMA IS USUALLY A QUICK FLASH IN THE PAN).  Unfortunately, the development of this diagnostic is very complicated and it usually requires two to three years of preliminary laboratory study.  A special laboratory test facility using an identical sector of vacuum vessel would be helpful for this study.  It requires intensive and immediate efforts in development and manufacture of these diagnostics for Thomson scattering to be available in the first plasma campaign. The other basic diagnostic system necessary for first-plasma experiments is a microwave interferometer, which can provide reliable measurements of plasma density and its time evolution.  It makes sense to start with simple 1 to 2 mm equipment, keeping the advanced FIR technique for the next experimental campaigns.

C.	Radiation shielding and radiation protection program

As soon as the NBI facilities are implemented in the KSTAR project, induced radiation will emerge as a new feature of tokamak operation.  No access into the test cell will be possible for 5 – 10 hours after NBI-heated plasma operation, and work on many components of diagnostic equipment will be restricted.  This situation will require that radiation shielding be built close to the tokamak facility and NB-injectors. Qualified special personnel and appropriate equipment will be needed to provide a radiation safety program. This issue seems to have been neglected in the existing project. (CALVIN: I’M NOT SURE THAT THIS IS REALLY TRUE, SINCE KSTAR WILL NOT USE TRITIUM, AS FAR AS I KNOW.. THERE WILL BE SOME ACTIVATION WITH NBI DRIVEN D-D BUT MY RECOLLECTION BASED ON TFTR EXPERIENCE WITH 30MW NBI IS THAT IT WILL NOT BE A MAJOR ISSUE. ON NSTX IT IS NOT AN ISSUE WITH 8MW OF NBI)

- The vacuum vessel of KSTAR and therefore the cryostat is designed to have 120 diagnostic and technologic ports. Such a large quantity of ports increases the hot area in the cryostat from 40 square meters (vacuum vessel itself) to 120 square meters, thus considerably increasing the inward heat flux and therefore the consumption of liquid helium.  There is a certain risk that the cooling down of the superconducting magnet will not be achieved in this cryostat.  There is also a risk that the capacity of the liquid helium production facility is not sufficient to feed KSTAR. Additional detailed and expert study of the cryostat is strongly recommended prior to the start of assembly of the facility.

- An electric power supply system that is able to provide the KSTAR facility with a peak power of over 100 MW is necessary.  This system must eventually utilize an energy-storage device (a motor-generator) to cover power peaks that occur during NBI, ECRH, and ICRH operations. While an MG system has been envisioned and planned, it is a very long lead item. This factor needs to be taken into account in the planning of the research program after first plasma and initial operating campaign.

COMMENTS ON THE SCHEDULE

There are several concerns related to the allotted schedule of the project between the completion of component manufacturing and the first plasma experiments. The first concern relates to cool-down and leak checking. First plasma will require the  full assembly of the machine, and testing and conditioning of the vacuum-vessel for plasma operation.  The leak tests of the vacuum vessel and the cryostat are some of the most difficult and time-consuming procedures involved in this project.  As soon as all leaks are sealed, a preliminary cool-down test must be performed.  More likely than not, this cool-down will cause new leaks  which will require repair, and additional leak testing.  At present these two steps, preliminary cool-down test and post-cool-down leak tests, are not accounted for in the schedule of the KSTAR project.  The second concern relates to the KSTAR assembly process. Due to the high complexity of the facility, it is reasonable to expect errors and incompatibility in some portion of the components.  This has certainly been the experience of many other tokamakconstruction projects.  Therefore, additional time will be needed for rebuilding, modifying,  and replacing of non-conforming parts, which is not factored into the present project schedule.  The third concern relates to the time interval between the completion of assembly and start of first plasma experiments.  The aims of this step are to reach high vacuum and to condition the walls of the vacuum vessel, using several technologies such as glow discharge, RF–dischargeplasma discharge, etc.  The success of these procedures provides the basis for satisfactory plasma performance during the tokamak’s initial operation.  The first tokamak operation after initial assembly may require more preparation in terms of pumping and conditioning than allowed by the present schedule.  For these reasons the time interval between the completion of assembly and start of first plasma experiments could extend beyond the 6 months allocated by the current schedule.

# E.	RECOMMENDATIONS

# Design

The basic design of KSTAR and the major KSTAR subsystems considered in this review process appear to be fundamentally sound.  Most major subsystems have passed successfully from the conceptual design stage, through engineering design and review, to the prototype stage, and are now ready for production.

# R&D

To date, most R&D tasks have focused on verification of concepts and on demonstration of readiness to proceed to detailed engineering design and production.  To this end, the program has been generally successful.  At present, further R&D activity may be justified to support the reduction of risk and cost in certain areas.

# Production/Assembly

As the various subsystems move into production, significantly tighter integration of all tasks becomes essential.  During production, uniformity and control of materials, processes, and nterfaces with other subsystems becomes even more important thanimproved performance, since even small changes made for seemingly good reasons on one subsystem can have a drastic impact on the performance of other subsystems or of the whole.  Close coordination of production schedules also ensures an efficient assembly of the overall system.

# QA/QC

The test programs carried out as part of the R&D activities for the various subsystems provide a firm basis for a successful QA/QC program but they do not substitute for it.  The KSTAR project is presently at the stage where it must make the transition from  testing to production to and ensure success by minimizing risk and unexpected costs, i.e. by implementing the necessary procedures and process controls, and QA/QC measures in each task area.

# Safety

A system as complex as KSTAR and that includes as many state-of-the-art subsystems, presents a variety of hazards – to personnel, to equipment, and to facilities.  At present, these safety issues appear to be left to the managers of the separate subsystem tasks, which may give rise to inconsistent coverage or even conflict.  It seems prudent to consolidate the responsibility for so important an issue under a single authority. As the project approaches the commissioning and first plasma phase, a review of readiness for operations would seem necessary and appropriate.

# Project Management

The project should hire a project management team.  The science team is a very strong one, but project managers with large scale engineering project management experience are required to assure the success of the project.  All of the subcontracts through Korean industrial construction companies have been professionally executed, and have delivered quickly with high quality.  The same type of experienced industrial project management needs to be applied to the KSTAR project.

## Contingency Planning

KSTAR is a very complex system, and planning for future uncertainties is essential to the success of the project.  The KSTAR team leaders have recognized this and are working toward effective contingency planning.

Milestones

We recommend that KSTAR consider attainment of first plasma as the next major milestone.

# Footnotes

There are at least three criteria for specifying the tolerable leak rate:

- Threshold for spoiling vacuum during operation of the magnet system

- Threshold for compromising insulation during VPI (pressure on inside greater than minimum pressure during VPI causing bubbles in the resin)

- Threshold for drawing appreciable quantity of resin into CICC during VPI (pressure on inside of CICC less than maximum pressure during VPI allowing resin to be drawn into the cable space and blocking flow).

The latter two are dependent on details of the process (relative pressure between inside and outside the conduit during impregnation).  In any case, a clear specification of the criteria and the resulting tolerable leak rate is important.  When and how often leak test is done may also depend on the criteria.  Certainly the completed magnet should be leak tested prior to installation with an allowable value based on potential for spoiling the cryostat vacuum, but it is also prudent to test prior to specific manufacturing stages where considerable value will be added, e.g. winding, heat treatment, and VPI.  It is conceivable that the allowable value could be different at each stage based on a careful evaluation of the relative risk vs cost of the test.