FAA Acquisition Program Baseline Instability:

Causes and Recommended Corrective Actions

NAS Configuration Management and Evaluation Staff

Program Evaluation Division (ACM-10)

Report #2000-10

February 4, 2000

# Executive Summary

Acquisition program baselines are management tools that are useful to the FAA in several ways.  First, they permit managers to measure progress internal to the agency.  Second, baselines allow upper management to plan and allocate scarce resources among program areas.  Finally, baselines permit the outside world to measure agency progress.  This evaluation examined baselined programs to determine the causes for baseline instability in FAA acquisition programs and to recommend practical solutions to address the identified causes.  The report also addresses an Office of Research and Acquisitions (ARA-1) inquiry concerning the conditions under which the FAA should rebaseline acquisition programs.

Overall, the evaluation team found that acquisition program baseline instability was caused by nine documented and three underlying factors.  Many of these causes were interrelated, and complete separation of the issues was not possible.  The nine documented causes were grouped into three broad areas as listed below:

- Problems during the planning phase

- Poorly defined or new requirements

- Human factors issues

- Unsuitable acquisition strategy

- Unrealistic baseline

- Inadequate risk assessment

- Problems during the solution implementation phase

- Software development difficulties

- Poor contractor performance

- Problems with multiple issues outside the Integrated Product Team’s control

- Unstable funding

- Interdependencies

The three underlying causes, all of which were derived from interview opinions, included lack of trust, lack of accountability, and lack of empowerment.  Although these causes have been reported in the past by both internal and external sources, analysis of program documentation revealed relatively little supporting data to verify these interview opinions.  Nevertheless, the team received widespread reiteration of these root causes in a majority of programs.

The team also found that acquisition documentation was not always consistent and needs to be better maintained.  During the evaluation, the team attempted to review program documentation and found that some of the required documents for the programs were missing.  Further investigation with the responsible FAA office, Integrated Product Team and other sources determined that, in several cases, the required documentation could not be located at all.

The team also found that, while the agency has undertaken a significant number of program rebaseline actions in the past two years, the process for modifying baselines has not been consistently applied.  Agency guidance related to the rebaseline process, including the documentation required for these actions, is vague and incomplete.  We believe the FAA should rebaseline programs for two purposes.  First, to restructure a program when the program goals, methods, or strategy have changed to such an extent that the baseline no longer provides a realistic measure of program progress.  Second, to reestablish a manageable measure of progress when one or more baseline parameters have been breached to such a significant extent that those measures are no longer applicable.

Finally, the evaluation team discovered multiple initiatives currently underway within the FAA that relate to baseline stability issues.  Some of these initiatives were designed to increase baseline stability; others were not necessarily so designed, but nevertheless may produce that effect.  All such initiatives discovered during the evaluation are presented in the body of the report for information purposes.  Some were referred to in the recommendations section.

The team also noted several trends and made other observations, including the following:

- Distinct patterns among the variance causes indicate that, without intervention, variances can be expected to continue, particularly in pre-Acquisition Management System programs.

- Most problems appeared to occur during the planning phase, indicating its importance in baseline stability.

- The agency lacks a process for dealing with issues arising from the use of commercial off-the-shelf/non-developmental items (COTS/NDI) as an acquisition strategy.

- Less complex, smaller programs appear to have a better chance of maintaining baseline stability, indicating the advisability of such strategies as evolutionary acquisition, spiral development, and baselining incremental segments of programs.

- In the past two years, funding fluctuations have increased in significance as a cause of baseline instability.

Summary of Recommendations

The team identified eleven specific recommendations to improve baseline stability within the FAA.  These recommendations are summarized below.  Specific steps to implement the recommendations, as well as potential points of contact, are identified in the body of the report.

- The FAA should continue to develop an integrated approach to the agency’s entire portfolio and implement that approach as soon as possible.  The portfolio management approach recently initiated within the agency may be a viable solution.

- When it employs a COTS/NDI acquisition strategy, the FAA should take specific steps to align the acquisition planning, implementation, sustainment, and budgeting processes with COTS/NDI.  These steps must be undertaken across all lines of business.

- The FAA should continue its efforts to improve customer service in the development and delivery of equipment and services.

- The FAA should continue its efforts to improve integration of human factors requirements into all stages of program planning and solution implementation.

- The FAA should take aggressive measures to implement its new policy on risk assessment and mitigation.

- FAA Integrated Product Teams should consider innovative ways of structuring and conducting acquisitions to reduce cycle time, minimize risks, and maximize product utility.

- The FAA should assess past performance for all contractors and use it as a factor in contract award.

- FAA Product Teams should share information among themselves, both formally and informally, on lessons learned throughout a program’s lifecycle.

- The FAA should improve its management of program documentation.

- The FAA should develop and implement a consistent policy on rebaselining programs.

- The FAA should appoint a central mechanism within the agency to coordinate all groups, initiatives, and efforts.  This mechanism would ensure that groups are properly chartered, are serving a useful purpose, and do not duplicate or overlap with established groups.

Table of Contents

Executive Summary	i

Introduction	1

Background	1

Purpose of Acquisition Program Baselines	1

Prior Reviews	1

Additional Request	2

Objectives	2

Scope	2

Methodology	2

Evaluation Results	5

Findings	7

Finding #1.  Acquisition program baseline instability was caused by nine documented and three underlying factors.	7

Requirements for Baseline Stability	7

Baseline Instability Continues to be a Problem	7

The Effects of Baseline Instability	8

The Causes of Baseline Instability	10

Finding #2:  Acquisition documentation was not always consistent and needs to be better maintained.	19

Finding #3.  Agency guidance on rebaselining programs needs improvement.	20

Evaluation of Rebaseline Actions in Our Sample	20

Justification for Rebaseline Actions	21

Other Matter—Multiple Agency Initiatives Addressing Baseline Instability Issues	23

Conclusion	28

Trends and Observations	29

Recommendations	31

Appendix A—Details for Causes of Baseline Instability	36

Appendix B—Reports Addressing Baseline Issues	42

Appendix C—Acronyms	44

# Introduction

## Background

#### Purpose of Acquisition Program Baselines

Acquisition program baselines are management tools that are useful to the FAA in several ways.  First, baselines allow program managers to measure progress internal to the agency.  Milestones provide effective points at which managers can determine if goals are being reached.  They also provide decision points for the agency to determine if additional investment in a particular product is warranted.  In addition, baselines are useful tools to hold managers and employees accountable for meeting performance objectives.

Second, baselines allow upper management to plan and allocate scarce resources among program areas.  Accurate and detailed predictions of program timelines and costs allow the agency to prepare for future upgrades to the National Airspace System (NAS) and to make trade-offs when scarce resources must be prioritized.  Such tools are necessary if the agency is to have an effective and integrated management process at an overall, strategic planning level.

Finally, baselines allow the outside world to measure agency progress.  Baselines are communicated to Congress and the entire aviation community and constitute a statement of intent on the part of the agency.  Congress and the Administration use baselines to measure FAA effectiveness in its modernization effort.  The aviation community, both domestic and international, makes plans for such diverse issues as aircraft equipage and facility upgrades based on these statements of intent.

#### Prior Reviews

Since the FAA was granted acquisition reform in April 1996, the Program Evaluation Division has reported three times on the status and success of acquisition reform.  These evaluations targeted different aspects of acquisition reform for review.  In conjunction with these evaluations, the Program Evaluation Division undertook a review of program baseline stability.

The objective of that review was to determine if FAA acquisition programs were maintaining better cost and schedule baseline stability under acquisition reform than was achieved before acquisition reform was implemented.  Originally, it was intended that these results would be published as part of the report entitled Evaluation of Acquisition Reform:  The First Three Years:  April 1996-March 1999.  However, because this evaluation measured baseline stability rather than true cost and schedule reductions, and because our sample differed from pre-acquisition reform and acquisition reform programs previously announced by the FAA, it was decided that the results would appear in a separate document.

The Program Evaluation Division’s Report #1999-05, entitled FAA Acquisition Program Baseline Stability:  Comparison between growth rates for programs conducted prior to acquisition reform and those conducted under acquisition reform (Baseline Stability Report), was published in September 1999.  The report concluded that the FAA was still experiencing significant cost and schedule growth in the period since acquisition reform was implemented.  That evaluation did not address the causes for continued growth in acquisition program baselines.  However, the report recommended that “The FAA Associate Administrator for Research and Acquisitions (ARA-1) should review the procedures and timing for establishing program baselines to determine if the process could be improved.”

#### Additional Request

At about the same time the Baseline Stability Report was published, ARA-1 requested an evaluation to answer the question “Under what circumstances should the FAA rebaseline programs, and why?”  The Program Evaluation Division undertook that evaluation and surmised that rebaselining might be a possible solution for addressing program instability.  Therefore, to respond to the ARA-1 query, the team first answered the question “Why do FAA Acquisition programs continue to experience baseline instability?”  The Division decided to combine the follow-on evaluation recommended in the Baseline Stability Report with the evaluation requested by ARA-1.

## Objectives

The objectives for this evaluation were to determine the causes for baseline instability in FAA acquisition programs and to recommend practical solutions for addressing the identified causes.

## Scope

Of the more than 100 programs in the FAA’s Capital Investment Plan (CIP), FAA considered 42 programs “baselined.”  The agency used this term to denote that the program had cost, schedule, performance, and/or benefits data documented in either an Acquisition Program Baseline (APB) or in a Parameter Sheet.  Data submitted by the 42 programs is tracked in the Simplified Program Information Reporting and Evaluation (SPIRE) system.  While all 42 programs had submitted baseline data into the tracking system at the time of our evaluation, eight of these programs were not reporting in SPIRE on a monthly basis.  We limited our review to the cost and schedule data being tracked in SPIRE on the 42 programs.  Benefits and performance data were not reviewed.

For this evaluation, we defined the “baseline process” as beginning with a program’s investment analysis process and ending with its last operational readiness demonstration (ORD) or November 1999 if the last ORD had not been reached.

## Methodology

To determine the causes for baseline instability and recommend solutions for addressing those causes, the team performed the following:

- Identified the evaluation universe as the 42 acquisition programs the agency was tracking in SPIRE.  Reviewed all programs reporting a variance of more than 10 percent as of June 1999 and one additional program that reported a variance of more than 10 percent in July 1999.  The programs reviewed were:  the Airport Movement Area Safety System (AMASS), Acquire, the Backup Emergency Communications system (BUEC), the Common Automated Radar Terminal System (Common ARTS), the NAS Infrastructure Management System Phase 1 (NIMS), the Operational and Supportability Implementation System (OASIS), the Oceanic Automation Program Build 1, the Standard Terminal Automation Replacement System (STARS), the Wide Area Augmentation System (WAAS), and the Weather and Radar Processor (WARP).  They are listed in Table 1 with the most recent variance information from the November 1999 Baseline Management Variance Report.

Table 1.  Reviewed programs with variances

|  | Program | Date of Variance | Type and Amount of Variance |
| --- | --- | --- | --- |
|  |  |  | Cost | Schedule |
| 1 | AMASS | 11/99 | 105% | 44% |
| 2 | Acquire | 2/98 | — | 14% |
| 3 | BUEC | 6/99 | — | 48% |
| 4 | Common ARTS | 6/99 | 3% | 22% |
| 5 | NIMS Phase 1 | 6/99 | 58% | 123% |
| 6 | OASIS | 6/99 | 27% | 23% |
| 7 | Oceanic Build 1 | 6/99 | — | 16% |
| 8 | STARS | 11/99 | 49% | 43% |
| 9 | WAAS | 11/99 | TBD | 100% |
| 10 | WARP | 11/99 | 14% | 20% |

- Divided the programs into two categories:  those initiated prior to acquisition reform, and those initiated under acquisition reform.  The team defined pre-acquisition reform programs as those initiated prior to October 1996.  This is consistent with the agency’s definition and conforms to the reporting requirements in Public Law 104-246.

- Examined the documentation from each of the 10 programs, APBs, Parameter Sheets, Baseline Management Notices (BMNs), and Baseline Management Variance Reports.  Documentation was collected from at least three months prior to variance reporting to January 2000 and from earlier timeframes when needed to track root causes.

- For the cost segment of baselines, primarily examined the Facilities and Equipment (F&E) portions of programs.  Research, Engineering and Development (R,E&D) funds were expended mostly in the portion of programs prior to baseline establishment, and Operations and Maintenance (O&M) funds were expended in the in-service portion of the program lifecycle, into which most programs reporting variances had not yet transitioned.  Within the scope of the evaluation, however, any O&M or R,E&D funds that contributed to baseline instability were examined.

- Reviewed numerous internal and external reports on baseline issues, including documents issued by the General Accounting Office (GAO), the Department of Transportation Office of the Inspector General (DOT OIG), and internal FAA reports.  See Appendix B for a list of these reports.

- Monitored program variances reported subsequent to July 1999.  As of November 1999, five additional pre-acquisition reform programs had reported variances of more than ten percent.  Although these programs were not formally examined as part of the evaluation, the team noted the documented causes of these variances.

- Reviewed documentation for several programs that had not experienced variances.  The team examined the process used to establish baselines, the status of these programs, and the point within the lifecycle the programs were traversing.  The team focused on any commonality of experience to account for the baseline stability these programs had achieved to date.

- Collected information from other agencies, including the Department of Defense and the National Aeronautics and Space Administration (NASA), to identify best-practice models.  The team also identified and collected data on internal FAA lessons learned and on the many initiatives underway within the FAA to address segments of the baseline process.  These data were analyzed to generate ideas for improvements to baseline processes that could help mitigate causes of baseline instability.

- Interviewed numerous parties inside and outside the agency, including Integrated Product Team (IPT) Leads, Product Team (PT) Leads, business managers, cost and schedule estimators, operational representatives, Investment Analysis (IA) Team members, Systems Engineering/Operational Analysis Team (SEOAT) members, and participants in initiatives designed to improve the baseline process.

# Evaluation Results

Baselines are required for all FAA programs.  Because of the complex nature and significant size of FAA programs, developing and maintaining stable baselines is a complex and difficult task to accomplish.  As documented in numerous reports, the FAA has constantly experienced problems maintaining baseline stability.  When baselines are not stable, the agency may lose its ability to plan and manage programs; may lose its ability to meet its customer and user needs, which affects its overall mission; may lose its credibility with Congress and other entities inside and outside of the FAA; and may lose the commitment of its employees due to a loss in employee morale.  We assessed ten baselined programs with variances of more than ten percent and found nine documented causes and three underlying causes for baseline instability.

We also found acquisition documentation was not always consistent and needs to be better maintained.  Six documents are mandated for programs under acquisition reform.  The team attempted to obtain some of this documentation, and, in some cases, the documents could not be located.  In addition, information being reported was not always accurate or consistent.  This is significant, because the agency needs complete and accurate documentation in order to track and measure programs’ success.

We also found that the process for modifying baselines has not been applied consistently, and agency guidance related to the rebaselining process, including the documentation required for these actions, is vague and incomplete.  In light of this, and in direct response to ARA-1’s question about when to rebaseline, we noted two situations in which the agency should consider rebaselining.

We also found numerous ongoing groups and initiatives in the agency.  Some appear to be addressing the causes identified in this report for baseline instability; others do not.

The team also noted several trends and made other observations, including the following:

- Distinct patterns among the variance causes indicate that, without intervention, variances can be expected to continue, particularly in pre-AMS programs.

- Most problems appeared to occur during the planning phase, indicating its importance in baseline stability.

- The agency lacks a process for dealing with issues arising from the use of commercial off-the-shelf/non-developmental items (COTS/NDI) as an acquisition strategy.

- Less complex, smaller programs appear to have a better chance of maintaining baseline stability, indicating the advisability of such strategies as evolutionary acquisition, spiral development, and baselining incremental segments of programs.

- In the past two years, funding fluctuations have increased in significance as a cause of baseline instability.

We worked collaboratively with numerous parties within and outside of the agency to address the issues identified in this report, and we have noted 11 recommendations for corrective action.

# Findings

## Finding #1.  Acquisition program baseline instability was caused by nine documented and three underlying factors.

FAA policy states that acquisition program baselines provide “performance and benefit objectives that are to be achieved within strict cost and schedule boundaries.”  Based on findings in our previous Baseline Stability Report, APBs have continued to experience significant growth in the years since acquisition reform was implemented.  Possible effects of instability include reduced ability to manage programs, effects on agency ability to meet customer needs, potential loss of credibility, and the potential for lowered employee morale.  The evaluation team identified causes of instability that occurred in the planning and solution implementation phases of a program lifecycle, causes that were outside the control of the implementing IPT, and some underlying causes of baseline instability.

#### Requirements for Baseline Stability

Section 2.11.3 of the Acquisition Management System (AMS) requires that every acquisition have an acquisition program baseline.  Section 2.11.3, “Stable Acquisition Program Baselines,” also states that baselines “are the control element in the AMS that enables the agency to plan realistically and commit to full funding of new programs.”  As such, baselines establish “performance and benefit objectives that are to be achieved within strict cost and schedule boundaries.”  Public Law 104–264 requires that, for programs initiated after October 1996, the agency must consider termination of any program having a variance of more than 10 percent.  Program baseline variances of more than 50 percent require the FAA Administrator to either terminate the program or notify Congress of the circumstances which necessitate its continuation.  General business practices and common sense dictate that baselines must be stable to properly manage programs.

#### Baseline Instability Continues to be a Problem

Our previous baseline stability evaluation found, and this evaluation confirmed, that baseline instability continued to be a concern in the FAA under acquisition reform.  Of the 42 programs with baselines currently being tracked, 18 reported variances between 1996 and June 1999, including 13 of 28 programs initiated prior to acquisition reform and 5 of 14 programs initiated under acquisition reform (i.e., after October 1996).  Table 2 contains a summary of these statistics.

Table 2.  Baselined FAA Programs and Their Variances

|  |  | Baseline Variances as of June 1999 |
| --- | --- | --- |
|  | Total programs | Total programs with variances | < 10% | > 10% | Percent |
| Pre-Acquisition Reform | 28 | 13 | 7 | 6 | 46% |
| Acquisition Reform | 14 | 5 | 2 | 3 | 36% |
| Total | 42 | 18 | 9 | 9 | 43% |

#### The Effects of Baseline Instability

The results of baseline instability are significant, and the agency is affected in at least four ways.  First, baseline instability may affect the agency’s ability to plan and manage programs.  Baselines provide a guideline for anticipating new capabilities and decommissioning old ones.  Further, they allow the FAA to predict resource requirements on macro and micro levels.  When baselines are not met, the agency cannot accurately anticipate either resource requirements or capabilities in the future.  Thus, the agency is forced to plan and budget on a short-term basis, creating a reactive environment in which crisis management becomes normal and expected.  Strategic planning becomes ineffective.  Few programs are allowed to remain stable, since funds must constantly be moved to “rescue” programs with significant variances.  Measurements of modernization progress become more difficult because baseline changes for funding reasons are so frequent.

Second, baseline instability can affect the agency’s mission when the FAA is unable to meet customer and user needs in a timely manner.  If programs required to modernize and sustain NAS capabilities cannot be delivered on schedule, potentially critical NAS capabilities will be missing.  The loss of benefits from unfielded systems also creates inefficiencies in the NAS.  The programs in our review contributed to safety, security, and system efficiency, as well as other agency mission functions.

Third, significant and sustained baseline instability may result in a loss of credibility with Congress, the flying public, the Office of the Secretary of Transportation, the Office of Management and Budget (OMB), and the domestic and international aviation communities.  In an environment of slipped program milestones, these important groups begin to perceive that the FAA cannot be trusted to finish planned tasks in a timely and cost-effective manner.  Such erosion in agency credibility creates lessened agency support and funding from the Administration and from Congress.  Such loss of funding exacerbates the effects listed above.  Loss of credibility may also create negative publicity for the FAA and may potentially affect the aviation industry.  Eventually, loss of credibility could lead to a lessening of the FAA’s position of leadership in the global aviation community.

Finally, baseline instability can negatively affect employee morale.  Employees may become cynical about establishing baselines since the chances are quite high that any established baseline will change almost immediately.  The process begins to be viewed as superficial and arbitrary, and employees may begin to manipulate the system.  Eventually, as negative feedback and the sense of frustration increase, employees may become less committed to the failed processes and may become discouraged enough to leave the agency.  Attracting qualified replacements in an agency perceived as ineffective may also become more difficult.

The relationship among listed effects is represented pictorially in Figure 1.

Figure 1.  The effects of FAA Acquisition Program Baseline Instability

#### The Causes of Baseline Instability

##### Documented Causes

The nine documented causes were grouped into three broad areas as listed below:

- Problems during the planning phase

- Poorly defined or new requirements

- Human factors issues

- Unsuitable acquisition strategy

- Unrealistic baseline

- Inadequate risk assessment

- Problems during the solution implementation phase

- Software development difficulties

- Poor contractor performance

- Problems with multiple issues outside the Integrated Product Team’s control

- Unstable funding

- Interdependencies

Many of these causes were interrelated, and complete separation of the issues was not possible.  However, the team concluded that each of these constituted a separate problem that deserved individual discussion.

A summary of the causes noted in each reviewed program is shown in Table 3 below, and a discussion is provided in the narrative that follows.

Table 3.  Summary of Baseline Instability Causes

|  |  |  | Problems During the Planning Phase | Problems During Solution Implementation Phase | Problems Outside Integrated Product Team’s Control |
| --- | --- | --- | --- | --- | --- |
| Program | Pre- Acq. Ref. | Acq. Ref. | Poorly Defined or New Requirements | Human Factors Issues | Unsuitable Acquisition Strategy | Unrealistic Baseline | Inadequate Risk Assessment | Software Development | Contractor Performance | Unstable Funding | Inter-dependencies |
|  |  |  |  |  |  |  |  |  |  | Internal | External |  |
| AMASS | X |  | X | X | X | X |  | X | X |  |  |  |
| Acquire |  | X |  |  |  |  |  |  |  |  |  |  |
| BUEC | X |  |  |  |  |  |  |  |  | X | X |  |
| ARTS | X |  |  | X |  |  |  |  | X |  |  |  |
| NIMS |  | X | X |  | X | X | X |  |  | X | X |  |
| OASIS |  | X | X | X | X |  |  |  |  | X | X |  |
| Oceanic | X |  | X |  |  |  |  |  | X |  |  | X |
| STARS | X |  | X | X | X | X |  | X | X | X |  |  |
| WAAS | X |  | X |  |  | X | X | X | X |  | X |  |
| WARP | X |  | X |  |  |  |  | X | X | X |  | X |
| Totals | 7 | 3 | 7 | 4 | 4 | 4 | 2 | 4 | 6 | 5 | 4 | 2 |

###### Problems during the planning phase

Causes within this group resulted from deficiencies during activities prior to the solution implementation phase.  This grouping included five of the nine documented causes; eight of the ten programs reviewed experienced problems during the planning phase. This finding indicates that the planning process is an area that requires specific improvements.  A summary of the finding is contained in the discussion below.  For more details of problems experienced by each affected program, see Appendix A.

1.  Poorly Defined or New Requirements.  In seven of the ten reviewed programs, user or system requirements were not adequately defined and documented to allow implementation of the program within the established baseline, or new requirements were added after the baseline was established.  These programs experienced both schedule delays and cost increases resulting at least partially from changes in requirements.

The requirements changes resulted from various planning shortfalls.  Some PTs did not understand the user requirements before beginning solution implementation.  Others experienced human factors issues that added program requirements.  Other programs had new requirements added after the baseline was established.

2.  Human Factors Issues.  For purposes of this evaluation, human factors issues included both human engineering and user preference issues.  Four of the ten programs incurred variances as a result of human factors issues identified after the program baseline was established, although in most cases there were indications that the acquisition approach involved some significant human factors risks.  The variances were the result of several different sets of circumstances.  For some programs, the issues were not anticipated; for others, they were ignored.  For example, in at least one instance, when the FAA decided to adopt a policy of acquiring commercial off-the-shelf/ nondevelopmental item (COTS/NDI) systems whenever possible, the agency erroneously believed that market place forces would provide an engineering solution that was sufficient to meet actual NAS requirements.  This lack of attention to detailed requirements led to a false assumption that any design difficulties could be easily, quickly, and inexpensively resolved.  Deficiencies in the design led to a complex relationship between redesign and engineering activities, union negotiations, and contractor–government deliberations on the program’s future cost and schedule.  Completion of the design changes resulted in increases to both cost and schedule for this program.

Other programs encountered human factors objections from field personnel during the solution implementation phase of the program.  The PTs negotiated a set of required changes with union representatives, and implementation of these changes resulted in increases to both cost and schedule.

3.  Unsuitable Acquisition Strategy.  Four of the ten programs selected an acquisition strategy that, in hindsight, was not commensurate with the requirements or with the commercial availability of the required product.  Some programs chose strategies that, in the interest of saving time, attempted to compress the acquisition cycle.  The results were longer development and deployment sequences and increased costs.  Other programs chose a COTS/NDI strategy without fully understanding the implications, resulting in increased costs and development delays.

4.  Unrealistic Baseline.  Four of the programs established unrealistic baselines from the beginning of the program.  Most of these baselines appeared to be driven by unrealistic expectations from both internal and external stakeholders.  For example, some programs promulgated cost and/or schedule baselines based on high-level management decisions that the PT knew to be unrealistic.  These decisions were apparently the result of political expectations.  Another program baseline was established with unrealistic cost and performance baselines due to an affordability assessment that forced program costs to fit available funding.

5.  Inadequate Risk Assessment.  At least two of the programs did not understand the risks involved at the beginning the program.  The original baseline was not based on a full understanding of the technical, institutional, and programmatic risks.  One of these programs was initiated prior to AMS, and a formal risk analysis was not performed.  Although these were the only documented cases of inadequate risk analysis per se, the two other programs that used a COTS/NDI strategy could also be placed in this category.  Neither program understood the risks of electing to acquire a COTS/NDI system to satisfy the requirements.

In the program planning area, two issues emerged that merit further discussion.  First, the evaluation team determined that acquisition reform planning process changes did not have an impact on baseline stability.  Seven of the ten programs were initiated prior to acquisition reform and, as a result, lacked the benefit of AMS-required planning functions.  For example, none of the seven programs completed an investment analysis report before solution implementation began,  although two of the programs (STARS and WAAS) have since completed mini-investment analysis reports. The baseline establishment process used in these programs lacked the rigor required under AMS.  Three of the ten reviewed programs were initiated under acquisition reform; investment analysis reports were completed for two of them (Acquire and OASIS), both of which were initiated near the beginning of the AMS time period.  One of these two programs, however, seemed to experience the same planning problems as those programs initiated prior to acquisition reform.  The third program initiated under acquisition reform (NIMS) was the first program to be conducted under AMS, and its investment analysis report was never officially published.  The NIMS affordability assessment was forced to fit a predetermined funding level.  These three programs did not have full success in applying AMS processes, but they all were initiated near the beginning of the AMS time period.

Second, AMS’s preference for COTS/NDI solutions has had a significant impact on the baseline process.  PTs experienced problems resulting from the selection and implementation of COTS/NDI equipment to meet user needs.  Several programs elected to use a COTS/NDI strategy, and each experienced similar planning problems associated with that choice.  Some of these problems seemed to arise from a lack of understanding about the consequences of choosing a COTS/NDI strategy in terms of lifecycle planning and budgeting, deployment, and sustainment.  Successfully adopting COTS/NDI as a procurement strategy entails recognition of a different set of risks and requires proactive management to mitigate those risks.  However, the FAA did not have policy or guidance concerning COTS/NDI strategy and its implications, and the affected PTs did not adapt their development, deployment, and sustainment strategies to plan for COTS.

The evaluation team did not attempt to determine if the agency policy on COTS/NDI was the “right” approach to acquisitions.  Other reports addressed that issue.  An internal report prepared by the FAA Office of Acquisitions entitled Effectiveness of COTS Solutions found that COTS programs tended to save the agency money in the procurement and deployment stages.  The Independent Assessment of the Federal Aviation Administration’s Acquisition Management System found that COTS implementation in the FAA may not save the agency money over the lifecycle of a program, given the higher costs for sustainment and technology refresh.  Research and lessons learned through the En Route IPT experiences with COTS/NDI indicated that, in some cases, given the current state of the market, the agency may not be able to avoid a COTS/NDI strategy.  Developmental programs are very costly.  At the same time, the government no longer drives the market, which gives impetus to move to a COTS/NDI solution for sustainability purposes.  The FAA, like other government acquirers, may be forced in some cases to move towards COTS/NDI and commercially available software (CAS) systems to meet user requirements.

###### Problems during the solution implementation phase

Causes within this group resulted from activities in the solution implementation phase of the program lifecycle.  Two specific causes were identified:  Software development problems, and contractor performance problems.  Six of the ten programs experienced variances resulting from one or both of these causes.

6.  Software Development Difficulties.  In a 1997 report, GAO stated that the FAA’s “processes for acquiring software…are ad hoc, sometimes chaotic, and not repeatable across projects.”  Although improvements have been made since that report, four of the ten programs experienced difficulties with software development that resulted in or contributed to cost and/or schedule variances.  These variances resulted from underestimation of lines of code required to meet user requirements and delays in development and integration of software.

7.  Poor Contractor Performance.  This issue is closely related to software development difficulties, since contractors are usually responsible for developing software for FAA systems.  Six of the ten programs experienced poor contractor performance, resulting in cost and/or schedule variances.  Problems included difficulties in attracting and retaining sufficient staff to perform the tasks, delays in software development and integration, and inability to deliver required functionality.

It should be noted that half of the programs in this evaluation remain in the development stage of the program lifecycle and have not yet begun to deploy the technology.  Only one of the programs has been completely deployed.  Given this status, other causes for baseline instability may exist that did not come to light during this evaluation.

###### Problems with multiple issues outside the IPT’s control

Causes within this group also resulted from activities in the program planning or solution implementation phase of the program lifecycle, but they were related to issues outside the control of the IPTs.  Two specific causes were identified:  unstable funding, and interdependencies.  Seven of the ten programs experienced variances resulting from one or both of these causes.

8.  Unstable Funding.  Funding stability was an important factor in an IPT’s ability to maintain stable baselines.  Programs that received substantially reduced funding in multiple years were not able to perform the program mission on schedule and within budget.  Funding instability can result from internal (i.e., FAA-imposed) cuts or adjustments to the program funding profile.  Funds may also be adjusted external to the agency by the Office of the Secretary of Transportation, the Office of Management and Budget (OMB), or Congress.

The team found that the perception among the majority of program personnel was that funding instability was the driving force behind the inability to meet program baselines.  Given that perception, the evaluation team conducted an analysis of historical funding profiles for all ten programs, focusing on external funding.  The results are displayed in Table 4.

Table 4. Request versus Appropriation Fiscal Year 1996–Fiscal Year 2000 ($M)

| Program | Requested | Appropriated | Difference | % Difference |
| --- | --- | --- | --- | --- |
| AMASS | 48.2 | 66.3 | 18.1 | 37.6% |
| Acquire |  |  |  |  |
| BUEC | 26.5 | 23.6 | –2.9 | –11.0% |
| Common ARTS |  |  |  |  |
| NIMS Phase 1 | 69.3 | 47.5 | –21.7 | –31.4% |
| OASIS | 71.1 | 52.4 | –18.7 | –26.4% |
| Oceanic Build 1 |  |  |  |  |
| STARS | 642.1 | 612.1 | –30.0 | –4.7% |
| WAAS | 488.5 | 499.7 | 11.2 | 2.3% |
| WARP | 89.7 | 91.9 | 2.1 | 2.4% |

Notes:

- Positive difference indicates appropriated more than requested.

- Negative difference indicates appropriated less than requested.

- Covers period Fiscal Year 1996–Fiscal Year 2000.

- No data for Common ARTS and Oceanic Build 1.

- ACQUIRE was funded internally.

The team discovered that funding instability indeed contributed greatly to external baseline instability for some programs, while others received nearly what was requested each year.  Three programs in particular were affected by external cuts.  However, the analysis was more complex than the data shown in Table 4.  For example, although some programs received within 10 percent of what was requested overall, the table does not indicate funding fluctuations from year to year.  These fluctuations were significant for some programs in specific years.  For example, the WAAS program was cut $28.1 million in Fiscal Year 2000.  Overall, this program seems to have received ample funding from FY96-FY00.  However, the cuts affected the program’s ability to meet the program baseline, since milestones for that year depended on timely funding.

Internal to FAA, the analysis became even more complex.  The team was unable to develop a concise summary of internal funding history for the programs.  The number of layers, iterations, and caveats quickly became unmanageable.  It was also difficult to distinguish which cuts were made as a result of Office of the Secretary of Transportation or OMB-imposed funding request restrictions.  However, the team concluded that internal funding fluctuations may have created greater impact on baseline stability than those imposed external to the agency.  Again, some programs appeared to have fared well in this process while others were significantly affected by internal adjustments.

Overall, six programs experienced funding reductions or adjustments that contributed to baseline variances.  These will be discussed in terms of internal and external funding instability.

Internal Funding Instability.  Five of the ten programs experienced internally-imposed funding reductions or adjustments to the funding profile that contributed to baseline variances.  These adjustments resulted from the agency’s efforts to address funding shortfalls.  In some cases, lower priority programs were cut or deferred to provide funding for higher priority programs.  In other cases, shortfalls in O&M funding or in other F&E lines were addressed in the funded baselines, increasing the costs for particular programs.

External Funding Instability.  Four of the ten programs experienced funding cuts from Congress that contributed to their inability to maintain baseline stability.

9.  Interdependencies.  Two programs experienced schedule variances as a result of the failures of interdependent programs to meet key milestones or performance standards.  These schedule delays resulted from either the requirement to wait for the required functionality to become available or the lack of sufficient resources elsewhere in the agency to work with multiple functionalities.

##### Underlying Causes

In addition to the documented causes discussed above, for which the evaluation team was able to obtain data to support our conclusions, we noted three underlying agency causes for baseline instability.  We discovered these causes solely through interviews with numerous IPT and PT members.  Interviewees were reluctant to discuss these underlying causes without our assurance of anonymity.  These causes included lack of trust, lack of accountability, and lack of empowerment.  These underlying causes are complex and interrelated, and their relationships to documented causes were not always readily apparent.

Although these causes have been reported many times by both internal and external sources, analysis of program documentation revealed relatively little supporting data to verify these interview opinions. Nonetheless, the team received widespread reiteration of these root causes in a majority of programs.

1.  Lack of Trust.  The team found indications of lack of trust at several different levels within the organization.  The most significant of these was distrust between FAA lines of business, particularly the Office of Research and Acquisitions (ARA) and the Office of Air Traffic Services (ATS).  Even among IPT members, the distinction between operations and acquisition was keenly felt.  Several ARA personnel expressed opinions that the ATS representatives were not empowered and could not make decisions for their organizations.  A few ATS representatives perceived that the ARA-led teams were secretive, withholding information from ATS team members.  This distrust seemed to contribute to several of the causes for baseline variances, including requirements changes and human factors issues.

Interviewees also expressed considerable frustration about management decisions that negatively affected program baselines.  These decisions included publicizing cost baselines that were unrealistic or schedule baselines that were artificially short.  Additionally, decisions about acquisition strategy and funding were made without the consent or approval of the responsible IPT.  Interviewees stated that this type of management direction illustrated a lack of trust in subordinates and an unwillingness to listen to the “experts” hired to make realistic projections.  This issue also relates to lack of empowerment, discussed below.

2.  Lack of Accountability.  Interviewees stated that baselines were subject to interference from those within the organization who had no accountability for variances.  The frustration was particularly widespread when interviewees spoke of funding issues.  Almost all interviewees expressed strong disapproval of the current practice of  “salami slicing” (i.e., slicing the funding of most programs to adjust to budget realities or to rescue other programs with variances).   They stated that decisions to cut many programs instead of terminating the lowest priority programs were made by those having no accountability for baseline stability.

Interviewees also expressed opinions that some lines of business felt free to hold up programs by delaying time-critical decisions because those lines of business were not accountable for program success.  This led to new requirements being introduced and led to an inability to resolve interdependency issues.

3.  Lack of Empowerment.  As stated above, many interviewees believed that members of IPTs were not sufficiently empowered to do the job.  Decisions reached by the IPT with the support of IPT representatives were overturned by their parent organizations, leading to additions of new requirements, requirements changes, and an inability to resolve issues in a timely manner.  Some of these changes were due to fluctuations in personnel.  When a new IPT representative appeared or a new boss emerged somewhere up the organizational chain, many interviewees suggested that all previous decisions became “up for grabs.”

The problems were compounded by the hierarchical structure in FAA.  The many layers of management fostered a controlling environment in which some employees did not feel empowered to make decisions or were not held accountable for the decisions they made.

## Finding #2:  Acquisition documentation was not always consistent and needs to be better maintained.

During the evaluation, the team attempted to review program documentation and found that some of the required documents for programs were missing.  Further investigation with the responsible FAA office, IPTs, and other sources determined that, in several cases, the required documentation could not be located at all.  We also found that some documentation was not accurate or consistent.  For example, in one case, the Joint Resources Council (JRC) minutes were inconsistent with other program documentation, and this inconsistency led to confusion about program status.  In addition, eight programs that were baselined in the SPIRE system were not reporting variances on a monthly basis.

Documentation requirements for acquisition programs are specified in the AMS, Section 2.12.  All programs are required to maintain six specific documents (Mission Need Statement, Requirements Document, Investment Analysis Report, Acquisition Program Baseline, Acquisition Strategy Paper, and Integrated Program Plan) developed during the planning stages of an acquisition. Guidance on variance reporting is provided in the Integrated Baseline Establishment and Management (I-BEAM) Process document, which instructs programs to report variances on a monthly basis.

The FAA maintains a central repository for AMS-required program documentation, located in the Document Control Center.  This location is required to contain approved versions of all applicable program documentation.  The SPIRE system has been established to collect program progress data, including monthly variance reports.  GAO has recommended that the SPIRE system also contain electronic versions of all program documentation.  The process of implementing this recommendation is underway but is not complete.  To date, the documentation contained in SPIRE is limited.

The lack of available documentation harms the FAA in several ways.  First, without documentation it becomes more difficult to track and measure progress or determine what methods were used to make critical program decisions.  Second, this inability to locate the documentation leads people to question the original purpose of developing the document.  If it cannot be located, it is obviously not in use.  In the case of many AMS-required documents (e.g., APBs and risk mitigation strategies), if the document is not to be used, the resources spent on its development may have been wasted.  Finally, an inability to locate required documentation reduces agency credibility in the eyes of outsiders such as Congress and the aviation community.  Inability to provide an audit trail of programmatic and technical decision-making creates the perception of lack of structure and accountability in these areas.  This lack of documentation has been noted by the GAO, the OIG, and the Program Evaluation Division in previous reports.

## Finding #3.  Agency guidance on rebaselining programs needs improvement.

While the agency has undertaken a significant number of program rebaseline actions in the past two years, the process for modifying baselines has not been consistently applied.  Agency guidance related to the rebaseline process, including what documentation is required for these actions, is vague and incomplete.  Considering that six of the ten programs in our sample were rebaselined at least once since September 1998 and two additional programs have recently requested rebaseline actions, we believe the agency needs to develop and implement clear and specific guidelines on the rebaselining process.

Since the FAA began tracking program baselines as a part of AMS in 1996, the agency has periodically rebaselined programs that exceed cost, schedule, performance, or benefits baselines.  Rebaseline actions approve and document the changes to baseline parameters.  These actions are perceived as a way for a program to “start over” when circumstances no longer make the current baseline realistic.

According to the FAA’s I-BEAM Process document, dated March 1999, “Rebaselinings will be approved by the JRC only if circumstances dictate that the program can no longer be managed to its original baseline.  Changes must be so extensive that the original baseline no longer has a value for measuring the performance of the agency with respect to its objectives.”  In September 1999, the agency developed a draft revision to the I-BEAM Process document that provides examples of events for which rebaselining would be appropriate, including changes to the program at contract award, changes in budget allocations, and changes in requirements.

#### Evaluation of Rebaseline Actions in Our Sample

Six of the ten programs in our sample were rebaselined at least once since September 1998.  Table 5 contains specific data on these programs.  Two additional programs, AMASS and BUEC, have recently requested re-baseline actions and are scheduled to appear before the JRC in March 2000.  While the JRC approved all six rebaseline actions, the rebaseline process and documentation requirements were not clear or consistent.  For example, it was not clear why one program needed to be rebaselined.  Also, while certain PTs updated the baseline parameters in the APBs, other PTs considered the BMN sufficient documentation of the new baseline parameters.  In addition, there was confusion within the agency about the effects of rebaselining.  While many interviewees believed that rebaselining allowed a clean start from the new baseline, others realized that the agency tracked and reported variances from the original baseline, irrespective of the new baseline.

Table 5. Reviewed Program Rebaselines

|  |  | Original Baseline | Most Recent Rebaseline | Total Number of Rebaselines |
| --- | --- | --- | --- | --- |
| 1 | AMASS | PS 10/98 | N/A | 0 |
| 2 | Acquire | APB 12/96 | N/A | 0 |
| 3 | BUEC | PS 10/98 | N/A | 0 |
| 4 | Common ARTS | APB 12/96 | N/A | 0 |
| 5 | NIMS Phase I | APB 3/97 | 7/99 | 1 |
| 6 | OASIS | APB 4/97 | 5/99 | 1 |
| 7 | Oceanic Build 1 | APB 6/96 | 9/98 | 1 |
| 8 | STARS | APB 3/96 | In process | 1 |
| 9 | WAAS | APB 1/98 | 9/99 | 1 |
| 10 | WARP | APB 3/95 | 8/99 | 1 |

#### Justification for Rebaseline Actions

In response to ARA-1’s question, “Under what circumstances should the FAA rebaseline programs, and why?” the team examined possible reasons from several different perspectives.  We considered such philosophical issues as whether programs should be rebaselined only when changes were driven by events beyond the agency’s control (e.g., funding reductions), and whether rebaselines should be considered a means of “starting over” for programs.  We determined that rebaseline criteria should be based on practical considerations.  Baselines are tools for managing program progress.  When such tools are no longer useful, they should be revised.  Based on our review, we believe that the FAA should rebaseline programs in two situations:

- To restructure a program when the program goals, methods, or strategy have changed to such an extent that the baseline no longer provides a realistic measure of the program progress.  Three of the six rebaselined programs evaluated experienced significant changes to program structure or performance parameters as well as significant baseline variances.  These programs needed to be rebaselined to allow the PTs to effectively manage to the programs’ extended baseline parameters.

- To reestablish a manageable measure of progress when one or more baseline parameters have been breached to such a significant extent that those measures are no longer applicable.  Two of the six rebaselined programs in our sample experienced baseline variances so large that the baseline was no longer a realistic measure of the program’s progress.  These programs needed to be rebaselined to establish a reasonable measure for which the current PT could be held accountable.

While the September 1999 draft revision to the I-BEAM Process document provides examples of events in which rebaselining would be appropriate, additional clarification needs to be developed and formally issued.  This guidance should clarify the role of rebaselining, the process for requesting and documenting a rebaseline action, and the required justification for rebaseline requests.  In addition, the guidance should include a mechanism for reviewing and approving rebaseline requests prior to the JRC presentation.

# Other Matter—Multiple Agency Initiatives Addressing Baseline Instability Issues

During the evaluation, the team discovered multiple teams and initiatives currently underway within the FAA that relate to baseline stability issues.  Some of these initiatives were designed to increase baseline stability; others were not necessarily so designed but nevertheless may produce that effect.  All such initiatives discovered during the evaluation are presented here for information purposes.  Some will be referred to in the recommendations section.

The team discovered these initiatives through referrals during interviews, examination of agency reports such as the Program Evaluation Division Report #1999-09, “Inventory of Agency Process Initiatives,” and other sources.  However, the team could locate no central repository for information on such agency initiatives.  Therefore, the following discussion may not include all applicable initiatives.

1.  Portfolio Management.  This initiative began formally with a memorandum signed in December 1999 by five FAA senior executives and was designed to “improve our capital investment decisions.”  Based on work completed by an Integrated Product Leadership Team sub-team, the initiative will “aggregate investment candidates into funding categories that correspond to the business model of the enterprise and allow senior management to manage the capital investment portfolio as a whole with the aim of increasing benefits and managing risks.”  The effort will essentially organize FAA operations and acquisitions into “integrated service teams.”  These teams will be led by a portfolio manager who will be responsible for managing all the resources required to provide the service.  Senior FAA management will be responsible for making trade-offs between the services.

If implemented widely, the effort has the potential to produce far-reaching changes within the FAA.  It could improve the agency’s ability to make sound capital investment decisions, manage program performance and risks, and improve FAA’s communication with Congress and other stakeholders.  On a deeper level, the effort could address the underlying causes identified in this report.

The effort is still rather early in its development.  In 2000, a working group will be formed to examine the broad issues of portfolio management, and a pilot will be initiated, using the Terminal/Surface Separation Assurance Service.  A schedule beyond 2000 has not yet been developed.

2.  COTS/NDI.  Efforts to improve the way the agency manages COTS/NDI-based acquisition programs do not really constitute an initiative.  However, we found that, throughout the agency, specific organizations have begun to recognize the far-reaching implications of the agency’s preference for COTS/NDI acquisition strategies and have initiated efforts to manage the changes such a strategy entails.  These efforts appear to be fragmented and sometimes uncoordinated.  They include:

- The En Route IPT (AUA-200).  This IPT seems to have taken the lead in ARA in terms of identifying COTS/NDI impacts on acquisition program management and execution, and has initiated several efforts aimed at changing the acquisition management processes to recognize the impacts of COTS/NDI.  AUA-200 began by instituting plans and processes within the En Route IPT.  These include:

- Successful deployment of the COTS-based Display System Replacement (DSR) program.  The DSR program ensured early user involvement and acceptance, effective in-service management planning and transition, budget stability, and technology refresh data requirements and planning.

- The Host and Oceanic Computer System Replacement (HOCSR) program was the first to have the operations budget baselined and to include technology refresh of the computer as part of the program baseline.

- Development of Section 5.0 of the En Route “Green Book” entitled “Sustainment and Technology Evolution Planning.”

- Development of the En Route Domain Infrastructure budget line.  This line combines technology refresh, pre-planned product improvement activities, and sustainment for the en route domain, recognizing that COTS/NDI systems require constant and often short-term refresh.

- Development of the Technology Refresh Planning Guide, dated January 5, 1998.

- The Voice Switching and Control System Sustainment and Technology Evolution Planning effort to develop and maintain system obsolescence profile for budget planning and defense.

Additionally, AUA-200 has attempted to expand these ideas and lessons learned to other parts of the agency.  Efforts include:

- Recent demonstration of COTS-sensitive life-cycle modeling tool.

- Development of a draft AUA position paper entitled “COTS and the FAA:  Ready or Not?”  This paper outlines actions the FAA needs to undertake to manage in a COTS environment.

- Presentation to the Air Traffic Automation (ATA) Integrated Management Team entitled “Technology Refresh, Foundation for Strategic COTS Management,” January 19, 2000.

- The Terminal IPT (AUA-300).  The STARS program established a COTS manager position to ensure obsolescence and pre-planned product improvement planning is executed.  This position is responsible to execute the contract option with the prime contractor specifically tailored to commercial product technology refresh planning.

- The Investment Analysis and Operations Research Division (ASD-400).  ASD-400 began an effort to develop a COTS-based modeling approach for the NAS.

- The Office of Acquisitions (ASU).  ASU established a flow chart for COTS/NDI hardware and custom software development and included it in the FAA Acquisition System Toolset.  They are also currently in the process of adding COTS-related data to the individual flow chart steps as guidance.

- The NAS Operations Service (AOP).  AOP released Policy 4560.1C in draft form for agency review in November 1998.  The intent of the new policy was to capture the data requirements for COTS-based systems and to reflect the transition of the FAA Logistics Center to a fee for service organization.  To date, the draft has not been updated.  Responsibility for the update of this policy has recently been transferred to the NAS Logistics Property Management Division (AFZ-500).

- The NAS Logistics Property Management Division (AFZ-500).  AFZ-500 created a position for a Contractor Depot Logistics Support (CDLS) funding coordinator to prioritize funding for CDLS Contracts used to manage COTS-based systems and to identify standard data requirements for CDLS contracts.

- The Configuration Management Division (ACM-20).  ACM-20 has recently updated the AMS and an FAA policy (Order 1800.66) to reflect the current NAS configuration management policy and process activities being implemented by the agency.  The configuration management of COTS/NDI systems and equipment are addressed by the policy and life cycle process. There is further work underway in the development of  NAS configuration management procedures that will provide a more detailed description of how to configuration manage COTS/NDI. The procedure development should be completed by May 2000.

We believe that these initiatives constitute a good start in attempting to improve the way the agency handles COTS/NDI acquisitions.

3.  Operations Baseline Team.  This group was established in August 1998 in response to recommendations made by the Budget Process Team.  One of the objectives in the Team’s charter is “the development of a recommended ATS Budget Formulation process that takes into account actual and projected costs of providing services, actual and projected costs of maintaining existing systems, results of investment decisions, and the inter-relationship between the F&E and O&M budgets.”  The group is currently engaged in breaking out operations funding for F&E programs on an annual basis.  It has selected 25 programs whose funding requirements represent 80 percent of total affected O&M costs and has begun to identify estimated O&M costs for each of those programs.  The group plans to develop the capability to report O&M requirements to Congress on a yearly basis.  Eventually, the O&M estimates will be included in SPIRE.  This initiative has the potential to create more realistic O&M baselines, which would increase baseline stability.

4.  Human Factors Process Group.  This group was formed in 1997 in reaction to the STARS design and development deficiencies related to human factors engineering.  In addition to the technical reports rendered by the effort, the group published two management or process related reports.  One related to general practices and considerations that were found to be obstacles to achieving a good human factors accommodation of two separate but related and often confused issues within the context of AMS (i.e., human factors engineering and user and union participation in system acquisitions).  The group summarized the problems in six major findings and recommended five broad actions to improve human factors processes within FAA.  The recommendations focused on placing more emphasis on human factors engineering (especially by acquiring more human factors expertise at the IPT level) and identifying formal ways to obtain user and union involvement in the acquisition process.  As a result of these recommendations, a follow-on group was tasked to develop a specific action plan for implementing the recommendations.  The implementation group has completed work on this action plan and will publish the results in the near future.  If successful, we believe that this initiative may address some of the causes identified in this report.

5.  Process Action Group—Customer Service Process Team.  This group was formed in 1999 as a result of Common ARTS problems with user acceptance at a specific field site.  The group conducted on-site interviews with field personnel and used the data to validate and refine the customer service process documented by PT members.  The group found that field personnel have been articulating problems, but headquarters has not always listened because field personnel may not have been considered “customers.”  It also concluded that headquarters personnel have been more concerned about pursuing aggressive implementation schedule deadlines than ensuring that new systems fully meet customer needs and expectations.  The group further concluded that headquarters personnel do not sufficiently understand customers, including their work environments, requirements and objectives.

As a result of the study, the Customer Service Process Team is in the process of developing an improved customer service process derived from a combination of industry and FAA best practices and recommendations from field customers.  It will emphasize listening to the customer and involving customers in the process earlier.  The new process should be ready for implementation by Fall 2000.  The team will use the Terminal IPT as a pilot, then initiate changes in AMS and the integrated Capability Maturity Model.

We believe that, if successful, this initiative has the potential to address some of the causes identified in this report.

6.  Development and Approval of a Five-Year Budget.  The JRC recently approved the agency’s first five-year F&E budget in an effort to attempt to stabilize funding both internally and externally by planning farther into the future.  A clear plan for the future allows players both internal and external to the FAA more insight into the agency’s priorities and intentions.  We believe this is a great start, but it is contingent on annual appropriation.  Also, the budget does not include O&M or R,E&D funds, which are necessary for stable baselines.

7.  Integrated Capability Maturity Model.  The agency has developed and is using the FAA integrated Capability Maturity Model as a unified approach for evaluating its processes and improving them to reach maximum efficiency.  A major initiative is currently underway to increase the maturity level of selected major software-intensive programs.  Many of these programs have achieved integrated Capability Maturity Model Level 2.  We believe that, if successfully implemented across FAA acquisition programs, this process may address some of the causes identified in this report.

8.  Baseline Acquisition Programs at Contract Award.  This initiative would amend AMS to allow acquisition programs to be baselined just before a major contract is awarded rather than at investment decision.  The rationale for the proposed change is that considerable cost, schedule, and technical uncertainty still exists at a program’s investment decision point, and some of that uncertainty should be eliminated between investment decision and contract award.  The change would thus lead to more stable baselines once they are approved.

Critics of the initiative pointed out that investment decisions without acquisition program baseline approval would assume little importance, and that few programs have experienced variances before contract award.  However, the initiative appears to have considerable energy behind it and has proceeded to the stage of coordination with OMB and Congress.

The team found that only one program we reviewed (Acquire) experienced a variance before contract award.  This three-month schedule variance occurred because the program office was dissatisfied with bids it had received and re-issued the solicitation.  In addition, one program not included in our review (NEXCOM) has recently reported a variance before contract award.

While implementing this initiative could result in more stable baselines once they are set, it does not address the causes identified in this report.

9.  Consolidation of JRC Meetings to Coincide with the Budget Process.  A recent informal effort has been initiated to reduce the number of JRC meetings held throughout the year.  This initiative would combine most program-related JRCs into three major meetings planned in accordance with the yearly budget cycle.  Programs would have the ability to appear before the JRC between these mass meetings if necessary but would be urged to plan needed decisions around these structured meetings.

This initiative has the potential to mitigate the effects of internal and external funding instability through implementation of a more structured planning and decision-making process.  JRC members would have the benefit of the most current budget information before making crucial program decisions.  The consolidation of several programs into one meeting would also assist the JRC in making trade-offs between programs due to resource scarcity.

This initiative appears to be underway, with the first mass JRC planned for March 2000.  The team could find no documentation of this effort and is unsure if any changes are needed to document and institutionalize this change.  We believe this initiative has the potential to mitigate some of the effects of baseline instability.

10.  Risk Management Added to AMS.  The January 2000 version of AMS includes new guidance to the agency on risk management.  The guidance stresses risk assessment and mitigation throughout the lifecycle of every program.  Risk assessment should begin in mission analysis and should continue through the in-service management phase of each program.  If implemented throughout the agency, this new guidance has the potential to address some of the causes identified in this report.

## Conclusion

As noted above, there are many existing groups and ongoing initiatives in the agency.  Many of these are worthwhile and, in some cases, we have endorsed their recommendations in this report.  However, the team also discovered that this proliferation of groups, initiatives, and other process change efforts produced significant frustration throughout the organization.  In particular, personnel participating in the IPT process expressed the belief that the staffing of these groups, while important, hindered the ability of the IPTs to produce their primary products.  Moreover, some of the groups appeared to overlap in their efforts; others produced recommendations that might have the effect of creating more layers of management or additional groups for coordination.  There appeared to be no central coordination mechanism among the efforts.

# Trends and Observations

In addition to the conclusions reached in our three findings, the team noted several broader trends and observations that cut across the findings.  We also noted that some of the initiatives listed in the Other Matter section may address the causes of baseline instability.  The additional trends and observations are noted below.

- Causes for FAA acquisition program baseline variances follow distinct patterns, indicating systemic problems within the agency.  Variances reported since the June 1999 cutoff for this report appear to be following the same patterns, indicating that, without intervention, the agency can expect more such variances to occur in future programs.

- Of 42 baselined programs, 28 were initiated prior to AMS.  None of these programs were planned under the more rigorous AMS procedures.  Seven of these programs have reported variances of more than 10 percent through July 1999.  Subsequently, four additional pre-AMS programs have reported variances greater than 10 percent.  These data indicate that, without intervention, variances may be expected in additional pre-AMS programs.

- Program planning issues such as establishing a realistic baseline, selecting a workable acquisition strategy, and conducting sound risk analysis affected half the programs.  Seven of the ten programs reviewed were undertaken prior to AMS’s introduction of a more rigorous planning process, but two of the three programs initiated under AMS experienced the same problems.

- Within the causes occurring in the planning phase of the acquisition lifecycle, a recurring pattern emerged relating to difficulties in planning for COTS/NDI acquisitions.  Although AMS stated a preference for COTS/NDI as an acquisition strategy, there appeared to be no overall agency recognition of the cultural, programmatic, or funding implications of such a strategy.  The agency has undertaken several initiatives to improve its management of COTS/NDI technology.  These efforts appeared to be somewhat fragmented and uncoordinated.

- Research into both Department of Defense (DoD) and FAA programs indicated that baseline stability may be related to size and complexity of program.  Programs maintaining baseline stability tended to be smaller and less complicated.  Strategies used in DoD and in the En Route IPT included segmentation of programs; that is, program baselines were developed in smaller sections.  When one segment neared completion, the estimate for the next segment was performed.  Other strategies included evolutionary acquisition and spiral development.

- Unstable funding was a problem that appeared to escalate in the last two years as budgets tightened.  Six of ten programs had variances caused in whole or part by funding instability.

- Poorly defined or new requirements continued to be a problem for programs we reviewed.  Seven of the ten programs were affected by the inability to maintain stable requirements.  The effects of improved requirements identification processes implemented by FAA in the past two years were not reflected in programs we reviewed, since each was initiated prior to these changes.

- Human factors issues were a factor in four of the ten programs.  Three of these programs were initiated prior to AMS; one was initiated under AMS.  New FAA measures have been and are being developed to introduce a more rigorous human factors approach into program planning and execution processes.  Some of these measures have yet to be implemented.

- Software development continued to be a problem for six of ten programs.  This problem has been identified previously, and the FAA is taking action to document and improve software development processes.  However, these changes appeared to have little effect on the programs we reviewed.

- Contractor performance was a problem in six of ten programs.  For large, complex programs, the FAA continued to award contracts to relatively few vendors, creating staffing conflicts.  The recent report Independent Assessment of the Federal Aviation Administration’s Acquisition Management System found that “a uniform process for collecting and applying past performance qualifications in source selections is not evident” in the FAA. This evaluation confirmed that the past performance database is currently not populated, and that plans to add data for past contracts are uncertain.  Moreover, the team became aware that the National Institutes of Health have a comprehensive contractor past performance database that federal agencies can access for a fee.  The FAA currently does not use that database.

- Program management–related lessons learned do not appear to be communicated among IPTs within the FAA.  The FAA’s “Acquisition Lessons Learned” database contains some contract-related data, but very little on program management issues.

# Recommendations

Achieving baseline stability is not an easy task.  FAA programs are quite complicated, span multiple years, and involve millions of dollars.  The systems acquired by the agency are sometimes state-of-the-art and always involve lots of uncertainties.  Between the time alternatives are analyzed and the decisions based on those analyses are implemented, changes in the environment, particularly in the area of the fast-emerging technology, may make the decisions outdated even before they can be implemented.  This phenomenon, coupled with program funding being uncertain and not completely within the control of the agency, makes achieving baseline stability for the agency’s programs nearly impossible.

Recognizing this difficult task, we have worked collaboratively with multiple parties within and outside the agency to develop recommendations that will address this important issue.  We do not purport that these recommendations will totally solve our baseline stability challenges, but we believe that they will help the agency focus on those areas most within our control.

- Because the agency is not provided sufficient funds to cover all the modernization it would like to implement, it must manage resources from a corporate standpoint and not on a program-by-program basis.  Accordingly, we recommend that the FAA continue to develop an integrated approach to the agency’s entire portfolio and implement that approach as soon as possible.  The portfolio management approach initiated within the agency may be a viable solution.  Whatever form such an initiative takes, it should provide for:

- The integration of service providers and service acquirers/developers into consolidated organizations centered around designated services.

- A streamlined budget process that requires managers to prioritize all required resources  (including acquisition programs required to provide the service) at appropriate levels.  The process should include both F&E and O&M costs.

- A process by which the agency can prioritize programs and fund only those programs for which sufficient resources are available.

- Empowerment of service level management to make resource and personnel decisions within the designated service.

- Accountability of management to provide specific services at a given resource level.

- The agency has stated its preference for COTS/NDI solutions, and these solutions come with a host of new challenges.  Therefore, we recommend that, when the agency employs a COTS/NDI acquisition strategy, the FAA takes specific steps to align the acquisition planning, implementation, sustainment, and budgeting processes with that strategy.  These steps must be undertaken across lines of business and include:

- Establish a common understanding of COTS/NDI and CAS product characteristics, risks, and challenges throughout the agency.  Strategies for achieving this common understanding could include forums, seminars, written materials, brown bags lunches, and formal training.

- Perform an assessment of the investment analysis process to determine ways to modify the process so that it is better suited to COTS/NDI solutions.  Examples of changes could be:  obtain cost models that consider COTS/NDI factors, ensure appropriate analysis time, factor in sustainment and technology refresh, and determine and document F&E and O&M funding trade-offs.

- Identify changes to business practices required when a COTS/NDI/CAS strategy is pursued.  Areas affected include planning, requirements definition, budgeting, contracting, systems engineering, test and integration, configuration management, human factors, maintenance, logistics, and general agency practices.

- Develop policy, guidance, process changes, and other documentation necessary to promulgate this information within the agency.

The En Route IPT is recommending that a new group be established under the Integrated Product Leadership Team to spearhead these and other actions.  In light of the considerable frustration over multiple efforts currently underway in other process improvement areas, we hesitate to recommend another group be formed at this time.  However, the importance of this issue merits immediate action.  Therefore, we also recommend that such a group be formed to facilitate implementation of the above recommendations.

- Because customer service is critical to the agency fulfilling its mission, we recommend that the FAA continue its efforts to improve customer service in the development and delivery of equipment and services.  Specific actions include:

- Recognize that the field users constitute an intermediate “customer” for the IPTs, and document this understanding in agency policy and guidance.

- Develop a formal process for customer involvement throughout the product development and delivery process.  The process should culminate with formal agreements between IPTs, field representatives, and involved unions.

This recommendation could be facilitated by the efforts of the Customer Service Process Team.

- Because early consideration of human factors issues is critical to baseline stability, we recommend that the FAA continue its efforts to improve integration of human factors requirements into all stages of program planning and solution implementation.  Specific actions include:

- Establish appropriate measures and mechanisms to ensure that all Integrated Requirements Teams, Investment Analysis Teams, and IPTs have qualified human factors expertise to participate as integral members of the team during all stages of analysis and program planning and development.

- Amend AMS policy and/or guidance to clarify roles and responsibilities for human factors activities in all phases of the acquisition lifecycle (see The Management of Human Factors in FAA Acquisition Programs, March 31, 1998, recommendation #2, for more details).

Efforts to achieve these steps could be facilitated by the work of the Human Factors Process Group.

- Because air traffic control systems take many years to reach fruition and the environment may change significantly during this time, we recommend that the FAA take aggressive measures to implement its new policy on risk assessment and mitigation, including:

- Develop detailed guidance for risk assessment and mitigation planning and execution and include this guidance in the FAA Acquisition System Toolset.

- Ensure all responsible personnel are aware of the guidance and of the importance of its implementation in both new and existing programs.  Possible mechanisms include incorporation into AMS training and refresher courses.

- Incorporate risk assessment and mitigation strategies into executive level reporting requirements.

The AMS assigns responsibility for development of risk mitigation processes to the various lines of business.  We endorse that designation but also recommend that coordination and review of these processes should be performed by one central organization (e.g., the Integrated Product Leadership Team).

- Because of the uncertainty that surrounds large, complex programs and the inherent difficulty built into the development of baselines with these conditions, we recommend that FAA IPTs consider innovative ways of structuring and conducting acquisitions to reduce cycle time, minimize risk, and maximize product utility, including:

- Baseline segments of programs as opposed to baselining the entire program at investment decision.

- Employ spiral development techniques.

- Employ evolutionary acquisition and simulation based acquisition tools.

- Because contractor performance is critical to the success of our operations and the agency has had problems with contractors in the past, we recommend that the FAA  assess past performance for all contractors and use it as a factor in contract award.  Specific actions include:

- Evaluate the utility and cost/benefits of using the National Institutes of Health past performance database versus populating and maintaining the FAA Past Performance database.

- Populate the selected past performance database with data from past contracts as soon as possible.

- Develop and promulgate guidance for populating the database with results from existing or future contracts when available.

- Develop and implement a training mechanism to make PTs aware of the importance of past performance as a criterion in contract awards.

The Office of Acquisitions (ASU) is the point of contact for the Past Performance database, and could be assigned responsibility for these actions.

- Because learning from our past experiences is critical to improving our operations and ensuring that we gain from those experiences, we recommend that FAA PTs share information among themselves, both formally and informally, on lessons learned throughout a program’s lifecycle.  Specific actions include:

- Populate the existing Acquisitions Lessons Learned database.

- Disseminate information about the database throughout the FAA acquisition community.

- Develop and promote an environment in which employees understand the benefits and feel free to exchange lessons learned information.  This could be accomplished through a concerted effort, supported by top management, to:

- Develop a forum for sharing such information (lessons learned meetings, lectures, brown bags, etc.).

- Encourage and reward participation in such efforts.

ASU is currently responsible for the Acquisitions Lessons Learned database.  These specific steps, however, could be integrated into development of the FAA Acquisition Workforce Learning System, currently the responsibility of the Office of Business Management (ABZ).

- Because accurate and complete data is imperative to the agency’s ability to monitor and assess programs, we recommend that the FAA improve its management of program documentation, including:

- Ensure that all required program documentation resides in the Document Control Center.  The NAS Configuration Management and Evaluation Staff (ACM) is currently assigned responsibility for this task.

- Designate SPIRE as the central repository for electronic versions of FAA documentation.  The NAS Programming and Financial Management Division (ASD-300) is assigned responsibility for SPIRE development and maintenance.

- Ensure that electronic versions are consistent with hard copies maintained in the Document Control Center.

- Because establishing and maintaining baselines is critical to the agency’s credibility, we recommend that the FAA develop and implement a consistent policy on rebaselining programs.  Specific actions include:

- Clarify the role that re-baselining plays in the acquisition management process.  This could be accomplished by ASD-300.

- Develop criteria and a process for re-baselining requests, and ensure they are followed.  The first steps in identifying criteria and process have been taken by ASD-300 in the draft update to the I-BEAM document.  These efforts should continue.

- Establish a review mechanism below the JRC to determine when a re-baseline request is appropriate.  This could be accomplished by the FAA Acquisition Executive Advisory Board (FAB).

- Because of the proliferation of groups and initiatives within the agency that appear to be uncoordinated, we recommend that the FAA appoint a central mechanism within the agency to coordinate all groups, initiatives and efforts.  This mechanism would ensure that groups are properly chartered, are serving a useful purpose, and do not duplicate or overlap with established groups.  This mechanism could reside with the Associate Administrator for Information Services (AIO).

# Appendix A—Details for Causes of Baseline Instability

This appendix provides program by program details for the nine documented causes of baseline instability.

1.  Poorly defined or new requirements

The NIMS program did not initially understand requirements, and did not have agreement on requirements and program philosophy from the user prospective.  The program used a spiral development process that necessitated refining requirements on an ongoing basis.  Although the team had early customer involvement and adequate sponsor support, the requirements were not identified at a level that facilitated fully informed customer agreement.  The program plan did not have the means to quantify the evolution of requirements and the resulting impact on cost and schedule baselines.  More development was required than initially anticipated, since COTS products did not fully meet the program requirements.  Additionally, information security (INFOSEC) requirements were not well defined in the operational requirements document, resulting in a later cost increase.

For the STARS, OASIS, and AMASS programs, the primary driver for requirements changes was human factors requirements that were not subjected to the appropriate level of analysis during the planning, design, and development stages.  See the discussion of human factors below for more details.  Additionally, the STARS program encountered new requirements in several additional areas ranging from site adaptation to conversion of remote towers to Terminal Radar Approach Control Facilities (TRACONs).  The OASIS program experienced increased costs due to a requirement to purchase additional hardware.  AMASS program costs increased due to revised requirements for initial lay-in of spare parts at both the depot and site levels.

Due in part to the extreme technical complexity of the program, the WAAS program underestimated technical requirements, such as the need for redundancy in the system’s ground components.  The program also failed to document operational requirements, including the need to certify system software, contributing to increases in both cost and schedule baselines.

The addition of a new requirement for additional Automatic Dependent Surveillance way point reporting necessary to standardize procedures with other nations’ Civil Aviation Authorities caused a 10.5 percent variance in schedule for the Oceanic Program (BMN #001).  This added requirement was later deleted when contractor performance issues led the Automatic Dependent Surveillance to be deleted from the baseline, descoping Oceanic Build 1 to Early Drop.

The WARP program initially established requirements for organic maintenance of the system.  However, Congressional and FAA funding cuts led to an agreement with the contractor to reduce costs by eliminating the organic maintenance requirements.  Subsequently, the requirement was re-introduced into the program, increasing costs by $6.2 million.  Additionally, a new requirement was added to the program to add a Free Flight Phase I interface to the FAA Bulk Weather Telecommunications Gateway.  These additional requirements contributed to the cost and schedule variances experienced by the program.

- Human Factors Issues

For the STARS and OASIS programs, the human factors issues were not explored because the FAA had decided to adopt a policy of acquiring COTS/NDI systems whenever possible, and the agency assumed the risk associated with resolving at the time of deployment any deficiencies that existed in the solution provided by the market place.  Completion of the changes resulted in increases to both cost and schedule for both programs.

The AMASS program did not acquire a COTS/NDI system but still failed to explore early indications of human factors deficiencies.  The PT negotiated a set of required changes, and implementation of these changes resulted in increases to both cost and schedule.

The Common ARTS program encountered difficulties in the deployment phase resulting from deployment of a software “national release” that was not compatible with site-specific adaptations at a particular site.  When the software was introduced, unforeseen software glitches rendered the software unsuitable to the users, resulting in a schedule delay for the program while the fixes were completed.

3.  Unsuitable Acquisition Strategy

The AMASS program elected to pursue concurrent development and production phases, which resulted in a longer full scale development period with associated increased costs.  The strategy also contributed to problems as a result of operational testing, causing further delays.

The NIMS program chose to conduct business process reengineering and product acquisition  simultaneously, using a spiral development approach.  This approach greatly increased software development risks for the program and contributed to cost and schedule delays.

Both the STARS and OASIS programs chose to employ a COTS/NDI strategy, in keeping with the guidance in AMS.  However, the programs did not fully understand the implications and risks of a COTS/NDI strategy and did not take adequate measures to address those risks.  For example, the programs did not obtain field agreement that a commercially available system would be acceptable, nor did they correctly estimate the costs associated with COTS/NDI.  This led to significant cost and schedule delays for both programs.

4.  Unrealistic Baseline

For the WAAS program, the FAA elected to present unrealistic cost and schedule baselines, stating that program costs would be held to $500 million even though internal cost estimates projected much higher costs.  Subsequent cost estimates did not include the costs of leasing required for geostationary satellites.  Further, the program cost estimations did not use past performance criteria to refine the accuracy of the cost information.  The initial schedule was also unrealistic, since it included concurrent software development and system acceptance processes, which were not possible in practice.  The WAAS program experienced significant cost and schedule delays.

The original STARS program cost and schedule baseline was based on a COTS product, and the schedule estimate compressed an estimated 32 months of development and testing into 25 months.  When it became apparent that a COTS product would not meet the requirements, a new baseline was established.  However, according to PT  personnel, the subsequent schedule of first ORD by December 1998 was not changed, although the PT network logic schedules indicated that December 1999 would be a more realistic milestone.  The PT did not meet the December 1998 milestone.

In an effort to meet politically driven milestones, the AMASS program developed a schedule that presented concurrent development and production phases.  The schedule was unrealistic and resulted in significant cost and schedule increases (see above discussion on unsuitable acquisition strategy).

The NIMS program was the first to undergo an affordability analysis under AMS.  However, the assessment was forced to fit a predetermined funding level, reducing the total funding from $140 million to $108 million.  The performance baseline was not adjusted to reflect the reduced funding.  Thus, the baseline presented in the NIMS acquisition program baseline document was unrealistic and was soon breached.

5.  Inadequate Risk Assessment

Since WAAS was a pre-AMS program, an investment analysis was not initially performed.  The PT did not fully understand the technical, institutional, and programmatic risks involved with the program before the work began.  The investment analysis conducted when WAAS was rebaselined in January 1998 underestimated the risk of selecting another government agency to acquire the geo-stationary satellites.  This understatement of risks contributed to both cost and schedule variances.

The NIMS program underestimated the risks of several programmatic assumptions.  The program assumed that prototype NIMS software could be used directly for NIMS with changes, that operational control center (OCC) systems would not be fully integrated, and that a minimal level of security would be required.  The risks in making these assumptions were not independently assessed.  The assumptions proved to be unrealistic, resulting in cost and schedule variances.

Although these were the only documented cases of inadequate risk analysis per se, the two other programs that used a COTS/NDI strategy (STARS and OASIS) could also be placed in this category.  Neither program understood the risks of electing to acquire a COTS/NDI system to satisfy the requirements.

6.  Software Development Difficulties

The WARP program experienced delays in contractor development and integration of software that resulted in a four-month slip to the program.

The AMASS program experienced difficulties in software development that delayed the test schedule by seven months and increased program costs.

The STARS program experienced software development difficulties, including underestimation of the lines of code required to meet user requirements and difficulties in contractor staffing to meet project milestones.

The WAAS program experienced software development delays in both design and integration, which resulted in non-delivery of critical software, increasing cost and schedule.

7.  Poor Contractor Performance

The AMASS contractor failed to meet full-scale development milestones due to software development and integration problems.  This inability to deliver resulted in deferment of the test schedule, resulting in cost increases and schedule delays for the program.

The Oceanic Build I program contractor was unable to deliver a key component of the system (automatic dependent surveillance), forcing the program to de-scope the requirements, removing the automatic dependent surveillance component from the performance and benefits baseline.  The result was a significant decrease in benefits and performance for the program.

The WARP and STARS program contractors experienced software development, integration, and testing difficulties.  Additionally, the STARS program contractor was initially unable to staff the project adequately, resulting in an inability to meet program milestones.

The initial WAAS program contractor failed to meet required milestones, resulting in a termination of the contract.  The project was awarded to a second contractor, which also experienced technical difficulties in software development and integration.

According to PT personnel, the Common ARTS contractor was insufficiently staffed to meet program milestones due to removal of key personnel to complete a bid on a larger FAA contract.  The resulting delays resulted in a restructuring of the contract from a cost-plus-fixed-fee to a firm-fixed-price, causing a schedule variance.

8.  Funding Instability

Internal Funding Instability.  The BUEC program purchased equipment to replace obsolete backup emergency communications equipment now installed in the field.  The equipment resides in warehouses; it will be removed and installed by FAA personnel as resources permit.  The program experienced significant FAA-imposed funding cuts in both FY98 and FY99, including a reduction from $17.7 million to $1.6 million in FY 99.  The equipment remains in storage; the warranty expires in 2006.

The NIMS program began the solution implementation phase with a $32.2 million shortfall imposed by the affordability assessment (see above discussion on unrealistic baselines).  In addition, the program experienced $13.6 million of internal cuts from FY 97–FY99.  These reductions, added to the external cuts that will b discussed below, contributed significantly to NIMS cost and schedule variances.

Three programs (OASIS, WARP, and STARS) experienced cost growth due to internally-imposed requirements to purchase equipment or services with the program’s F&E funds that were not originally intended to be a part of the program requirements.  These requirements arose because of funding shortfalls in both F&E and O&M accounts.  These three were the only documented cases of this problem from our review.  However, during the interviews, several additional PTs expressed concerns about this issue and indicated that additional impacts may be expected in the future.

The OASIS program variance was caused in part by the additional requirement to replace flight service station consoles.  BMN #035 reported a variance of $15.8 million to replace flight service automated system consoles “that were designed with little or no regard for human factors.  The flight service station console human interface requirements are not part of the OASIS baseline.”  Replacing instead of modifying existing consoles caused a variance to the OASIS F&E costs.

According to BMN #056, the WARP program experienced a $16.8 million cost growth stemming from a requirement “to accommodate telecommunications funding shortfall due to O&M funding reduction in FY99 and beyond.”

The STARS program currently faces an issue in which facility upgrade funds may be allocated to the STARS program due to F&E funding instability in the NAS Transition and Implementation Directorate (ANS).  Many of these upgrades are required completely independently of the STARS program requirements.  If these additional requirements are incorporated into the baseline, STARS costs will increase significantly.

External Funding Instability.  The BUEC program, already discussed above, suffered a $2.92 million cut from Congress in FY00 that increased the program’s inability to maintain its schedule.

In addition to the internal reductions mentioned above, the NIMS program experienced $12.7 million in Congressional cuts from FY98–FY00, and a $14.2 million cut from OMB in FY00.

Congress reduced the OASIS program funding by $11.5 million in FY00.  The program, rebaselined for other reasons in May 1999, will return to the JRC to request another rebaselining action.  The PT does not believe it can operate under the current APB due to this large funding reduction.

The WAAS program has experienced several large external funding cuts, including a substantial Congressional reduction in FY00.  These reductions were at least partially the result of the FAA’s failure to meet Congressional deadlines for reporting.

9.  Interdependencies

The WARP program experienced variances as a result of interdependencies with several FAA programs, including delays in Next Generation Weather Radar (NEXRAD) testing, unavailability of the Display System Replacement interface for testing, and National Airspace Data Interchange Network (NADIN) telecommunications performance issues.  The NADIN system could not accommodate the WARP bandwidth requirements, and the subsequent redesign caused a schedule delay and a cost increase for the WARP program.

The Oceanic Build 1 program experienced a 16.3 percent schedule variance due to resource issues at field facilities.  The New York Air Route Traffic Control Center lacked sufficient time and resources to support the target date for Initial Operating Capability, due to higher priorities for Host and Oceanic Computer System Replacement (HOCSR) and Display System Replacement implementation.

# Appendix B—Reports Addressing Baseline Issues

During the course of our evaluation, we noted numerous reports that addressed baseline and related issues.  These reports are listed below.

| Source | Report Title | Report Date | Report Number |
| --- | --- | --- | --- |
| ACM-10 | Evaluation of FAA Acquisition Reform, The First Year: April 1996-March 1997 | May-97 | N/A |
| ACM-10 | Evaluation of FAA Acquisition Reform, The First Two Years: April 1996-March 1998 | May-98 | 1998-01 |
| ACM-10 | Evaluation of FAA Acquisition Reform, The First Three Years: April 1996-March 1999 | May-99 | 1999-04 |
| ACM-10 | FAA Acquisition Program Baseline Stability: Comparison Between Growth Rates for Programs Conducted Prior to Acquisition Reform and Those Conducted Under Acquisition Reform | Sep-99 | 1999-05 |
| ASD-300 | Baseline Management Variance Report April 1998 | Apr-98 | N/A |
| ASD-300 | Baseline Management Variance Report December 1998 | Dec-99 | N/A |
| ASD-300 | Baseline Management Variance Report June 1999 | Jun-99 | N/A |
| ASD-300 | Baseline Management Variance Report November 1999 | Nov-99 | N/A |
| ASU-100 | Effectiveness of COTS Solutions | Feb-99 | N/A |
| Booz-Allen & Hamilton | Independent Assessment of the FAA’s Acquisition Management System | Sep-97 | N/A |
| Booz-Allen & Hamilton | Independent Assessment of the Federal Aviation Administration's Acquisition Management System | Jul-99 | N/A |
| Customer Service Process Team | Common ARTS Customer Service: Findings from FAA Field Personnel Interviews | Sep-99 | N/A |
| DOT OIG | FAA’s Standard Terminal Automation Replacement System (STARS) | Nov-97 | AV-1998-012 |
| DOT OIG | Air Traffic Control Modernization | Mar-98 | AV-1998-089 |
| DOT OIG | Wide Area Augmentation System | May-98 | AV-1998-117 |
| DOT OIG | FAA Financing and Cost Control | Mar-99 | AV-1999-066 |
| DOT OIG | Air Traffic Control Modernization | Mar-99 | AV-1999-065 |
| FAA Internal Report - ASU-1 | Acquisition Management System (AMS) Schedule and Cost Performance | Sep-99 | N/A |
| FAA Internal Report - STARS Human Factors Process Group | STARS Human Factors Management Process | Dec-97 | N/A |
| FAA Internal Report - STARS Human Factors Steering Committee | The Management of Human Factors in FAA Acquisition Programs | Mar-98 | N/A |
| GAO | DOT’s Budget-Management and Performance Issues Facing the Department in Fiscal Year 1999 | Feb-88 | T-RCED- AIMD-98-76 |
| GAO | National Airspace System-Comprehensive FAA Plan for Global Positioning System is Needed | May-95 | RCED-95-26 |
| GAO | DOT’s Budget-Challenges Facing the Department in Fiscal Year 1997 and Beyond | Mar-96 | N/A |
| GAO | Aviation Acquisition-A Comprehensive Strategy is Needed for Cultural Change at FAA | Aug-96 | RCED-96-159 |
| GAO | Air Traffic Control-Improved Cost Information Needed to Make Billion Dollar Modernization Investment Decisions | Jan-97 | AIMD-97-20 |
| GAO | Air Traffic Control – Immature Software Acquisition Processes Increase FAA System Acquisition Risks | Mar-97 | AIMD-97-47 |
| GAO | National Airspace System-Observations on the Wide Area Augmentation System | Oct-97 | T-RCED-98-12 |
| GAO | Air Traffic Control-Observations on FAA’s Modernization Program | Feb-98 | T-RCED- AIMD-98-93 |
| GAO | Air Traffic Control-Evolution and Status of FAA’s Automation Program | Mar-98 | T-RCED- AIMD-98-85 |
| GAO | National Airspace System-Status of Wide Area Augmentation System Project | Apr-98 | RCED-98-79 |
| GAO | Air Traffic Control – Status of FAA’s Modernization Program | Dec-98 | RCED-99-25 |
| GAO | Air Traffic Control – FAA’s Modernization Investment Management Approach Could Be Strengthened | Apr-99 | RCED-99-98 |
| National Civil Aviation Review Commission | Avoiding Aviation Gridlock and Reducing the Accident Rate-A Consensus for Change | Dec-97 | N/A |

# Appendix C—Acronyms

ACM			FAA’s NAS Configuration Management and Evaluation Staff

AMASS		Airport Movement Area Safety System

AMS			Acquisition Management System

APB			Acquisition Program Baseline

ARA			FAA’s Office of Research and Acquisitions

ASU			FAA’s Office of Acquisitions

ATS			FAA’s Office of Air Traffic Services

BMN			Baseline Management Notice

BUEC			Backup Emergency Communications

CAS			Commercially Available Software

CIP			Capital Investment Plan

Common ARTS	Common Automated Radar Terminal System

COTS/NDI		Commercial Off-The-Shelf/Non-Developmental Item

DOT OIG		Department of Transportation Office of Inspector General

FAA			Federal Aviation Administration

FY			Fiscal Year

F&E			Facilities and Equipment

GAO			General Accounting Office

I-BEAM		Integrated Baseline Establishment and Management

IPT			Integrated Product Team

JRC			Joint Resources Council

NAS			National Airspace System

NEXCOM		Next Generation Air/Ground Communication System

NIMS			NAS Infrastructure Management System

O&M			Operations and Maintenance

OASIS			Operational and Supportability Implementation System

OMB			Office of Management and Budget

ORD			Operational Readiness Demonstration

PT			Product Team

R,E&D		Research, Engineering, and Development

SEOAT		Systems Engineering/Operational Analysis Team

SPIRE			Simplified Program Information Reporting and Evaluation

STARS		Standard Terminal Automated Replacement System

WAAS			Wide Area Augmentation System

WARP			Weather and Radar Processor

# Footnotes

In December 1999, the PT determined that the cost variance was 146.76%.

These programs were the Low-Level Windshear Alert System (LLWAS), the Airport Surveillance Radar (ASR-11) program, the Voice Recorder Replacement Program (VRRP), the Airport Surface Detection Equipment (ASDE) program, and the Next Generation Air-Ground Communication System (NEXCOM).

Note that our sample lists seven pre-AMS programs with variances.  One of these, Weather and Radar Processor (WARP), was not included in the June 1999 Variance Report.  The WARP variance was reported in SPIRE in July 1999.

The sample of 10 programs includes one additional program that reported a variance in July 1999.

Although 42 programs resided in the FAA tracking system, only 34 were reporting on a monthly basis at the time of this evaluation.

This issue is closely related to human factors issues.  Several of the programs experienced both of these problems.

These programs did complete a Cost Benefit Analysis.

Some FAA internal sources have recognized these risks.  See “A Risk Management Approach for COTS/CAS Based Air Traffic Control Systems Acquisition and Sustainment.”  Presentation for National Aeronautics and Space Administration  2nd Annual Workshop on Risk Management,  October 28, 1999.

Immature Software Acquisition Processes Increase FAA System Acquisition Risks, GAO/AIMD-97-47, March 1997.

In some, cases, program funding was deferred until later years.  These deferrals did not change the program’s estimate at completion but still affected both cost and schedule.

Note that five programs are affected by internal and four by external funding problems.  However, several of these programs overlap, creating a total of six affected by funding overall.

For example, see GAO Report RCED-96-159, A Comprehensive Strategy for Culture Change is Needed at FAA, August 1996; National Civil Aviation Review Commission, Avoiding Aviation Gridlock and Reducing the Accident Rate-A Consensus for Change, December 1997; GAO Report RCED-99-25, December 1998; STARS Human Factors Process Group, STARS Human Factors Management Process, December 8, 1997; and STARS Human Factors Steering Committee, The Management of Human Factors in FAA Acquisition Programs, March 31, 1998.

See GAO Report RCED-96-159 and The Management of Human Factors in FAA Acquisition Programs for further evidence about this problem.

The OASIS program has requested a second rebaseline as a result of Congressional budget cuts.

This is the APB from which the agency is tracking WAAS costs.  However, the original WAAS baseline was defined in 1994.

Rebaseline was approved by the JRC pending final cost estimates.

These variances are documented in the November 1999 Baseline Management Variance Report, and include changes to the LLWAS, ASR-11, VRRP, and ASDE programs.

The report, dated June 1999, was prepared for the FAA by Booz-Allen & Hamilton, Inc.

GAO Report: DOT’s Budget Management and Performance Issues Facing the Department in Fiscal Year 1999, T-RCED/AIMD-98-76, February 12, 1998.  We also confirmed the accuracy of this statement with program personnel.

In FY00, the program was cut by Congress for the first time.  See discussion on external cuts below.

According to the PT, this decision is awaiting more concrete estimates of STARS operations costs.

This information was initially gleaned from PT personnel, and was confirmed by Congressional language.

# Text boxes

PS—Parameter Sheet

APB—Acquisition Program Baseline