FEDERAL COMMITTEE FOR METEOROLOGICAL

SERVICES AND SUPPORTING RESEARCH (FCMSSR)

WORKING GROUP FOR URBAN METEOROLOGY (WG/UM)

JOINT ACTION GROUP FOR JOINT URBAN TEST BEDS (JAG/JUTB)

Meeting 2007-5

Final Record of Actions

June 27, 2007

Attendees:

| Dr. Walter Bach, Jr. | Cochair | DOD/USA/AMSRD-ARL-RO-EN |
| --- | --- | --- |
| Lt Col David Andrus, USAF | Executive Secretary | OFCM |
| Mr. Mark Evangelista | Member | EPA |
| Mr. Kurt Nelson | Alternate | DOD/Navy/N7CTB |

- Welcoming/Administrative Remarks.  Dr. Walter Bach, Jr., provided introductory remarks, and started the meeting.  The goal of this meeting is to work together to better develop an operational concept document for JUTB.

- The draft ROA for the last meeting was approved.

- Action Item Update

  - Action Item 07-2.1.  Dr. Bach will review the Urban Forum report for identification of user needs.  Open.

    - 24 Apr 07.  Dr. Bach continues to work on this.

    - 6 Jun 07.  No update.

    - 27 Jun 07.  No update.

  - Action Item 07-2.2.  Dr. Garvey will review the 2003 NRC report entitled "Tracking and Predicting the Atmospheric Dispersion of Hazardous Material Releases" and will document user needs and requirements identified therein.  Open.

    - 24 Apr 07.  Dr. Garvey continues to work on this.

    - 6 Jun 07.  Dr. Garvey was unable to attend this meeting.

    - 27 Jun 07.  No update.

  - Action item 07-3.2.  Mr. Pendergrass will provide the JAG with a list of users who pull Urbanet data.  Open.

    - 6 Jun 07.  Mr. Pendergrass was unable to attend meeting.  No update.

    - 27 Jun 07.  No update.

  - Action item 07-3.3.  Mr. Pendergrass will provide the JAG with a straw man of “local scale” considerations.  Open.

    - 6 Jun 07.  Mr. Pendergrass was unable to attend meeting.

    - 27 Jun 07.  No update.

  - Action item 07-3.4.  Mr. Pendergrass will develop a portion of the JUTB concept document based upon NWS components, which addresses the first few lines of paragraph 2.e. in our Terms of Reference.  Open.

    - 6 Jun 07.  Mr. Pendergrass was unable to attend meeting. No update.

    - 27 Jun 07.  No update.

  - Action item 07-3.5.  Dr. Garvey will examine existing test beds throughout the world and will report on how we can build upon their successes.  Open.

    - 6 Jun 07.  Dr. Garvey was unable to attend meeting.  No update

    - 27 Jun 07.  No Update.

  - Action item 07-4.2.  GMU AT&D Conference.  Dr. Bach will provide an overview of the JUTB effort; past, present, and future.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.3.  GMU AT&D Conference.  Mr. Pendergrass will provide a briefing on Urbanet.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.4.  GMU AT&D Conference.  Jason Ching will provide information on the National Urban Database and Portal Tool.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.5.  GMU AT&D Conference.  Mr. Miller will provide a briefing which will cover work on a chemical preparedness tool.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.6.  GMU AT&D Conference.  Dr. Jasinski will provide a briefing on current and planned remote sensing capabilities, with an emphasis on those appropriate for urban environments.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.7.  GMU AT&D Conference.  Mr. Evangelista will not be able to attend, but will provide a briefing for someone else to give.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.8.  GMU AT&D Conference.  Ms. Nandi will consider providing a briefing.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.9.  GMU AT&D Conference.  Mr. Matthews will consider providing a briefing.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.10.  GMU AT&D Conference.  Dr. Bach will engage DTRA representatives regarding a briefing.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.11.  GMU AT&D Conference.  Dr. Bach will engage Dr. Garvey regarding a briefing.

    - 27 Jun 07.  Preparations for the conference have been made.  Closed.

  - Action item 07-4.12.  Dr. Bach requested that all JUTB participants review the latest operational concept documents, available at http://www.ofcm.gov/jag-jutb/meetings.htm, and provide input.  Open.

    - 27 Jun 07.  Lt Col Andrus will make the document available on Google Documents for JAG JUTB participant review and collaboration.

    - 27 Jun 07.  This was made available on Google Documents.  JAG JUTB participant review and collaboration is still needed.

  - Action item 07-4.13.  Mr. Matthews will investigate his potential future involvement with this JAG and will provide information on how his work is prioritized.  Open.

    - 27 Jun 07.  No update.

  - Action item 07-4.14.  Dr. Bach will further develop a section of the operational concept document within the next couple of weeks and this will be provided to the JAG for feedback prior to the next JUTB meeting.

    - 27 Jun 07.  Dr. Bach drafted up the management section and the selection process sections.  Both have now been incorporated into the operational concept document and are available for review and collaboration on Google Documents.  Closed.

- Discussion.

  - The JAG discussed participation in the GMU AT&D conference 10-12 July 2007.  OFCM has a 2-hour block of time.  Plans are fully developed.

  - The draft operational concept document was reviewed.  No changes were made.  The latest draft version is available at Google Documents.  A link can be obtained by contacting Lt Col Andrus, Dr. Bach, or Mr. Pendergrass.

- New Action Items: None

- Next Meeting:  The next meeting is tentatively planned for 17 July 2007 from 1:00 PM to 3:00 PM EDT at OFCM to further develop the operational concept document.