## Main
Type
Station Name | Site ID | Region |  | Legacy System | Tentative Decomm. Date | Target install date (D-Day | Site receives and installs RWS | Site receives and installs Operator Training Material | Initial telecon briefing to provide overview | WFO receives Site Installation Plan, Deployment Plan & Disposal Plan | Site returns Ops Immediate data via FAX | Site provides comments against SIP | Second telecon briefing to review SIP comments | Site receives GPS repeater FMK | Site receives final SIP | Final telecon briefing | GPS repeater FMK installed | AWIPS Admin Note 15 completed | Training Telecon | Operators complete computer based training material | El Tech completes RRS Maint. Couse at NWSTC | Site MIC proposes tentative decommis-sioning date | Site Receives NLSC shipments | Site receives required permits | Required electrical and ground work completed | Final Site Readiness Telecon | Operator Training Cert signed | ART decommissioning checklist signed | Site completes and returns Facilities Readiness Cert | Site receives TRS | Site disassembles ART
[7 empty] | 115 | 115 | 110 | 105 | 100 | 90 | 85 | 85 | 80 | 70 | 45 | 45 | 45 | 30 | 30 | 30 | 25 | 25 | 25 | 20 | 20 | 15 | 15 | 7 | 3
OAT GROUP
Sterling | LWX | ER | OAT | ART-2 | 2005-07-29 | 2005-07-25 | 2005-04-01 | 2005-04-01 | 2005-04-06 | 2005-04-11 | 2005-04-16 | 2005-04-26 | 2005-05-01 | 2005-05-01 | 2005-05-06 | 2005-05-16 | 2005-06-10 | 2005-06-10 | 2005-06-10 | 2005-06-25 | 2005-06-25 | 2005-06-25 | 2005-06-30 | 2005-06-30 | 2005-06-30 | 2005-07-05 | 2005-07-05 | 2005-07-10 | 2005-07-10 | 2005-07-18 | 2005-07-22
Chanhassen | MPX | CR | OAT | ART-2 | 2005-08-18 | 2005-08-22 | 2005-04-29 | 2005-04-29 | 2005-05-04 | 2005-05-09 | 2005-05-14 | 2005-05-24 | 2005-05-29 | 2005-05-29 | 2005-06-03 | 2005-06-13 | 2005-07-08 | 2005-07-08 | 2005-07-08 | 2005-07-23 | 2005-07-23 | 2005-07-23 | 2005-07-28 | 2005-07-28 | 2005-07-28 | 2005-08-02 | 2005-08-02 | 2005-08-07 | 2005-08-07 | 2005-08-15 | 2005-08-19
Salt Lake City | SLC | WR | OAT | ART-2 | 2005-09-21 | 2005-09-12 | 2005-05-20 | 2005-05-20 | 2005-05-25 | 2005-05-30 | 2005-06-04 | 2005-06-14 | 2005-06-19 | 2005-06-19 | 2005-06-24 | 2005-07-04 | 2005-07-29 | 2005-07-29 | 2005-07-29 | 2005-08-13 | 2005-08-13 | 2005-08-13 | 2005-08-18 | 2005-08-18 | 2005-08-18 | 2005-08-23 | 2005-08-23 | 2005-08-28 | 2005-08-28 | 2005-09-05 | 2005-09-09
Corpus Christi | CRP | SR | OAT | ART-2 | 2005-09-24 | 2005-09-26 | 2005-06-03 | 2005-06-03 | 2005-06-08 | 2005-06-13 | 2005-06-18 | 2005-06-28 | 2005-07-03 | 2005-07-03 | 2005-07-08 | 2005-07-18 | 2005-08-12 | 2005-08-12 | 2005-08-12 | 2005-08-27 | 2005-08-27 | 2005-08-27 | 2005-09-01 | 2005-09-01 | 2005-09-01 | 2005-09-06 | 2005-09-06 | 2005-09-11 | 2005-09-11 | 2005-09-19 | 2005-09-23
FIRST GROUP
Tallahassee, Fl | TAE | SR |  | ART-1 |  | 2006-03-06 | 2005-11-11 | 2005-11-11 | 2005-11-16 | 2005-11-21 | 2005-11-26 | 2005-12-06 | 2005-12-11 | 2005-12-11 | 2005-12-16 | 2005-12-26 | 2006-01-20 | 2006-01-20 | 2006-01-20 | 2006-02-04 | 2006-02-04 | 2006-02-04 | 2006-02-09 | 2006-02-09 | 2006-02-09 | 2006-02-14 | 2006-02-14 | 2006-02-19 | 2006-02-19 | 2006-02-27 | 2006-03-03
Lake Charles,LA | LCH | SR |  | ART-2 |  | 2006-03-20 | 2005-11-25 | 2005-11-25 | 2005-11-30 | 2005-12-05 | 2005-12-10 | 2005-12-20 | 2005-12-25 | 2005-12-25 | 2005-12-30 | 2006-01-09 | 2006-02-03 | 2006-02-03 | 2006-02-03 | 2006-02-18 | 2006-02-18 | 2006-02-18 | 2006-02-23 | 2006-02-23 | 2006-02-23 | 2006-02-28 | 2006-02-28 | 2006-03-05 | 2006-03-05 | 2006-03-13 | 2006-03-17
Shreeveport,LA | SHV | SR |  | ART-1 |  | 2006-04-03 | 2005-12-09 | 2005-12-09 | 2005-12-14 | 2005-12-19 | 2005-12-24 | 2006-01-03 | 2006-01-08 | 2006-01-08 | 2006-01-13 | 2006-01-23 | 2006-02-17 | 2006-02-17 | 2006-02-17 | 2006-03-04 | 2006-03-04 | 2006-03-04 | 2006-03-09 | 2006-03-09 | 2006-03-09 | 2006-03-14 | 2006-03-14 | 2006-03-19 | 2006-03-19 | 2006-03-27 | 2006-03-31
Midland,TX | MAF | SR |  | ART-2 |  | 2006-04-17 | 2005-12-23 | 2005-12-23 | 2005-12-28 | 2006-01-02 | 2006-01-07 | 2006-01-17 | 2006-01-22 | 2006-01-22 | 2006-01-27 | 2006-02-06 | 2006-03-03 | 2006-03-03 | 2006-03-03 | 2006-03-18 | 2006-03-18 | 2006-03-18 | 2006-03-23 | 2006-03-23 | 2006-03-23 | 2006-03-28 | 2006-03-28 | 2006-04-02 | 2006-04-02 | 2006-04-10 | 2006-04-14
Amarillo, TX | AMA | SR |  | ART-1 |  | 2006-05-01 | 2006-01-06 | 2006-01-06 | 2006-01-11 | 2006-01-16 | 2006-01-21 | 2006-01-31 | 2006-02-05 | 2006-02-05 | 2006-02-10 | 2006-02-20 | 2006-03-17 | 2006-03-17 | 2006-03-17 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2006-04-06 | 2006-04-06 | 2006-04-06 | 2006-04-11 | 2006-04-11 | 2006-04-16 | 2006-04-16 | 2006-04-24 | 2006-04-28
Spokane,WA | OTX | WR |  | ART-1 |  | 2006-05-15 | 2006-01-20 | 2006-01-20 | 2006-01-25 | 2006-01-30 | 2006-02-04 | 2006-02-14 | 2006-02-19 | 2006-02-19 | 2006-02-24 | 2006-03-06 | 2006-03-31 | 2006-03-31 | 2006-03-31 | 2006-04-15 | 2006-04-15 | 2006-04-15 | 2006-04-20 | 2006-04-20 | 2006-04-20 | 2006-04-25 | 2006-04-25 | 2006-04-30 | 2006-04-30 | 2006-05-08 | 2006-05-12
Flagstaff, AR | FGZ | WR |  | ART-2 |  | 2006-06-12 | 2006-02-17 | 2006-02-17 | 2006-02-22 | 2006-02-27 | 2006-03-04 | 2006-03-14 | 2006-03-19 | 2006-03-19 | 2006-03-24 | 2006-04-03 | 2006-04-28 | 2006-04-28 | 2006-04-28 | 2006-05-13 | 2006-05-13 | 2006-05-13 | 2006-05-18 | 2006-05-18 | 2006-05-18 | 2006-05-23 | 2006-05-23 | 2006-05-28 | 2006-05-28 | 2006-06-05 | 2006-06-09
Reno, NV | REV | WR |  | ART-2 |  | 2006-06-26 | 2006-03-03 | 2006-03-03 | 2006-03-08 | 2006-03-13 | 2006-03-18 | 2006-03-28 | 2006-04-02 | 2006-04-02 | 2006-04-07 | 2006-04-17 | 2006-05-12 | 2006-05-12 | 2006-05-12 | 2006-05-27 | 2006-05-27 | 2006-05-27 | 2006-06-01 | 2006-06-01 | 2006-06-01 | 2006-06-06 | 2006-06-06 | 2006-06-11 | 2006-06-11 | 2006-06-19 | 2006-06-23
SECOND GROUP
Rapid City,SD | UNR | CR |  | ART-2 |  | 2006-07-17 | 2006-03-24 | 2006-03-24 | 2006-03-29 | 2006-04-03 | 2006-04-08 | 2006-04-18 | 2006-04-23 | 2006-04-23 | 2006-04-28 | 2006-05-08 | 2006-06-02 | 2006-06-02 | 2006-06-02 | 2006-06-17 | 2006-06-17 | 2006-06-17 | 2006-06-22 | 2006-06-22 | 2006-06-22 | 2006-06-27 | 2006-06-27 | 2006-07-02 | 2006-07-02 | 2006-07-10 | 2006-07-14
Aberdeen,SD | ABR | CR |  | ART-2 |  | 2006-07-31 | 2006-04-07 | 2006-04-07 | 2006-04-12 | 2006-04-17 | 2006-04-22 | 2006-05-02 | 2006-05-07 | 2006-05-07 | 2006-05-12 | 2006-05-22 | 2006-06-16 | 2006-06-16 | 2006-06-16 | 2006-07-01 | 2006-07-01 | 2006-07-01 | 2006-07-06 | 2006-07-06 | 2006-07-06 | 2006-07-11 | 2006-07-11 | 2006-07-16 | 2006-07-16 | 2006-07-24 | 2006-07-28
Bismarck, ND | BIS | CR |  | ART-2 |  | 2006-08-14 | 2006-04-21 | 2006-04-21 | 2006-04-26 | 2006-05-01 | 2006-05-06 | 2006-05-16 | 2006-05-21 | 2006-05-21 | 2006-05-26 | 2006-06-05 | 2006-06-30 | 2006-06-30 | 2006-06-30 | 2006-07-15 | 2006-07-15 | 2006-07-15 | 2006-07-20 | 2006-07-20 | 2006-07-20 | 2006-07-25 | 2006-07-25 | 2006-07-30 | 2006-07-30 | 2006-08-07 | 2006-08-11
Riverton, WY | RIW | CR |  | ART-2 |  | 2006-08-28 | 2006-05-05 | 2006-05-05 | 2006-05-10 | 2006-05-15 | 2006-05-20 | 2006-05-30 | 2006-06-04 | 2006-06-04 | 2006-06-09 | 2006-06-19 | 2006-07-14 | 2006-07-14 | 2006-07-14 | 2006-07-29 | 2006-07-29 | 2006-07-29 | 2006-08-03 | 2006-08-03 | 2006-08-03 | 2006-08-08 | 2006-08-08 | 2006-08-13 | 2006-08-13 | 2006-08-21 | 2006-08-25
Grand Junction, CO | GJT | CR |  | ART-2 |  | 2006-09-11 | 2006-05-19 | 2006-05-19 | 2006-05-24 | 2006-05-29 | 2006-06-03 | 2006-06-13 | 2006-06-18 | 2006-06-18 | 2006-06-23 | 2006-07-03 | 2006-07-28 | 2006-07-28 | 2006-07-28 | 2006-08-12 | 2006-08-12 | 2006-08-12 | 2006-08-17 | 2006-08-17 | 2006-08-17 | 2006-08-22 | 2006-08-22 | 2006-08-27 | 2006-08-27 | 2006-09-04 | 2006-09-08
Gray, ME | GYX | ER |  | ART-2 |  | 2006-09-25 | 2006-06-02 | 2006-06-02 | 2006-06-07 | 2006-06-12 | 2006-06-17 | 2006-06-27 | 2006-07-02 | 2006-07-02 | 2006-07-07 | 2006-07-17 | 2006-08-11 | 2006-08-11 | 2006-08-11 | 2006-08-26 | 2006-08-26 | 2006-08-26 | 2006-08-31 | 2006-08-31 | 2006-08-31 | 2006-09-05 | 2006-09-05 | 2006-09-10 | 2006-09-10 | 2006-09-18 | 2006-09-22
Buffalo, NY | BUF | ER |  | ART-2 |  | 2006-10-09 | 2006-06-16 | 2006-06-16 | 2006-06-21 | 2006-06-26 | 2006-07-01 | 2006-07-11 | 2006-07-16 | 2006-07-16 | 2006-07-21 | 2006-07-31 | 2006-08-25 | 2006-08-25 | 2006-08-25 | 2006-09-09 | 2006-09-09 | 2006-09-09 | 2006-09-14 | 2006-09-14 | 2006-09-14 | 2006-09-19 | 2006-09-19 | 2006-09-24 | 2006-09-24 | 2006-10-02 | 2006-10-06
Boise, ID | BOI | WR |  | ART-2 |  | 2006-10-23 | 2006-06-30 | 2006-06-30 | 2006-07-05 | 2006-07-10 | 2006-07-15 | 2006-07-25 | 2006-07-30 | 2006-07-30 | 2006-08-04 | 2006-08-14 | 2006-09-08 | 2006-09-08 | 2006-09-08 | 2006-09-23 | 2006-09-23 | 2006-09-23 | 2006-09-28 | 2006-09-28 | 2006-09-28 | 2006-10-03 | 2006-10-03 | 2006-10-08 | 2006-10-08 | 2006-10-16 | 2006-10-20
Norman, OK | OUN | SR |  | None |  | 2006-11-06 | 2006-07-14 | 2006-07-14 | 2006-07-19 | 2006-07-24 | 2006-07-29 | 2006-08-08 | 2006-08-13 | 2006-08-13 | 2006-08-18 | 2006-08-28 | 2006-09-22 | 2006-09-22 | 2006-09-22 | 2006-10-07 | 2006-10-07 | 2006-10-07 | 2006-10-12 | 2006-10-12 | 2006-10-12 | 2006-10-17 | 2006-10-17 | 2006-10-22 | 2006-10-22 | 2006-10-30 | 2006-11-03
Formulas:
Site receives and installs RWS = [Target install date (D-Day]-H3
Site returns Ops Immediate data via FAX = [Target install date (D-Day]-L3
Site provides comments against SIP = [Target install date (D-Day]-M3
Site receives GPS repeater FMK = [Target install date (D-Day]-O3
Site receives final SIP = [Target install date (D-Day]-P3
Final telecon briefing = [Target install date (D-Day]-Q3
GPS repeater FMK installed = [Target install date (D-Day]-R3
AWIPS Admin Note 15 completed = [Target install date (D-Day]-S3
Training Telecon = [Target install date (D-Day]-T3
Site Receives NLSC shipments = [Target install date (D-Day]-X3
Site receives required permits = [Target install date (D-Day]-Y3
Final Site Readiness Telecon = [Target install date (D-Day]-AA3
Operator Training Cert signed = [Target install date (D-Day]-AB3
ART decommissioning checklist signed = [Target install date (D-Day]-AC3
Site receives TRS = [Target install date (D-Day]-AE3
Site disassembles ART = [Target install date (D-Day]-AF3

## HQ Dates
Station Name | Site ID | Target install date (D-Day | Ship Training Material and RWS and send first e-mail | Confirm Site Received RWS and Training Materials | Schedule First Telecon | Hold first Telecon and Ship Plans | Issue general info. Request e-mail | Ops-Immed Response Due | All Plan Comments Received and General Info/Photos received | Issue GPS repeater kit J700-2A4-KIT & 2A4MP2 | Request 7460 | Send Ops Immed to IMET | Schedule Second Telecon | Hold Second Telecon | Send Final SIP | Schedule Final Telecon | Hold Final Telecon | Permit reminder | Notify Debbie Pickerign | Schedule Training Telecon | Hold Training Telecon | Prelim. Decomm. Date Due | All Gov Permits Due | Exchange encription Keys, Record PWs | Issue NLSC Kits (Tools, Radome GPS, Sondes, RWS Cables,SPS etc.) | Notify NLSC for LRU Containers | Notify target backup sites of pending installation and products | Schedule Site Readiness Telecon | Site Readiness Telecon | Facilities Checklist Due | Site Decomm. Checklist Due | Distance Learning Cert Due | Notify Maint and Logistics of pending Installation | Get current RRS Software & Ghost CD | Issue Hotline request to access FTP server | Notify NCDC and NCEP that RWS install is pending
|  |  | 120 | 115 | 115 | 110 | 105 | 100 | 90 | 90 | 90 | 90 | 90 | 85 | 75 | 75 | 70 | 60 | 60 | 50 | 45 | 30 | 30 | 30 | 30 | 21 | 21 | 20 | 15 | 15 | 15 | 15 | 10 | 10 | 5 | 5
SAMPLE | xxx | 2005-01-01 | 2004-09-03 | 2004-09-08 | 2004-09-08 | 2004-09-13 | 2004-09-18 | 2004-09-23 | 2004-10-03 | 2004-10-03 | 2004-10-03 | 2004-10-03 | 2004-10-03 | 2004-10-08 | 2004-10-18 | 2004-10-18 | 2004-10-23 | 2004-11-02 | 2004-11-02 | 2004-11-12 | 2004-11-17 | 2004-12-02 | 2004-12-02 | 2004-12-02 | 2004-12-02 | 2004-12-11 | 2004-12-11 | 2004-12-12 | 2004-12-17 | 2004-12-17 | 2004-12-17 | 2004-12-17 | 2004-12-22 | 2004-12-22 | 2004-12-27 | 2004-12-27
|  |  | -120 | -115 | -115 | -110 | -105 | -100 | -90 | -90 | -90 | -90 | -90 | -85 | -75 | -75 | -70 | -60 | -60 | -50 | -45 | -30 | -30 | -30 | -30 | -21 | -21 | -20 | -15 | -15 | -15 | -15 | -10 | -10 | -5 | -5
Sterling | LWX | 2005-07-25 | 2005-03-27 | 2005-04-01 | 2005-04-01 | 2005-04-06 | 2005-04-11 | 2005-04-16 | 2005-04-26 | 2005-04-26 | 2005-04-26 | 2005-04-26 | 2005-04-26 | 2005-05-01 | 2005-05-11 | 2005-05-11 | 2005-05-16 | 2005-05-26 | 2005-05-26 | 2005-06-05 | 2005-06-10 | 2005-06-25 | 2005-06-25 | 2005-06-25 | 2005-06-25 | 2005-07-04 | 2005-07-04 | 2005-07-05 | 2005-07-10 | 2005-07-10 | 2005-07-10 | 2005-07-10 | 2005-07-15 | 2005-07-15 | 2005-07-20 | 2005-07-20
Chanhassen | MPX | 2005-08-22 | 2005-04-24 | 2005-04-29 | 2005-04-29 | 2005-05-04 | 2005-05-09 | 2005-05-14 | 2005-05-24 | 2005-05-24 | 2005-05-24 | 2005-05-24 | 2005-05-24 | 2005-05-29 | 2005-06-08 | 2005-06-08 | 2005-06-13 | 2005-06-23 | 2005-06-23 | 2005-07-03 | 2005-07-08 | 2005-07-23 | 2005-07-23 | 2005-07-23 | 2005-07-23 | 2005-08-01 | 2005-08-01 | 2005-08-02 | 2005-08-07 | 2005-08-07 | 2005-08-07 | 2005-08-07 | 2005-08-12 | 2005-08-12 | 2005-08-17 | 2005-08-17
Salt Lake City | SLC | 2005-09-12 | 2005-05-15 | 2005-05-20 | 2005-05-20 | 2005-05-25 | 2005-05-30 | 2005-06-04 | 2005-06-14 | 2005-06-14 | 2005-06-14 | 2005-06-14 | 2005-06-14 | 2005-06-19 | 2005-06-29 | 2005-06-29 | 2005-07-04 | 2005-07-14 | 2005-07-14 | 2005-07-24 | 2005-07-29 | 2005-08-13 | 2005-08-13 | 2005-08-13 | 2005-08-13 | 2005-08-22 | 2005-08-22 | 2005-08-23 | 2005-08-28 | 2005-08-28 | 2005-08-28 | 2005-08-28 | 2005-09-02 | 2005-09-02 | 2005-09-07 | 2005-09-07
Corpus Christi | CRP | 2005-09-26 | 2005-05-29 | 2005-06-03 | 2005-06-03 | 2005-06-08 | 2005-06-13 | 2005-06-18 | 2005-06-28 | 2005-06-28 | 2005-06-28 | 2005-06-28 | 2005-06-28 | 2005-07-03 | 2005-07-13 | 2005-07-13 | 2005-07-18 | 2005-07-28 | 2005-07-28 | 2005-08-07 | 2005-08-12 | 2005-08-27 | 2005-08-27 | 2005-08-27 | 2005-08-27 | 2005-09-05 | 2005-09-05 | 2005-09-06 | 2005-09-11 | 2005-09-11 | 2005-09-11 | 2005-09-11 | 2005-09-16 | 2005-09-16 | 2005-09-21 | 2005-09-21
FIRST GROUP
Tallahassee, Fl | TAE | 2006-03-06 | 2005-11-06 | 2005-11-11 | 2005-11-11 | 2005-11-16 | 2005-11-21 | 2005-11-26 | 2005-12-06 | 2005-12-06 | N/A | 2005-12-06 | 2005-12-06 | 2005-12-11 | 2005-12-21 | 2005-12-21 | 2005-12-26 | 2006-01-05 | 2006-01-05 | 2006-01-15 | 2006-01-20 | 2006-02-04 | 2006-02-04 | 2006-02-04 | 2006-02-04 | N/A | 2006-02-13 | 2006-02-14 | 2006-02-19 | 2006-02-19 | 2006-02-19 | 2006-02-19 | 2006-02-24 | 2006-02-24 | 2006-03-01 | 2006-03-01
Lake Charles,LA | LCH | 2006-03-20 | 2005-11-20 | 2005-11-25 | 2005-11-25 | 2005-11-30 | 2005-12-05 | 2005-12-10 | 2005-12-20 | 2005-12-20 | 2005-12-20 | 2005-12-20 | 2005-12-20 | 2005-12-25 | 2006-01-04 | 2006-01-04 | 2006-01-09 | 2006-01-19 | 2006-01-19 | 2006-01-29 | 2006-02-03 | 2006-02-18 | 2006-02-18 | 2006-02-18 | 2006-02-18 | 2006-02-27 | 2006-02-27 | 2006-02-28 | 2006-03-05 | 2006-03-05 | 2006-03-05 | 2006-03-05 | 2006-03-10 | 2006-03-10 | 2006-03-15 | 2006-03-15
Shreeveport,LA | SHV | 2006-04-03 | 2005-12-04 | 2005-12-09 | 2005-12-09 | 2005-12-14 | 2005-12-19 | 2005-12-24 | 2006-01-03 | 2006-01-03 | 2006-01-03 | 2006-01-03 | 2006-01-03 | 2006-01-08 | 2006-01-18 | 2006-01-18 | 2006-01-23 | 2006-02-02 | 2006-02-02 | 2006-02-12 | 2006-02-17 | 2006-03-04 | 2006-03-04 | 2006-03-04 | 2006-03-04 | 2006-03-13 | 2006-03-13 | 2006-03-14 | 2006-03-19 | 2006-03-19 | 2006-03-19 | 2006-03-19 | 2006-03-24 | 2006-03-24 | 2006-03-29 | 2006-03-29
Midland,TX | MAF | 2006-04-17 | 2005-12-18 | 2005-12-23 | 2005-12-23 | 2005-12-28 | 2006-01-02 | 2006-01-07 | 2006-01-17 | 2006-01-17 | 2006-01-17 | 2006-01-17 | 2006-01-17 | 2006-01-22 | 2006-02-01 | 2006-02-01 | 2006-02-06 | 2006-02-16 | 2006-02-16 | 2006-02-26 | 2006-03-03 | 2006-03-18 | 2006-03-18 | 2006-03-18 | 2006-03-18 | 2006-03-27 | 2006-03-27 | 2006-03-28 | 2006-04-02 | 2006-04-02 | 2006-04-02 | 2006-04-02 | 2006-04-07 | 2006-04-07 | 2006-04-12 | 2006-04-12
Amarillo, TX | AMA | 2006-05-01 | 2006-01-01 | 2006-01-06 | 2006-01-06 | 2006-01-11 | 2006-01-16 | 2006-01-21 | 2006-01-31 | 2006-01-31 | 2006-01-31 | 2006-01-31 | 2006-01-31 | 2006-02-05 | 2006-02-15 | 2006-02-15 | 2006-02-20 | 2006-03-02 | 2006-03-02 | 2006-03-12 | 2006-03-17 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2006-04-01 | 2006-04-10 | 2006-04-10 | 2006-04-11 | 2006-04-16 | 2006-04-16 | 2006-04-16 | 2006-04-16 | 2006-04-21 | 2006-04-21 | 2006-04-26 | 2006-04-26
Spokane,WA | OTX | 2006-05-15 | 2006-01-15 | 2006-01-20 | 2006-01-20 | 2006-01-25 | 2006-01-30 | 2006-02-04 | 2006-02-14 | 2006-02-14 | N/A | 2006-02-14 | 2006-02-14 | 2006-02-19 | 2006-03-01 | 2006-03-01 | 2006-03-06 | 2006-03-16 | 2006-03-16 | 2006-03-26 | 2006-03-31 | 2006-04-15 | 2006-04-15 | 2006-04-15 | 2006-04-15 | 2006-04-24 | 2006-04-24 | 2006-04-25 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-04-30 | 2006-05-05 | 2006-05-05 | 2006-05-10 | 2006-05-10
Flagstaff, AR | FGZ | 2006-06-12 | 2006-02-12 | 2006-02-17 | 2006-02-17 | 2006-02-22 | 2006-02-27 | 2006-03-04 | 2006-03-14 | 2006-03-14 | N/A | 2006-03-14 | 2006-03-14 | 2006-03-19 | 2006-03-29 | 2006-03-29 | 2006-04-03 | 2006-04-13 | 2006-04-13 | 2006-04-23 | 2006-04-28 | 2006-05-13 | 2006-05-13 | 2006-05-13 | 2006-05-13 | 2006-05-22 | 2006-05-22 | 2006-05-23 | 2006-05-28 | 2006-05-28 | 2006-05-28 | 2006-05-28 | 2006-06-02 | 2006-06-02 | 2006-06-07 | 2006-06-07
Reno, NV | REV | 2006-06-26 | 2006-02-26 | 2006-03-03 | 2006-03-03 | 2006-03-08 | 2006-03-13 | 2006-03-18 | 2006-03-28 | 2006-03-28 | N/A | 2006-03-28 | 2006-03-28 | 2006-04-02 | 2006-04-12 | 2006-04-12 | 2006-04-17 | 2006-04-27 | 2006-04-27 | 2006-05-07 | 2006-05-12 | 2006-05-27 | 2006-05-27 | 2006-05-27 | 2006-05-27 | 2006-06-05 | 2006-06-05 | 2006-06-06 | 2006-06-11 | 2006-06-11 | 2006-06-11 | 2006-06-11 | 2006-06-16 | 2006-06-16 | 2006-06-21 | 2006-06-21
SECOND GROUP
Rapid City,SD | UNR | 2006-07-17 | 2006-03-19 | 2006-03-24 | 2006-03-24 | 2006-03-29 | 2006-04-03 | 2006-04-08 | 2006-04-18 | 2006-04-18 | N/A | 2006-04-18 | 2006-04-18 | 2006-04-23 | 2006-05-03 | 2006-05-03 | 2006-05-08 | 2006-05-18 | 2006-05-18 | 2006-05-28 | 2006-06-02 | 2006-06-17 | 2006-06-17 | 2006-06-17 | 2006-06-17 | 2006-06-26 | 2006-06-26 | 2006-06-27 | 2006-07-02 | 2006-07-02 | 2006-07-02 | 2006-07-02 | 2006-07-07 | 2006-07-07 | 2006-07-12 | 2006-07-12
Aberdeen,SD | ABR | 2006-07-31 | 2006-04-02 | 2006-04-07 | 2006-04-07 | 2006-04-12 | 2006-04-17 | 2006-04-22 | 2006-05-02 | 2006-05-02 | 2006-05-02 | 2006-05-02 | 2006-05-02 | 2006-05-07 | 2006-05-17 | 2006-05-17 | 2006-05-22 | 2006-06-01 | 2006-06-01 | 2006-06-11 | 2006-06-16 | 2006-07-01 | 2006-07-01 | 2006-07-01 | 2006-07-01 | 2006-07-10 | 2006-07-10 | 2006-07-11 | 2006-07-16 | 2006-07-16 | 2006-07-16 | 2006-07-16 | 2006-07-21 | 2006-07-21 | 2006-07-26 | 2006-07-26
Bismarck, ND | BIS | 2006-08-14 | 2006-04-16 | 2006-04-21 | 2006-04-21 | 2006-04-26 | 2006-05-01 | 2006-05-06 | 2006-05-16 | 2006-05-16 | 2006-05-16 | 2006-05-16 | 2006-05-16 | 2006-05-21 | 2006-05-31 | 2006-05-31 | 2006-06-05 | 2006-06-15 | 2006-06-15 | 2006-06-25 | 2006-06-30 | 2006-07-15 | 2006-07-15 | 2006-07-15 | 2006-07-15 | 2006-07-24 | 2006-07-24 | 2006-07-25 | 2006-07-30 | 2006-07-30 | 2006-07-30 | 2006-07-30 | 2006-08-04 | 2006-08-04 | 2006-08-09 | 2006-08-09
Riverton, WY | RIW | 2006-08-28 | 2006-04-30 | 2006-05-05 | 2006-05-05 | 2006-05-10 | 2006-05-15 | 2006-05-20 | 2006-05-30 | 2006-05-30 | 2006-05-30 | 2006-05-30 | 2006-05-30 | 2006-06-04 | 2006-06-14 | 2006-06-14 | 2006-06-19 | 2006-06-29 | 2006-06-29 | 2006-07-09 | 2006-07-14 | 2006-07-29 | 2006-07-29 | 2006-07-29 | 2006-07-29 | 2006-08-07 | 2006-08-07 | 2006-08-08 | 2006-08-13 | 2006-08-13 | 2006-08-13 | 2006-08-13 | 2006-08-18 | 2006-08-18 | 2006-08-23 | 2006-08-23
Grand Junction, CO | GJT | 2006-09-11 | 2006-05-14 | 2006-05-19 | 2006-05-19 | 2006-05-24 | 2006-05-29 | 2006-06-03 | 2006-06-13 | 2006-06-13 | 2006-06-13 | 2006-06-13 | 2006-06-13 | 2006-06-18 | 2006-06-28 | 2006-06-28 | 2006-07-03 | 2006-07-13 | 2006-07-13 | 2006-07-23 | 2006-07-28 | 2006-08-12 | 2006-08-12 | 2006-08-12 | 2006-08-12 | 2006-08-21 | 2006-08-21 | 2006-08-22 | 2006-08-27 | 2006-08-27 | 2006-08-27 | 2006-08-27 | 2006-09-01 | 2006-09-01 | 2006-09-06 | 2006-09-06
Gray, ME | GYX | 2006-09-25 | 2006-05-28 | 2006-06-02 | 2006-06-02 | 2006-06-07 | 2006-06-12 | 2006-06-17 | 2006-06-27 | 2006-06-27 | 2006-06-27 | 2006-06-27 | 2006-06-27 | 2006-07-02 | 2006-07-12 | 2006-07-12 | 2006-07-17 | 2006-07-27 | 2006-07-27 | 2006-08-06 | 2006-08-11 | 2006-08-26 | 2006-08-26 | 2006-08-26 | 2006-08-26 | 2006-09-04 | 2006-09-04 | 2006-09-05 | 2006-09-10 | 2006-09-10 | 2006-09-10 | 2006-09-10 | 2006-09-15 | 2006-09-15 | 2006-09-20 | 2006-09-20
Buffalo, NY | BUF | 2006-10-09 | 2006-06-11 | 2006-06-16 | 2006-06-16 | 2006-06-21 | 2006-06-26 | 2006-07-01 | 2006-07-11 | 2006-07-11 | 2006-07-11 | 2006-07-11 | 2006-07-11 | 2006-07-16 | 2006-07-26 | 2006-07-26 | 2006-07-31 | 2006-08-10 | 2006-08-10 | 2006-08-20 | 2006-08-25 | 2006-09-09 | 2006-09-09 | 2006-09-09 | 2006-09-09 | 2006-09-18 | 2006-09-18 | 2006-09-19 | 2006-09-24 | 2006-09-24 | 2006-09-24 | 2006-09-24 | 2006-09-29 | 2006-09-29 | 2006-10-04 | 2006-10-04
Boise, ID | BOI | 2006-10-23 | 2006-06-25 | 2006-06-30 | 2006-06-30 | 2006-07-05 | 2006-07-10 | 2006-07-15 | 2006-07-25 | 2006-07-25 | 2006-07-25 | 2006-07-25 | 2006-07-25 | 2006-07-30 | 2006-08-09 | 2006-08-09 | 2006-08-14 | 2006-08-24 | 2006-08-24 | 2006-09-03 | 2006-09-08 | 2006-09-23 | 2006-09-23 | 2006-09-23 | 2006-09-23 | 2006-10-02 | 2006-10-02 | 2006-10-03 | 2006-10-08 | 2006-10-08 | 2006-10-08 | 2006-10-08 | 2006-10-13 | 2006-10-13 | 2006-10-18 | 2006-10-18
Norman, OK | OUR | 2006-11-06 | 2006-07-09 | 2006-07-14 | 2006-07-14 | 2006-07-19 | 2006-07-24 | 2006-07-29 | 2006-08-08 | 2006-08-08 | 2006-08-08 | 2006-08-08 | 2006-08-08 | 2006-08-13 | 2006-08-23 | 2006-08-23 | 2006-08-28 | 2006-09-07 | 2006-09-07 | 2006-09-17 | 2006-09-22 | 2006-10-07 | 2006-10-07 | 2006-10-07 | 2006-10-07 | 2006-10-16 | 2006-10-16 | 2006-10-17 | 2006-10-22 | 2006-10-22 | 2006-10-22 | 2006-10-22 | 2006-10-27 | 2006-10-27 | 2006-11-01 | 2006-11-01
Formulas:
Schedule First Telecon = [Target install date (D-Day]-F3
Hold first Telecon and Ship Plans = [Target install date (D-Day]-G3
Issue general info. Request e-mail = [Target install date (D-Day]-H3
Ops-Immed Response Due = [Target install date (D-Day]-I3
Request 7460 = [Target install date (D-Day]-L3
Send Ops Immed to IMET = [Target install date (D-Day]-M3
Schedule Second Telecon = [Target install date (D-Day]-N3
Hold Second Telecon = [Target install date (D-Day]-O3
Send Final SIP = [Target install date (D-Day]-P3
Schedule Final Telecon = [Target install date (D-Day]-Q3
Hold Final Telecon = [Target install date (D-Day]-R3
Permit reminder = [Target install date (D-Day]-S3
Notify Debbie Pickerign = [Target install date (D-Day]-T3
Schedule Training Telecon = [Target install date (D-Day]-U3
Hold Training Telecon = [Target install date (D-Day]-V3
Prelim. Decomm. Date Due = [Target install date (D-Day]-W3
All Gov Permits Due = [Target install date (D-Day]-X3
Exchange encription Keys, Record PWs = [Target install date (D-Day]-Y3
Notify NLSC for LRU Containers = [Target install date (D-Day]-AA3
Schedule Site Readiness Telecon = [Target install date (D-Day]-AC3
Site Readiness Telecon = [Target install date (D-Day]-AD3
Facilities Checklist Due = [Target install date (D-Day]-AE3
Site Decomm. Checklist Due = [Target install date (D-Day]-AF3
Distance Learning Cert Due = [Target install date (D-Day]-AG3
Get current RRS Software & Ghost CD = [Target install date (D-Day]-AI3

## Per site
Enter the three character Site ID in Column B of this row | OUN
Enter the installation date in Column B of this row | 2006-11-06
OUN - Ship RWS, Tng. Mat., Issue e-mail #1, Deployment Team Action, 07/09/2006 , 8:00 AM
OUN - Verify RWS received, Deployment Team Action, 07/14/2006 , 8:00 AM
OUN - Schedule first telecon, issue e-mail #2, Deployment Team Action, 07/14/2006 , 8:00 AM
OUN - First telecon, Proposed Telecon, 07/19/2006 , 8:00 AM
OUN - Request general data, Deployment Team Action, 07/24/2006 , 8:00 AM
OUN - Ops immediate data due, Forecast Office Action, 07/29/2006 , 8:00 AM
OUN - SIP comments and data due, Forecast Office Action, 08/08/2006 , 8:00 AM
OUN - Issue GPS repeater kit, Deployment Team Action, 08/08/2006 , 8:00 AM
OUN - Submit 7460 request, Deployment Team Action, 08/08/2006 , 8:00 AM
OUN - Send Ops Immed. To IMET, Deployment Team Action, 08/08/2006 , 8:00 AM
OUN - Schedule second telecon , Deployment Team Action, 08/08/2006 , 8:00 AM
OUN - Second telecon, Proposed Telecon, 08/13/2006 , 8:00 AM
OUN - Send final SIP, Deployment Team Action, 08/23/2006 , 8:00 AM
OUN - Schedule final telecon, Deployment Team Action, 08/23/2006 , 8:00 AM
OUN - Final telecon, Proposed Telecon, 08/28/2006 , 8:00 AM
OUN - Permit reminder call, Deployment Team Action, 09/07/2006 , 8:00 AM
OUN - Notify Debbie P, Deployment Team Action, 09/07/2006 , 8:00 AM
OUN - Schedule training telecon, Deployment Team Action, 09/17/2006 , 8:00 AM
OUN - Training telecon, Proposed Telecon, 09/22/2006 , 8:00 AM
OUN - Prelim. Decomm. Date due, Forecast Office Action, 10/07/2006 , 8:00 AM
OUN - Permits due, Deployment Team Action, 10/07/2006 , 8:00 AM
OUN - Exchange keys & PWs, Deployment Team Action, 10/07/2006 , 8:00 AM
OUN - Issue NLSC kits, Deployment Team Action, 10/07/2006 , 8:00 AM
OUN - Notify NLSC to ship crates, Deployment Team Action, 10/16/2006 , 8:00 AM
OUN - Notify BU sites, Deployment Team Action, 10/16/2006 , 8:00 AM
OUN - Schedule readiness telecon, Deployment Team Action, 10/17/2006 , 8:00 AM
OUN - Readiness telecon, Proposed Telecon, 10/22/2006 , 8:00 AM
OUN - Facilities checklist due, Forecast Office Action, 10/22/2006 , 8:00 AM
OUN - Decomm. Checklist due, Forecast Office Action, 10/22/2006 , 8:00 AM
OUN - Operator training cert due, Forecast Office Action, 10/22/2006 , 8:00 AM
OUN - Notify Maint & logistics, Deployment Team Action, 10/27/2006 , 8:00 AM
OUN - Get RRS SW, Deployment Team Action, 10/27/2006 , 8:00 AM
OUN - Notify Hotline, Deployment Team Action, 11/01/2006 , 8:00 AM
OUN - Notify NDCD & NCEP, Deployment Team Action, 11/01/2006 , 8:00 AM
OUN - Installation, Deployment Team Action, 11/06/2006 , 8:00 AM

## Deployment staffing
Station Name | Site ID | Target install date (D-Day | OPS11 staff | OPS11 TDY (to) | OPS11 TDY (from) | QSS Staff #1 | QSS staff #1 TDY (to) | QSS staff #1 TDY (from) | QSS Staff #2 | QSS staff #2 TDY (to) | QSS staff #2 TDY (from)
|  |  |  | -1 | 5 |  | 1 | 11 |  | 7 | 11
SAMPLE | xxx | 2005-01-01
Sterling | LWX | 2005-07-25
Chanhassen | MPX | 2005-08-22
Salt Lake City | SLC | 2005-09-12
Corpus Christi | CRP | 2005-09-26
FIRST GROUP
Tallahassee, Fl | TAE | 2006-03-06 | Paul/Barrett | 2006-03-05 | 2006-03-11 | Ashby Hawse | 2006-03-07 | 2006-03-17 | Fitz Shelton | 2006-03-08 | 2006-03-17
Lake Charles,LA | LCH | 2006-03-20 | Monte/Modracek | 2006-03-19 | 2006-03-25 | Nick Schmid | 2006-03-21 | 2006-03-31 | Paul Rockwood | 2006-03-27 | 2006-03-31
Shreeveport,LA | SHV | 2006-04-03 | Paul | 2006-04-02 | 2006-04-08 | Paul Rockwood | 2006-04-04 | 2006-04-14 | Robert Thomas | 2006-04-05 | 2006-04-14
Midland,TX | MAF | 2006-04-17 | Monte/Barrett | 2006-04-16 | 2006-04-22 | Fitz Shelton | 2006-04-18 | 2006-04-28 | Paul Rockwood | 2006-04-24 | 2006-04-28
Amarillo, TX | AMA | 2006-05-01 | Modracek | 2006-04-30 | 2006-05-06 | Fitz Shelton | 2006-05-02 | 2006-05-12 | Nick Schmid | 2006-05-08 | 2006-05-12
Spokane,WA | OTX | 2006-05-15 | Paul | 2006-05-14 | 2006-05-20 | Robert Thomas | 2006-05-16 | 2006-05-26 | TBD | 2006-05-22 | 2006-05-26
Boise, ID | BOI | #REF! | Barrett | #REF! | #REF! | Paul Rockwood | #REF! | #REF! | Robert Thomas | #REF! | #REF!
Flagstaff, AR | FGZ | 2006-06-12 | Monte | 2006-06-11 | 2006-06-17 | Nick Schmid | 2006-06-13 | 2006-06-23 | Paul Rockwood | 2006-06-19 | 2006-06-23
Reno, NV | REV | 2006-06-26 | Barrett | 2006-06-25 | 2006-07-01 | Robert Thomas | 2006-06-27 | 2006-07-07 | TBD | 2006-07-03 | 2006-07-07
SECOND GROUP
Rapid City,SD | UNR | 2006-07-17 | Paul | 2006-07-16 | 2006-07-22 | Paul Rockwood | 2006-07-18 | 2006-07-28 | TBD | 2006-07-24 | 2006-07-28
Aberdeen,SD | ABR | 2006-07-31 | Modracek | 2006-07-30 | 2006-08-05 | Nick Schmid | 2006-08-01 | 2006-08-11 | Paul Rockwood | 2006-08-07 | 2006-08-11
Bismarck, ND | BIS | 2006-08-14 | Monte | 2006-08-13 | 2006-08-19 | Robert Thomas | 2006-08-15 | 2006-08-25 | TBD | 2006-08-21 | 2006-08-25
Riverton, WY | RIW | 2006-08-28 | Barrett | 2006-08-27 | 2006-09-02 | Paul Rockwood | 2006-08-29 | 2006-09-08 | TBD | 2006-09-04 | 2006-09-08
Grand Junction, CO | GJT | 2006-09-11 | Paul | 2006-09-10 | 2006-09-16 | Fitz Shelton | 2006-09-12 | 2006-09-22 | Nick Schmid | 2006-09-18 | 2006-09-22
Gray, ME | GYX | 2006-09-25 | Modracek | 2006-09-24 | 2006-09-30 | Paul Rockwood | 2006-09-26 | 2006-10-06 | Fitz Shelton | 2006-10-02 | 2006-10-06
Buffalo, NY | BUF | 2006-10-09 | Paul | 2006-10-08 | 2006-10-14 | Paul Rockwood | 2006-10-10 | 2006-10-20 | Robert Thomas | 2006-10-16 | 2006-10-20
Wilmington,OH | ILN | 2006-10-23 | Barrett | 2006-10-22 | 2006-10-28 | Fitz Shelton | 2006-10-24 | 2006-11-03 | Nick Schmid | 2006-10-30 | 2006-11-03
Morehead Cty, NC | MHX | 2006-11-06 | Modracek | 2006-11-05 | 2006-11-11 | Paul Rockwood | 2006-11-07 | 2006-11-17 | TBD | 2006-11-13 | 2006-11-17
Blacksburg, VA | RNK | 0 | Paul | -1 | 1900-01-04 | Fitz Shelton | 1899-12-31 | 1900-01-10 | Paul Rockwood | 1900-01-06 | 1900-01-10
Greensboro, NC | GSO | 0 | Monte | -1 | 1900-01-04 | Nick Schmid | 1899-12-31 | 1900-01-10 | TBD | 1900-01-06 | 1900-01-10
Key West, FL | EYW | TBD | TBD
Caribou, ME | CAR | TBD | TBD |  |  | Paul Rockwood |  |  | Nick Schmid
Formulas:
OPS11 TDY (to) = [Target install date (D-Day]+F4
OPS11 TDY (from) = [Target install date (D-Day]+G4
QSS staff #1 TDY (to) = [Target install date (D-Day]+J4
QSS staff #1 TDY (from) = [Target install date (D-Day]+K4
QSS staff #2 TDY (from) = [Target install date (D-Day]+O4
QSS staff #2 TDY (to) = [Target install date (D-Day]+N4

## Dialed Backups
RRS COMMUNICATIONS PATHS
2005-05-24
UA OFC | OFC_NAME | PRIMARY COMMS | BACKUP 1 | BACKUP 2
CR
KABR | Aberdeen, SD | ABR | CRH | ERH
KAPX | North Central Lower Michigan, MI | APX | CRH | ERH
KBIS | Bismarck, ND | BIS | CRH | ERH
KDDC | Dodge City, KS | DDC | CRH | ERH
KDNR | Denver, CO | BOU | CRH | ERH
KDTX | Detroit, MI | DTX | CRH | ERH
KDVN | Quad Cities, IA | DVN | CRH | ERH
KGJT | Grand Junction, CO | GJT | CRH | ERH
KGRB | Green Bay, WI | GRB | CRH | ERH
KILX | Central Illinois, IL | ILX | CRH | ERH
KINL | International Falls, MN | INL | CRH | ERH
KLBF | North Platte, NE | LBF | CRH | ERH
KMPX | Minneapolis, MN | MPX | CRH | ERH
KOAX | Omaha, NE | OAX | CRH | ERH
KRIW | Riverton, WY | RIW | CRH | ERH
KSGF | Springfield, MO | SGF | CRH | ERH
KTOP | Topeka, KS | TOP | CRH | ERH
KUNR | Rapid City, SD | UNR | CRH | ERH
ER
KALY | Albany, NY | ALY | ERH | CRH
KBUF | Buffalo, NY | BUF | ERH | CRH
KCAR | Caribou, ME | CAR | ERH | CRH
KCHH | Chatham, MA | BOX | ERH | CRH
KCHS | Charleston, SC | CHS | ERH | CRH
KGSO | Greensboro, NC | RAH | ERH | CRH
KGYX | Portland, ME | GYX | ERH | CRH
KILN | Wilmington, OH | ILN | ERH | CRH
KLWX | Baltimore, MD/Washington, DC | LWX | ERH | CRH
KMHX | Morehead City, NC | MHX | ERH | CRH
KOKX | New York City, NY | OKX | ERH | CRH
KPBZ | Pittsburgh, PA | PBZ | ERH | CRH
KRNK | Blackburg, VA | RNK | ERH | CRH
KWAL | Wallops Island, VA | AKQ | ERH | CRH
PR
PGUM | Guam, GU | GUM
SR
KABQ | Albuquerque, NM | ABQ | SRH | WRH
KAMA | Amarillo, TX | AMA | SRH | WRH
KBMX | Birmingham, AL | BMX | SRH | WRH
KBRO | Brownsville, TX | BRO | SRH | WRH
KCRP | Corpus Christi, TX | CRP | SRH | WRH
KDRT | Del Rio, TX | MAF | SRH | WRH
KEPZ | El Paso, TX | EPZ | SRH | WRH
KEYW | Key West, FL | EYW | SRH | WRH
KFFC | Atlanta, GA | FFC | SRH | WRH
KFWD | Dallas/Fort Worth, TX | FWD | SRH | WRH
KJAN | Jackson, MS | JAN | SRH | WRH
KJAX | Jacksonville, FL | JAX | SRH | WRH
KLCH | Lake Charles, LA | LCH | SRH | WRH
KLIX | New Orleans/Baton Rouge, LA | LCH | SRH | WRH
KLZK | Little Rock, AR | LZK | SRH | WRH
KMAF | Midland/Odessa, TX | MAF | SRH | WRH
KMFL | Miami, FL | MFL | SRH | WRH
KOHX | Nashville, TN | OHX | SRH | WRH
KOUN | Oklahoma City, OK | OUN | SRH | WRH
KSHV | Shreveport, LA | SHV | SRH | WRH
KSJU | San Juan, PR | SJU | SRH | WRH
KTAE | Tallahassee, FL | TAE | SRH | WRH
KTBW | Tampa Bay Area, FL | TBW | SRH | WRH
WR
KBOI | Boise, ID | BOI | WRH | SRH
KDRA | Las Vegas, NV | VEF | WRH | SRH
KFGZ | Flagstaff, AZ | FGZ | WRH | SRH
KGGW | Glasgow, MT | GGW | WRH | SRH
KLKN | Elko, NV | LKN | WRH | SRH
KMFR | Medford, OR | MFR | WRH | SRH
KNKX | San Diego, CA | SGX | WRH | SRH
KOAK | Oakland, CA | STO | WRH | SRH
KOTX | Spokane, WA | OTX | WRH | SRH
KREV | Reno, NV | REV | WRH | SRH
KSLC | Salt Lake City, UT | SLC | WRH | SRH
KSLE | Salem, OR | MFR | WRH | SRH
KTFX | Great Falls, MT | TFX | WRH | SRH
KTUS | Tucson, AZ | TWC | WRH | SRH
KUIL | Quillayute, WA | SEW | WRH | SRH
71
CRH Dialup # 816-891-6324
ERH Dialup # 631-589-7236
SRH Dialup # 817-978-0045
WRH Dialup # 801-524-5119

## 0006CLIN
Station Name | CLIN 0006 | - 100' Increment of Direct Burial FO Cable
06 Installations
Spokane (OTX) | 1
Boise (BOI) | 0
Flagstaff (FGZ) | 4
Reno (REV) | 2
Rapid City (UNR) | 1
Aberdeen (ABR) | 1
Bismarck (BIS) | 4
Riverton (RIW) | 2
Grand Junction (GJT) | 1
Gray (GYX) | 8
Buffalo (BUF) | 0
Wilmington (ILN) | 7
Morehead City (MHX) | 2
Blacksburg (RNK) | 9
Greensboro (GSO) | ??

## Training SW
Station Name | Site ID | RWS Operating System Version | RRS Operational Version | Training CD Version | Transition DVD Version
SAMPLE | xxx
Sterling | LWX
Chanhassen | MPX
Salt Lake City | SLC
Corpus Christi | CRP
FIRST GROUP
Tallahassee, Fl | TAE | 1.03 | 1.1.3.0 Jan 18, 2006 | 2004-04-18 | 2005-08-01
Lake Charles,LA | LCH | 1.03
Shreeveport,LA | SHV | 1.03
Midland,TX | MAF | 1.03
Amarillo, TX | AMA | 1.03
Spokane,WA | OTX | 1.03
Boise, ID | BOI | 1.03 | 1.1.3.0 Jan 18, 2006 | 2004-04-18 | 2005-08-01
Flagstaff, AR | FGZ
Reno, NV | REV | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
SECOND GROUP
Rapid City,SD | UNR | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
Aberdeen,SD | ABR | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
Bismarck, ND | BIS | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
Riverton, WY | RIW | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
Grand Junction, CO | GJT | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
Gray, ME | GYX
Buffalo, NY | BUF | 1.03 | 1.1.3.0 Jan 18, 2006 | 2005-04-18 | 2005-08-01
Wilmington,OH | ILN
Morehead Cty, NC | MHX
Blacksburg, VA | RNK
Greensboro, NC | GSO
Key West, FL | EYW
Caribou, ME | CAR