## NOAA FY07
Detail information on the major IT systems, i.e. the OMB Circular A-11 Exhibit 300 information, can be found within eCPIC.
IT Systems with a variance "+" or "-" 10% are hi-lighted in orange
NOAAs IT Portfolio FY 2007 |  | Fiscal Year 2007
Line Office | Name of Major IT System | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
|  | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date
NESDIS | CLASS - Comprehensive Large Array-data Stewardship System | 0.5533% | 0.8337% | 11/31/2006 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | ESPC - Environmental Satellite Processing Center | 0% | 2.683% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | Global Earth Observation Integrated Data Environment (GEO IDE) | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | GOES Ground - Geostationary Operational Environmental Satellite Ground System | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | NDE - NPOESS Data Exploitation | 0.115% | 3.224% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | NPOESS - Ground -National Polar-orbiting Operational Environmental Satellite System Ground System | -0.2746% | 2.614% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | OSDPD - Office of Satellite Data Processing and Distribution Systems, CIP | -3.65% | -0.3842% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | POES Ground - Polar-orbiting Operational Environmental Satellite Ground System | 0% | -0.6% | 11/31/2006 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NWS | AQF - Air Quality Forecasting | -0.02283% | 0.2667% | 2006-12-31 | -2.231% | -0.5002% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | AWIPS | -0.02302% | 0.9172% | 2006-12-31 | -0.1912% | 0.4309% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | HazCollect | 0% | -12.41% | 2006-12-31 | 0% | -12.4% | 2007-02-28 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | NERON | -6.461% | -2.725% | 2006-12-31 | -6.359% | -2.562% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | NPI - Next Generation Weather Radar (NEXRAD) Planned Product Improvement (PPI) | -0.3101% | 4.208% | 2006-12-31 | -0.3322% | 4.903% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | NWSTG - National Weather Service Telecommunications Gateway Systems | -7.64% | -3.758% | 2006-12-31 | -7.634% | -3.755% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | OHD - Office of Hydrological Development | 3.036% | 1.737% | 2006-12-31 | 1.439% | -0.09584% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd

## Comments
Date | System Name | Comments
2006-05-06 | NERON | TBD -- The NOAA Executive Committee (NEC) and NOAA Observing System Council (NOSC) recently redefined the NERON project to focus on modernizing the approximately 1,000 Historical Climate Network sites. The NERON project previously involved modernizing 8,000 Cooperative Observer sites (which included the HCN sites). The EVMS that has been reported since 2004 has primarily focused on the risk reduction effort in New England where about 100 sites were installed. The New England effort has been completed. OST briefed the NOSC on 5/31/06 and provided a revised Project Plan. Action items from the NOSC meeting are being completed. The NOSC briefed the NEC on NERON on 6/14/06 and action items are pending but expected by the end of June. Once final disposition is received from the NEC, the EVMS will need to be rebaselined to reflect the redefined project (as reported last month). Substantial time and effort will be required to perform the rebaselining and the planned completion is 1Q07.
2006-06-30 | NERON | TBD -- The NOAA Executive Committee (NEC) and NOAA Observing System Council (NOSC) recently redefined the NERON project to focus on modernizing the approximately 1,000 Historical Climate Network sites. The NERON project previously involved modernizing 8,000 Cooperative Observer sites (which included the HCN sites). The EVMS that has been reported since 2004 has primarily focused on the risk reduction effort in New England where about 100 sites were installed. The New England effort has been completed. OST briefed the NOSC on 5/31/06 and provided a revised Project Plan. Action items from the NOSC meeting are being completed. The NOSC briefed the NEC on NERON on 6/14/06 and action items are being completed and will be briefed to the NOSC on August 15. The EVMS will need to be rebaselined to reflect the redefined project (as reported last month). Substantial time and effort will be required to perform the rebaselining and the planned completion is 1Q07.
2006-07-31 | NERON | TBD -- The NOAA Executive Committee (NEC) and NOAA Observing System Council (NOSC) recently redefined the NERON project to focus on modernizing the approximately 1,000 Historical Climate Network sites. The NERON project previously involved modernizing 8,000 Cooperative Observer sites (which included the HCN sites). The EVMS that has been reported since 2004 has primarily focused on the risk reduction effort in New England where about 100 sites were installed. The New England effort has been completed. OST re-briefed the NOSC on 8/15/06 for Key Decision Point 1 and the project received conditional approval. OST management is continuing to work to form the NERON project team, integrated work teams, and bring on contractor support. The EVMS will need to be rebaselined to reflect the redefined project. Substantial time and effort will be required to perform the rebaselining once the project team is in place and the planned completion is 2Q07.
2006-08-30 | NERON | TBD -- The NOAA Executive Committee (NEC) and NOAA Observing System Council (NOSC) recently redefined the NERON project to focus on modernizing the approximately 1,000 Historical Climate Network sites. The NERON project previously involved modernizing 8,000 Cooperative Observer sites (which included the HCN sites). The EVMS that has been reported since 2004 has primarily focused on the risk reduction effort in New England where about 100 sites were installed. The New England effort has been completed. OST re-briefed the NOSC on 8/15/06 for Key Decision Point 1 and the NOSC has requested minor revisions to the briefing. Briefing will be revised and provided to NOSC by 9/31/06 for review. Expectation is that NOSC will recommend approval of KDP1 to NEP. OST management is continuing to work to form the NERON project team, integrated work teams, and bring on contractor support. The EVMS will need to be rebaselined to reflect the redefined project. Substantial time and effort will be required to perform the rebaselining once the project team is in place and the planned completion is 2Q07.
2007-01-22 | POES GS | In Sept 06, the Jason project (DME) was moved from the SOCC CDA 300 into the POES GS. At the same time, all the other DME activity in POES GS was reviewed and determined to be Steady State (technological refresh, etc.). With these changes: - JASON is the only remaining DME in the POES GS 300. Like CLASS, the contractor EVM reporting requirements lag the NOAA/NESDIS by 30 days, thus the POES GS reports will also lag by 30 days. - The DME total for the project was reduced to $18,529K, the OMB 300 will be changed to reflect this during the next update.
2007-01-22 | GOES GS | In Sept 06, all the DME activity in GOES GS was reviewed and most determined to be Steady State (technological refresh, etc.). With these changes: - The DME total for the project was reduced to $14,319K, the OMB 300 will be changed to reflect this during the next update. - 88% of the GOES DME is now completed. In FY07 only $420K of DME activity will occur. Given that the previous DME reporting processes has resulted in perfect scores (SV and CV = 0%) and the FY07 activity represents only 3% of the total DME, its is almost impossible for this activity to take the GOES GS EV outside of the +/- 10% threshold. Thus, GOES GS will request a waiver for FY07 reporting.
2007-01-22 | GEO IDE | GEO IDE initial funding request was approved by Do,C but cut by OMB. NOAA internally funded FY05/6 with small scale planning activities ($150K/yr). An additional $600K from ORF Climate Program and NESDIS funds is expected to continue the initial planning of the project in FY2007. This meager funding and the assoiciated activities is not enough to require EV reporting. Especially since the contracts in place equal only $600K and do not EV requirements mandated due to the type of task activities the contractor is performing (initial planning efforts to fully determine follow-on requirements). Thus GEO IDE will request an EV reporting waiver for FY07.
2007-01-22 | NPOESS GS | NPOESS GS BAC has fluctuated over the last year due to the Nunn-Mceardy program restructure. Tthe current BAC is valid through September, 2007. It is planned that in September, 2007 the restructured program will be in place and that the BAC will reflect the new lifecycle costs of the program.
2006-12-31 | HazCollect | Explanation of Variance The NWS Operational Acceptance Test (OAT) concluded successfully on 11/30/06. The HazCollect capability is now deployed to all sites and will remain activated at the OAT sites. The NWS is now beginning the transition to operations phase. Once all transition activities are completed, the system may be activated nation wide. This is expected to be completed by June 30, 2007. Once complete, the system will be considered operational and Operational Analysis reporting will begin.
2007-02-28 | HazCollect | Explanation of Variance The NWS Operational Acceptance Test (OAT) concluded successfully on 11/30/06. The HazCollect capability is now deployed to all sites and will remain activated at the OAT sites. The NWS is now beginning the transition to operations phase. Once all transition activities are completed, the system may be activated nation wide. This is expected to be completed by June 30, 2007. Once complete, the system will be considered operational and Operational Analysis reporting will begin.
2007-03-19 | OHD | The correct BAC for the sum of our DME activities in AHPS and Water Resources is 20553, not 21053. This is an artifact of an accounting mistake in prior years (we had planning $$ listed for a steady state activity in FY04 and FY05).

## NOAA FY06
Detail information on the major IT systems, i.e. the OMB Circular A-11 Exhibit 300 information, can be found within eCPIC.
IT Systems with a variance "+" or "-" 10% are hi-lighted in orange
NOAAs IT Portfolio FY 2006 and 2007 |  | Fiscal Year 2006 | [11 empty] | Fiscal Year 2007
Line Office | Name of Major IT System | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
|  | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date | Schedule Variance % | Cost Variance % | As of Date
NESDIS | CLASS - Comprehensive Large Array-data Stewardship System | -0.04456% | 0.3269% | 2005-12-31 | 0.2954% | 0.2352% | 2006-03-31 | 0.532% | 0.4997% | 2006-06-30 | 0.5855% | 0.8028% | 2006-09-30 | 0.5533% | 0.8337% | 11/31/2006 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | ESPC - Environmental Satellite Processing Center | 0% | 14.09% | 2005-12-31 | 0% | 10.16% | 2006-03-31 | 0% | 2.962% | 2006-06-30 | 0% | 2.746% | 2006-09-30 | 0% | 2.683% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | Global Earth Observation Integrated Data Environment (GEO IDE) | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | GOES Ground - Geostationary Operational Environmental Satellite Ground System | 0% | 0% | 2005-12-31 | 0% | 0% | 2006-03-31 | 0% | 0% | 2006-06-30 | 0% | 0% | 2006-09-30 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | NDE - NPOESS Data Exploitation | tbd | tbd | tbd | tbd | tbd | tbd | -7.425% | -0.874% | 2006-06-30 | -6.248% | -1.589% | 2006-09-30 | 0.115% | 3.224% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | NPOESS - Ground -National Polar-orbiting Operational Environmental Satellite System Ground System | tbd | tbd | tbd | 1.638% | 2.735% | 2006-03-31 | 0.5882% | 2.279% | 2006-06-30 | 0.8198% | 2.456% | 2006-09-30 | -0.2746% | 2.614% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | OSDPD - Office of Satellite Data Processing and Distribution Systems, CIP | 0% | 0% | 2005-12-31 | 0 | 0% | 2006-03-31 | -4.99% | 1.136% | 2006-06-30 | -5.012% | -0.3833% | 2006-09-30 | -3.65% | -0.3842% | 2006-12-31 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NESDIS | POES Ground - Polar-orbiting Operational Environmental Satellite Ground System | 0% | 0% | 2005-12-31 | 0% | -0.6621% | 2006-03-31 | 0% | -0.6221% | 2006-06-30 | 0% | -0.6376% | 2006-09-30 | 0% | -0.6% | 11/31/2006 | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd | tbd
NWS | AQF - Air Quality Forecasting | -0.4029% | 2.578% | 2005-12-31 | -3.21% | 3.04% | 2006-03-31 | 0.5125% | 2.908% | 2006-06-30 | 1.236% | 1.424% | 2006-09-30 | -0.02283% | 0.2667% | 2006-12-31 | -2.231% | -0.5002% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | AWIPS | 0% | -2.221% | 2005-12-31 | 0% | -1.003% | 2006-03-31 | 0% | -0.6266% | 2006-06-30 | -0.02576% | 0.7402% | 2006-09-30 | -0.02302% | 0.9172% | 2006-12-31 | -0.1912% | 0.4309% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | NERON | -0.5468% | -6.311% | 2005-12-31 | -2.353% | -8.517% | 2006-03-31 | 7.434% | -6.743% | 2006-04-30 | tbd | tbd | tbd | -6.461% | -2.725% | 2006-12-31 | -6.359% | -2.562% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | NPI - Next Generation Weather Radar (NEXRAD) Planned Product Improvement (PPI) | -16.75% | -0.8149% | 2005-12-31 | -5.703% | 5.44% | 2006-03-31 | -0.5562% | 4.559% | 2006-06-30 | 1.043% | 2.61% | 2006-09-30 | -0.3101% | 4.208% | 2006-12-31 | -0.3322% | 4.903% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | NWSTG - National Weather Service Telecommunications Gateway Systems | -7.912% | -0.3907% | 2005-12-31 | -10.06% | -5.423% | 2006-03-31 | -6.775% | -2.647% | 2006-06-30 | -7.252% | -3.262% | 2006-09-30 | -7.64% | -3.758% | 2006-12-31 | -7.634% | -3.755% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd
NWS | OHD - Office of Hydrological Development | 4.644% | 3.681% | 2005-12-31 | 4.134% | 3.62% | 2006-03-31 | 3.621% | 4.189% | 2006-06-30 | 4.073% | 4.258% | 2006-09-30 | 3.036% | 1.737% | 2006-12-31 | 1.439% | -0.09584% | 2007-01-31 | tbd | tbd | tbd | tbd | tbd | tbd

## NESDIS CLASS
NESDIS CLASS |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) | 84888 | 84888 | 84888 | 84888 | 84888 | 84888 | 84888 | 84888 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544 | 77544
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 544.74 | 1054.271 | 26932 | 27414.783 | 28021.091 | 28683.022 | 29319.155 | 29914.54 | 30539.244 | 31115.65 | 31728.633 | 32302.012 | 32984.886 | 33528.6655 | 34071.7237 | 34686.2493 | 35302.9014 | 36046.578 | 36748.2925 | 37452.5459 | 38172.2232 | 38784.209 | 39464.125 | 40133.293
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 551.918 | 1010.743 | 26920 | 27478.577 | 28073.106 | 28767.74 | 29433.042 | 30042.818 | 30701.726 | 30959.737 | 31889.524 | 32491.146 | 33170.591 | 33714.189
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 547.728 | 1048.565 | 26832 | 27478.577 | 28009.311 | 28700.068 | 29338.326 | 29926.637 | 30548.297 | 30802.062 | 31667.036 | 32230.307 | 32887.854 | 33433.118
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1.0132 | 0.95871 | 0.99955 | 1.0023 | 1.0019 | 1.003 | 1.0039 | 1.0043 | 1.0053 | 0.99499 | 1.0051 | 1.0059 | 1.0056 | 1.0055 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | 7.178 | -43.528 | -12 | 63.794 | 52.015 | 84.718 | 113.887 | 128.278 | 162.482 | -155.913 | 160.891 | 189.134 | 185.705 | 185.5235 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 1.0076 | 0.96393 | 1.0033 | 1 | 1.0023 | 1.0024 | 1.0032 | 1.0039 | 1.005 | 1.0051 | 1.007 | 1.0081 | 1.0086 | 1.0084 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | 4.19 | -37.822 | 88 | 0 | 63.795 | 67.672 | 94.716 | 116.181 | 153.429 | 157.675 | 222.488 | 260.839 | 282.737 | 281.071 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 1.318% | -4.129% | -0.04456% | 0.2327% | 0.1856% | 0.2954% | 0.3884% | 0.4288% | 0.532% | -0.5011% | 0.5071% | 0.5855% | 0.563% | 0.5533% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | 0.7592% | -3.742% | 0.3269% | 0% | 0.2272% | 0.2352% | 0.3218% | 0.3867% | 0.4997% | 0.5093% | 0.6977% | 0.8028% | 0.8524% | 0.8337% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 1.0209 | 0.92413 | 1.0028 | 1.0023 | 1.0041 | 1.0053 | 1.0071 | 1.0082 | 1.0104 | 1.0001 | 1.0121 | 1.014 | 1.0143 | 1.014 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## ESPC
NESDIS ESPC |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) |  | 8793 | 8793 | 8793 | 8793 | 8793 | 8793 | 8793 | 8793 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776 | 16776
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) |  | 982.525 | 1720.65 | 2458.775 | 3119.5 | 3812.6 | 4413.4 | 5025.5 | 5634.7 | 3190.5 | 3794.1 | 4392.7 | 4610.55 | 4828.4 | 5046.25 | 5264.1 | 5481.95 | 5699.8 | 5858.9 | 6018 | 6177.1 | 6336.2 | 6495.3 | 6654.4
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) |  | 982.525 | 1720.65 | 2458.775 | 3119.5 | 3812.6 | 4413.4 | 5025.5 | 5634.7 | 3190.5 | 3794.1 | 4392.7 | 4610.55 | 4828.4 | 5046.25
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) |  | 761.6 | 1478.2 | 2138.3 | 2779.9 | 3425.2 | 4096.858 | 4773.816 | 5467.774 | 3043.874 | 3687.274 | 4272.074 | 4501.274 | 4681.374 | 4910.874
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | N/A | 1 | [11 empty] | 1 | 1 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | bar: 2005-12-31 to 2006-10-31
Schedule Variance (SV) is defined as (BCWP - BCWS) | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | N/A | 1.2901 | 1.164 | 1.1499 | 1.1222 | 1.1131 | 1.0773 | 1.0527 | 1.0305 | 1.0482 | 1.029 | 1.0282 | 1.0243 | 1.0314 | 1.0276 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | N/A | 220.925 | 242.45 | 320.475 | 339.6 | 387.4 | 316.542 | 251.684 | 166.926 | 146.626 | 106.826 | 120.626 | 109.276 | 147.026 | 135.376 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | N/A | 0% | [11 empty] | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | bar: 2005-12-31 to 2006-10-31
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | N/A | 22.49% | 14.09% | 13.03% | 10.89% | 10.16% | 7.172% | 5.008% | 2.962% | 4.596% | 2.816% | 2.746% | 2.37% | 3.045% | 2.683% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | N/A | 1.2901 | 1.164 | 1.1499 | 1.1222 | 1.1131 | 1.0773 | 1.0527 | 1.0305 | 1.0482 | 1.029 | 1.0282 | 1.0243 | 1.0314 | 1.0276 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## GEO IDE
NESDIS GEO IDE |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 41900 | 41900 | 41900 | 41900 | 41900 | 41900 | 41900 | 41900 | 41900 | 41900 | 41900 | 41900
BY Exh.300.I.B.SOS Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
Budget at Completion (BAC) |  |  | 2006-10-31: 42140 | 42140 | 42140 | 42140 | 42140 | 42140 | 42140 | 42140 | 42140 | 42140 | 42140 | 42140
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV)
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV)
Actual Cost of Work Performed (ACWP) or Actual Cost (AC)
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance (SV) is defined as (BCWP - BCWS) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## GOES
NESDIS GOES Ground |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) |  | 24869 | 24869 | 24869 | 30954 | 30954 | 30954 | 30954 | 30954 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444 | 18444
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 150 | 300 | 4550 | 10885 | 11134 | 12329 | 12704 | 12739 | 12739 | 12639 | 12639 | 12639
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 150 | 300 | 4550 | 10885 | 11134 | 12329 | 12704 | 12739 | 12739 | 12639 | 12639 | 12639
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 150 | 300 | 4550 | 10885 | 11134 | 12329 | 12704 | 12739 | 12739 | 12639 | 12639 | 12639
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance (SV) is defined as (BCWP - BCWS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## NDE
NESDIS NPOESS Data Exploitation |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) |  |  | 2006-05-31: 2977.887; 2006-06-30: 2977.887; 2006-07-31: 44798; 2006-08-30: 44798; 2006-09-30: 44798; 2006-10-31: 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798 | 44798
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) |  |  | 2006-05-31: 262.146; 2006-06-30: 448.761; 2006-07-31: 882.831; 2006-08-30: 1202.079; 2006-09-30: 1442.957; 2006-10-31: 1677.346 | 1860.816 | 2036.99 | 2229.247 | 2408.377 | 2607.802 | 2798.869 | 2999.488 | 3188.164 | 3374.453 | 3567.906 | 3737.48
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) |  |  | 2006-05-31: 252.141; 2006-06-30: 415.439; 2006-07-31: 839.085; 2006-08-30: 1115.196; 2006-09-30: 1352.795; 2006-10-31: 1581.918 | 1751.948 | 2039.332
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) |  |  | 2006-05-31: 248.348; 2006-06-30: 419.07; 2006-07-31: 842.194; 2006-08-30: 1147.762; 2006-09-30: 1374.289; 2006-10-31: 1608.039 | 1776.484 | 1973.574
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.96183 | 0.92575 | 0.95045 | 0.92772 | 0.93752 | 0.94311 | 0.94149 | 1.0011 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -10.005 | -33.322 | -43.746 | -86.883 | -90.162 | -95.428 | -108.868 | 2.342 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.0153 | 0.99134 | 0.99631 | 0.97163 | 0.98436 | 0.98376 | 0.98619 | 1.0333 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3.793 | -3.631 | -3.109 | -32.566 | -21.494 | -26.121 | -24.536 | 65.758 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -3.817% | -7.425% | -4.955% | -7.228% | -6.248% | -5.689% | -5.851% | 0.115% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1.504% | -0.874% | -0.3705% | -2.92% | -1.589% | -1.651% | -1.4% | 3.224% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0.97652 | 0.91773 | 0.94694 | 0.9014 | 0.92285 | 0.92779 | 0.92849 | 1.0345 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## NPOESS
NESDIS NPOESS |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 813231 | 813231 | 813231 | 813231 | 813231 | 813231 | 813231 | 813231 | 813231 | 813231 | 813231 | 813231
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 14424 | 14424 | 14424 | 14424 | 14424 | 14424 | 14424 | 14424 | 14424 | 14424 | 14424 | 14424
Budget at Completion (BAC) | 441055 | 441055 | 441055 | 441055 | 92341 | 92341 | 92341 | 92610 | 92610 | 92610 | 92610 | 140966 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655 | 827655
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) |  |  |  |  | 33629 | 42010 | 48127 | 54015 | 60690 | 65584 | 71072 | 77703 | 85357 | 90750 | 96492 | 99906 | 104911 | 110926 | 115964 | 121019 | 126638 | 130900 | 135424 | 140966
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) |  |  |  |  | 33999 | 42698 | 48194 | 53951 | 61047 | 66116 | 71409 | 78340 | 85602 | 90381 | 96227
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) |  |  |  |  | 33581 | 41530 | 47326 | 53216 | 59656 | 64187 | 69347 | 76416 | 83567 | 88555 | 93712
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | N/A | N/A | N/A | N/A | 1.011 | 1.0164 | 1.0014 | 0.99882 | 1.0059 | 1.0081 | 1.0047 | 1.0082 | 1.0029 | 0.99593 | 0.99725 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | N/A | N/A | N/A | N/A | 370 | 688 | 67 | -64 | 357 | 532 | 337 | 637 | 245 | -369 | -265 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | N/A | N/A | N/A | N/A | 1.0124 | 1.0281 | 1.0183 | 1.0138 | 1.0233 | 1.0301 | 1.0297 | 1.0252 | 1.0244 | 1.0206 | 1.0268 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | N/A | N/A | N/A | N/A | 418 | 1168 | 868 | 735 | 1391 | 1929 | 2062 | 1924 | 2035 | 1826 | 2515 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | N/A | N/A | N/A | N/A | 1.1% | 1.638% | 0.1392% | -0.1185% | 0.5882% | 0.8112% | 0.4742% | 0.8198% | 0.287% | -0.4066% | -0.2746% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | N/A | N/A | N/A | N/A | 1.229% | 2.735% | 1.801% | 1.362% | 2.279% | 2.918% | 2.888% | 2.456% | 2.377% | 2.02% | 2.614% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | N/A | N/A | N/A | N/A | 1.0236 | 1.045 | 1.0198 | 1.0126 | 1.0293 | 1.0384 | 1.0346 | 1.0336 | 1.0273 | 1.0165 | 1.024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## OSDPD
NESDIS OSDPD CIP |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) |  |  |  |  | 12897.742 | 12897.742 | 12897.742 | 12897.742 | 12897.742 | 13675.742 | 13675.742 | 13675.742 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779 | 13779
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 50 | 50 | 50 | 5876 | 4609 | 4609 | 4650.665 | 4774.332 | 4924.999 | 4973.205 | 5528.6 | 6770.913 | 6970.077 | 7098.825 | 7453.817 | 7622.617 | 7740.839 | 7932.359 | 8227.359 | 8412.679 | 8520.519 | 8923.339 | 8990.839 | 9057.639
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 50 | 50 | 50 | 4659 | 4609 | 4609 | 4609 | 4630.96 | 4679.253 | 4819.316 | 5883.128 | 6431.544 | 6576.426 | 6820.955 | 7181.782
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 50 | 50 | 50 | 4659 | 4609 | 4609 | 4609 | 4620.167 | 4626.12 | 4781.003 | 5883.044 | 6456.198 | 6670.062 | 6781.103 | 7209.371
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1 | 1 | 1 | 0.79289 | 1 | 1 | 0.99104 | 0.96997 | 0.9501 | 0.96906 | 1.0641 | 0.94988 | 0.94352 | 0.96086 | 0.9635 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | 0 | 0 | 0 | -1217 | 0 | 0 | -41.665 | -143.372 | -245.746 | -153.889 | 354.528 | -339.369 | -393.651 | -277.87 | -272.035 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0023 | 1.0115 | 1.008 | 1 | 0.99618 | 0.98596 | 1.0059 | 0.99617 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.793 | 53.133 | 38.313 | 0.084 | -24.654 | -93.636 | 39.852 | -27.589 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 0% | 0% | 0% | -20.71% | 0% | 0% | -0.8959% | -3.003% | -4.99% | -3.094% | 6.413% | -5.012% | -5.648% | -3.914% | -3.65% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2331% | 1.136% | 0.795% | 0.001428% | -0.3833% | -1.424% | 0.5843% | -0.3842% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 1 | 1 | 1 | 0.79289 | 1 | 1 | 0.99104 | 0.97224 | 0.96101 | 0.97682 | 1.0641 | 0.94625 | 0.93028 | 0.9665 | 0.95982 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## POES
NESDIS POES GS |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) |  | 19247 | 19247 | 19247 | 27143 | 27143 | 27143 | 27143 | 27143 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112 | 20112
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 224 | 448 | 1047 | 9053 | 10028 | 10874 | 11266 | 11464 | 11734 | 10915 | 11183 | 11450 | 12368.6407 | 12703.974 | 13039.3073 | 13374.6407 | 13709.974 | 14045.3073 | 14380.6407 | 14715.974 | 15051.3073 | 15386.6407 | 15721.974 | 16057.3073
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 224 | 448 | 1047 | 9053 | 10028 | 10874 | 11194 | 11464 | 11734 | 10915 | 11183 | 11450 | 12368.6407 | 12703.974
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 224 | 448 | 1047 | 9053 | 10101 | 10946 | 11194 | 11536 | 11807 | 10987 | 11255 | 11523 | 12442.8525 | 12780.1978
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1 | 1 | 1 | 1 | 1 | 1 | 0.99361 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | 0 | 0 | 0 | 0 | 0 | 0 | -72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 1 | 1 | 1 | 1 | 0.99277 | 0.99342 | 1 | 0.99376 | 0.99382 | 0.99345 | 0.9936 | 0.99366 | 0.99404 | 0.99404 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | 0 | 0 | 0 | 0 | -73 | -72 | 0 | -72 | -73 | -72 | -72 | -73 | -74.2118 | -76.2238 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 0% | 0% | 0% | 0% | 0% | 0% | -0.6391% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | 0% | 0% | 0% | 0% | -0.728% | -0.6621% | 0% | -0.6281% | -0.6221% | -0.6596% | -0.6438% | -0.6376% | -0.6% | -0.6% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 1 | 1 | 1 | 1 | 0.99277 | 0.99342 | 0.99361 | 0.99376 | 0.99382 | 0.99345 | 0.9936 | 0.99366 | 0.99404 | 0.99404 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## NWS AQF
NWS Air Quality Forecasting |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) |  |  | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 9829.8 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969 | 97969
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 7001.3 | 7256.5 | 7372.2 | 7653.6 | 8056.7 | 8462.3 | 8782.1 | 8992.2 | 9210.2 | 9330.5 | 9483.4 | 9829.8 | 14329.8 | 14579.8 | 14891 | 15479.4
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 6997.1 | 7121.2 | 7342.5 | 7541.6 | 7850.4 | 8190.7 | 8624.7 | 8996.4 | 9257.4 | 9445.9 | 9596.5 | 9951.3 | 14216.6 | 14793.9 | 14887.6 | 15134.1
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 6960.8 | 7056.5 | 7153.2 | 7247.6 | 7592.3 | 7941.7 | 8374.3 | 8741 | 8988.2 | 9265.2 | 9537.4 | 9809.6 | 14310.3 | 14562.2 | 14847.9 | 15209.8
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 0.9994 | 0.98135 | 0.99597 | 0.98537 | 0.97439 | 0.9679 | 0.98208 | 1.0005 | 1.0051 | 1.0124 | 1.0119 | 1.0124 | 0.9921 | 1.0147 | 0.99977 | 0.97769 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance (SV) is defined as (BCWP - BCWS) | -4.2 | -135.3 | -29.7 | -112 | -206.3 | -271.6 | -157.4 | 4.2 | 47.2 | 115.4 | 113.1 | 121.5 | -113.2 | 214.1 | -3.4 | -345.3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 1.0052 | 1.0092 | 1.0265 | 1.0406 | 1.034 | 1.0314 | 1.0299 | 1.0292 | 1.03 | 1.0195 | 1.0062 | 1.0144 | 0.99345 | 1.0159 | 1.0027 | 0.99502 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | 36.3 | 64.7 | 189.3 | 294 | 258.1 | 249 | 250.4 | 255.4 | 269.2 | 180.7 | 59.1 | 141.7 | -93.7 | 231.7 | 39.7 | -75.7 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | -0.05999% | -1.865% | -0.4029% | -1.463% | -2.561% | -3.21% | -1.792% | 0.04671% | 0.5125% | 1.237% | 1.193% | 1.236% | -0.79% | 1.468% | -0.02283% | -2.231% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | 0.5188% | 0.9086% | 2.578% | 3.898% | 3.288% | 3.04% | 2.903% | 2.839% | 2.908% | 1.913% | 0.6158% | 1.424% | -0.6591% | 1.566% | 0.2667% | -0.5002% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 1.0046 | 0.99035 | 1.0223 | 1.0253 | 1.0075 | 0.99825 | 1.0114 | 1.0297 | 1.0352 | 1.0321 | 1.0182 | 1.027 | 0.9856 | 1.0308 | 1.0024 | 0.97283 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## AWIPS
NWS AWIPS |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 189616 | 189616 | 189616 | 189616 | 189616 | 189616 | 189616 | 189616 | 189616 | 189616 | 189616 | 189616
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 42623 | 42623 | 42623 | 42623 | 42623 | 42623 | 42623 | 42623 | 42623 | 42623 | 42623 | 42623
Budget at Completion (BAC) |  |  | 90960.6 | 90960.6 | 90960.6 | 90951.9 | 90951.9 | 90951.9 | 90951.9 | 90951.9 | 90951.9 | 90951.9 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239 | 232239
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 20589.6 | 20888.6 | 21162.3 | 21452.9 | 21743.4 | 22084.5 | 22530.9 | 23172 | 23172 | 24124.7 | 25028.9 | 26782 | 26916 | 27137.5 | 27362.3 | 27459.7 | 27905.5 | 28467.5 | 29029.5 | 29433.4 | 29837.3 | 30001 | 30164.8 | 30328.6
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 20589.6 | 20888.6 | 21162.3 | 21452.9 | 21743.4 | 22084.5 | 22530.9 | 23172 | 23172 | 24124.7 | 25026 | 26775.1 | 26916.8 | 27136.3 | 27356 | 27407.2
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 21214.5 | 21401.5 | 21632.4 | 21735.5 | 21901 | 22306 | 22656.9 | 23317.2 | 23317.2 | 24566.1 | 24802.3 | 26576.9 | 26728.1 | 26891.7 | 27105.1 | 27289.1
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.99988 | 0.99974 | 1 | 0.99996 | 0.99977 | 0.99809 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.9 | -6.9 | 0.8 | -1.2 | -6.3 | -52.5 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 0.97054 | 0.97603 | 0.97827 | 0.987 | 0.9928 | 0.99007 | 0.99444 | 0.99377 | 0.99377 | 0.98203 | 1.009 | 1.0075 | 1.0071 | 1.0091 | 1.0093 | 1.0043 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | -624.9 | -512.9 | -470.1 | -282.6 | -157.6 | -221.5 | -126 | -145.2 | -145.2 | -441.4 | 223.7 | 198.2 | 188.7 | 244.6 | 250.9 | 118.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -0.01159% | -0.02576% | 0.002972% | -0.004422% | -0.02302% | -0.1912% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | -3.035% | -2.455% | -2.221% | -1.317% | -0.7248% | -1.003% | -0.5592% | -0.6266% | -0.6266% | -1.83% | 0.8939% | 0.7402% | 0.701% | 0.9014% | 0.9172% | 0.4309% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 0.97054 | 0.97603 | 0.97827 | 0.987 | 0.9928 | 0.99007 | 0.99444 | 0.99377 | 0.99377 | 0.98203 | 1.0089 | 1.0072 | 1.0071 | 1.0091 | 1.009 | 1.0024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## HazCollect
NWS HazCollect |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4762 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242 | 5242
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 4431.5 | 4598 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4698 | 4718 | 4749 | 4762 | 4764 | 4766 | 4768
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 3993.6 | 4143 | 4354 | 4120 | 4213 | 4310 | 4446 | 4553 | 4623 | 4672 | 4695 | 4731 | 4740 | 4762 | 4764 | 4766 | 4768
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 4294.3 | 4428 | 4637 | 4739 | 4820 | 4887 | 5016 | 5117 | 5196 | 5253 | 5280 | 5306 | 5332 | 5353 | 5355 | 5357 | 5359
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 0.90118 | 0.90104 | 0.92678 | 0.87697 | 0.89676 | 0.91741 | 0.94636 | 0.96914 | 0.98404 | 0.99447 | 0.99936 | 1.0028 | 0.9981 | 1 | 1 | 1 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance (SV) is defined as (BCWP - BCWS) | -437.9 | -455 | -344 | -578 | -485 | -388 | -252 | -145 | -75 | -26 | -3 | 13 | -9 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 0.92998 | 0.93564 | 0.93897 | 0.86938 | 0.87407 | 0.88193 | 0.88636 | 0.88978 | 0.88972 | 0.8894 | 0.8892 | 0.89163 | 0.88897 | 0.88959 | 0.88964 | 0.88968 | 0.88972 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | -300.7 | -285 | -283 | -619 | -607 | -577 | -570 | -564 | -573 | -581 | -585 | -575 | -592 | -591 | -591 | -591 | -591 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | -9.882% | -9.896% | -7.322% | -12.3% | -10.32% | -8.259% | -5.364% | -3.086% | -1.596% | -0.5534% | -0.06386% | 0.2755% | -0.1895% | 0% | 0% | 0% | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | -7.53% | -6.879% | -6.5% | -15.02% | -14.41% | -13.39% | -12.82% | -12.39% | -12.39% | -12.44% | -12.46% | -12.15% | -12.49% | -12.41% | -12.41% | -12.4% | -12.4% | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 0.83808 | 0.84305 | 0.87022 | 0.76242 | 0.78383 | 0.80909 | 0.83882 | 0.86232 | 0.87552 | 0.88447 | 0.88864 | 0.89409 | 0.88729 | 0.88959 | 0.88964 | 0.88968 | 0.88972 | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## NERON
NWS NERON |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 34496 | 34496 | 34496 | 34496 | 34496 | 34496 | 34496 | 34496 | 34496 | 34496 | 34496 | 34496
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600
Budget at Completion (BAC) | 200498 | 201125 | 201125 | 201125 | 201125 | 201125 | 201125 | 4698 | 4698 | 4698 | 4698 | 4762 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096 | 40096
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 46.253 | 169.42 | 214.353 | 347.626 | 467.7 | 604.728 | 1015.678 | 0 | 0 | 0 | 0 | 0 | 0 | 12218 | 12474 | 12674 | 12874 | 13118 | 13418 | 13718 | 14022 | 14322 | 14622 | 16448
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 46.253 | 168.248 | 213.181 | 346.454 | 482.8 | 590.496 | 1091.183 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 11668 | 11868
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 46.793 | 181.702 | 226.635 | 402.325 | 513.4 | 640.791 | 1164.763 | 0 | 0 | 0 | 0 | 0 | 0 | 11818 | 11986 | 12172
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1 | 0.99308 | 0.99453 | 0.99663 | 1.0323 | 0.97647 | 1.0743 | N/A | N/A | N/A | N/A | N/A | N/A | 0.94123 | 0.93539 | 0.93641 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | 0 | -1.172 | -1.172 | -1.172 | 15.1 | -14.232 | 75.505 | N/A | N/A | N/A | N/A | N/A | N/A | -718 | -806 | -806 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 0.98846 | 0.92596 | 0.94064 | 0.86113 | 0.9404 | 0.92151 | 0.93683 | N/A | N/A | N/A | N/A | N/A | N/A | 0.97309 | 0.97347 | 0.97502 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | -0.54 | -13.454 | -13.454 | -55.871 | -30.6 | -50.295 | -73.58 | N/A | N/A | N/A | N/A | N/A | N/A | -318 | -318 | -304 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 0% | -0.6918% | -0.5468% | -0.3371% | 3.229% | -2.353% | 7.434% | N/A | N/A | N/A | N/A | N/A | N/A | -5.877% | -6.461% | -6.359% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | -1.167% | -7.997% | -6.311% | -16.13% | -6.338% | -8.517% | -6.743% | N/A | N/A | N/A | N/A | N/A | N/A | -2.765% | -2.725% | -2.562% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 0.98846 | 0.91955 | 0.93549 | 0.85823 | 0.97076 | 0.89982 | 1.0065 | N/A | N/A | N/A | N/A | N/A | N/A | 0.91591 | 0.91057 | 0.91302 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## NPI
NWS NEXRAD PPI |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 90820 | 90820 | 90820 | 90820 | 90820 | 90820 | 90820 | 90820 | 90820 | 90820 | 90820 | 90820
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 7672 | 7672 | 7672 | 7672 | 7672 | 7672 | 7672 | 7672 | 7672 | 7672 | 7672 | 7672
Budget at Completion (BAC) | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98060 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492 | 98492
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 43023 | 44728 | 46286 | 47486 | 48374 | 49203 | 49991 | 50717 | 51421 | 52118 | 52825 | 53698 | 54535 | 55282 | 56119 | 56885 | 57409 | 57953 | 58436 | 58920 | 59403 | 60050 | 60697
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 35401 | 37178 | 38534 | 42176 | 44237 | 46397 | 47954 | 49573 | 51135 | 52151 | 53037 | 54258 | 54738 | 55314 | 55945 | 56696
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 35853 | 37420 | 38848 | 39657 | 41374 | 43873 | 45708 | 47482 | 48804 | 50265 | 52351 | 52842 | 53142 | 53455 | 53591 | 53916
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 0.82284 | 0.8312 | 0.83252 | 0.88818 | 0.91448 | 0.94297 | 0.95925 | 0.97744 | 0.99444 | 1.0006 | 1.004 | 1.0104 | 1.0037 | 1.0006 | 0.9969 | 0.99668 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | N/A
Schedule Variance (SV) is defined as (BCWP - BCWS) | -7622 | -7550 | -7752 | -5310 | -4137 | -2806 | -2037 | -1144 | -286 | 33 | 212 | 560 | 203 | 32 | -174 | -189 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | N/A
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 0.98739 | 0.99353 | 0.99192 | 1.0635 | 1.0692 | 1.0575 | 1.0491 | 1.044 | 1.0478 | 1.0375 | 1.0131 | 1.0268 | 1.03 | 1.0348 | 1.0439 | 1.0516 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | -452 | -242 | -314 | 2519 | 2863 | 2524 | 2246 | 2091 | 2331 | 1886 | 686 | 1416 | 1596 | 1859 | 2354 | 2780 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | -17.72% | -16.88% | -16.75% | -11.18% | -8.552% | -5.703% | -4.075% | -2.256% | -0.5562% | 0.06332% | 0.4013% | 1.043% | 0.3722% | 0.05789% | -0.3101% | -0.3322% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | -1.277% | -0.6509% | -0.8149% | 5.973% | 6.472% | 5.44% | 4.684% | 4.218% | 4.559% | 3.616% | 1.293% | 2.61% | 2.916% | 3.361% | 4.208% | 4.903% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 0.81247 | 0.82583 | 0.82579 | 0.94459 | 0.97776 | 0.99722 | 1.0064 | 1.0205 | 1.0419 | 1.0382 | 1.0172 | 1.0375 | 1.0339 | 1.0354 | 1.0407 | 1.0481 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## NWSTG
NWS NWSTG |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) | 6808.08 | 6808.08 | 6808.08 | 6808.08 | 6808.08 | 6808.08 | 6808.08 | 14454.892 | 14454.892 | 14454 | 14454 | 14454 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647 | 22647
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 6949.57 | 7168.04 | 7532.61 | 7707.11 | 7977.43 | 8184.58 | 8332.25 | 14870.55 | 14996 | 15061.95 | 15228.67 | 15406.8 | 15591.93 | 15781.7 | 15910.51 | 15921.84 | 15933.539 | 15945.238 | 15956.938 | 15968.637
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 6266.28 | 6475.51 | 6936.64 | 7062.1 | 7321.21 | 7361.5 | 7457.75 | 13883.29 | 13980 | 14013.89 | 14154.19 | 14289.49 | 14424.79 | 14578.16 | 14694.98 | 14706.31
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 6393.73 | 6596.05 | 6963.74 | 7086.42 | 7315.95 | 7760.75 | 7868.78 | 14243.75 | 14350 | 14402.79 | 14574.19 | 14755.6 | 14937 | 15130.36 | 15247.18 | 15258.51
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 0.90168 | 0.90339 | 0.92088 | 0.91631 | 0.91774 | 0.89944 | 0.89505 | 0.93361 | 0.93225 | 0.93042 | 0.92944 | 0.92748 | 0.92514 | 0.92374 | 0.9236 | 0.92366 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | N/A | N/A | N/A | N/A
Schedule Variance (SV) is defined as (BCWP - BCWS) | -683.29 | -692.53 | -595.97 | -645.01 | -656.22 | -823.08 | -874.5 | -987.26 | -1016 | -1048.06 | -1074.48 | -1117.31 | -1167.14 | -1203.54 | -1215.53 | -1215.53 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | N/A | N/A | N/A | N/A
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 0.98007 | 0.98173 | 0.99611 | 0.99657 | 1.0007 | 0.94856 | 0.94776 | 0.97469 | 0.97422 | 0.973 | 0.97118 | 0.96841 | 0.96571 | 0.9635 | 0.96378 | 0.96381 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | -127.45 | -120.54 | -27.1 | -24.32 | 5.26 | -399.25 | -411.03 | -360.46 | -370 | -388.9 | -420 | -466.11 | -512.21 | -552.2 | -552.2 | -552.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | -9.832% | -9.661% | -7.912% | -8.369% | -8.226% | -10.06% | -10.5% | -6.639% | -6.775% | -6.958% | -7.056% | -7.252% | -7.486% | -7.626% | -7.64% | -7.634% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | -2.034% | -1.861% | -0.3907% | -0.3444% | 0.07185% | -5.423% | -5.511% | -2.596% | -2.647% | -2.775% | -2.967% | -3.262% | -3.551% | -3.788% | -3.758% | -3.755% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 0.88371 | 0.88688 | 0.9173 | 0.91317 | 0.9184 | 0.85316 | 0.84829 | 0.90998 | 0.90821 | 0.90529 | 0.90266 | 0.89818 | 0.89342 | 0.89003 | 0.89015 | 0.89023 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## OHD
NWS OHD |  |  | FY06Q1 |  |  | FY06Q2 |  |  | FY06Q3 |  |  | FY06Q4 |  |  | FY07Q1 |  |  | FY07Q2 |  |  | FY07Q3 |  |  | FY07Q4
| $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K | $K
| 2005-10-31 | 11/31/2005 | 2005-12-31 | 2006-01-31 | 2006-02-28 | 2006-03-31 | 2006-04-30 | 2006-05-31 | 2006-06-30 | 2006-07-31 | 2006-08-30 | 2006-09-30 | 2006-10-31 | 11/31/2006 | 2006-12-31 | 2007-01-31 | 2007-02-28 | 2007-03-31 | 2007-04-30 | 2007-05-31 | 2007-06-30 | 2007-07-31 | 2007-08-30 | 2007-09-30
BY Exh.300.I.B.SOS.SubTot-Planning & Acq. Total Years |  |  | 2006-10-31: 21053 | 21053 | 21053 | 21053 | 21053 | 21053 | 21053 | 21053 | 21053 | 21053 | 21053 | 21053
BY Exh.300.I.B.SOS.Govt. FTE Planning & Acq. Total Years |  |  | 2006-10-31: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Budget at Completion (BAC) | 11253 | 11253 | 11253 | 11253 | 11253 | 11253 | 11253 | 11253 | 11253 | 11253 | 20553 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533 | 20533
Budget Cost of Work Scheduled (BCWS) or Planned Value (PV) | 3555 | 3632 | 3661 | 3722 | 3784 | 3846 | 3908 | 3970 | 4032 | 4094 | 4323 | 4468 | 4637 | 4806 | 4974 | 5143 | 5312 | 5481 | 5649 | 5818 | 5987 | 6156 | 6324 | 6493
Budgeted Cost of Work Performed (BCWP) or Earned Value (EV) | 3787 | 3831 | 3831 | 3934 | 3971 | 4005 | 4043 | 4054 | 4178 | 4207 | 4480 | 4650 | 4839 | 5003 | 5125 | 5217
Actual Cost of Work Performed (ACWP) or Actual Cost (AC) | 3570 | 3630 | 3690 | 3750 | 3815 | 3860 | 3919 | 3953 | 4003 | 4105 | 4324 | 4452 | 4615 | 4810 | 5036 | 5222
Schedule Performance Index (SPI) is defined as (BCWP/BCWS) or (EV/PV) | 1.0653 | 1.0548 | 1.0464 | 1.057 | 1.0494 | 1.0413 | 1.0345 | 1.0212 | 1.0362 | 1.0276 | 1.0363 | 1.0407 | 1.0436 | 1.041 | 1.0304 | 1.0144 | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input | SPI pending EV input
Schedule Variance (SV) is defined as (BCWP - BCWS) | 232 | 199 | 170 | 212 | 187 | 159 | 135 | 84 | 146 | 113 | 157 | 182 | 202 | 197 | 151 | 74 | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input | SV pending EV input
Cost Performance Index (CPI) is defined as (BCWP/ACWP) or (EV/AC) | 1.0608 | 1.0554 | 1.0382 | 1.0491 | 1.0409 | 1.0376 | 1.0316 | 1.0256 | 1.0437 | 1.0248 | 1.0361 | 1.0445 | 1.0485 | 1.0401 | 1.0177 | 0.99904 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance (CV) is defined as (BCWP - ACWP) | 217 | 201 | 141 | 184 | 156 | 145 | 124 | 101 | 175 | 102 | 156 | 198 | 224 | 193 | 89 | -5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Schedule Variance Percent (SV%) is defined as (BCWP - BCWS) / BCWS | 6.526% | 5.479% | 4.644% | 5.696% | 4.942% | 4.134% | 3.454% | 2.116% | 3.621% | 2.76% | 3.632% | 4.073% | 4.356% | 4.099% | 3.036% | 1.439% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Variance Percent (CV%) is defined as (BCWP - ACWP) / BCWP | 5.73% | 5.247% | 3.681% | 4.677% | 3.928% | 3.62% | 3.067% | 2.491% | 4.189% | 2.425% | 3.482% | 4.258% | 4.629% | 3.858% | 1.737% | -0.09584% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Cost Schedule Index (CSI) is the product (CPI X SPI) | 1.13 | 1.1132 | 1.0864 | 1.1088 | 1.0923 | 1.0805 | 1.0673 | 1.0472 | 1.0815 | 1.0531 | 1.0737 | 1.087 | 1.0942 | 1.0828 | 1.0486 | 1.0134 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A