Acknowledgments

The data gathering and analysis that provided the basis for this document were performed by the members of the Program Evaluation Branch with the assistance and support of other individuals.  The members of this evaluation team, which included FAA Headquarters and Regional personnel and FAA support contractor personnel, were responsible for planning the evaluation, executing the plan, and reporting the results.

The team would like to thank all of those interviewed and surveyed for their time and their suggestions.  The evaluation team also extends special thanks to those high level officials who reviewed the various drafts of the report.  These individuals, who represented the Research and Acquisitions and Air Traffic Services lines of business and the Office of the General Counsel, provided valuable inputs.

Executive Summary

On November 15, 1995, the President signed the Department of Transportation and Related Agencies Appropriations Act of 1996 (Public Law 104–50), which directed the FAA Administrator to:

(develop and implement(an Acquisition Management System for the Federal Aviation Administration that addresses the unique needs of the agency and, at a minimum, provides for more timely and cost-effective acquisition of equipment and materials.

The FAA Reauthorization Act of 1996 (Public Law 104–264, dated October 9, 1996), expanding the procurement reforms previously authorized by Public Law 104–50, provided the FAA Administrator increased autonomy in carrying out the functions of the office and the authority to enter into contracts, grants, cooperative agreements, and other transactions with public and private entities on such terms and conditions as were considered appropriate.

The FAA developed its Acquisition Management System (AMS) in response to Public Laws 104–50 and 104–264.  On April 1, 1996, the system went into effect.  In June 1997, the FAA published a revised and updated version of the AMS policy document developed to further clarify and refine basic concepts of AMS.

This report presents the results of the second annual evaluation of FAA acquisition reform.  When acquisition reform was initiated, the Associate Administrator for Research and Acquisitions directed the Program Evaluation Branch to report annually on the status of acquisition reform.  The FAA Program Evaluation Branch reported the results of the implementation of AMS in the first year in its report, “Evaluation of FAA Acquisition Reform, The First Year:  April 1996–March 1997,” dated May 1997.

The first year evaluation report observed the progress of AMS implementation, the impact of AMS on the FAA, and the effectiveness of some parts of the acquisition process.  The second annual evaluation covered the two-year period April 1996–

March 1998, and assessed whether the FAA was on track to achieve its goal of more timely and cost-effective acquisitions of equipment and materials.  The second annual evaluation was also planned and performed, and results were reported, under the direction of the FAA Program Evaluation Branch.

The objective for the second annual evaluation of AMS was to determine whether the FAA was on track to achieve more timely and cost-effective acquisitions of equipment and materials.  To make that determination, the evaluation team chose six component areas and developed an evaluation objective for each area.  The six critical areas represented key processes, decision making bodies, and systems within acquisition reform, and included:  (1) mission analysis, (2) investment analysis, (3) baseline management, (4) the Joint Resources Council (JRC), (5) the Integrated Product Development System (IPDS), and (6) procurement.  The following table lists the objectives for each of the six component areas evaluated.

Evaluation Objectives for Component Areas

| Evaluated Area | Evaluation Objective |
| --- | --- |
| Mission Analysis | Determine whether the FAA’s mission analysis process identified and prioritized shortfalls and opportunities for meeting its mission. |
| Investment Analysis | Determine whether the investment analysis process, including Systems Engineering/Operational Analysis Team activities, complied with AMS and provided adequate support to permit sound investment decisions. |
| Baseline Management | Determine whether the FAA established effective baselines and used each baseline as a primary tool to measure and monitor a program’s progress. |
| The Joint Resources Council | Determine whether the Joint Resources Council made fully supported decisions in a timely manner and documented its decisions, rationale, and assigned actions. |
| The Integrated Product Development System | Determine whether the Integrated Product Development System structure for acquisition programs was fully implemented, operated free of unnecessary constraints, and was effective in supporting successful acquisitions. |
| Procurement | Determine whether procurements under AMS resulted in more cost-effective procurements and whether there were impacts on social goals and competition. |

This second annual report covers the first two years of AMS.  During the first year review, the evaluation team relied more on perceptions and opinions of affected and surveyed individuals because AMS was so new and little documentation existed at the time of the review.  During the second year review, the evaluation team relied more on supporting documentation and evidence.

Second year evaluation activities addressed those AMS processes, systems, and decision making bodies that were crucial to the success of acquisition reform.  The Program Evaluation Branch relied on a variety of data sources for its analysis of acquisition reform progress in the FAA, including:

- reviews of AMS policy, guidance, and procedure documents;

- interviews and surveys of FAA and contractor personnel;

- reviews of meeting minutes and Records of Decision from the JRC, the Systems Engineering/Operational Analysis Team (SEOAT), and IPDS teams;

- analyses of outputs from FAA databases and information systems;

- analyses of AMS-related program documents (e.g., Mission Need Statements, Investment Analysis Reports, Acquisition Program Baselines (APBs) and other baseline documents, Requirements Documents, Integrated Program Plans, Acquisition Strategy Papers); and

- reviews of IPDS organizational charters and Integrated Product Team/Product Team (IPT/PT) Plans.

In addition, samples were selected and reviewed within each of the six evaluation areas.  The samples selected for all six areas also included four selected acquisition programs that moved through various stages of the lifecycle acquisition process.  These four programs included:

- Air Traffic Control Beacon Interrogator Replacement (ATCBI–R),

- National Airspace System Infrastructure Management System (NIMS),

- Operational and Supportability-Implementation System (OASIS), and

- Standard Terminal Automation Replacement System (STARS).

These four programs were selected because, in addition to providing the evaluation team with a common set of acquisition programs from which to measure results, they represented high-visibility FAA acquisitions being accomplished through the new AMS planning, analysis, and execution processes.

# Results

AMS has been in place for two years, and the FAA has made significant progress toward implementing procedures designed to achieve cost and schedule goals.  After the second year, the AMS process was moving in the right direction, but it was still too early to validate the success of acquisition reform.

The agency has achieved more timely acquisitions, but further improvements are necessary if acquisition reform is going to meet the agency’s ambitious goals of reducing the time to field quality products and services by 50 percent and the cost by 20 percent in the third year.  It is essential that improvements identified be fully implemented quickly so the effects can, at the very least, be measured to determine if the FAA’s goals have been realized.

# Progress

Continuous improvements from the first year evaluation report were identified in every major area.  Following are some of the achievements and highlighted improvements implemented under AMS:

- FAA employees, managers, and executives were serious about acquisition reform and AMS, and they made diligent efforts to follow the AMS processes.

- Cross-functional, multi-disciplinary teams did exist and worked together.

- Major procurements were more timely.

- Most FAA employees endorsed and accepted the IPDS structure.

- Content of JRC Records of Decision improved significantly.

- The agency held numerous acquisition reform and AMS training classes in the various AMS processes and concepts.

- Many FAA Investment Analysis Teams formed according to AMS policy.

- The percentage of FAA Facilities and Equipment funded programs having JRC-approved baseline documentation increased from 13 percent reported in the first year of AMS to 54 percent in the second year of AMS.

- The IPDS structure was implemented, acquisitions were included within this structure, and almost half of the IPT/PTs had a formal plan for guidance.

- After an initial decline immediately following the implementation of AMS, the FAA made progress toward achieving socio-economic goals.

- The FAA increased the percentage of major procurements awarded through competition.

# Improvements Needed

Although there were continuous improvements during the second year of AMS, the evaluation team found additional improvements were necessary.  Specifically, the team found that improvements were needed:

- in the mission analysis process, including improvements in identifying, validating, and prioritizing mission needs; receiving full support from all lines of business; and coordinating between the Mission Analysis Steering Group (MASG) and the National Airspace System (NAS) Architecture core team;

- in the investment analysis process in documenting management intervention in solution identification;

- to AMS in addressing SEOAT activities dealing with affordability assessments;

- in baseline management, including establishing complete baselines and compiling and tracking baseline information to assist the agency in measuring and monitoring a program’s progress;

- in the JRC activities to ensure Operations and Maintenance funds were fully considered in lifecycle funding decisions and to ensure action items were tracked and monitored;

- to the FAA Joint Resources Council Guidance to develop a realistic time frame for disseminating Records of Decisions;

- in the IPDS structure to ensure IPDS was fully implemented, operated free of unnecessary constraints, and was effective in supporting successful acquisitions;

- in the procurement segment to ensure the accuracy and completeness of data used to measure results; and

- to the FAA’s overall planning process.

# Findings

Finding 1:  Improvements were needed in identifying, validating, and prioritizing mission needs.

The agency did identify critical needs and did move forward under AMS to address these critical needs.  We found the agency conducted mission analysis on the six programs reviewed in our sample.  We also found the agency had documented 329 mission needs in Mission Need Statements.  However the agency did not follow the AMS process in validating and prioritizing all critical needs that were identified and structured under mission analysis.  Additionally, in some cases, a structured mission analysis was not conducted and a Mission Need Statement was not prepared.

This occurred because:  (1) some critical needs had been previously addressed in programs approved prior to AMS, (2) the lines of business did not always recognize the necessity for identifying and developing Mission Need Statements, and (3) the MASG had not developed guidance on how to prioritize new and existing mission needs.

When critical needs were identified and validated, the agency was better able to plan for the most cost-effective use of resources and provide support for future budget and resource requests.  Prioritizing agency needs would also improve the FAA’s ability to plan effectively.

Finding 2:  Improvements were needed in support of mission analysis and in coordination between the Mission Analysis Steering Group and the National Airspace System Architecture core team.

We found the Associate Administrators for the two lines of business heavily involved in the acquisition process, Air Traffic Services and Research and Acquisitions, complied with AMS and supported the mission analysis process.  The other five lines of business did not have the direct need to become as active in mission analysis and did not have the resources to support mission analysis to the level described by AMS.  We found those five lines of business had not established mission analysis teams and had not provided their staffs with sufficient training in the mission analysis area.  Recognizing this difficulty, the MASG and Air Traffic Services indicated their willingness to provide the needed support in the area of mission analysis to these other lines of business.

We also found that while many MASG members supported the mission analysis process, as many as half of the MASG members were not fully involved, indicating mission analysis was given a low priority by the MASG members and by their respective lines of business.

In addition, improvement was needed in coordination between the NAS Architecture core team and the MASG.  We found the NAS Architecture core team did not coordinate its critical needs and opportunities with the MASG in preparation of the NAS Architecture Version 3.0.  In turn, the MASG did not coordinate mission analysis with the NAS Architecture core team for critical needs and opportunities.  Improving coordination between the NAS Architecture Core team and the MASG would reduce the likelihood of duplicated mission analysis effort, improve capability to identify all needs and eliminate conflicting overall FAA mission needs, and provide for the more efficient use of agency resources.

Finding 3:  Management control improvements were needed for the FAA mission analysis process.

We found the FAA had not established internal controls to ensure Mission Need Statements would be revalidated, when necessary.  As a result, the agency did not know if 56 mission needs were still valid and up to date, or if four new Mission Need Statements duplicated needs identified on prior Mission Need Statements.

We also found the FAA did not establish internal controls to ensure all historical records related to mission needs were collected in a central repository.  We found the agency did establish an official repository for all JRC-approved documents in the Evaluation and Configuration Management Division (ASD-200) and an unofficial repository for other acquisition planning and control documents in the National Airspace System Concept Development Branch (ASD-130).  However, lines of business did not maintain or provide copies of all supporting documentation for acquisition planning and control documents to the unofficial repository.  This occurred because the FAA (1) had not formally established a repository for historical records, other than for JRC-approved documents, relating to all submitted Mission Need Statements, and (2) had not established an internal control to ensure the lines of business maintained all supporting records and provided these supporting documents to a central repository.

Finding 4:  Investment Analysis Teams formed according to AMS, but investment analysis actions were not fully documented.

The FAA Investment Analysis Teams were formed according to AMS policy in five of the  six sample programs reviewed.  However, we found the sponsor or upper level management identified or limited solutions prior to the completion of the alternatives analysis process in two of the six cases, and paperwork prepared to support the investment analysis process did not necessarily document what actually occurred.  For example, in one case, the Requirements Document was written by the sponsor to drive a specific solution, and the sponsor was reluctant to negotiate and identify a core set of top level requirements.  In another case, the solution for a high priority program was identified by upper level management while the Investment Analysis Team was still evaluating different options.

When upper level management intervened in the investment analysis process, it limited the scope of the investment analysis but did not reduce the level of effort required by the Investment Analysis Team.  Because management intervention was not fully documented, it was not clear whether there was a problem within the investment analysis process or whether other concerns drove management’s need to intervene.  In addition, when the intervention was not fully documented, the full decision body may not have been aware an intervention occurred.

Finding 5:  SEOAT affordability assessment requirements under AMS need to be revised.

We found the SEOAT affordability assessment activities did not comply with AMS and may not be able to comply with AMS.  AMS required the SEOAT to perform an affordability assessment on all candidate solutions.  In most cases, the SEOAT performed an affordability assessment on the recommended candidate solution only.  This occurred because time and resource constraints did not permit the level of effort necessary to perform an affordability assessment on each candidate solution.

Finding 6:  The FAA did not establish complete baselines.

During this review, the evaluation team discovered the FAA had not established definitions for, or designations of, “programs,” “substantial programs,” or “major systems acquisitions,” which were essential in identifying the number of programs requiring an APB.  In addition, since the FAA Administrator was required to consider terminating “substantial programs” that failed to meet defined goals, the agency needed to define what a “substantial program” was and set goals for those programs.  The agency also was required to report on “major systems acquisitions” and needed to define that term in order to comply.

Although programs were not defined by the agency, the evaluation team defined and identified 94 Capital Investment Plan programs that should have had APBs.  The Capital Investment Plan included Facilities and Equipment (F&E) funded programs; we found no JRC-approved baseline documentation for Research, Engineering and Development (R,E&D) only or Operations and Maintenance (O&M) only programs.  For the 94 Capital Investment Plan programs, the evaluation team found 51 (54 percent) had some form of baseline documentation:  5 programs had APBs and 46 had Parameter Sheets.  While the other 43 programs had no JRC-approved baseline documentation at all, the 54 percent that did have JRC-approved baseline documentation represented a dramatic improvement over the 13 percent that had JRC-approved baseline documentation in the first year of AMS.

Of the 51 programs with JRC-approved baseline documentation, we found those documents did not always include enough information to measure and monitor the program’s performance.  The evaluation team found that baseline data included in APBs was significantly more complete and comprehensive than baseline data in Parameter Sheets.  For example, performance baselines were complete in APBs, but were incomplete in most Parameter Sheets.  Benefits baselines were complete in most APBs, but were incomplete in most Parameter Sheets.  Schedule baselines were incomplete for most APBs, but were incomplete for all Parameter Sheets.  Cost baselines for all fundings appeared complete for APBs, but was incomplete for all Parameter Sheets.

The evaluation team found R,E&D funding was frequently not included in baseline documents because it was regarded as a “sunk cost” by the time the investment decision was made and the APB was approved.  In addition, O&M funding was not always included on the baseline documents because (1) although O&M funding was provided by the sponsor for each program baseline, it was unclear which organization, if

any, was responsible for all planning and programming for O&M funds; (2) little, if any, current or historical O&M funding data existed, and what was available tended to be unreliable; and (3) the FAA did not have a cost accounting system capable of identifying real O&M costs for existing systems or projected O&M costs for future new systems.  As a result, there was very little credibility associated with the O&M cost estimates contained in APBs and Parameter Sheets.  These poor or inaccurate cost estimates contributed to the incompleteness of the baseline documentation and limited the FAA’s ability to make sound investment decisions based on the economic merits of a proposal.

Even though APBs were more complete than Parameter Sheets, neither type of document was always sufficient to measure a program’s progress or to allow decision makers to make sound decisions on continuing investments.  Approved baseline documentation was intended to provide a mutual agreement between FAA management, represented by the JRC, and the provider, which was typically the IPT.  The absence of formal baseline documentation against which to measure progress restricted decision makers’ abilities to make sound decisions on continued investment.

Finding 7:  Baseline data was not compiled and tracked to assist the agency in measuring and monitoring a program’s progress.

The FAA collected and reported numerous baseline data, but did not collect or track complete or consistent baseline data in order to measure and monitor a program’s progress.  This occurred because the numerous systems and processes used for tracking program status were not integrated, and the FAA did not ensure a standard set of data was collected for comparisons.  Also, the data in these systems and processes did not necessarily reflect current JRC-approved program baselines.  As a result, there was no thorough oversight or tracking of some baselines, and there was no commitment to periodic revalidation of baselines.  In addition, FAA management received limited visibility into program status after the investment decision.

Finding 8:  The Joint Resources Council did not make fully supported and timely decisions.

We found the JRC did not make fully supported decisions when it committed the FAA to full lifecycle funding without consistently considering O&M funds.  Although the JRC had the responsibility to make decisions committing the FAA to full lifecycle funding, the JRC did not have the data needed to commit the FAA’s O&M funding.  The FAA did not have a cost accounting system in place that enabled identification of realistic O&M costs.  The agency was developing a cost accounting system, which is expected to be in place by October 1, 1998.  Without an operational cost accounting system or an effective financial baseline for the required O&M funds, the FAA could not determine if a program was affordable over its full lifecycle.  There was also confusion over the role and authority of the Resource Management Council.

In addition, while we found JRC meeting attendance was generally good, meetings were frequently rescheduled, which delayed JRC decisions.  JRC meetings were rescheduled when a key JRC member requested the meeting be rescheduled, on a case-by-case basis if key participants were not ready for the meeting or had a conflicting obligation, or the required documentation was not provided three days prior to the meeting.  When JRC meetings were rescheduled, decisions that would have been made at those meetings were delayed.  This had the potential to impact other phases of the acquisition process, program schedules and contractual activities.  It also caused staff time to be lost.

Finding 9:  The Joint Resources Council fully documented its decisions and rationale for decisions; however, timeliness in disseminating information and tracking action items needed improvement.

We found the JRC fully documented its decisions and rationale for decisions during the second year of AMS.  During the second year of AMS, JRC Records of Decision were expanded from a one-page document with little information to a full explanation of JRC decisions, including rationale, discussion, and participant quotes.  With improved JRC Records of Decision, the FAA had a better historical record of what occurred at JRC meetings and better documentation of the rationale for decisions made.

Timeliness in disseminating information and tracking action items, however, needed improvement.  The FAA Joint Resources Council Guidance required the JRC Record of Decision to be prepared and issued within five working days.  We found it took an average of 36 working days to disseminate these Records of Decision during the first year of AMS and 36.9 working days the second year of AMS.  While we believe 36 working days was too long, 5 working days was unrealistic.

We also found there was no formal process in place to track action items assigned at JRC meetings during the time of our review.  The informal process being used to track action items assigned at JRC meetings was not adequate, and some JRC meetings adjourned without a clear understanding among JRC members and participants of the specific action items assigned, including what was required, who was responsible, and when the action was to be completed.  JRC members and participants were sometimes confused about assigned action items, responsible organizations, and due dates.  Although action items were recorded in the JRC Records of Decision, they were not always captured effectively during the meetings to ensure JRC members and participants understood and agreed to them.  Because JRC Records of Decision were the only formal documentation of JRC decisions, until they were signed and disseminated, some actions required by the JRC decision were not implemented.  As a result, actions may not have been completed appropriately.  In addition, without a tracking process to close out completed action items, the JRC could not monitor action items assigned.  Before we completed our review, we confirmed that an automated system to track, follow up on, and close assigned action items was being designed to address some of these concerns.

Finding 10:  Some constraints impacted the support of successful acquisitions within the Integrated Product Development System.

The agency initiated IPDS prior to acquisition reform and formally incorporated IPDS into the acquisition reform process during the development of AMS.  Technically, an IPDS structure can consist of something as informal as the contracting officer and someone requesting the product.  Using this as a basis, we concluded that the IPDS structure was implemented.  Irrespective of that broad definition, we found that most acquisitions were included within the formal IPDS structure, and almost half of the IPT/PTs had a formal plan for guidance.  There were some constraints, however, which impacted IPDS in supporting successful acquisitions.  There were also areas where AMS requirements were more stringent than necessary under the circumstances.

Constraints impacting the ability of the IPDS structure to support successful acquisitions included: (1) conflicts between the horizontal (IPDS team lifecycle responsibilities concept) and vertical (line of business functional responsibilities concept) structures, (2) the lack of authority of IPT/PT leadership over all team members, and  (3) an inability of IPDS teams to resolve major agency issues.  These constraints delayed decisions, which could have prolonged the acquisition process and, in turn, could have increased acquisition costs.

In addition, we found some areas where AMS requirements or IPDS Team Plan Guidelines were more stringent than necessary under the circumstances.  For example, we found not all acquisitions were suitable for inclusion within the formal IPT structure as required by AMS.  Acquisitions such as facilities or services may not need to be under the IPT structure; however, there were no guidelines to clarify which acquisitions did not need to be under a formal IPT structure.  The IPDS Team Plan Guidelines required IPT/PTs to have formal plans.  However, some IPT/PTs may not need to be under a formal plan at this time.  We found some IPT/PTs were able to manage acquisitions without a formal plan.  We did find, however, that 25 out of 53 (47 percent) of the IPT/PTs were under formal plans during the second year under AMS, representing a marked improvement over the first year of AMS.  The goal to have a formal plan for all formal IPDS teams is a good one and should continue to be implemented.

Finding 11:  Major procurements were more timely under AMS.

Major procurements were more timely under AMS while costs to conduct procurements changed very little.  Based on analysis of the random sample selected, the evaluation team determined contracts were awarded an average of 56.2 days faster after the implementation of AMS while dollars expended to award contract actions dropped from $8 million to $7.6 million.  The overall goal of FAA acquisition reform was to reduce the time to acquire and field new systems by 50 percent and to reduce the costs of acquisitions by 20 percent, both by April 1999.  These results would be measured from the investment decision through first commissioning of a new system.  The portion of procurement timeliness covered in this section of the AMS evaluation report represents the procurement segment of the acquisition process only.

While major procurements were more timely under AMS, and costs to conduct procurements changed very little, the evaluation team was still unable to quantify whether procurements were more cost-effective because cost-effectiveness includes more than just quicker (more timely) procurements.  Cost-effectiveness also includes costs to conduct the procurements, the cost of the procurements themselves, and all other acquisition costs.  Because sufficient information did not exist to analyze costs of acquisitions, we looked only at the costs to conduct the procurements.  We found dollars expended to award contract actions dropped from $8 million to $7.6 million while contract dollars awarded dropped from $551 million to $495 million.  Since the implementation of AMS, total dollars expended for procurement operations, total number of employees conducting procurement operations, and total dollars awarded for contracts all decreased.  However, without a detailed cost accounting system to         (1) segregate procurement operations conducted by procurement personnel but not related to procurement award activities, such as contract administration, etc., from the total procurement expense; and (2) capture full costs of acquisitions, we were unable to make a conclusion on whether procurements were more cost-effective.

Finding 12:  The FAA appeared to have made progress toward achieving socio-economic goals.

After an initial decline immediately following the implementation of AMS, the FAA appeared to have made progress toward achieving socio-economic goals.  However, because the data used to report progress in this area was incomplete or inaccurate, the evaluation team could not accurately determine the true impact of AMS on socio-economic goals.

Although awards to businesses identified in the socio-economic program goals decreased in the six-month period immediately following the implementation of AMS, the FAA made steady improvement in awards to those businesses after the initial six-month period.  For example, the percentage of awards to small businesses in general decreased from 27 percent in the last six-month period prior to AMS to 18 percent for the six-month period immediately following the implementation of AMS.  By contrast, when the evaluation team compared the results from the first six-month period following the implementation of AMS to the results from the full seven quarters following AMS, we determined that the percentage of awards to small businesses increased from             18 percent to 52 percent.  Similarly, set-aside awards to disadvantaged businesses certified by the Small Business Administration under Section 8(a) (referred to as SEDB awards) increased from 10 percent for the first six-month period to 12 percent for the full seven quarters following AMS, and awards to disadvantaged businesses that were self-certified or certified by the Small Business Administration but received awards through a process other than the set-aside process (referred to as SDB awards), increased from 2 percent to 3 percent.

The evaluation team identified these improvements based on information from Major Procurement Program Goals reports submitted to the FAA’s Small Business Utilization Staff.  However, we determined information submitted for the Major Procurement Program Goals reports was frequently incomplete or inaccurate.  In addition, reporting was inconsistent among the FAA Regions, Centers, and Headquarters.

In a separate report entitled “Impact of Acquisition Reform on Awards to Disadvantaged Businesses” issued May 20, 1998, the FAA’s Program Evaluation Branch also identified inconsistencies in the data and weaknesses in the systems used to collect and report the FAA’s progress in meeting socio-economic goals.

Without accurate data, the FAA cannot know whether or not it is meeting established socio-economic goals, whether additional efforts to meet those goals are necessary, or whether any additional efforts put in place were effective.

Finding 13:  The percentage of contract dollars awarded through competition increased.

The FAA increased the percentage of major procurement contracts awarded through competition.  To determine the level of competition under AMS, the evaluation team collected and compared data from the Contract Information System database for the eight quarters pre-AMS and the seven quarters under AMS.  The Contract Information System contained data for procurements over $25,000 and identified whether the contracts were awarded through competition or through a noncompetitive process.  After averaging to allow for the different number of quarters for the pre-AMS and AMS periods, we found awards through competition increased from 64 percent before AMS to 70 percent under AMS.

Finding 14:  The FAA’s overall planning process needed improvement.

While performing the six component evaluations, the evaluation team identified one issue that crossed almost all acquisition processes and functional areas.  Because of the interrelated and recurring nature of this issue, we separated it from the rest of the evaluation chapters.

We found that the agency cut funding to multiple and, in some cases, high priority programs to meet its funding levels and changing priorities because it had not properly planned for these issues.  During the past year, there were two major issues that affected funding levels of numerous agency programs.  First, the agency assumed it would receive a fiscal year 1999 funding level that was almost $500 million greater than what was agreed to by the Office of Management and Budget (OMB).  Second, the agency did not anticipate $167 million of reprogramming priorities that surfaced in fiscal year 1998 after the agency received its budget for the year.

The FAA planned and approved program funding profiles within the agency and submitted its fiscal year 1999 budget request to the OMB for almost $500 million higher than the OMB outyear-target-level guidance (i.e., OMB guidance on the maximum funding level to request from the Congress).  In conjunction, the FAA prepared the NAS Architecture with the assumption that OMB would submit this higher request to Congress.  The OMB denied the FAA’s higher budget request to Congress.  When this was disallowed, many Capital Investment Plan lines had to be reworked.  The FAA’s submission of a budget request higher than the OMB outyear-target-level was a one time action on FAA’s part and will not likely reoccur.

In the case of the fiscal year 1998 appropriation from Congress, four unplanned emerging priorities surfaced.  These four priorities were (1) Year 2000, (2) Host and Oceanic Computer System Replacement (HOCSR), (3) additional Standard Terminal Automation Replacement System (STARS) requirements, and (4) additional security funding.  These four unplanned emerging priorities resulted in a $167 million shortage which forced the FAA to reprogram funding on 35 of 113 programs.  One of the four unplanned emerging priorities (the security issue) was outside of the FAA’s control; however, the other three issues were under the FAA’s control and required better planning.

Because the agency was not able to plan based on realistic funding levels and did not anticipate the emerging priority needs, the agency had to adjust cost baselines and reprogram funding from numerous programs.  These actions resulted in deferring the planned implementation of crucial programs and diminished trust between planners, developers, and decision makers when their program work was undermined by deviations from baseline expectations and agreements.

# Recommendations

The following lists all the recommendations included in this report.  The recommendation numbers correlate to the finding numbers; not all of the findings had recommendations.  We limited our recommendations to specific problems identified during the evaluation.  Our evaluation was limited to acquisition reform and did not address all of the FAA’s operations.  While we believe there are other recommendations that could help the FAA improve its overall operations, we limited our recommendations in this report to those issues we found within acquisition reform.  In addition, we were intentionally broad and not specific in our recommendations.  The purpose of our recommendations was to highlight areas that needed to be addressed by the FAA management.  Any solution that corrects the problems identified in our findings would be acceptable.  The ultimate goal is to ensure that acquisition reform succeeds.

The evaluation team recommends:

1A	The FAA Administrator ensure that all critical needs and opportunities emerge from structured mission analysis, are developed into Mission Need Statements with a recommended prioritization, are reviewed for validation, and, if approved, are assigned a prioritization relative to all other approved Mission Need Statements, in accordance with AMS.

1B	The chairperson of the Mission Analysis Steering Group prepare guidance on how to prioritize new and existing mission needs for Joint Resources Council  approval, and ensure approved guidance is implemented.

2A	The chairperson of the Mission Analysis Steering Group ensure the Mission Analysis Steering Group representatives (both members and their alternates) fulfill their responsibilities to the Mission Analysis Steering Group, to include ensuring the AMS mission analysis process is followed and that all mission analysis work in the agency, including the National Airspace System Architecture, is coordinated with the Mission Analysis Steering Group.

2B	The Associate Administrator for each line of business ensure sufficient qualified and trained staff and the appropriate resources are available to perform mission analysis work or delegate this responsibility and authority to the Mission Analysis Steering Group or Air Traffic Services mission analysis team as appropriate and agreed upon.

3A	The chairperson of the Mission Analysis Steering Group develop guidance and procedures on how to conduct and document revalidation of mission needs, and establish a plan with a schedule for accomplishing revalidations.

3B	The chairperson of the Mission Analysis Steering Group develop guidance to establish a central repository for historical records of all supporting documentation for submitted Mission Need Statements, and to ensure each line of business submits all acquisition planning and control supporting documentation to this central repository.

4A	The FAA Acquisition Executive require the changed direction and rationale for any intervention in the investment analysis process be documented at the time of the intervention, and ensure this documentation is included in the Investment Analysis Report used at the investment decision.

5A	The chairperson of the Acquisition System Advisory Group revise the AMS to allow the Systems Engineering/Operational Analysis Team, in conjunction with the Investment Analysis Team, flexibility to determine, on a case-by-case basis, how many viable candidate solutions will have an affordability assessment completed.

6A	The FAA Administrator ensure definitions are developed for “program,” “substantial program,” and “major systems acquisitions,” and that all FAA programs are designated in the appropriate category.

6B	The FAA Acquisition Executive ensure every program, existing or new, has an Acquisition Program Baseline as required by the AMS, or an alternate baseline document, that includes all applicable cost (Facilities and Equipment; Research, Engineering and Development; and Operations and Maintenance), schedule, benefits, and performance parameters.

6C	The FAA Administrator require those organizations or individuals with signature authority for funding, including Facilities and Equipment; Research, Engineering and Development; and Operations and Maintenance, provide all the funding data and their signatures to authorize and commit these funds for each Acquisition Program Baseline.

7A	The FAA Administrator designate a single focal point for all program baseline management and reporting activities.

7B	The FAA Administrator direct the development of an adequate tracking and validation system for benefits, or revise the AMS if it is determined the benefits baselining requirement should not be retained.

7C	The FAA Administrator design and implement procedures for tracking and reporting program status against all approved baselines.

8A	The FAA Administrator combine the responsibility and authority for full lifecycle funding under one Associate/Assistant Administrator level body and clearly define its role, responsibilities, and authority.

8B	The FAA Acquisition Executive ensure each Joint Resources Council member designates a single alternate and empowers this alternate to act in his/her place, and each key Joint Resources Council meeting participant designates a single alternate and empowers this alternate to act in his/her place in order to reduce rescheduling caused by calendar conflicts and to maintain consistency at meetings.  These alternates should possess sufficient knowledge of the duties and responsibilities of the Joint Resources Council member or key participant and should have the appropriate corporate level perspective to serve in this position.

9A	The FAA Acquisition Executive revise the FAA Joint Resources Council Guidance requirement to issue Records of Decision within five days to a realistic period of time; and, develop and document a process for the timely preparation, approval, and dissemination of Joint Resources Council Records of Decision, and ensure that process is followed.

9B	The FAA Acquisition Executive establish an effective means to capture assigned action items during Joint Resources Council meetings (including what is required, who is responsible, and when the action is to be completed) to ensure members and participants understand and agree to all action items assigned; and define and implement a process to track, follow up, close, and disseminate results of action items after Joint Resources Council meetings.

10A	The FAA Administrator ensure that Integrated Product Teams/Product Teams and functional management/organizations jointly select team members, document agreements clarifying team members’ roles and responsibilities, and evaluate team member performance.

10B	The chairperson of the Integrated Product Leadership Team ensure issues raised within the Integrated Product Development System structure are resolved.

12A	The Special Assistant, Small Business Utilization Staff, ensure that FAA Regions, Centers, and Headquarters have accurate, current guidance for development of Major Procurement Program Goals reports and comply with that guidance.

Additional recommendations related to achieving socio-economic goals were addressed in Report #1998-01, “Impact of Acquisition Reform on Awards to Disadvantaged Businesses,” dated May 20, 1998.

14A	The FAA Administrator ensure that the agency performs better planning for its future funding needs to avoid constant funding reductions to on-going programs.  This would involve improving the agency’s (1) mission analysis capabilities, which must be tied strongly to the agency’s approved National Airspace System Architecture; (2) investment analysis capabilities; and            (3) managing of program cost, schedule, performance, and benefits baselines.

Contents

Executive Summary	i

Results	iii

Progress	iii

Improvements Needed	iv

Findings	v

Recommendations	xiii

Second Year Evaluation Overview	1

Evaluation Objectives	1

Scope	2

Methodology	3

Overall Evaluation Results in Brief	3

Follow-Up from the First Year Evaluation	6

Chapter 1(Mission Analysis	7

Evaluation Objective	7

Scope and Methodology	7

Mission Analysis Results in Brief	8

Finding 1:  Improvements were needed in identifying, validating, and prioritizing mission needs.	8

Finding 2:  Improvements were needed in support of mission analysis and in coordination between the Mission Analysis Steering Group and the National Airspace System Architecture core team.	10

Finding 3:  Management control improvements were needed for the FAA mission analysis process.	11

Chapter 2(Investment Analysis	13

Evaluation Objective	13

Scope and Methodology	13

Investment Analysis Results in Brief	14

Finding 4:  Investment Analysis Teams formed according to AMS, but investment analysis actions were not fully documented.	14

Finding 5:  SEOAT affordability assessment requirements under AMS need to be revised.	15

Chapter 3(Baseline Management	17

Evaluation Objective	17

Scope and Methodology	17

Baseline Management Results in Brief	17

Finding 6:  The FAA did not establish complete baselines.	18

Finding 7:  Baseline data was not compiled and tracked to assist the agency in measuring and monitoring a program’s progress.	21

Chapter 4(The Joint Resources Council	25

Evaluation Objective	25

Scope and Methodology	25

Joint Resources Council Results in Brief	26

Finding 8:  The Joint Resources Council did not make fully supported and timely decisions.	26

Finding 9:  The Joint Resources Council fully documented its decisions and rationale for decisions; however, timeliness in disseminating information and tracking action items needed improvement.	28

Chapter 5(The Integrated Product Development System	31

Evaluation Objective	32

Scope and Methodology	32

Integrated Product Development System Results in Brief	32

Finding 10:  Some constraints impacted the support of successful acquisitions within the Integrated Product Development System.	33

Chapter 6(Procurement	37

Evaluation Objective	37

Scope and Methodology	37

Procurement Results in Brief	38

Finding 11:  Major procurements were more timely under AMS.	38

Finding 12:  The FAA appeared to have made progress toward achieving socio-economic goals.	39

Finding 13:  The percentage of contract dollars awarded through competition increased.	42

Chapter 7(Interrelated and Recurring Issue	43

Finding 14:  The FAA’s overall planning process needed improvement.	43

Recommendations	45

Appendix A(Criteria	A–1

Appendix B(List of Acronyms	B–1

List of Tables

Table 1–1.  Evaluation Objectives for Component Areas

Table 1–2.  AMS Training Statistics

Table 1–3.  Status of First Year Evaluation Recommendations

Table 3–1.  Completeness of Baseline Documents

Table 3–2.  Program Reporting

Table 6–1.  Socio-economic Program Goals:  Comparison of Six-month Periods Preceding and Following AMS

Table 6–2.  Socio-economic Program Goals:  Comparison of First Six-month Period to First Seven Quarters Following AMS

Table 7–1.  High Priority Programs With Reprogramming Reductions

List of Figures

Figure 3–1.  Baseline Document Status	19

Figure 5–1.  IPDS Structure	31

Figure 5–2.  Vertical vs. Horizontal Structure	34

Second Year Evaluation Overview

On November 15, 1995, the President signed the Department of Transportation and Related Agencies Appropriations Act of 1996 (Public Law 104–50), which directed the FAA Administrator to:

(develop and implement(an Acquisition Management System for the Federal Aviation Administration that addresses the unique needs of the agency and, at a minimum, provides for more timely and cost-effective acquisition of equipment and materials.

The FAA Reauthorization Act of 1996 (Public Law 104–264, dated October 9, 1996), expanding the procurement reforms previously authorized by Public Law 104–50, provided the FAA Administrator increased autonomy in carrying out the functions of the office and the authority to enter into contracts, grants, cooperative agreements, and other transactions with public and private entities on such terms and conditions as were considered appropriate.

The FAA developed its Acquisition Management System (AMS) in response to Public Laws 104–50 and 104–264.  On April 1, 1996, the system went into effect.  In June 1997, the FAA published a revised and updated version of the AMS policy document developed to further clarify and refine basic concepts of AMS.  The current version of all AMS policy, guidance, templates, and tools may be found in the FAA Acquisition System Toolset (FAST) located on the World Wide Web at http://fast.faa.gov.  FAST is the official repository for all AMS documentation and is updated monthly under strict configuration control.

# Evaluation Objectives

In response to the congressional mandate to provide for more timely and cost-effective acquisition of equipment and materials, the Program Evaluation Branch set as its overall objective to determine whether the FAA was on track to achieve more timely and cost-effective acquisitions of equipment and materials.  The evaluation team chose six component areas and developed evaluation objectives for each area to demonstrate whether the overall objective was achieved.  These critical areas, which represented key processes, decision making bodies, and systems within acquisition reform, included:

- mission analysis,

- investment analysis,

- baseline management,

- the Joint Resources Council (JRC),

- the Integrated Product Development System (IPDS), and

- procurement.

Table 1–1 lists the objective for each of the six component areas evaluated.

Table 1–1.  Evaluation Objectives for Component Areas

| Evaluated Area | Evaluation Objective |
| --- | --- |
| Mission Analysis | Determine whether the FAA’s mission analysis process identified and prioritized shortfalls and opportunities for meeting its mission. |
| Investment Analysis | Determine whether the investment analysis process, including Systems Engineering/Operational Analysis Team activities, complied with AMS and provided adequate support to permit sound investment decisions. |
| Baseline Management | Determine whether the FAA established effective baselines and used each baseline as a primary tool to measure and monitor a program’s progress. |
| The Joint Resources Council | Determine whether the Joint Resources Council made fully supported decisions in a timely manner and documented its decisions, rationale, and assigned actions. |
| The Integrated Product Development System | Determine whether the Integrated Product Development System structure for acquisition programs was fully implemented, operated free of unnecessary constraints, and was effective in supporting successful acquisitions. |
| Procurement | Determine whether procurements under AMS resulted in more cost-effective procurements and whether there were impacts on social goals and competition. |

# Scope

The second annual report generally covered the period between April 1, 1996, and March 30, 1998.  Each of the six segments, however, covered a particular time frame within this two-year period.  It remained difficult to measure the results of acquisition reform after only two years under AMS, since no acquisitions moved totally through the full lifecycle within that time.  As a result, the Program Evaluation Branch focused its efforts on key lifecycle processes, systems, and decision making bodies within the FAA.  The first year evaluation report observed the progress of AMS implementation, the impact of AMS on the FAA, and the effectiveness of some parts of the acquisition process.  This second year report assessed whether the FAA was on track to achieve its goal of more timely and cost-effective acquisitions of equipment and materials, and the third year evaluation will attempt to report on whether the agency has reached that goal.  Because AMS was so new and little documentation existed at the time of the first year review, the evaluation team at that time relied more on perceptions and opinions of affected and surveyed individuals.  During the second year review, the evaluation team relied more on supporting documentation and evidence.

In addition to the individual samples selected within the six evaluation areas, the evaluation team reviewed four selected acquisition programs as they passed through each phase of the lifecycle acquisition process.  These four programs included:

- Air Traffic Control Beacon Interrogator Replacement (ATCBI–R),

- National Airspace System Infrastructure Management System (NIMS),

- Operational and Supportability Implementation System (OASIS), and

- Standard Terminal Automation Replacement System (STARS).

The team selected these four programs because they represented high-visibility FAA acquisitions being accomplished through the new AMS planning, analysis, and execution processes.  These programs provided the evaluation team with a common set of acquisition programs from which to measure acquisition reform.  These programs were in various stages of the acquisition process when AMS was implemented; reviewing these programs provided concrete and illustrative examples of how AMS worked.

# Methodology

Second year evaluation activities addressed those AMS processes, systems, and decision making bodies that were crucial to the success of acquisition reform.  The Program Evaluation Branch relied on a variety of data sources for its analysis of acquisition reform progress in the FAA, including the following:

- reviews of AMS policy, guidance, and procedure documents;

- interviews and surveys of FAA personnel;

- reviews of meeting minutes and Records of Decision from the JRC, the Systems Engineering/Operational Analysis Team (SEOAT), and IPDS teams;

- analyses of outputs from FAA databases and information systems;

- analyses of AMS-related program documents (e.g., Mission Need Statements, Investment Analysis Reports, Acquisition Program Baselines and other baseline documents, Requirements Documents, Integrated Program Plans, Acquisition Strategy Papers); and

- reviews of IPDS organizational charters and Integrated Product Team/Product Team Plans.

# Overall Evaluation Results in Brief

AMS has been in place for two years, and the FAA has made significant progress toward implementing procedures designed to achieve cost and schedule goals.  Continuous improvements from the first year evaluation report were identified in every major area.  Following are some of the achievements and highlighted improvements implemented under AMS:

- FAA employees, managers, and executives were serious about acquisition reform and AMS and made diligent efforts to follow the AMS processes.

- Cross-functional, multi-disciplinary teams did exist and worked together.

- Major procurements were more timely.

- Most FAA employees endorsed and accepted the IPDS structure, which established a framework in which to resolve issues and brought teams and people together to solve problems sooner.

- Content of JRC Records of Decision improved significantly.  During the first year of AMS, the Records of Decision were one-page documents and included only the JRC decisions with little reference to what led to those decisions.  During the second year of AMS, the Records of Decision included JRC decisions, rationale, and discussion.  Improved Records of Decision resulted in FAA having a better historical record of what occurred at JRC meetings and better documentation of the rationale for decisions.

Table 1–2.  AMS Training Statistics

| Acquisition Management System Training Course | Approximate Number of Persons in Attendance |
| --- | --- |
| Fundamentals of AMS | 100 |
| Acquisition Forum | 500 |
| Procurement Training Conference | 300 |
| Mission Analysis | 400 |
| Introduction to Investment Analysis and Investment Analysis Workshop | 100 |
| Integrated Product Team Workshop | 1,300 |
| FAA Acquisition System Toolset Training | 300 |
| Systems View Requirements: Roles and Responsibilities of Employees in the AMS Process | 200 |
| Working Together Effectively: Introduction to Effective IPDS Team Skills | 900 |
| Collaborative Team Processes: Advanced Effective IPDS Team Skills | 700 |

- The agency held numerous acquisition reform and AMS training classes following the establishment of AMS.  FAA employees and contract assistance personnel attended training courses in various AMS processes and concepts.  Table 1–2 includes some of the courses offered and the number of persons in attendance for each respective course.

- Many FAA Investment Analysis Teams formed according to AMS policy.

- The percentage of FAA Facilities and Equipment funded programs having         JRC-approved baseline documentation increased from 13 percent reported in the first year of AMS to 54 percent in the second year of AMS.

- The IPDS structure was implemented, acquisitions were included within this structure, and almost half of the Integrated Product Teams/Product Teams had a formal plan for guidance.

- After an initial decline immediately following the implementation of AMS, the FAA made progress toward achieving socio-economic goals.

- The FAA increased the percent of major procurements awarded through competition under AMS.

In any industry or agency, developing and implementing a completely new process or system could reasonably be expected to take several years before the full benefits could be realized.  Based on the average duration for process innovation cited in the Program Evaluation Branch’s Interim Acquisition Reform Report, dated March 1997, industry improvement efforts averaged 4.2 years and government organization’s efforts averaged 5.1 years.  The range of durations spanned from 3.5 to 7 years before full benefits were realized.  This is the case with AMS.  After the second year, the FAA was moving in the right direction, but it was still too early to validate the success of acquisition reform.  The agency has achieved more timely acquisitions, but further improvements are necessary before acquisition reform can meet the agency’s ambitious goals of reducing the time to field quality products and services by 50 percent and the cost by 20 percent.  The agency was extremely optimistic in establishing the timeline for meeting these goals at three years.  Because of the ambitious goals and the optimistic time frame, it is essential that improvements identified be fully implemented quickly so that the effects can, at the very least, be measured within the third year to determine if the FAA’s goals have been realized.

Although there were continuous improvements during the second year of AMS, the evaluation team found additional improvements were necessary.  Specifically, the team found that improvements were needed:

- in the mission analysis process, including improvements in identifying, validating, and prioritizing mission needs; receiving full support from all lines of business; and coordinating between the Mission Analysis Steering Group and the National Airspace System (NAS) Architecture core team;

- in the investment analysis process in documenting management intervention in solution identification;

- to AMS in addressing Systems Engineering/Operational Analysis Team activities dealing with affordability assessments;

- in baseline management, including establishing complete baselines and compiling and tracking baseline information to assist the agency in measuring and monitoring a program’s progress;

- in the JRC activities to ensure Operations and Maintenance funds were fully considered in lifecycle funding decisions and to ensure action items were tracked and monitored;

- to the FAA Joint Resources Council Guidance to develop a realistic time frame for disseminating Records of Decisions;

- in the IPDS structure to ensure IPDS was fully implemented, operated free of unnecessary constraints, and was effective in supporting successful acquisitions;

- in the procurement segment to ensure the accuracy and completeness of data used to measure results; and

- to the FAA’s overall planning process.

# Follow-Up from the First Year Evaluation

The first year evaluation report issued in May 1997 contained nine recommendations to the FAA.  These recommendations and their completion status are listed in Table 1–3.  Various FAA officials provided recommendation status information to the evaluation team; the team did not confirm this status information independently.  When recommendations addressed one of the six areas evaluated for this second year report, the team looked into them further and made additional recommendations where appropriate.

Table 1–3.  Status of First Year Evaluation Recommendations

| Recommendation | Status |
| --- | --- |
| Establish a focused, rigorous plan for the Integrated Product Teams to reduce the time to field new systems by 50 percent and reduce acquisition costs by 20 percent. Establish an appropriate, effective reporting system to monitor progress. | In Progress |
| Obtain the Administrator’s approval of the revised AMS core policy. | Completed |
| Develop an integrated metrics program and educate the workforce on its use and value. | In Progress |
| Establish and enforce a baseline management policy and procedures, and expedite the establishment of baselines for legacy programs. | In Progress |
| Complete the solution implementation guidance for systems/software as soon as possible and expedite the remaining processes, guidance, and tools. | In Progress |
| Prioritize programs, functions, and processes and reallocate resources accordingly, eliminating low priorities. Centralize processes where efficiency or effectiveness gains are possible. | In Progress |
| Merge the Joint Resources Council and the Resource Management Council into a single Assistant and Associate Administrator level body to optimize investment decisions and resource allocation across all FAA appropriations. An expanded Systems Engineering/Operational Analysis Team could support the merged council. | In Progress |
| Fully fund and staff the Office of Dispute Resolution and complete the required processes and procedures. | Completed |
| Determine the requirements for, and articulate the benefit of small, economically disadvantaged business contracts and implement guidance accordingly. | Completed |
| Key: | Completed In Progress | This recommendation has been addressed fully. Action was under way to complete this recommendation. |

Chapter 1(Mission Analysis

Mission analysis within the FAA was planned as the continuous analytical activity to evaluate the capacity of agency assets to satisfy existing and emerging demands for services.  It was designed to focus on the National Airspace System and to address all other agency critical needs and opportunities.  Mission analysis was intended to enable the agency to determine and prioritize its most critical capability shortfalls and its best technological opportunities for improving the National Airspace System overall safety, security, capacity, efficiency, and effectiveness in providing services to its customers.  As such, mission analysis was expected to be conducted within the framework of, and to contribute strongly to, the National Airspace System (NAS) Architecture, which was the long-range plan defining the needs of the National Airspace System and encompassing the long-range strategic goals of the agency.

# Evaluation Objective

Determine whether the FAA’s mission analysis process identified and prioritized shortfalls and opportunities for meeting its mission.

# Scope and Methodology

In order to answer the evaluation objective, the evaluation team performed an assessment of quality and compliance with AMS for two of the six Mission Need Statements approved under AMS during the period from April 1, 1996, to       December 31, 1997, [En Route/Oceanic Domain and Workforce Information Next Generation System (WINGS)] and for four Mission Need Statements approved prior to AMS for the four selected acquisition programs [Air Traffic Control Beacon Interrogator Replacement (ATCBI–R), NAS Infrastructure Management System (NIMS), Operational and Supportability Implementation System (OASIS), and Standard Terminal Automation Replacement System (STARS)].  The team also assessed how the agency’s lines of business conducted mission analysis, reviewed the relationship between the NAS Architecture and the mission analysis process, reviewed the operations of the Mission Analysis Steering Group (MASG), and reviewed the draft MASG charter.

The evaluation team gathered data from the following sources:

- AMS policy,

- Mission Need Statements,

- National Airspace System Mission Need Statement Database,

- Mission Analysis Process Guidelines,

- interviews with individuals actively involved with the NAS Architecture, and

- interviews and surveys of the MASG representatives from each of the seven lines of business (Air Traffic Services, Airports, Regulation and Certification, Civil Aviation Security, Administration, Commercial Space Transportation, and Research and Acquisitions).

# Mission Analysis Results in Brief

The agency identified critical needs and moved forward under AMS to address these critical needs.  We found the agency conducted mission analysis on the six programs reviewed in our sample.  We also found the agency had documented 329 mission needs in Mission Need Statements.  However, the agency did not follow the AMS process in validating and prioritizing all critical needs that were identified and structured under mission analysis.  Additionally, in some cases, a structured mission analysis was not conducted and a Mission Need Statement was not prepared.  [See finding 1 for details.]

We found two Associate Administrators for FAA’s lines of business most heavily involved in the acquisition process supported the mission analysis process.  In addition, many MASG members, who were representatives from the various lines of business, supported the mission analysis process.  However, we found some lines of business did not fully implement the mission analysis process and some MASG members were not fully involved.  In addition, improvements were needed in coordination between the NAS Architecture core team and the MASG.  [See finding 2 for details.]

We also found management control improvements were needed to ensure Mission Need Statements were revalidated as necessary and to assure all historical records related to mission needs were collected in a central repository.  The FAA needed to establish internal controls to ensure Mission Need Statements would be revalidated when necessary.  Without this revalidation, the agency did not know the status of all mission needs.  The agency did create an official repository for all mission analysis documents approved by the Joint Resources Council (JRC), but did not establish controls to ensure all unofficial supporting documentation related to mission needs were also maintained as historical records.  [See finding 3 for details.]

## Finding 1:  Improvements were needed in identifying, validating, and prioritizing mission needs.

The agency did identify critical needs and did move forward under AMS to address these critical needs.  We found the agency conducted mission analysis on the six programs reviewed in our sample.  We also found the agency had documented 329 mission needs in Mission Need Statements.  However, the agency did not follow the AMS process in validating and prioritizing all critical needs that were identified and structured under mission analysis.  Additionally, in some cases, a structured mission analysis was not conducted and a Mission Need Statement was not prepared.

AMS Sections 2.3 through 2.3.4:

- required each line of business to perform mission analysis for all critical agency needs and opportunities within its business area and to sponsor a Mission Need Statement for those needs and opportunities which emerged from the structured mission analysis process;

- tasked the MASG to formulate action in response to mission needs arising outside the lines of business and to recommend a priority ranking for all Mission Need Statements to the JRC; and

- designated the JRC as the responsible authority to approve Mission Need Statements and assign a priority rank to each approved Mission Need Statement relative to all approved mission needs.

We found the agency conducted mission analysis on the six programs reviewed in our sample.  In addition, the agency validated and documented critical needs in a Mission Need Statement for some emerging critical programs, such as the Host and Oceanic Computer System Replacement (HOCSR).  However, we also found a structured mission analysis was not conducted and a Mission Need Statement was not prepared, validated, or prioritized for other critical needs and opportunities.  For example, the  Year 2000 and Flight 2000 initiatives were critical needs for which the agency planned, but which were not validated or documented in the form of a Mission Need Statement.  Year 2000 was a recognized need, and the agency moved forward in addressing this need, but it was not documented in a Mission Need Statement.  Flight 2000 was a Research, Engineering and Development funded program that did not have a Mission Need Statement.  Under AMS, when a Mission Need Statement was not prepared, it could have resulted in a delay in the entire acquisition process or programs may have been initiated without any analysis of a need for the program.

Critical needs were not always structured under the AMS mission analysis process because some of these needs had been previously addressed in programs that were already approved prior to AMS.  In addition, because agency needs, both critical and noncritical, were many and varied, the lines of business did not always recognize the necessity to identify and develop Mission Need Statements for all critical needs and opportunities.

While we found the agency had developed and documented mission needs in           329 Mission Need Statements in the National Airspace System Mission Need Statement Data Base, none of these Mission Need Statements had a recommended priority ranking by the MASG, and none had been assigned a prioritization by the JRC.  This occurred because the MASG had not developed guidance on how to prioritize new and existing mission needs.

When critical needs were identified and validated, the agency was better able to plan for the most cost-effective use of resources and to provide support for future budget and resource requests.  If a critical need was not recognized at the earliest stage, whether or not it was fully articulated, the agency could have lost an opportunity to address and plan for the need before it became a crisis.  Prioritizing agency needs would also improve the FAA’s ability to plan effectively.

### Recommendations

We recommend:

1A	The FAA Administrator ensure that all critical needs and opportunities emerge from structured mission analysis, are developed into Mission Need Statements with a recommended prioritization, are reviewed for validation, and, if approved, are assigned a prioritization relative to all other approved Mission Need Statements, in accordance with AMS.

1B	The chairperson of the Mission Analysis Steering Group prepare guidance on how to prioritize new and existing mission needs for Joint Resources Council approval, and ensure the approved guidance is implemented.

## Finding 2:  Improvements were needed in support of mission analysis and in coordination between the Mission Analysis Steering Group and the National Airspace System Architecture core team.

We found the Associate Administrators for the FAA lines of business most heavily involved in the acquisition process supported the mission analysis process.  In addition, many MASG members, who were representatives from the various lines of business, supported the mission analysis process.  However, we found some lines of business did not fully implement the mission analysis process and some MASG members were not fully involved.  In addition, improvements were needed in coordination between the NAS Architecture core team and the MASG.

AMS Section 2.3.3 and Appendix A required that each line of business provide a representative to the MASG and perform mission analysis using staffs of qualified analysts.  The Mission Analysis Process Guideline, Version 1.0, Section 2.3 recommended each FAA line of business establish a mission analysis team to conduct mission analysis and to develop Mission Need Statements.

We found the Associate Administrators for the two lines of business heavily involved in the acquisition process, Air Traffic Services and Research and Acquisitions, complied with AMS and supported the mission analysis process.  The other five lines of business did not have the direct need to become as active in mission analysis and did not have the resources to support mission analysis to the level described by AMS.  We found the Associate Administrators for five of the seven lines of business had not established mission analysis teams.  These lines of business were also unable to provide their staffs with sufficient training in the mission analysis area.  Recognizing this difficulty, the MASG and Air Traffic Services indicated their willingness to provide the needed support in the area of mission analysis to these other lines of business.

While lines of business did provide representatives to the MASG, as many as half of the members were not fully involved.  We found, on average, only four of the nine members attended the 16 MASG meetings held during the evaluation period.  This low level of attendance indicated mission analysis was given a low priority by the MASG members and by their respective lines of business.

In addition, improvement was needed in coordination between the NAS Architecture core team and the MASG.  AMS Section 2.3.3 required the FAA to conduct mission analysis within the framework of the NAS Architecture.  We found the NAS Architecture core team did not coordinate its critical needs and opportunities with the MASG in preparation of the NAS Architecture Version 3.0.  In turn, the MASG did not coordinate mission analysis with the NAS Architecture core team for critical needs and opportunities.

The NAS Architecture was established as the FAA’s long-range plan to define the needs of the National Airspace System over the next 15–20 years.  It was intended to provide the framework for mission analysis.  Improving coordination between the NAS Architecture core team and the MASG would reduce the likelihood of duplicated mission analysis effort, improve capability to identify all needs and eliminate conflicting overall FAA mission needs, and provide for the more efficient use of agency resources.

### Recommendations

We recommend:

2A	The chairperson of the Mission Analysis Steering Group ensure the Mission Analysis Steering Group representatives (both members and their alternates) fulfill their responsibilities to the Mission Analysis Steering Group, to include ensuring the AMS mission analysis process is followed and that all mission analysis work in the agency, including the National Airspace System Architecture, is coordinated with the Mission Analysis Steering Group.

2B	The Associate Administrator for each line of business ensure sufficient qualified and trained staff and the appropriate resources are available to perform mission analysis work or delegate this responsibility and authority to the Mission Analysis Steering Group or Air Traffic Services mission analysis team as appropriate and agreed upon.

## Finding 3:  Management control improvements were needed for the FAA mission analysis process.

Management control improvements were needed to ensure Mission Need Statements were revalidated as necessary and to assure all historical records related to mission needs were collected in a central repository.

Revalidated Mission Need Statements were required under AMS.  AMS Section 2.7 and Appendix A required Mission Need Statements to be revalidated by the Associate Administrators of the lines of business as necessary during various stages of the lifecycle acquisition management process.  We found the FAA did not establish internal controls to ensure Mission Need Statements would be revalidated when necessary.  As a result, the agency did not know:

- if 56 mission needs were still valid and up to date, or

- if four new Mission Need Statements duplicated needs identified on prior Mission Need Statements.

Maintaining historical records and documentation was only partially required under AMS.  AMS Appendix B required the maintenance of a central repository of all approved acquisition planning and control documents within the Evaluation and Configuration Management Division (ASD–200).  We found the agency did establish an official repository for all JRC-approved documents in the Evaluation and Configuration Management Division (ASD–200).  Although AMS did not address other acquisition planning and control documents, we found the agency also established an unofficial repository in the National Airspace System Concept Development Branch (ASD–130) for these documents.  Both repositories provided a reference of historical acquisition documents.

We found the lines of business appropriately relied on the Evaluation and Configuration Management Division (ASD–200) to collect and maintain official records relating to JRC-approved Mission Need Statements.  The lines of business, therefore, did not maintain or provide copies of all supporting documentation for acquisition planning and control documents.  This occurred because the FAA (1) had not formally established a repository for historical records, other than for JRC-approved documents, relating to all submitted Mission Need Statements, and (2) had not established an internal control to ensure the lines of business maintained all supporting records and provided these supporting documents to a central repository.  With improved historical mission need records, the FAA would be better able to:

- identify the population of mission needs and of submitted Mission Need Statements in order to track the need through the acquisition process;

- share and use mission need information throughout the FAA, reducing duplication of effort; and

- conduct current and future mission analysis, revalidate mission needs, or prioritize mission needs agency-wide with the benefit of historical data.

### Recommendations

We recommend the chairperson of the Mission Analysis Steering Group:

3A	Develop guidance and procedures on how to conduct and document revalidation of mission needs, and establish a plan with a schedule for accomplishing revalidations.

3B	Develop guidance to establish a central repository for historical records of all supporting documentation for submitted Mission Need Statements, and to ensure each line of business submits all acquisition planning and control supporting documentation to this central repository.

Chapter 2(Investment Analysis

Investment analysis was designed to generate information for the Joint Resources Council (JRC) to use at investment decision to determine the best overall solution for satisfying a mission need.  Investment analysis was planned as a partnership between the sponsoring and acquiring organizations to ensure critical needs of the user and customer were satisfied by an affordable solution.  Investment analysis was structured to translate mission needs into top-level performance and supportability requirements by:  (1) conducting a thorough market analysis; (2) performing alternative solutions analysis; (3) developing an affordability assessment to determine the affordability of identified solutions; and (4) quantifying the cost, schedule, performance, and benefits baselines for the solution.  Investment Analysis Teams were expected to analyze viable alternative solutions to mission needs thoroughly and equally.  The role of the Systems Engineering/Operational Analysis Team (SEOAT) in investment analysis was to perform affordability assessments of all candidate solutions to a mission need and to maintain a relative priority listing of all agency programs based on standard evaluation criteria approved by the JRC.

# Evaluation Objective

Determine whether the investment analysis process, including SEOAT activities, complied with AMS and provided adequate support to permit sound investment decisions.

# Scope and Methodology

The evaluation team selected and reviewed six programs that were in the investment analysis process between April 1, 1996, and January 9, 1998.  The sample selection did not require the programs to have moved completely through the investment analysis process during that time, only that they were somewhere in the investment analysis process between those dates.  The six programs included three of the four selected acquisition programs:  Air Traffic Control Beacon Interrogator Replacement (ATCBI–R), National Airspace System Infrastructure Management System (NIMS), and Operational and Supportability Implementation System (OASIS).  The fourth selected acquisition program, Standard Terminal Automation Replacement System (STARS), was not included in this review because STARS was already beyond investment decision when AMS was implemented.  In addition to the three selected acquisition programs, the evaluation team reviewed Workforce Information Next Generation System (WINGS), Modernization of Procurement Automation (ACQUIRE), and Host and Oceanic Computer System Replacement (HOCSR).  WINGS was selected because it had gone through the investment analysis process without leading to an investment decision.  ACQUIRE was selected because it had both a Mission Need Statement approval and investment decision during the period of our review.  HOCSR was selected because it had a financial impact on other programs evaluated during this review.  The team evaluated the overall investment analysis process, including team formation, alternative solutions generation and analysis, market analysis, affordability assessment, and the JRC decision process.  The team also reviewed SEOAT activities supporting the investment analysis process.  The evaluation team gathered data from the following sources:

- AMS policy;

- Investment Analysis Guidelines;

- program documentation (Mission Need Statements, Requirements Documents, Affordability Analyses, and Acquisition Program Baselines);

- JRC presentations, briefing materials, and Records of Decision;

- Investment Analysis Reports; and

- interviews with FAA personnel involved in investment analysis, including:

- Integrated Product Team members;

- FAA and contractor investment analysis personnel;

- representatives from agency financial management, including SEOAT members; and,

- representatives from the Architecture and Systems Engineering Division.

# Investment Analysis Results in Brief

The FAA Investment Analysis Teams were formed according to AMS policy in most cases.  However, we found solutions were sometimes selected or limited by upper level management prior to the completion of the alternatives analysis process.  When this occurred, the reasons and justification were not documented in the file.  As a result, we could not determine whether there was a problem with the investment analysis process or whether other concerns drove management’s need to intervene.  Without written documentation to explain the rationale for the interventions, the FAA cannot determine what changes, if any, should be made to AMS to address the investment analysis process.  [See finding 4 for details.]

We also found SEOAT affordability assessment requirements under AMS needed to be revised.  SEOAT affordability assessment activities did not comply with AMS and may not be able to comply with AMS.  AMS required the SEOAT to perform an affordability assessment on all candidate solutions.  We found this task was difficult, if not impossible, to accomplish with the available resources.  [See finding 5 for details.]

## Finding 4:  Investment Analysis Teams formed according to AMS, but investment analysis actions were not fully documented.

The FAA Investment Analysis Teams were formed according to AMS policy in five of the  six sample programs reviewed.  The Investment Analysis Teams created matrix partnerships and developed and analyzed alternatives in light of requirements definitions.  However, we found two of the solutions from the six programs reviewed were selected or limited prior to the completion of the alternatives analysis process, and paperwork prepared to support the investment analysis process did not necessarily document what actually occurred.

AMS Section 2.4 described investment analysis as the process to generate information used by the JRC at investment decision to determine the best overall solution for satisfying a mission need.  AMS Section 2.4 further described investment analysis as a partnership between the sponsoring and acquiring organizations to ensure the critical needs of the user and customer were satisfied by an affordable solution.  AMS Section 2.4.2 identified principal activities of investment analysis, including identifying alternatives, surveying the market and analyzing alternatives.  In analyzing alternatives, AMS Section 2.4.2 tasked the Investment Analysis Team with determining “the most advantageous and reasonable solution to a core set of top-level requirements, not necessarily all initial requirements.” [Emphasis included in AMS document.]

We found the sponsor or upper level management identified or limited solutions prior to the completion of the alternatives analysis process in two of the six cases reviewed.  For example, in the case of ATCBI–R, the Requirements Document was written by the sponsor to drive a specific solution, and the sponsor was reluctant to negotiate and identify a core set of top level requirements.  In HOCSR, which was a high priority project, the solution was identified by upper level management while the Investment Analysis Team was still evaluating different options.

When upper level management intervened in the investment analysis process, it limited the scope of the investment analysis but did not reduce the level of effort required by the Investment Analysis Team.  Because management intervention was not fully documented, it was not clear whether there was a problem within the investment analysis process or whether other concerns drove management’s need to intervene.  Without written documentation to explain the rationale for the interventions, FAA cannot determine what changes, if any, should be made to AMS to address the investment analysis process.  In addition, when the intervention was not fully documented, the full decision body may not have been aware an intervention occurred.  At least one JRC member stated it would have affected the decision if that person had known an intervention had occurred.

### Recommendations

We recommend the FAA Acquisition Executive:

4A	Require the changed direction and rationale for any intervention in the investment analysis process be documented at the time of the intervention, and ensure this documentation is included in the Investment Analysis Report used at the investment decision.

## Finding 5:  SEOAT affordability assessment requirements under AMS need to be revised.

SEOAT affordability assessment requirements under AMS need to be revised.  SEOAT affordability assessment activities did not comply with AMS and may not be able to comply with AMS.  The SEOAT was required to perform an affordability assessment on all candidate solutions.  We found this task was difficult, if not impossible, to accomplish with the available resources.

AMS Section 2.4 required the SEOAT to perform an affordability assessment of all candidate solutions to a mission need.

SEOAT affordability assessment activities were not able to comply with AMS.  In most cases, the SEOAT performed an affordability assessment on the recommended candidate solution only.  The SEOAT could not complete affordability assessments on each candidate solution because time and resource constraints did not permit that level of effort.  In addition, there were conflicting instructions for SEOAT activities between AMS and the Investment Analysis Guidelines.  AMS Section 2.4 stated, “The…SEOAT performs an affordability assessment of all candidate solutions to a mission need…” and Section 2.4.2 stated, “The SEOAT assesses the affordability of each candidate against all other programs in the agency’s financial baseline based on their relative priority.”  However, Section 2.2.4.1 of the Investment Analysis Guidelines stated, “It is probable that the SEOAT will only perform the affordability analysis on the recommended candidate solution unless the [Investment Analysis Team] or the SEOAT requests otherwise.”  We found the SEOAT followed the Investment Analysis Guidelines rather than AMS; we determined this was reasonable.

### Recommendations

We recommend the chairperson of the Acquisition System Advisory Group:

5A	Revise the AMS to allow the Systems Engineering/Operational Analysis Team, in conjunction with the Investment Analysis Team, flexibility to determine, on a case-by-case basis, how many viable candidate solutions will have an affordability assessment completed.

Chapter 3(Baseline Management

Under AMS, when the Joint Resources Council (JRC) established an acquisition program at the investment decision, the JRC was also expected to approve performance and benefit objectives to be achieved within strict cost and schedule boundaries, as defined in the Acquisition Program Baseline (APB).  Performance, benefit, cost, and schedule were the four parameters comprising a program’s baseline; these baselines were intended to be the control elements enabling the agency to plan realistically when committing to full funding for new programs.  Individual program baselines were built from agency planning and budgeting profiles.  AMS required every acquisition to have an APB approved by the JRC.  For new acquisition programs, the APB was to be established at the investment decision.  For existing programs without a baseline, the responsible manager was required to propose and obtain JRC approval of an APB.

# Evaluation Objective

Determine whether the FAA established effective baselines and used each baseline as a primary tool to measure and monitor a program’s progress.

# Scope and Methodology

The evaluation team assessed the status and completeness of baselines for programs as of January 23, 1998.  We used the FAA’s Capital Investment Plan and identified    113 programs funded with Facilities and Equipment (F&E) funds.  Of these 113 programs, 19 were still in investment analysis and were not expected to have an APB.  The remaining 94 programs, however, should have had an APB. Our review focused on these 94 programs.  With respect to these programs, the team reviewed the general quality of baselines, compliance of  baselines with AMS, and both the agency-level and operational-level management of baselines.

The evaluation team gathered data from the following sources:

- AMS policy;

- AMS guidance documents;

- APBs;

- Parameter Sheets, which represented JRC-approved interim baseline documents; and

- interviews with Integrated Product Team (IPT) and Product Team (PT) leads from a sample of programs.

# Baseline Management Results in Brief

The FAA had not defined “programs,” “substantial programs,” or “major systems acquisitions” in order to comply with congressional and Office of Management and Budget reporting requirements, and had not established JRC-approved baselines for all programs. Those baselines that were JRC-approved were usually not comprehensive.  (For example, baselines did not always contain complete information on cost, schedule, performance, and benefits.)  In addition, the JRC allowed Parameter Sheets to substitute for required APBs in some existing programs, and permitted other programs to avoid developing any JRC-approved baseline document.  Parameter Sheets were used in lieu of APBs because the JRC needed a way to expedite baselining for existing programs.  However, Parameter Sheets were not fully effective because essential elements, such as Research, Engineering and Development (R,E&D) funding and Operations and Maintenance (O&M) funding, were not included in the majority of the Parameter Sheets reviewed.  As a result, the FAA did not always have formal baseline documentation against which to measure progress, and decision makers were limited in their abilities to make sound decisions on continuing investments.  [See finding 6 for details.]

We also found the FAA collected incomplete or inconsistent baseline data to measure and monitor program progress.  This occurred because the numerous systems and processes used for tracking program status were not integrated and the FAA did not ensure a standard set of data was collected for comparisons.  Also, the data in these systems and processes did not necessarily reflect current JRC-approved program baselines.  As a result, there was no thorough oversight or tracking of some baselines, and there was no commitment to periodic revalidation of baselines.  In addition, FAA management received limited visibility into program status after the investment decision.  [See finding 7 for details.]

## Finding 6:  The FAA did not establish complete baselines.

The FAA had not defined “programs,” “substantial programs,” or “major systems acquisitions;” and did not establish baselines for all programs.  During this review, the evaluation team discovered the FAA had not established definitions for, or designations of, “programs,” “substantial programs,” or “major systems acquisitions,” which made it difficult to identify the number of programs in existence.  Because all programs required an APB, a definition of what constituted a “program” was essential.  Since the FAA Administrator was required to consider terminating “substantial programs” that fail to meet defined goals, the agency needed to define what a “substantial program” was and set goals for those programs.  In addition, since the agency was required to report on “major systems acquisitions,” the agency needed to define that term and identify those programs.

Although programs were not defined by the agency, we defined for our purposes what a program was and identified 94 Capital Investment Plan programs that should have had APBs.  The Capital Investment Plan included F&E funded programs; we found no JRC-approved baseline documentation for R,E&D only or O&M only programs.  For these 94 Capital Investment Plan programs, the evaluation team found 51 (54 percent) had some form of baseline documentation:  5 programs had APBs and 46 had Parameter Sheets.  While the other 43 programs had no JRC-approved baseline documentation at all, the 54 percent that did have JRC-approved baseline documentation represented a dramatic improvement over the 13 percent that had JRC-approved baseline documentation in the first year of AMS.

Of the 51 programs with JRC-approved baseline documentation, we found those documents did not always include enough information to measure and monitor the programs’ performance.  The evaluation team found that baseline data included in APBs was significantly more comprehensive than Parameter Sheets, but neither APBs nor Parameter Sheets were always in compliance with the AMS.  For example, 25 of 29  (86 percent) sampled baseline documents did not contain all the cost data, and          27 of 29 (93 percent) did not contain enough scheduling information to measure or monitor program performance.

Public Law 104–264 required the FAA Administrator to consider terminating “substantial programs” that failed to meet defined goals.  Office of Management and Budget Circulars A–109 and A–11 required designation and reporting on “major systems acquisitions.”

AMS Section 2.11.3 required every acquisition to have an APB approved by the JRC.  According to AMS, an individual APB defined a program’s cost and schedule boundaries, and performance and benefits objectives.  These four parameters comprised a program’s baseline.  For new acquisition programs, AMS Section 2.11.3 required a baseline to be established at the investment decision and required all programs to have an APB.  For existing programs or Capital Investment Plan lines without a baseline, AMS required the responsible manager to propose and obtain JRC approval of a baseline.

On June 13, 1997, the JRC approved a plan that allowed exceptions to the AMS requirement for all programs to have an APB.  Specifically, the JRC decided that programs with low F&E funding totals, programs that were nearly completed, and programs representing certain level-of-effort criteria (e.g., Air Route Traffic Control Center Modifications and the Aeronautical Center Lease) did not require JRC-approved baselines.  With this decision, the JRC intended to reduce to a manageable level the number of programs requiring documented and approved baselines.

To expedite baselining for existing programs, the JRC also decided not to enforce the AMS requirement for an APB and approved the Parameter Sheet as an alternate baseline document.  The Parameter Sheet was considered an interim baseline document, and no written guidance or standards were developed for its preparation.

Figure 3–1.  Baseline Document Status

To assess the effectiveness of the baselines, the evaluation team selected a sample of 29 programs from the 94 Capital Investment Plan programs.  Of the 29 programs selected for the sample, 5 had a JRC-approved APB, 19 had a JRC-approved Parameter Sheet, and 5 had no JRC-approved baseline document.  Using this sample, the team evaluated the quality of the baseline data for the four baseline parameters (cost, schedule, performance, and benefits), to determine if there was enough information to measure the program’s progress or to allow decision makers to make sound decisions on continuing investments.

Table 3–1.  Completeness of Baseline Documents

| Baseline Documents | Cost Baseline | Schedule Baseline | Performance Baseline | Benefits Baseline |
| --- | --- | --- | --- | --- |
| Acquisition Program Baselines | 63% | 53% | 76% | 61% |
| Parameter Sheets | 42% | 18% | 23% | 18% |

The team found the evaluated APBs were significantly more complete than the evaluated Parameter Sheets.  Performance baselines were complete in APBs, but were incomplete in most Parameter Sheets.  Benefits baselines were complete in most APBs, but were incomplete in most Parameter Sheets.  Schedule baselines were incomplete for most APBs, but were incomplete for all Parameter Sheets.  Cost baselines for all funding appeared complete for APBs, but were incomplete for all Parameter Sheets. Specifically, the evaluation team found R,E&D funding was frequently not included in baseline documents because it was regarded as a “sunk cost” by the time the investment decision was made and the APB was approved.  In addition, O&M funding was not always included on the baseline documents because (1) although O&M funding was provided by the sponsor for each program baseline, it was unclear which organization, if any, was responsible for all planning and programming for O&M funds; (2) little, if any, current or historical O&M funding data existed, and what was available tended to be unreliable; and (3) the FAA did not have a cost accounting system capable of identifying real O&M costs for existing systems or projected O&M costs for future new systems.  As a result, there was very little credibility associated with the O&M cost estimates contained in APBs and Parameter Sheets.  These poor or inaccurate cost estimates contributed to the incompleteness of the baseline documentation and limited the FAA’s ability to make sound investment decisions based on the economic merits of a proposal.  (See Table 3–1 for the evaluation team’s assessment of baseline documentation completeness for the sampled documents.)

While APBs were prepared with input from IPT/PT members, Parameter Sheets were prepared by Research and Acquisitions line of business personnel that did not always have sufficient baseline data.  In addition, while APBs required signatures from the FAA Acquisition Executive, the IPT/PT, and the sponsor, Parameter Sheets required no approving signatures signifying concurrence and agreement by FAA management, the IPT/PT, or the sponsor.

Even though APBs were more complete than Parameter Sheets, neither type of document was always sufficient to measure a program’s progress or to allow decision makers to make sound decisions on continuing investments.  Baseline documents did not always provide an adequate depiction of lifecycle costs or lifecycle linkage.  Although F&E estimates were usually complete, O&M funding requirements were poorly documented and often did not relate chronologically to the development cycle.  In addition, R,E&D costs were not included in any Parameter Sheet.  No baseline documentation existed for programs requiring only R,E&D funds, such as the Aging Aircraft program, or for programs requiring only O&M funds, such as the Leased Interfacility National Airspace System Communication System.

Approved baseline documentation was intended to provide a mutual agreement between FAA management, represented by the JRC, and the provider, which was typically the IPT.  Because the JRC permitted specific programs to avoid developing an approved baseline, many programs had no baseline documentation.  As a result, the FAA was restricted from having adequate program control to measure and monitor program progress.  The absence of formal baseline documentation against which to measure progress restricted decision makers’ abilities to make sound decisions on continued investment.  In addition, when Parameter Sheets were allowed to substitute for APBs, the amount of data was reduced, which also limited the ability of FAA to make sound decisions based on those baselines.

### Recommendations

We recommend:

6A	The FAA Administrator ensure definitions are developed for “program,” “substantial program,” and “major systems acquisitions,” and that all FAA programs are designated in the appropriate category.

6B	The FAA Acquisition Executive ensure every program, existing or new, has an Acquisition Program Baseline as required by AMS, or an alternate baseline document, that includes all applicable cost (Facilities and Equipment; Research, Engineering and Development; and Operations and Maintenance), schedule, benefits, and performance parameters.

6C	The FAA Administrator require those organizations or individuals with signature authority for funding, including Facilities and Equipment; Research, Engineering and Development; and Operations and Maintenance, provide all the funding data and their signatures to authorize and commit these funds for each Acquisition Program Baseline.

## Finding 7:  Baseline data was not compiled and tracked to assist the agency in measuring and monitoring a program’s progress.

The FAA collected and reported numerous baseline data, but did not collect or track complete or consistent baseline data in order to measure and monitor a program’s progress.  The evaluation team found that although the FAA had numerous systems and processes for collecting and reporting baselines, data to monitor a program’s progress was not useful to the agency in measuring, monitoring and comparing all programs’ progress.

The AMS policy document did not specifically address baseline status reporting requirements, but AMS Section 1.13 did require metrics and indicators to be established at the investment decision for each acquisition program and actual performance and benefits to be measured and reported against planned values.  Also, AMS Section 2.5.5 required the reporting of baseline status, including cost, schedule, performance, and benefits, as part of acquisition reviews.

Public Law 104–264 required the Administrator to report to Congress on any program that was to be continued if it was more than 50 percent over the cost goal established for the program, it failed to achieve at least 50 percent of the performance goals established for the program, or it was more than 50 percent behind schedule as determined in the schedule boundary established for the program.

The Capital Programming Guide, Supplement to OMB Circular A–11, Part 3, Section IV:  Step IV.3, required the planning and procurement process to be evaluated 3 to 12 months after a new asset became operational to determine whether benefits from the new asset had been accurately predicted.

The agency had numerous systems and processes for collecting, reporting and tracking program status and for measuring it against the established baselines. No commonality existed among reporting systems; however, and there was little ability to interface systems with each other or with agency-level systems already in place, such as the Master Schedule System.  In addition, reporting system interfaces with other acquisition-related activities were poorly defined.  The agency’s numerous systems and processes contained inconsistent, conflicting, or incomplete data, and did not reflect all baseline parameters from the JRC-approved baseline documents. A comparison of a sample of some of these reports and reviews, and the baseline elements they included, is shown in Table 3–2.

These various systems and reports were established because policy and guidance responsibilities were diffused within the FAA, many FAA organizations levied separate reporting requirements on the IPTs and programs, and there was no centralized coordination of these information needs.

With respect to the benefits baselines, there was no thorough oversight or tracking and no commitment to its periodic revalidation.  Tracking benefits baselines with these multiple systems and processes was difficult, and IPTs lacked confidence in the results of revalidated benefits.  The FAA did not establish a requirement to revalidate, track, and report benefits status.

With respect to schedule baselines, the agency had no reliable monitoring data that correlated to program baseline documents.  As a result, the FAA could not compare programs and could not capture historical data.  Without defined schedule milestones, the FAA also could not establish consistent schedule baselines to monitor progress throughout program lifecycles.  Without consistent schedule baselines, the agency could not track the acquisition reform goal of 50 percent schedule reduction or the congressional reporting requirements.

Table 3–2.  Program Reporting

| Report /Review | Frequency | Baseline Elements | Percent of the 113 Capital Investment Plan Programs | Comments |
| --- | --- | --- | --- | --- |
|  |  | C | S | P | B | Captured |  |
| Capital Investment Plan | Annual |  |  |  |  | 100% | No cost data Milestones not same as APB No benefits data |
| Acquisition Reviews | Semi-Annual |  |  |  |  | 22% | No benefits data |
| ARA Wallboard | Monthly |  |  |  |  | 20% | Measures funds, not cost No forecast at complete No benefits data |
| 7–Up Metrics | Monthly |  |  |  |  | 20% | Only prime contractor level costs Only cumulative milestones |
| Master Schedule System / Master Schedule Baseline Report | Monthly |  |  |  |  | 80% | No minimum standard set of defined milestones Status often against current work plan No cost data No benefits data |
| Program Status Report | Monthly |  |  |  |  | 80% | No impact assessment Measures funds, not cost No forecast at complete No benefits data |
| Integrated Product Team Lead Reports/Reviews | Monthly |  |  |  |  | 100% | No benefits data |
| Key: |  – Consistent with APB  – Inconsistent with APB  – No Data |  | C – Cost S – Schedule | P – Performance B – Benefits |

Multiple and inconsistent reporting requirements resulted in a lack of credibility for FAA data.  In addition, collecting and analyzing data and preparing these multiple reports created a significant workload for the IPTs and for FAA management.  Because no one report tracked all baseline data, and FAA management did not direct all program status reporting to be tracked to the JRC-approved baselines, there was no single agency-wide approach for comparing actual performance against JRC-approved baselines.  As a result, the FAA had no reliable early warning of schedule and cost baseline problems, no interrelated impact assessment, and no forecast of cost growth to provide a reliable program cost estimate at completion.

### Recommendations

We recommend the FAA Administrator:

7A	Designate a single focal point for all program baseline management and reporting activities.

7B	Direct the development of an adequate tracking and validation system for benefits, or revise the AMS if it is determined the benefits baselining requirement should not be retained.

7C	Design and implement procedures for tracking and reporting program status against all approved baselines.

Chapter 4(The Joint Resources Council

The Joint Resources Council (JRC) was the FAA body responsible for making corporate level acquisition decisions.  Membership of the JRC consisted of:

- Associate Administrators representing all the FAA lines of business (Air Traffic Services, Airports, Regulation and Certification, Civil Aviation Security, Administration, Commercial Space Transportation, and Research and Acquisitions);

- Assistant Administrators for System Safety and for Policy, Planning and International Aviation;

- FAA Acquisition Executive;

- Chief Financial Officer; and

- Legal Counsel.

In addition to these JRC members, JRC meetings were also attended by key participants responsible for briefing the JRC members on a particular issue relevant to that JRC meeting.  These key participants often included Integrated Product Team leads, Investment Analysis Team leads, Systems Engineering/Operational Analysis Team representatives, or others.

The deliberations of the JRC were focused on five investment-related decisions:          (1) mission need decisions, which determined what capabilities the agency would pursue; (2) investment decisions, which determined what solutions the agency would approve and fund to fulfill mission needs; (3) Acquisition Program Baseline change decisions, which altered the cost, schedule, performance and/or benefits baselines established at the investment decision; (4) Research, Engineering and Development and Facilities and Equipment annual budget submission decisions; and (5) National Airspace System (NAS) Architecture baseline decisions.  The JRC also participated in development of the agency’s annual operations budget submission.

# Evaluation Objective

Determine whether the JRC made fully supported decisions in a timely manner and documented its decisions, rationale, and assigned action items.

# Scope and Methodology

The evaluation team measured the effectiveness of JRC processes; whether and to what extent the processes had been implemented; and what issues, potential issues, and barriers existed to success.  The evaluation covered all JRC meetings and events that occurred between April 1, 1996, and January 31, 1998.  Of the 55 JRC meetings held during this time period, the evaluation team reviewed documentation and results from a sample of 24 meetings (44 percent).  The sample included one JRC baselining meeting; a JRC budget meeting; all JRC meetings related to the four selected acquisition programs [Air Traffic Control Beacon Interrogator Replacement (ATCBI–R), NAS Infrastructure Management System (NIMS), Operational and Supportability Implementation System (OASIS), and Standard Terminal Automation Replacement System (STARS)]; as well as other JRC meetings.  The evaluation team gathered data from the following sources:

- AMS policy;

- FAA Joint Resources Council Guidance;

- JRC briefing packages, scheduling data, and Records of Decision;

- interviews with JRC members, Integrated Product Team leads, and other JRC key participants; and

- action items assigned by the JRC.

# Joint Resources Council Results in Brief

We found the JRC did not make fully supported decisions when it committed the FAA to full lifecycle funding without consistently considering Operations and Maintenance (O&M) funds.  Although the JRC had the responsibility to make decisions committing the FAA to full lifecycle funding, the JRC did not have the data needed to commit the FAA’s O&M funding.  The FAA did not have a cost accounting system in place that enabled identification of realistic O&M costs.  The agency was in the process of developing a cost accounting system, which is expected to be in place by October 1, 1998.  Without an operational cost accounting system or an effective financial baseline for the required O&M funds, the FAA could not determine if a program was affordable over its full lifecycle.  There was also confusion over the role and authority of the Resource Management Council.  In addition, while we found JRC meeting attendance was generally good, meetings were frequently rescheduled, which delayed JRC decisions.  [See finding 8 for details.]

We found the JRC fully documented its decisions and rationale for decisions during the second year of AMS.  During the second year of AMS, JRC Records of Decision were expanded from a one-page document with little information to a full explanation of JRC decisions, including rationale, discussion, and participant quotes.  With improved JRC Records of Decision, the FAA had a better historical record of what occurred at JRC meetings and better documentation of the rationale for decisions made.  Timeliness in disseminating information and tracking action items, however, needed improvement.  [See finding 9 for details.]

## Finding 8:  The Joint Resources Council did not make fully supported and timely decisions.

We found the JRC did not make fully supported decisions when it committed the FAA to full lifecycle funding without considering O&M funds.  We also found that, while the JRC meeting attendance was generally good, meetings were frequently rescheduled, delaying some decisions.

### Lifecycle Funding

AMS Appendix A gave the JRC responsibility to commit the FAA to full lifecycle funding of programs.  Lifecycle funding included all acquisition, development, and operational costs.  We found the JRC did not fully consider operational costs, which were included within the FAA’s O&M funds, when the JRC made decisions.  The JRC did not fully consider operational costs for two reasons:

- First, while the JRC had the responsibility to make decisions committing the FAA to full lifecycle funding, it did not have the data needed to commit the FAA’s O&M funding.  In addition, there was confusion over the role and authority of the Resource Management Council, which made decisions on O&M funds.

- Second, the FAA did not have a cost accounting system and had not developed and maintained an operations financial baseline to determine current and future operational costs.  The basic framework that existed for F&E funding did not exist for O&M funding.  This problem was unrelated to AMS and could not be corrected entirely by AMS processes.  The FAA was developing a cost accounting system, which is expected to be in place by October 1, 1998.

When the JRC made investment decisions, the associated required O&M funds commitment did not have to be honored by the Resource Management Council.  This split in funding decision making negatively affected lifecycle planning, data quality, and decision making in the investment analysis, baseline management, and Integrated Product Development System processes.  Without an operational cost accounting system or an effective financial baseline for the required O&M funds, the FAA could not determine if a program was affordable over its full lifecycle.

### JRC Meeting Attendance

The JRC meeting attendance by members was generally good.  However, we found meetings were frequently rescheduled, delaying some decisions.

The FAA Joint Resources Council Guidance required that:

- JRC meetings be scheduled around the calendars of the FAA Acquisition Executive, the sponsoring Associate Administrator and the Associate Administrator for Air Traffic Services;

- the Chief Financial Officer be present when a major program was involved; and

- required documentation be provided to JRC members at least three full working days in advance of the JRC meetings.

JRC meetings were rescheduled when a key JRC member requested the meeting be rescheduled, on a case-by-case basis if key participants were not ready for the meeting or had a conflicting obligation, or if the required documentation was not provided three days prior to the meeting.

When JRC meetings were rescheduled, decisions that would have been made at those meetings were delayed.  This had the potential to impact other phases of the acquisition process, program schedules, and contractual activities.  It also caused staff time to be lost.

Recommendations

We recommend:

8A	The FAA Administrator combine the responsibility and authority for full lifecycle funding under one Associate/Assistant Administrator level body and clearly define its role, responsibilities, and authority.

8B	The FAA Acquisition Executive ensure each Joint Resources Council member designates a single alternate and empowers this alternate to act in his/her place, and each key Joint Resources Council meeting participant designates a single alternate and empowers this alternate to act in his/her place in order to reduce rescheduling caused by calendar conflicts and to maintain consistency at meetings.  These alternates should possess sufficient knowledge of the duties and responsibilities of the Joint Resources Council member or key participant and should have the appropriate corporate level perspective to serve in this position.

## Finding 9:  The Joint Resources Council fully documented its decisions and rationale for decisions; however, timeliness in disseminating information and tracking action items needed improvement.

The JRC fully documented decisions and rationale for decisions during the second year of AMS.  Timeliness in disseminating information and tracking action items, however, needed improvement.

The FAA Joint Resources Council Guidance designated the Evaluation and Configuration Management Division (ASD–200) as the JRC’s executive secretariat and required it to prepare and issue the JRC Records of Decision.  These JRC Records of Decision represented the minutes of the JRC meetings and documented JRC decisions and the rationale for the decisions. These minutes, or JRC Records of Decision, were issued after JRC meetings.  The content of these JRC Records of Decision improved significantly during the second year under AMS.  During the first year of AMS, the JRC Records of Decision were one-page documents that included only the JRC decisions with little reference to what led to those decisions.  During the second year of AMS, the JRC Records of Decision included JRC decisions, rationale, discussion, and participant quotes.  With improved JRC Records of Decision, the FAA had a better historical record of what occurred at JRC meetings and better documentation of the rationale for decisions made.

While the quality of the JRC Records of Decision improved significantly, timeliness in disseminating these documents did not improve.  The FAA Joint Resources Council Guidance required the JRC Records of Decision to be prepared and issued within five working days.  We found it took an average of 36 working days to disseminate these Records of Decision during the first year of AMS and 36.9 working days the second year of AMS.  On average for the first two years under AMS, it took 36.4 working days to disseminate JRC Records of Decision after the meetings.  While we believe 36 working days was too long, 5 working days was unrealistic.  We found the time to disseminate documents was extended because the agency had no efficient process for the timely preparation, approval, and dissemination of JRC Records of Decision.  The JRC Records of Decision were reviewed by many levels before being signed and issued in final form, and the number of days within which respondents were required to reply was not specified.  As a result, turnaround time varied greatly between and among the different levels of review.

We found there was no formal process in place to track action items assigned at JRC meetings during the time of our review.  The informal process being used to track action items assigned at JRC meetings was not adequate, and some JRC meetings adjourned without a clear understanding among JRC members and participants of the specific action items assigned, including what was required, who was responsible, and when the action was to be completed.  JRC members and participants were sometimes confused about assigned action items, responsible organizations, and due dates.  Although action items were recorded in the JRC Records of Decision, they were not always captured effectively during the meetings to ensure JRC members and participants understood and agreed to them.  Because JRC Records of Decision were the only formal documentation of JRC decisions, until they were signed and disseminated, some actions required by the JRC decision were not implemented.  As a result, actions may not have been completed appropriately.  We found one-third        (60 of 184) of the action items assigned during JRC meetings since the implementation of AMS remained open and were overdue.  Because a formal tracking process did not exist, the evaluation team could not identify the exact area where delays occurred.  In addition, without a tracking process to close out completed action items, the JRC could not monitor action items assigned.  Before we completed our review, we confirmed that an automated system to track, follow up on, and close assigned action items was being designed to address some of these concerns, but not all of them.

### Recommendations

We recommend the FAA Acquisition Executive:

9A	Revise the FAA Joint Resources Council Guidance requirement to issue Records of Decision within five days to a realistic period of time; and, develop and document a process for the timely preparation, approval, and dissemination of Joint Resources Council Records of Decision, and ensure that process is followed.

9B	Establish an effective means to capture assigned action items during Joint Resources Council meetings (including what is required, who is responsible, and when the action is to be completed) to ensure members and participants understand and agree to all action items assigned; and define and implement a process to track, follow up on, close, and disseminate results of action items after Joint Resources Council meetings.

Chapter 5(The Integrated Product Development System

The Integrated Product Development System (IPDS) was designed as the implementing arm for the lifecycle acquisition management system.  The philosophy of IPDS was to team functional disciplines systematically and thereby integrate and apply all relevant processes to produce an effective, efficient product or service that satisfied customer needs.  The system, built on the concept of “teams leading teams,” stressed cutting across organizational boundaries and emphasized full lifecycle responsibility from program inception to disposal of products, and termination of services.

Figure 5–1.  IPDS Structure

IPDS was initiated prior to acquisition reform and was formally made a part of the FAA’s acquisition reform process during the development of AMS.  There were four levels of teams within IPDS composed of Integrated Product Leadership Team, Integrated Management Team, Integrated Product Team (IPT), and Product Team (PT) (i.e., a  sub-IPT when there were multiple products or services requiring a division of the IPT for manageability).  FAA Headquarters implemented an IPDS structure composed of          1 Integrated Product Leadership Team overseeing 3 Integrated Management Teams composed of 17 IPTs, many of which were subdivided into a total of 36 PTs.         Figure 5–1 illustrates the IPDS structure.

# Evaluation Objective

Determine whether the IPDS structure for acquisition programs was fully implemented, operated free of unnecessary constraints, and was effective in supporting successful acquisitions.

# Scope and Methodology

The evaluation team reviewed the IPDS put into place between April 1, 1996, and January 31, 1998.  The evaluation team gathered data from the following sources:

- AMS policy;

- IPDS Team Plan Guidelines;

- Integrated Product Leadership Team and Integrated Management Team Charters;

- IPT and PT Plans;

- Integrated Product Leadership Team and Integrated Management Team meeting minutes;

- IPDS survey of agency organizations; and

- interviews with Integrated Product Leadership Team, Integrated Management Team, IPT/PT, and Implementation Working Group members.

# Integrated Product Development System Results in Brief

The agency initiated IPDS prior to acquisition reform and formally incorporated IPDS into the acquisition reform process during the development of AMS.  Technically, an IPDS structure can consist of something as informal as the contracting officer and someone requesting the product.  Using this as a basis, we concluded that the IPDS structure was implemented.  Irrespective of that broad definition, we found that most acquisitions were included within the formal IPDS structure, and almost half of the IPT/PTs had a formal plan for guidance.  There were some constraints, however, which impacted IPDS in supporting successful acquisitions.  There were also areas where AMS requirements were more stringent than necessary under the circumstances.

Constraints impacting the ability of the IPDS structure to support successful acquisitions included:  (1) conflicts between the horizontal (IPDS team lifecycle responsibilities concept) and vertical (line of business functional responsibilities concept) structures, (2) the lack of authority of IPT/PT leadership over all team members, and (3) an inability of IPDS teams to resolve major agency issues.  These constraints delayed decisions, which could have prolonged the acquisition process and, in turn, could have increased acquisition costs.  [See finding 10 for details.]

In addition, we found some areas where AMS requirements or IPDS Team Plan Guidelines were more stringent than necessary under the circumstances.  For example, we found not all acquisitions were suitable for inclusion within the formal IPT structure as required by AMS.  Acquisitions such as facilities or services may not need to be under the IPT structure; however, there were no guidelines to clarify which acquisitions did not need to be under a formal IPT structure.  The IPDS Team Plan Guidelines required IPT/PTs to have formal plans.  However, some IPT/PTs may not need to be under a formal plan at this time.  We found some IPT/PTs were small and were able to manage acquisitions without a formal plan.  We did find, however, that 25 out of 53 (47 percent) of the IPT/PTs were under formal plans during the second year under AMS, representing a marked improvement over the first year of AMS.  The goal to have a formal plan for all formal IPDS teams is a good one and should continue to be implemented.

## Finding 10:  Some constraints impacted the support of successful acquisitions within the Integrated Product Development System.

The evaluation team found some constraints impacted the ability of IPDS to support successful acquisitions.  Conflicts between the horizontal and vertical structures created the primary constraint to the IPDS.  Horizontal structure refers to the IPDS concept of teams with full lifecycle responsibilities over acquisitions.  Vertical structure refers to the concept of individuals with functional responsibilities to their FAA lines of business.  Further constraints included a lack of IPT/PT authority over all team members and the inability of IPDS teams to resolve major agency issues.

AMS Section 1.11 and Appendix A:

- defined the philosophy of IPDS was to team functional disciplines systematically, thereby integrating and applying all relevant processes to produce an effective and efficient product or service that satisfied customer needs;

- empowered teams at the lowest level to make binding, team-based decisions on their programs;

- tasked the Integrated Product Leadership Team with oversight of the entire IPDS operation and resolution of high level, cross-domain issues requiring senior management assistance and support; and

- required the Joint Resources Council (JRC) to resolve issues not resolved within the IPDS structure.

### Horizontal vs. Vertical

Agency implementation of IPDS placed a horizontal organizational structure over an existing vertical organizational structure (see Figure 5–2) without reconciling conflicts or overlaps.  In some cases, this resulted in team members experiencing conflicts in goals, responsibilities, and priorities.  For example, IPT lifecycle responsibilities prescribed by AMS were perceived to be in conflict with functional responsibilities.  In addition, Integrated Management Team and Integrated Product Leadership Team members stated they spent 75 percent of their time on vertical activities as opposed to horizontal activities.

Conflicts and overlaps between the horizontal and vertical structures increased with the perception that IPDS was an initiative of the Research and Acquisitions line of business. This perception was reinforced by the fact that the Research and Acquisitions line of business (1) filled most IPT lead positions, (2) housed most IPTs and team members physically, and (3) led most acquisition processes.  Conflicts and overlaps, combined with this perception that IPDS was an initiative of the Research and Acquisitions line of business, made achievement of team consensus difficult and extended the decision making process.

Figure 5–2.  Vertical vs. Horizontal Structure

### IPT/PT Authority

IPTs/PTs lacked appropriate authority over all of their team members, further hindering IPDS effectiveness.  IPT/PTs included members who were not equally empowered.  Teams depended on their members to make decisions that would be supported by the vertical organizations they represented, but there was tension between the teams and the vertical organizations.  When team members were not fully empowered, representatives had to consult with their vertical organizations on all issues and it took longer to make decisions.  Team leads had no formal input into all team members’ performance appraisals, and team members were formally accountable only to their vertical organizations.  The evaluation team found IPT/PT leads believed they were held accountable by the agency for program performance, while team members believed they were not held accountable for much of anything.  Team leads proposed that all team member performance appraisals include the same critical element related to a team’s overall performance.

### Resolution of Major Issues

Major issues raised to the Integrated Product Leadership Team were not always resolved to the satisfaction of the IPT/PTs.  In one example, team members experienced conflicts between their teams and their vertical organizations regarding second level maintenance issues.  In this case, the IPT believed it was more cost-effective to replace equipment than to repair it.  But the lines of business believed it was less costly to repair or replace part of the equipment than to replace it all.  The Integrated Product Leadership Team may not have been sufficiently empowered to resolve the second level maintenance issue.  Resolution would have required the full integration of vertical and horizontal roles and responsibilities, which also would have required strong leadership commitment from senior FAA management.  When major issues such as this were not resolved, it was difficult for IPTs/PTs to make key decisions regarding full lifecycle responsibility.

### Recommendations

We recommend:

10A	The FAA Administrator ensure that Integrated Product Teams/Product Teams and functional management/organizations jointly select team members, document agreements clarifying team members’ roles and responsibilities, and evaluate team member performance.

10B	The chairperson of the Integrated Product Leadership Team ensure issues raised within the Integrated Product Development System structure are resolved.

Chapter 6(Procurement

The goal of the FAA procurement system was to obtain high quality products, services, and real property in a timely, cost-effective manner, and at prices that were fair and reasonable.  The procurement system allowed the agency to be innovative and creative so the best vendor could be selected to implement a solution.  The procurement system was established as an integral part of the acquisition process focusing primarily on identifying sources, awarding contracts, and administering contracts.  Under AMS, the procurement system was designed to:

- emphasize competition as the preferred method of contracting,

- enable selection of the contractor with the best value,

- provide attainable and reasonable opportunities for small businesses,

- promote open communications with industry,

- provide an internal protest forum, and

- promote sound business judgment and flexibility.

# Evaluation Objective

Determine whether procurements under AMS resulted in more cost-effective procurements and whether there were impacts on socio-economic goals and on competition.

# Scope and Methodology

The evaluation team compared procurement records and data from all FAA Regions, Centers, and Headquarters for eight quarters pre-AMS (from April 1, 1994, through March 31, 1996), and seven quarters under AMS (from April 1, 1996, through December 31, 1997).  At the time of our review, data was unavailable beyond this time period.  The evaluation team compared award time and cost to the value of award dollars for each period, measured the percent of contract dollars awarded to businesses identified in socio-economic program goals against the established goals, and identified the percentage of competitive and single-source awards for both periods.

To assess procurement timeliness, the evaluation team reviewed a data list of contracts from the Contract Information System for the evaluation time periods.  The team eliminated duplicate contract numbers and added additional contracts from the System for Acquisition Management.  From the consolidated list, the evaluation team identified a random sample of contracts based on a criteria of 90 percent accuracy with a confidence level of plus-or-minus 5 percent.  The random sample of 86 contracts included 41 contracts from the pre-AMS period and 45 contracts from the AMS period.  For pre-AMS actions, the team computed the average time from the issuing of a Request for Proposals to award of the contract.  For AMS actions, the team computed the average time from the issuing the first Screening Information Request used for initial screening of vendors to award of the contract.

The evaluation team gathered data from the following sources:

- AMS policy;

- FAA procurement personnel, including:

- Office of Acquisitions,

- Small Business Utilization Staff,

- procurement office managers and procurement administrative officers,

- contracting officers and contracting officers’ representatives, and

- program managers;

- Contract Information System;

- System for Acquisition Management; and

- Major Procurement Program Goals reports.

# Procurement Results in Brief

Major procurements were more timely under AMS while costs to conduct procurements changed very little.  Based on analysis of the random sample selected, the evaluation team found contracts were awarded an average of 56.2 days faster after the implementation of AMS.  At the same time, dollars expended to award contract actions dropped from $8 million to $7.6 million.  [See finding 11 for details.]

After an initial decline immediately following the implementation of AMS, the FAA made progress toward achieving socio-economic goals.  However, because the data used to report progress in this area was incomplete or inaccurate, the evaluation team could not accurately determine the true impact of AMS on socio-economic goals.  [See finding 12 for details.]

The FAA also increased the percent of major procurements awarded through competition under AMS.  [See finding 13 for details.]

## Finding 11:  Major procurements were more timely under AMS.

Major procurements were more timely under AMS while costs to conduct procurements changed very little.  Based on analysis of the random sample selected, the evaluation team determined contracts were awarded an average of 56.2 days faster after the implementation of AMS while dollars expended to award contract actions dropped from $8 million to $7.6 million.

AMS Section 1.1 described reducing the time and decreasing the cost of delivering needed services as two intended purposes of acquisition reform.  The overall goal of FAA acquisition reform was to reduce the time to acquire and field new systems by     50 percent and to reduce the costs of acquisitions by 20 percent, both by April 1999.  These results would be measured from the investment decision through first commissioning of a new system.  The portion of procurement timeliness covered in this section of the AMS evaluation report represents the procurement segment of the acquisition process only.

The evaluation team defined time to award procurement actions as the time from solicitation for a proposal to contract award.  Based on the sample data, the average elapsed time from issuing a Request for Proposals or Screening Information Request to awarding the contract was 119.8 days pre-AMS and 63.6 days under AMS, representing a 47 percent reduction in the time required for this phase of the acquisition process.

While major procurements were more timely under AMS, and costs to conduct procurements changed very little, the evaluation team was still unable to quantify whether procurements were more cost-effective because cost-effectiveness includes more than just quicker (more timely) procurements.  Cost-effectiveness also includes costs to conduct the procurements, the cost of the procurements themselves, and all other acquisition costs.  Because sufficient information did not exist to analyze costs of acquisitions, we looked only at the costs to conduct the procurements.

To determine whether the costs to conduct procurements were more cost-effective after the implementation of AMS, the evaluation team examined the time to award procurement actions, the total expenditures for procurement operations, and contract dollars awarded.  Total expenditures for procurement operations were defined in terms of dollars spent for FAA employees and for contracted assistance personnel used to conduct procurement operations. The evaluation team found dollars expended to award contract actions dropped from $8 million to $7.6 million while contract dollars awarded dropped from $551 million to $495 million.

Although we do not know the exact causes, since the implementation of AMS, total dollars expended for procurement operations, total number of employees conducting procurement operations, and total dollars awarded for contracts all decreased.  However, without a detailed cost accounting system to (1) segregate procurement operations conducted by procurement personnel but not related to procurement award activities, such as contract administration, etc., from the total procurement expense; and (2) capture full costs of acquisitions, we were unable to make a conclusion on whether procurements were more cost-effective.

## Finding 12:  The FAA appeared to have made progress toward achieving socio-economic goals.

After an initial decline immediately following the implementation of AMS, the FAA appeared to have made progress toward achieving socio-economic goals.  However, because the data used to report progress in this area was incomplete or inaccurate, the evaluation team could not accurately determine the true impact of AMS on socio-economic goals.

Congress mandated that Federal agencies establish goals, representing the nation’s social goals, for awarding contracts to small business concerns in general, and to small business concerns owned and controlled by socially and economically disadvantaged individuals specifically.  Although the Department of Transportation and Related Agencies Appropriation Act of 1996 exempted the FAA from the Federal Acquisition Regulation and from the Small Business Act, AMS Section 3.6.1.2 required the FAA to “implement and aggressively strive to provide small businesses and small businesses owned and controlled by socially and economically disadvantaged individuals attainable and reasonable opportunities to participate as prime contractors and subcontractors for products and services procured by the FAA.”  AMS Section 3.6.1.3.1 required the FAA to establish measurable annual agency-wide procurement program goals for these businesses.  The FAA established goals between 5 and 25 percent for these categories.

Table 6–1.  Socio-economic Program Goals:  Comparison of Six-month Periods Preceding and Following AMS

(dollars in thousands)

|  | Small Business Award Value | Small Business Award Percent | SEDB Award Value | SEDB Award Percent | SDB Award Value | SDB Award Percent | Total FAA Award Value |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal FY1996 | ( | 25% | ( | 15% | ( | 5% | ( |
| October 1995–March 1996 (Last Six-month Period Pre-AMS) |
| Actual | $253,352 | 27% | $129,567 | 14% | $217,693 | 23% | $943,267 |
| April 1996–September 1996 (First Six-month Period Under AMS) |
| Actual | $151,499 | 18% | $79,730 | 10% | $19,500 | 2% | $828,325 |
| Note: Data for the total dollars awarded to subcontracting was not available to calculate the percentage of the subcontracting goal achieved. SEDB award refers to set-aside awards to disadvantaged businesses certified by the Small Business Administration under Section 8(a). SDB award refers to awards to disadvantaged businesses that were self-certified or certified by the Small Business Administration but received awards through a process other than the set-aside process. |

Awards to businesses identified in the socio-economic program goals decreased in the six-month period immediately following the implementation of AMS.  However, the evaluation team found the FAA made steady improvement in awards to those businesses after the initial six-month period.  To make this comparison, we used Major Procurement Program Goals reports maintained by the FAA’s Small Business Utilization Staff.  This Staff had the responsibility for consolidating and reporting the FAA’s progress in meeting socio-economic goals.  As shown in Table 6–1 below, we compared the first six-month period following the implementation of AMS to the last  six-month period before AMS and determined that the percentage of awards to all small businesses identified in the FAA’s socio-economic goals declined immediately following the implementation of AMS.  For example, the percentage of awards to small businesses in general decreased from 27 percent in the last six-month period prior to AMS to 18 percent for the six-month period immediately following the implementation of AMS.  Similarly, set-aside awards to disadvantaged businesses certified by the Small Business Administration under Section 8(a) (referred to as SEDB awards) decreased from 14 percent for the last six-month period prior to AMS to 10 percent for the first    six-month period immediately following the implementation of AMS, and awards to disadvantaged businesses that were self-certified or certified by the Small Business Administration but received awards through a process other than the set-aside process (referred to as SDB awards) decreased from 23 percent to 2 percent.  The FAA attributed the initial decline in awards to businesses identified in the socio-economic program goals in part to the confusion surrounding AMS set-aside programs and to the industry’s lack of familiarity with the new procurement process under AMS.

Table 6–2.  Socio-economic Program Goals:  Comparison of First Six-month Period to First Seven Quarters Following AMS

(dollars in thousands)

|  | Small Business Award Value | Small Business Award Percent | SEDB Award Value | SEDB Award Percent | SDB Award Value | SDB Award Percent | Total FAA Award Value |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Goal FY 1996 FY 1997 | ( — | 25% 20% | ( — | 15% 5% | ( — | 5% 5% | ( — |
| April 1996–September 1996 (First Six-month Period Under AMS) |
| Actual | $151,499 | 18% | $79,730 | 10% | $19,500 | 2% | $828,325 |
| April 1996–December 1997 (First Seven Quarters Under AMS) |
| Actual | $1,885,784 | 52% | $446,489 | 12% | $112,893 | 3% | $3,648,497 |
| Note: Data for the total dollars awarded to subcontracting was not available to calculate the percentage of the subcontracting goal achieved. SEDB award refers to set-aside awards to disadvantaged businesses certified by the Small Business Administration under Section 8(a). SDB award refers to awards to disadvantaged businesses that were self-certified or certified by the Small Business Administration but received awards through a process other than the set-aside process. |

By contrast, when the evaluation team compared the results from the first six-month period following the implementation of AMS to the results from the full seven quarters following AMS, we determined that the percentages of awards increased for all three categories.  As shown in Table 6–2, the percentage of awards to small businesses increased from 18 percent in the first six-month period following AMS to 52 percent for the full seven quarters following AMS.  Similarly, set-aside awards to disadvantaged businesses certified by the Small Business Administration under Section 8(a) (referred to as SEDB awards) increased from 10 percent for the first six-month period to 12 percent for the full seven quarters following AMS, and awards to disadvantaged businesses that were self-certified or certified by the Small Business Administration but received awards through a process other than the set-aside process (referred to as SDB awards), increased from 2 percent to 3 percent.

The evaluation team identified these improvements based on information from Major Procurement Program Goals reports submitted to the Small Business Utilization Staff.  However, we determined information submitted for the Major Procurement Program Goals reports was frequently incomplete or inaccurate.  In addition, reporting was inconsistent among the FAA Regions, Centers, and Headquarters.  The evaluation team found some Major Procurement Program Goals reports were incomplete or inaccurate.  For example, we found awards from credit card purchases were not reported, commas were used when decimal points were appropriate, and totals did not always add up correctly.  We also found individuals submitting the report information did not always understand the definitions or the format of the Major Procurement Program Goals reports.  In addition, FAA Regions, Centers, and Headquarters were not consistent in capturing and reporting information on the Major Procurement Program Goals reports.  Some sites reported minority awards from credit card purchases based on a percentage established by that site, while other sites did not report credit card activity at all.  Some sites reported awards in actual dollars, while some rounded to the nearest thousand, and others rounded to the nearest million.  Some sites reported subcontracting award results, while others did not.  In addition, not all sites recorded the same data in the same categories on the Major Procurement Program Goals reports.

In a separate report entitled “Impact of Acquisition Reform on Awards to Disadvantaged Businesses” issued May 20, 1998, the FAA Program Evaluation Branch also identified inconsistencies in the data and weaknesses in the systems used to collect and report the FAA’s progress in meeting socio-economic goals.  Specifically, the report stated that multiple systems were used to collect contract award information, and information collected to produce the Major Procurement Program Goals reports was inconsistent throughout the FAA.  As a result, the Program Evaluation Branch limited the scope of its review for that report to one system and one location.  The May 20, 1998, report discussed the FAA’s progress in meeting socio-economic goals for FAA Headquarters only, while this AMS evaluation report includes a review of FAA’s progress agency-wide.  Because there were substantial inconsistencies in collecting and reporting information among the FAA Regions, Centers, and Headquarters, neither report was able to quantify the impact of acquisition reform on socio-economic goals accurately.  Although there was some initial confusion in data collection under AMS, the FAA’s data collection and reporting inaccuracies were not created by AMS; they were only highlighted by AMS.

As a result of the errors and inconsistencies in the reporting process, socio-economic program goal data reported to the Office of the Secretary of Transportation and the Small Business Administration may not have been accurate.  Without accurate data, the FAA cannot know whether or not it is meeting established socio-economic goals, whether additional efforts to meet those goals are necessary, or whether any additional efforts put in place were effective.

### Recommendations

We recommend:

12A	The Special Assistant, Small Business Utilization Staff, ensure that FAA Regions, Centers, and Headquarters have accurate, current guidance for development of Major Procurement Program Goals reports and comply with that guidance.

Additional recommendations related to achieving socio-economic goals were addressed in Report #1998–01, “Impact of Acquisition Reform on Awards to Disadvantaged Businesses,” dated May 20, 1998.

## Finding 13:  The percentage of contract dollars awarded through competition increased.

The FAA increased the percentage of major procurement contracts awarded through competition.  To determine the level of competition under AMS, the evaluation team collected and compared data from the Contract Information System database for the eight quarters pre-AMS and the seven quarters under AMS.  The Contract Information System contained data for procurements over $25,000 and identified whether the contracts were awarded through competition or through a noncompetitive process.  After averaging to allow for the different number of quarters for the pre-AMS and AMS periods, we found awards through competition increased from 64 percent before AMS to 70 percent under AMS.

Chapter 7(Interrelated and Recurring Issue

While performing the six component evaluations, the evaluation team identified one issue that crossed almost all acquisition processes and functional areas.  Because of the interrelated and recurring nature of this issue we separated it from the rest of the evaluation chapters.

We found that the agency cut funding to multiple and, in some cases, high priority programs to meet its funding levels and changing priorities because it had not properly planned for these issues.  This resulted in delayed implementation of crucial programs and diminished trust between planners, developers, and decision makers when their program work was undermined by deviations from baseline expectations and agreements.

## Finding 14:  The FAA’s overall planning process needed improvement.

During the past year, there were two major issues that affected funding levels of numerous agency programs.  First, the agency assumed it would receive a fiscal year 1999 funding level that was almost $500 million greater than what was agreed to by the Office of Management and Budget (OMB).  Second, the agency did not anticipate  $167 million of reprogramming priorities that surfaced in fiscal year 1998 after the agency received its budget for the year.

The FAA planned and approved program funding profiles within the agency and submitted its fiscal year 1999 budget request to the OMB for almost $500 million higher than the OMB outyear-target-level guidance (i.e., OMB guidance on the maximum funding level to request from the Congress).  In conjunction, the FAA prepared the National Airspace System (NAS) Architecture with the assumption that OMB would submit this higher request to Congress.  The OMB denied the FAA’s higher budget request to Congress.  When this was disallowed, many Capital Investment Plan lines had to be reworked.

In the case of the fiscal year 1998 appropriation from Congress, four unplanned emerging priorities surfaced.  These four priorities were (1) Year 2000, a computer problem; (2) Host and Oceanic Computer System Replacement (HOCSR);                  (3) additional Standard Terminal Automation Replacement System (STARS) requirements; and (4) additional security funding.  These four unplanned emerging priorities resulted in a $167 million shortage which forced the FAA to reprogram funding on 35 of 113 programs.  These programs already had Capital Investment Plan lines established.  (As discussed in chapter 3, not all of the agency’s programs had  JRC-approved baselines.  However, program planners, developers, and decision makers had expectations of a certain level of program funding.)  The reprogramming reductions impacted high priority programs and could affect the success of the programs and the agency’s acquisition reform efforts.  Some examples of these funding cuts for ten high priority programs are shown in Table 7–1.

Table 7–1.  High Priority Programs With Reprogramming Reductions

| High Priority Program | SEOAT Ranking | Amount Reprogrammed |
| --- | --- | --- |
| Air Route Traffic Control Center Modifications | 492 | $8.0 million |
| Next Generation VHF A/G Communication System (NEXCOM) | 480 | $3.2 million |
| Long Range Radar (LRR) Improvements | 460 | $2.2 million |
| Weather Radar Program (NEXRAD) | 458 | $1.0 million |
| Technical Support Services Contract (TSSC) | 450 | $4.3 million |
| National Airspace System Infrastructure Management System (NIMS) | 437.5 | $1.3 million |
| Aviation Safety Analysis System (ASAS) | 429 | $1.0 million |
| Data Multiplexing Network (DMN) | 420 | $2.6 million |
| Department of Defense Base Closures | 410 | $1.0 million |
| Back-Up Emergency Communications (BUEC) | 407.5 | $2.5 million |
| Note: SEOAT ranking can range from 1 to 500, with 500 being the highest priority. |

Because the agency was not able to plan based on realistic funding levels and did not anticipate the emerging priority needs, the agency had to adjust cost baselines and reprogram funding from numerous programs.  These actions resulted in deferring the planned implementation of crucial programs [e.g., Next Generation VHF A/G communication System (NEXCOM) and Long Range Radar (LRR) Improvements] and diminished trust between planners, developers, and decision makers when their program work was undermined by deviations from baseline expectations and agreements.

The FAA’s submission of a budget request higher than the OMB outyear-target-level was a one time action on the FAA’s part and will not likely reoccur.  One of the four unplanned emerging priorities (the security issue) was outside of the FAA’s control; however, the other three issues were under the FAA’s control and required better planning.

### Recommendation

We recommend the FAA Administrator:

14A	Ensure that the agency performs better planning for its future funding needs to avoid constant funding reductions to on-going programs.  This would involve improving the agency’s (1) mission analysis capabilities, which must be tied strongly to the agency’s approved National Airspace System Architecture;       (2) investment analysis capabilities; and (3) managing of program cost, schedule, performance, and benefits baselines.

Recommendations

The following lists all the recommendations included in this report.  The recommendation numbers correlate to the finding numbers; not all of the findings had recommendations.

We limited our recommendations to specific problems identified during the evaluation.  Our evaluation was limited to acquisition reform and did not address all of the FAA’s operations.  While we believe there are other recommendations that could help the  FAA improve its overall operations, we limited our recommendations in this report to those issues we found within acquisition reform.  For example, one recommendation was to combine the responsibility and authority for full lifecycle funding of programs under one Associate/Assistant Administrator level body.  We did not address Airport Improvement Program funds in this evaluation, so we did not address including those funds in the recommendation.  The FAA Administrator may decide it is necessary to expand this recommendation to include all funds.  We believe the expansion of this recommendation, along with the expansion of other recommendations, may be appropriate.

In addition, we were intentionally broad and not specific in our recommendations.  The purpose of our recommendations was to highlight areas that needed to be addressed by the FAA management.  It was not our intent to dictate specific solutions.  We believe it is best to allow the action officials flexibility in deciding the best approach to solving a problem, since those officials best know their operations and other factors that need to be considered.  Any solution that corrects the problems identified in our findings would be acceptable.  The ultimate goal is to ensure that acquisition reform succeeds.

The evaluation team recommends:

1A	The FAA Administrator ensure that all critical needs and opportunities emerge from structured mission analysis, are developed into Mission Need Statements with a recommended prioritization, are reviewed for validation, and, if approved, are assigned a prioritization relative to all other approved Mission Need Statements, in accordance with AMS.

1B	The chairperson of the Mission Analysis Steering Group prepare guidance on how to prioritize new and existing mission needs for Joint Resources Council approval, and ensure the approved guidance is implemented.

2A	The chairperson of the Mission Analysis Steering Group ensure the Mission Analysis Steering Group representatives (both members and their alternates) fulfill their responsibilities to the Mission Analysis Steering Group, to include ensuring the AMS mission analysis process is followed and that all mission analysis work in the agency, including the National Airspace System Architecture, is coordinated with the Mission Analysis Steering Group.

2B	The Associate Administrator for each line of business ensure sufficient qualified and trained staff and the appropriate resources are available to perform mission analysis work or delegate this responsibility and authority to the Mission Analysis Steering Group or Air Traffic Services mission analysis team as appropriate and agreed upon.

3A	The chairperson of the Mission Analysis Steering Group develop guidance and procedures on how to conduct and document revalidation of mission needs, and establish a plan with a schedule for accomplishing revalidations.

3B	The chairperson of the Mission Analysis Steering Group develop guidance to establish a central repository for historical records of all supporting documentation for submitted Mission Need Statements, and to ensure each line of business submits all acquisition planning and control supporting documentation to this central repository.

4A	The FAA Acquisition Executive require the changed direction and rationale for any intervention in the investment analysis process be documented at the time of the intervention, and ensure this documentation is included in the Investment Analysis Report used at the investment decision.

5A	The chairperson of the Acquisition System Advisory Group revise the AMS to allow the Systems Engineering/Operational Analysis Team, in conjunction with the Investment Analysis Team, flexibility to determine, on a case-by-case basis, how many viable candidate solutions will have an affordability assessment completed.

6A	The FAA Administrator ensure definitions are developed for “program,” “substantial program,” and “major systems acquisitions,” and that all FAA programs are designated in the appropriate category.

6B	The FAA Acquisition Executive ensure every program, existing or new, has an Acquisition Program Baseline as required by AMS, or an alternate baseline document, that includes all applicable cost (Facilities and Equipment; Research, Engineering and Development; and Operations and Maintenance), schedule, benefits, and performance parameters.

6C	The FAA Administrator require those organizations or individuals with signature authority for funding, including Facilities and Equipment; Research, Engineering, and Development; and Operations and Maintenance, provide all the funding data and their signatures to authorize and commit these funds for each Acquisition Program Baseline.

7A	The FAA Administrator designate a single focal point for all program baseline management and reporting activities.

7B	The FAA Administrator direct the development of an adequate tracking and validation system for benefits, or revise the AMS if it is determined the benefits baselining requirement should not be retained.

7C	The FAA Administrator design and implement procedures for tracking and reporting program status against all approved baselines.

8A	The FAA Administrator combine the responsibility and authority for full lifecycle funding under one Associate/Assistant Administrator level body and clearly define its role, responsibilities, and authority.

8B	The FAA Acquisition Executive ensure each Joint Resources Council member designates a single alternate and empowers this alternate to act in his/her place, and each key Joint Resources Council meeting participant designates a single alternate and empowers this alternate to act in his/her place in order to reduce rescheduling caused by calendar conflicts and to maintain consistency at meetings.  These alternates should possess sufficient knowledge of the duties and responsibilities of the Joint Resources Council member or key participant and should have the appropriate corporate level perspective to serve in this position.

9A	The FAA Acquisition Executive revise the FAA Joint Resources Council Guidance requirement to issue Records of Decision within five days to a realistic period of time; and, develop and document a process for the timely preparation, approval, and dissemination of Joint Resources Council Records of Decision, and ensure that process is followed.

9B	The FAA Acquisition Executive establish an effective means to capture assigned action items during Joint Resources Council meetings (including what is required, who is responsible, and when the action is to be completed) to ensure members and participants understand and agree to all action items assigned; and define and implement a process to track, follow up on, close, and disseminate results of action items after Joint Resources Council meetings.

10A	The FAA Administrator ensure that Integrated Product Teams/Product Teams and functional management/organizations jointly select team members, document agreements clarifying team members’ roles and responsibilities, and evaluate team member performance.

10B	The chairperson of the Integrated Product Leadership Team ensure issues raised within the Integrated Product Development System structure are resolved.

12A	The Special Assistant, Small Business Utilization Staff, ensure that FAA Regions, Centers, and Headquarters have accurate, current guidance for development of Major Procurement Program Goals reports and comply with that guidance.

Additional recommendations related to achieving socio-economic goals were addressed in Report #1998–01, “Impact of Acquisition Reform on Awards to Disadvantaged Businesses,” dated May 20, 1998.

14A	The FAA Administrator ensure that the agency performs better planning for its future funding needs to avoid constant funding reductions to on-going programs.  This would involve improving the agency’s (1) mission analysis capabilities, which must be tied strongly to the agency’s approved National Airspace System Architecture; (2) investment analysis capabilities; and            (3) managing of program cost, schedule, performance, and benefits baselines.

Appendix A(Criteria

The following documents and citations formed the criteria against which the evaluation team measured FAA acquisition reform efforts and processes.  Documents include (in order of precedence) public laws, Office of Management and Budget circulars, the AMS policy document, and AMS guidance documents.  In this evaluation report, all references to the AMS policy document are to the June 1997 version.

Chapter 1(Mission Analysis

Finding 1

AMS Section 2.3:  “Mission analysis is a strong, forward-looking, and continuous analytical activity that evaluates the capacity of agency assets to satisfy existing and emerging demands for services…Mission analysis enables the agency to determine and prioritize its most critical capability shortfalls and best technology opportunities…All Mission Need Statements will emerge from structured mission analysis.”

AMS Section 2.3.3:  “Each FAA line of business…performs mission analysis for its business area…The Mission Analysis Steering Group coordinates mission analysis among the lines of business; recommends to the Joint Resources Council a priority ranking for each Mission Need Statement; and formulates action in response to mission needs arising outside the lines of business (e.g., system safety, environmental, international).”

AMS Section 2.3.4:  “An FAA line of business must sponsor a Mission Need Statement…The Joint Resources Council assigns a priority rank to each approved Mission Need Statement relative to all approved mission needs.”

Finding 2

AMS Section 2.3.3:  “Each FAA line of business…performs mission analysis for its business area using staffs of qualified analysts.  These analysts conduct mission analysis within the broad framework of NAS Architecture, congressional mandates, and agency strategic planning.  The Mission Analysis Steering Group coordinates mission analysis among the lines of business; recommends to the Joint Resources Council a priority ranking for each Mission Need Statement; and formulates action in response to mission needs arising outside the lines of business (e.g., system safety, environmental, international).”

AMS Appendix A:  “The Mission Analysis Steering Group is composed of representatives from each line of business.”

AMS Mission Analysis Process Guideline Section 2.3:  “Sponsoring lines of business are normally responsible for:…

- Establishing a line of business Mission Analysis Team (MAT) and supporting staff to conduct mission analysis and to develop Mission Need Statements.”

Finding 3

AMS Section 2.7:  “Mission need must be revalidated (and updated if the need has changed) by the mission analysis staff of the original sponsoring line of business…” [sic]

AMS Appendix A:  The Line of Business Associate Administrator:

- “Revalidates Mission Need Statements as required during various stages of the lifecycle acquisition management process.”

AMS Appendix B:  “This appendix contains the purpose, description, approval authority, distribution, and content for the six mandatory acquisition planning and control documents in the Lifecycle Acquisition Management System…Send a copy [of the approved Mission Need Statement] to ASD–200, Program Evaluation Office, which maintains a central repository of approved acquisition documents for the Joint Resources Council.”

Chapter 2(Investment Analysis

Finding 4

AMS Section 2.4:  “Investment analysis generates the information used by the Joint Resources Council at the investment decision to determine the best overall solution for satisfying a mission need.  It is conducted as a partnership between the sponsoring and acquiring organizations to ensure the critical needs of the user and customer are satisfied by an affordable solution.  …  The intent of investment analysis is to define in functional and performance terms the capability the agency must have to satisfy mission need, and to determine and baseline the best overall solution(s) for achieving that capability.”

AMS Section 2.4.2:  “The principal activities of investment analysis are:

- Identify alternatives and survey the market…

- Analyze alternatives…This process involves multiple iterations back through requirements…to determine the most advantageous and reasonable solution to a core set of top-level requirements, not necessarily all initial requirements.” [sic]

Finding 5

AMS Section 2.4:  “…The Systems Engineering/Operational Analysis Team (SEOAT) performs an affordability assessment of all candidate solutions to a mission need…”

AMS Section 2.4.2:  “…The SEOAT assesses the affordability of each candidate against all other programs in the agency’s financial baseline based on their relative priority…”

Investment Analysis Guidelines Section 2.2.4.1:  “It is probable that the SEOAT will only perform the affordability analysis on the recommended candidate solution unless the [Investment Analysis Team] or the SEOAT requests otherwise.”

Chapter 3(Baseline Management

Finding 6

Public Law 104–264 Subtitle B Section 252:  “The Administrator shall consider terminating…any substantial acquisition program…”

Office of Management and Budget Circular A–11:  “Exhibit 300B covers major acquisitions(those requiring special management attention because of their importance to the agency mission; high development, operating, or maintenance costs; high risk; high return; or their significant role in the administration of agency programs, finances, property, or other resources…Agencies should report on all major acquisitions.”

Office of Management and Budget Circular A–109 Section 5.h:  “Major system acquisition programs are those programs that (1) are directed at and critical to fulfilling an agency mission, (2) entail the allocation of relatively large resources, and (3) warrant special management attention.”

AMS Section 2.11.3:  “The Acquisition Management System requires every acquisition to have an Acquisition Program Baseline approved by the Joint Resources Council.  For new acquisition programs, the baseline is established at the investment decision.  For existing programs or [Capital Investment Plan] lines without a baseline, the responsible manager must propose and obtain Joint Resources Council approval or a baseline.” [sic]

“Key” statement in the margin of AMS Section 2.11.3:  “All programs must have an Acquisition Program Baseline.”

Finding 7

Public Law 104–264 Subtitle B Section 252:  “The Administrator of the Federal Aviation Administration shall terminate any acquisition program initiated after the date of the enactment of the Air Traffic Management System Performance Improvement Act of 1996 and funded under the Facilities and Equipment account that(

(1) is more than 50 percent over the cost goal established for the program;

(2) fails to achieve at least 50 percent of the performance goals established for the program; or

(3) is more than 50 percent behind schedule as determined in accordance with the schedule goal established for the program.”

Public Law 104–264 Subtitle B Section 252:  “…if the Administrator determines that termination [of a program] would be inconsistent with the development or operation of the national air transportation system in a safe and efficient manner…[ and decides to continue a program that fails to meet its cost, performance, or schedule goal by more than 50 percent] …the Administrator shall transmit a copy of the determination, together with a statement of the basis for the determination…” to the Congress.

The Capital Programming Guide of OMB Circular A–11, Section IV:  Step IV.3:  “Three to twelve months after a new asset becomes operational, the planning and procurement process should be evaluated to determine whether they accurately predicted the benefits to be derived from the new asset.”

AMS Section 1.13:  “In compliance with the Government Performance and Results Act of 1993 (GPRA), the Acquisition Management System requires performance indicators and metrics to be established at the investment decision for each acquisition program.  Actual performance and benefits will be measured and reported against planned values.”

AMS Section 2.5.5:  “Topics for [acquisition] reviews should include baseline status (cost, schedule, performance, benefits)…”

Chapter 4(The Joint Resources Council

Finding 8

AMS Appendix A:  The JRC roles and responsibilities include committing “…the agency to full lifecycle funding of the program.”

The FAA Joint Resources Council Guidance, October 1996, (p.6):  “If a major program is involved and the Chief Financial Officer cannot attend, the JRC meeting will be canceled.”

The FAA Joint Resources Council Guidance (p.7):  “JRC meetings will be scheduled around the calendars of the FAE, the Sponsoring Associate Administrator, and the Associate Administrator for Air Traffic Services.”

The FAA Joint Resources Council Guidance (p.8):  Requires the meeting to be canceled “…if the required material has not been provided at least three full working days in advance of the meeting.”

Finding 9

The FAA Joint Resources Council Guidance (p. 5):  “The Program Evaluation Division is the executive secretariat for the JRC…The Division prepares and issues the final decision record and action items within five working days of the JRC meeting.  The Division also maintains files which document all JRC decisions.”

Chapter 5(The Integrated Product Development System

Results in Brief

IPDS Team Plan Guidelines Section 1:  “…PTs will prepare stand-alone Product Team Plans, consistent with these guidelines, which will serve as their governing ‘rule book’.”

IPDS Team Plan Guidelines Section 4:  “The IPT…Plan should address the same topics, in the same order as the Product Team Plans.”

Finding 10

AMS Section 1.11:  “The philosophy of the Integrated Product Development System (IPDS) is to team functional disciplines systematically, and thereby integrate and apply all relevant processes to produce an effective and efficient product or service that satisfies customer needs.  This system is built on the concept of ‘teams leading teams,’ and requires a cultural and organizational focus that understands and accommodates the mechanics and dynamics of team operation.  It stresses cutting across organizational ‘stovepipes,’ and emphasizes full lifecycle responsibility from program inception to disposal for products and termination for services.”

AMS Section 1.11:  “IPTs or PTs, as appropriate, are the primary lifecycle acquisition teams.  They are empowered at the lowest level to make binding, team-based decisions on the programs within their purview in the interests of all stakeholders, users, and customers in accomplishing their mission…”

AMS Section 1.11:  “The Integrated Product Leadership Team, consisting of director-level managers, oversees the entire IPDS operation and resolves high-level, cross-domain issues requiring senior management assistance and support.”

AMS Appendix A:  The Joint Resources Council

- “Resolves issues not resolved within the Integrated Product Development System structure.”

Chapter 6(Procurement

Finding 11

AMS Section 1.1:  AMS “…is intended to simplify, integrate, and unify the elements of lifecycle acquisition management into an efficient and effective system that increases the quality, reduces the time, and decreases the cost of delivering needed services to its customers.”

Finding 12

Public Law 104–50 Section 348:  “The following provisions of Federal acquisition law shall not apply to the new acquisition management system developed and implemented pursuant to subsection (a):…

(4) The Small Business Act (15 U.S.C. 631 et seq.), except that all reasonable opportunities to be awarded contracts shall be provided to small business concerns and small business concerns owned and controlled by socially and economically disadvantaged individuals.”

AMS Section 3.6.1.2:  “The FAA shall implement and aggressively strive to provide small businesses and small businesses owned and controlled by socially and economically disadvantaged individuals attainable and reasonable opportunities to participate as prime contractors and subcontractors for the products and services procured by the FAA.”

AMS Section 3.6.1.3.1:  “Prior to the end of each fiscal year, measurable annual       FAA wide major procurement program goals (including subcontracting goals) will be established to provide attainable and reasonable opportunities for small businesses and small businesses owned and controlled by socially and economically disadvantaged individuals to participate in contracts awarded by the FAA for the next fiscal year.”

Appendix B(List of Acronyms

AMS		Acquisition Management System

APB		Acquisition Program Baseline

ASD		Office of System Architecture and Investment Analysis

ATCBI–R	Air Traffic Control Beacon Interrogator Replacement

F&E		Facilities and Equipment

FAA		Federal Aviation Administration

FAST		FAA Acquisition System Toolset

HOCSR	Host and Oceanic Computer System Replacement

IPDS		Integrated Product Development System

IPT		Integrated Product Team

JRC		Joint Resources Council

MASG		Mission Analysis Steering Group

NAS		National Airspace System

NIMS		NAS Infrastructure Management System

OASIS		Operational and Supportability Implementation System

O&M		Operations and Maintenance

OMB		Office of Management and Budget

PT		Product Team

R,E&D		Research, Engineering and Development

SEOAT		Systems Engineering/Operational Analysis Team

STARS		Standard Terminal Automation Replacement System

WINGS		Workforce Information Next Generation System